Model PIP under National Tobacco Control Programme (NTCP) for seeking financial assistance by State Governments under NHM Flexipool

- Background

Tobacco is the foremost preventable cause of death and disease in the world today, killing half of the people who use it. Globally, it kills nearly 6 million people, of these 0.6 million premature deaths can be attributed to exposure to second hand smoke (SHS). As per WHO, if current trends continue, by 2030 tobacco use will kill more than 8 million people worldwide each year. It is estimated that 80% of these premature deaths will occur among people living in low-and middle-income countries.

As per report of the Tobacco Control of India 2004, more than 0.8 million people die due to tobacco consumption every year in India. There are studies to indicate that approximately 40% of the disease burden in the country is associated with some form of tobacco or other.  Approximately 50% of all cancers in males and 20% cancers in females can be attributed to tobacco use.  As per studies carried out by ICMR  in 1998-99 (extrapolated in 2002-03), the burden to the economy for treating just 3 major diseases (cancer, cardio-vascular diseases and lung disorders) attributable to tobacco use was more than Rs. 30,800 crore.

- Goals and Objectives:

The goal of the National Tobacco Control Programme is to reduce the prevalence of the tobacco use by 5% at the end of the 12th FYP.

The objectives of NTCP are as under:

- To build up capacity of the States / Districts to effectively implement the  tobacco control initiatives;

- To train the health and social workers;

- To undertake appropriate IEC activities and mass awareness campaigns, including in schools, workplaces,  etc.;

- To set up a regulatory mechanism to monitor/ implement the Tobacco Control Laws;

- To establish a system of tobacco product regulation.

- Provide facilities for treatment of tobacco dependence

- To conduct Adult Tobacco Survey/Youth Survey for surveillance, etc.

- To take necessary action, in co-ordination with other Ministries and stakeholders, to fulfill the obligation(s) under the WHO Framework Convention on Tobacco Control.

It is proposed to cover more districts by establishing new Tobacco Cessation Centres at District Hospital/ other Govt. Health Institution and District Tobacco Control Cells under District NCD Cell/ District Health Society across India in a phased manner.

- Implementation Mechanism (along with key strategies/ activities):

Tobacco is a major risk factor for a number of non-communicable diseases. Hence, it is proposed to bring in synergy between the National Tobacco Control Programme (NTCP) and National Programme for Prevention and Control of Cancer, Diabetes, Cardiovascular Diseases & Stroke (NPCDCS) schemes in the 12th FYP for optimum resource utilisation and for increasing the outreach / impact of the programme. It is proposed that the State and District Tobacco Control Cells under NTCP shall be housed in the State / District NCD Cell/ Health Society and the administrative and programme resources be shared accordingly. For this purpose, it is desirable to have a single focal point/nodal officer for NTCP as well as NPCDCS at state and district level.

The NTCP shall be implemented through a three tiered structure .i.e. National Tobacco Control Cell, State Tobacco control Cell & District Tobacco Control Cell. The National Tobacco Control Cell (NTCC) will be responsible for overall policy formulation, planning, monitoring and evaluation of the different activities envisaged under the programme.  Likewise the State Tobacco Control Cell (STCC) shall monitor and review all the activities under NTCP carried out in the state.

The District Tobacco Control Cell (DTCC): The District Tobacco Control Cell (DTCC) shall be established at District level under the umbrella of the District NCD Cell/District Health Society and this cell will be the focal point for all the activities carried out at district and sub-district level. The district level contractual manpower under NPCDCS/NCD, already engaged/to be engaged (Epidemiologist/ Public Health Specialist, District Programme Coordinator, Finance cum logistics consultant and DEO) shall extend their support towards different activities under the NTCP. The contractual manpower at the CHC and the District NCD Clinic (Doctor, Physiotherapist, Counsellor and DEO) shall also extend support towards tobacco cessation services. Support shall also be made available at district level for pharmacological treatment of tobacco dependence.

Key activities at district level include

- Training of health and social workers, NGOs, school teachers, enforcement officers etc.

- Information, Education and Communication (IEC) activities.

- School Programmes.

- Monitoring tobacco control laws.

- Co-ordination with Panchayati Raj Institutions for village level activities.

- Setting-up and strengthening of cessation facilities including provision of pharmacological treatment facilities at district  level.

4. 	Manpower (district level):

4.1. District Level: Minimum 2 contractual positions i.e. (i) Consultant, (ii) Social Worker

Provision for engaging at least two manpower namely District Consultant and Social Worker has been kept for the District Tobacco Control Cell (DTCC).  Other contractual manpower at the District NCD Cell shall also facilitate the NTCP as indicated at point no. 3 above. However, some of the NTCP districts may not be the designated NPCDCS/NCD districts. Keeping this in mind along with other practicalities, the existing district level staff will be retained as under:

- Existing Psychologist/Counsellor of the DTCC will be kept in the Tobacco Cessation Centre to be established in the District Hospital at a revised remuneration provided in the guidelines under NTCP.

- Existing Social Worker will be retained in the DTCC at a revised remuneration provided in the guidelines under NTCP.

- The due remuneration of the existing staff (Psychologist/Counsellor, Social Worker and DEO) will be met out from the Flexible Pool head as per the remuneration approved in the 11th Five Year Plan. Necessary funds may be demanded for the payment of the due remuneration up to the month of March, 2013 as committed expenditure in Flexible Pool head. Revised remuneration will come into effect from the financial year 2013-14 only i.e. from April, 2013 onwards.

- If the existing district under NTCP has not been covered under NPCDCS, the position of Data Entry Operator (DEO) may be provisioned under the Flexible Pool head at a monthly remuneration proposed for the similar position in the District NCD Cell i.e. (Rs. 12,000/-) per month. This will also be applicable for the continuation of services of the existing DEOs under various DTCCs from April, 2013 onwards till these districts are covered under NPCDCS/NCD.

4.2. Setting up and strengthening cessation facilities:

One Counsellor/ Psychologist will be provided in Tobacco Cessation Centre (TCC) to be established in the District Hospital. The existing Counsellor/ Psychologist under DTCC will be placed in this TCC for providing tobacco cessation facilities at District Hospitals. If there is no existing staff for this purpose, the staff will be recruited as per the guidelines of NTCP. This centre will be supported by basic equipments for running the clinic.

- Physical Targets at District Level – year wise breakup

It is suggested that from the year 2014-15 during up-scaling of the programme, the states will possibly select the same district for NTCP where NPCDCS programme has been launched so as to bring in synergy and share the resources.  The phasing of the NTCP shall be done as per the instructions/ guidelines / allocated or available budget for the year by NTCC, MoHFW.

- Requirement of Financial Resources (Recurring and non-recurring):

Annual allocation of DTCC budget

| SI. No | Details of Activity | Amount (INR) |
| --- | --- | --- |
| A. | Non – Recurring |  |
| i. | One time grant for office establishment | 100,000.00 |
|  | TOTAL non-Recurring | 100,000.00 |
| B. | Recurring |  |
| i. | Training of Key Stakeholders | 500,000.00 |
| ii. | Development of IEC/Campaign materials etc | 700,000.00 |
| iii. | Implementation of School Programmes | 700,000.00 |
| iv. | Mobility Support @Rs. 25,000.00 per month | 300,000.00 |
| v. | Provision for Pharmacological Treatment of tobacco dependence @Rs. 200,000.00 per year | 200,000.00 |
| vi. | Manpower support: - Social Worker – (1) @ Rs. 25,000.00 per month - Consultant – (1) @ Rs. 40,000.00 per month Note: Epidemiologist/ Public Health Specialist, District Programme Coordinator, Finance cum logistics consultant, DEO etc would be shared with NPCDCS/NCD programmes. | 780,000.00 |
| vii. | Flexible Pool | 7,20,000.00 |
|  | TOTAL Recurring | 3900,000.00 |
|  | GRAND TOTAL (A+B) | 4,000,000.00 |

The contractual manpower under NTCP will be given 10% hike in each subsequent year. Necessary provision may be kept accordingly.

The states are advised to carry out the activities as indicated above. They may also incorporate any other activity in view of the specific local needs/requirements to be funded under the flexible pool component indicated above within the maximum limit of budget provided by GoI. However, States/UTs have flexibility to undertake additional activities to be funded additionally by State/UT Governments.

Annual allocation Tobacco Cessation Budget

| SI. No | Details of Activity | Amount (INR) |
| --- | --- | --- |
| A. | Non – Recurring |  |
| i. | Procurement of equipment for setting and running TCC | 250,000.00 |
|  | TOTAL non-Recurring | 250,000.00 |
| B. | Recurring |  |
| i. | Training and outreach | 100,000.00 |
| ii. | Contingency and Miscl | 100,000.00 |
| iii. | Manpower support: - Psychologist/Counselor @Rs. 25,000 per month | 300,000.00* |
|  | TOTAL Recurring | 500,000.00 |
|  | GRAND TOTAL (A+B) | 750,000.00 |

*The amount indicated is for the 1st Year only, for each subsequent year an increment of 10% shall be factored in.

The ratio of the share of GOI and state would be 75:25 for Non-NE states and 90:10 for North Eastern States. State Governments are therefore accordingly requested to prepare and submit the PIPs for consideration under NHM-NCD flexi-pool indicating their contribution as well as the contribution of GOI. The PIP document, to be submitted by States should clearly specify the GoI and State contribution in the detailed budget sheet as well as detailed plan for the implementation of the different activities under the Programme.