National Health Mission – Free Drugs Service Initiatives in Mizoram

Program Implementation Plan (PIP) for 2014-2015

The component for this initiative has been set up following the supportive communication received from Secretary, MoHFW, GOI vide  D.O No.Z-13012/5/2013-stats (Pt) dated 1st April 2014 and the recommendation of the Mizoram State Drug Policy 2014 which has already provided composite and structural administrative organogram and machineries to improve drug administration in the state.

Goal

Provision of free generic drugs through public health facilities and service delivery points to reduce out of pocket expenses for poor and vulnerable groups to ensure access to free generic medicines by the major health seeking population of the economically challenged group of the society.

Specific objectives:

To ensure the delivery of the following indicators

- Robust procurement system

- Ensure fully functional IT backed drugs supply chain and logistics system

- Realize a system of facility wise Essential drug list

- Availability of treatment guidelines

- Prescription audit system in place

Problem analysis and scenario

Mizoram is a young dynamic tribal state identified by early staged sub-nation attributes on cultures, education, self identification, political self governance on democracy just over half a century from a primitive Chieftaincy, nature worship and head hunting which was no supreme than the bushmen culture universally known. Public Health scenario reveals the need to drive away myths and misconception, illusive consumerism activities on health etc. The critical role of the state Health department cannot be undermined, given the fact the opportunities of intelligent scholars to access health proficiency to the level of PG degrees on allopathic courses, pharmacy, nursing care etc which poses greater risk of focussing on individual economic pursuit rather than championing community health, preventive approach and feasible curative and preventive drug administration.

Hence, the promotion of economic approach to public health care through standardized pharmaceutical services and cost effective expenditure system assumed more importance.

The MoHFW initiative opening the provision of free generic drugs through public health facilities is a giant leap to reduce a financially herculean burden on health care medicinal cost for the meagre 1 million populated tribal state whose main economic survival rest with fund from the union government. Hence, the proposal under consideration is one of such vital solutions to the health and economic challenges.

Defining the road map

As per the State Drug policy the list of essential drugs has also been laid enclosed as Annexure I. Given the open administrative and financial opportunities provided by the MoHFW to cater to provision of free generic drugs through public health facilities to clients form the poor and vulnerable population, furtherly strengthened by the 12th plan the dashboard of implementation process (roadmap) has been framed as follows in eventual sequences:

- Contract with CDAC for the identified implementation unit of 78 and 100 personnel for carrying out actual reporting unit level task performance.

- Finalize infrastructure and HR requirement/strengthening which will be committed to by the state competent entities after consultation

- Institutional strengthening (this will also assess current capacity and strength) and capacity building with outsourced entity i.e CDAC in the 1st month.

- Renovation of 9 district warehouses and sub-warehouses @ 12 CHC level and 57 PHCs commencing from the 6st month and completion by the 11th month. And Sub Centre SCM to be made with mobile phone software system as they would not be having computers and internet facility.

- Analyse and validate EDL in the 2nd month with complete reports with the CDAC from District Hospitals to ASHA/AWW. This will entail field/grass-root level data with multi-stake-holder forum within the health caregivers community. (AWW/ICDS has been included to mainstream vitamin supplements from ICDS)

- Initiate DVDMs and define exit protocol

- Review and assess the immediate output and long term impact on an annual basis (2nd year)

Activity Dashboard and budget

| s/n | Activity | Time line | Budget implication (INR in lakhs) | remarks |
| --- | --- | --- | --- | --- |
| 1 | Contracting with CDAC | 1st month | 175.00 | Detail enclosed as per prescribed format in annexure II |
| 2 | Renovation/refurbishment of 9 CMO warehouses | 6-11 months | 45.00 | Estimate made as per CPWD manual and validated onsite needs assessment @ 5 lacs/CMO |
| 3 | Renovation/refurbishment of 12 CHC sub-ware-house | 6-11 months | 24.00 | Repairing works, minor civil works |
| 4 | Provision of refrigerator to 370 Sub-centres | 11th month | 44.40 | Storage facility for Sub-centre is absent and steel almirahs/wooden almirah are used currently |
| 7 | Provision of mobile phone based software and hardware to 370 Sub-centres | At the onset of DVDM installation or 2nd month | 11.10 | @ Rs.3000/handset including software cost user fee for 12 month |
| TOTAL |  |  | 299.60 |  |