Mobility Support (Supportive Supervision) for 2014-15

Supportive Supervision on Programme Implementation of NHM in the State will be conducted on a regular basis to promote  and to strengthen the quality of  health system and identification of problem arises in  the implementation of the programme. This monitoring process will recognize good practices and help services providers to maintain their high level achievement in services delivery.

Supportive supervision  play  the key role to achieve  Physical and Financial target set under  NHM. The State therefore will put up all necessary efforts in monitoring and supervision through field visit from State Headquarters to District  to  CHC/PHC/Main Centre to Sub Centre on monthly and quarterly basis  for  Physical and Financial performance of all programme under NRHM.

State level and District level monitoring team are already in place. At the state level the team is led by Mission Director and other members are Programme Officers, Nodal Officer / Consultant and other designated staff. Chief Medical Officer of the respective district are monitoring team leaders, Other member are SMO/DIO, DPM, Accounts Managers, DEO etc. All the monitoring visits will be incorporated with  the Prescribed formats of Govt. of India, Ministry of Health and Family Welfare.

Supportive supervision will cover the following items  .

- Maternal Health

Supportive supervision of implementation of JSSK, JSY, VHND, tracking of pregnant mother and anaemic pregnant mother.  Availability of Infrastructure, Skill based trained HR and supply of drugs and equipments at Delivery point.

- Child Health

Attention will be given for tracking of child immunisation, LBW and anaemic children. And also for infant death review and Auditing system implemented in the state.

- Family Planning

Under family planning, supportive supervision of services deliver by Skill based trained HR for IUCD insertion, MTP, mini-lap and post partum tubectomy.  It will also attempt to recognise for which method of family planning services un-met need prevail in those areas. Compensation claims for acceptors and Sterilisation failure and following death Insurance claims   for Permanent family planning methods users. Update of IUCD acceptors and availability of Oral pills, Condoms and IUCD kit.

- ARSH and School Health

Supportive supervision on School health team and fix day static at facilities.

- Immunisation

Increasing full immunisation, Prevalence of drop out children from BCG to Measles, session planed and vaccine indent procedures and cold chain management will be given priority.

- Skill based training and services delivery

Posting of Skill based trained HR at facility and their performance reports and returns.

- Infrastructures, supply of drugs and equipments and Human resources

Requirement of infrastructure at facility, availability essential drugs and equipments, update and indent system. Staff position and evaluation of performance.

- Physical performance and  Financial  reports

Physical performance on specified activity. Performance like JSSK, JSY, Delivery points RTI/STI Maternal and Infant death report under Maternal & Infant Death Review, VHND and Financial reports for utilisation of fund released to the Facility.

- Financial Management

Authentication and guidelines for fund utilisation, maintenance of Cash register, and utilisation report for fund released to the facility.

- Services of ASHA

Monitoring and supervision of ASHA performance, ASHA Mobilisers, Co-ordinators for Health services delivery to assess the overall functionality of ASHA and their contribution in outcomes/output indicators.

- Referral and MMU and Ambulance services

Referral pregnant  mother, sick new-born to facility under JSSK, frequency and services of MMU, Ambulance and services of Call Centre..

Finding and outcomes will be shared at Quarterly State and district level Review meeting and also at monthly CHC/PHC/Main centre level Review meeting. The Findings and action taken thereof will be shared amongst all concerned.

Monthly and quarterly tentative plan for supportive supervision at State, district and CHC/PHC/Main centre level are work out as given below for each of facility. The supportive supervision will be conducted on monthly basis by the monitoring team from State Hqtrs and CHC/PHC/Main centre (inside district capital) respectively and district Hqtrs on quarterly basis.

- SUPPORTIVE SUPERVISION PLAN AT  STATE LEVEL

| S.No | District | Month | Facility | Mission Director | State Programme Manager | Senior Officer of State Directorate/ State Technical Programme Officer |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | April | CHC/DH | Saitual CHC | Sakawrdai CHC, | Saitual CHC |
|  |  |  | PHC | Thingsulthialh | Darlawn | Khawruhlian |
|  |  |  | SC | Keifang SC, Situal SC, | New vervek SC, Vaitin SC | Khawruhlian |
| 2 | Aizawl West | May | CHC/DH | Kulikawn SDH | DH Aizawl West |  |
|  |  |  | PHC | Lengpui PHC | Reiek | Sialsuk |
|  |  |  | SC | Hmunpui SC, Lengte SC | Ailawng, West Lungdar | Sailam, Samlukhai |
| 3 | Champhai | June | CHC/DH | DH Champhai | Ngopa CHC | Biate CHC |
|  |  |  | PHC | Hnahlan | Kawlkulh | Khawhai |
|  |  |  | SC | Tualcheng, Vaikhawtlang | Ngopa Kawlbem | Riangtlei, Tlangmawi |
| 4 | Kolasib | July | CHC/DH | DH Kolasib | Vairengte CHC | DH Kolasib |
|  |  |  | PHC | Kawnpui | Bilkhawthlir | Bukpui |
|  |  |  | SC | Bualpui | Zanlawn | Serkhan |
|  | Lawngtlai | August | CHC/SDH/DH | Lawngtlai DH | Chawngte CHC | Lawngtlai DH |
|  |  |  | PHC | S.Bungtlang | Borapansuri | Vaseitlang |
|  |  |  | SC | M Kawnpui | Borapansuri | Vaseikai |
|  | Lunglei | September | CHC/SDH/DH | Lunglei DH | Hnahthial CHC | Tlabung SDH |
|  |  |  | PHC | Haulawng | S.Vanlaiphai | Bunghmun |
|  |  |  | SC | Ramlaitui | Tuipui D | Kawnpui W |
|  | Mamit | October | CHC/DH | Mamit DH | Mamit DH | Kawrthah CHC |
|  |  |  | PHC | W Phaileng | Rawpuichhip | Zawlnuam |
|  |  |  | SC | W Phaileng | Tuidam | Kanhmun |
|  | Saiha | November | CHC/SDH/DH | Saiha DH | Saiha DH | Saiha DH |
|  |  |  | PHC | Tuipang | Chakhang | Chhuarlung |
|  |  |  | SC | Theiri | Siata | Niawhtlang |
|  | Serchhip | December | CHC/SDH/DH | DH Serchhip | Thenzawl CHC | E Lungdar |
|  |  |  | PHC | Khawlailung | Chhingchhip | Khawlailung |
|  |  |  | SC | Hmuntha | Hriangtlang | Leng, Sailulak |
| 9 | Lawngtlai | January | CHC/SDH/DH | Lawngtlai DH | Sangau PHC | Lawngtlai DH |
|  |  |  | PHC | S Lungpher | Bualpui NG PHC | S.Bungtlang |
|  |  |  | SC | Siachangkawn | Vombuk | Lungtian |
| 11 | Mamit | February | CHC/SDH/DH | Kawrthah CHC | Mamit DH | Mamit DH |
|  |  |  | PHC | Rawpuichhip | W Phaileng | Zawlnuam |
|  |  |  | SC | Rulpuihlim | Silsury | Kanhmun |
| 12 | Saiha | March | CHC/SDH/DH | Saiha DH | Saiha DH | Saiha DH |
|  |  |  | PHC | Chakhang | Chhuarlung | Phura |
|  |  |  | SC | Rawmibawk | Theiri | Lawngban |

| 2.DISTRICT MONITORING FIELD VISIT PLAN FOR CHIEF MEDICAL OFFICER FOR THE YEAR 2014 - 15 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S NO. | Month | Week | Aizawl East | Aizawl West | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip |
| 1 | April | 1 | Saitual SDH, Keifang SC, Situal SC, | Aibawk PHCSateek SC, Phulpui SC | Khawhai PHC, Vangtlang SC, Chalrang SC | Hortoki Sc,Kawnpui SC | Sangau PHC, Lungpher S PHC, Cheural SC, Bualpui NG PHC, Vawmbuk SC | Bunghmun PHC, Laisawral S/C, Sesawm S/C | Rawpuichhip PHC, Dapchhuah clinic | Chakhang PHC, Siata SC, Ainak | Chhingchhip PHC, Hmuntha SC, Hualtu SC |
| 2 |  | 3 | Tualbung SC, Lenchim SC, BuhbanSC | Reiek PHCAilawng SC, West Lungdar SC | Sialhawk PHC, Tlangmawi SC, Tlangpui SC | Bualpui SC,Zanlawn SC,Serkhan SC | DH Lawngtlai, Kawlchaw SC, Paithar SC, Mampui SC &Thingkah SC | Darngawn S/C, Thlengang S/C, Thenhlum S/C | Sabual SC, Damdiai SC, Suarhliap SC | Chhuarlung PHC, Niawhtlang SC, Lungbun SC | Chhingchhip SC, Khawbel SC, Thentlang SC |
| 3 | May | 1 | Sakawrdai CHC, New vervek SC, Vaitin SC | Lengpui PHC(munpui SC, Lengte SC | Hnahlan PHC, Tualcheng SC, Vaikhawtlang SC | N.Chaltlang SC,Bukpui SC,Bukpui PHC | Chawngte CHC, Hmunlai SC, Rualalung & | Tlabung SDH, Nunsuri S/C, Tiperaghat S/C, Chawilung S/C | Darlak SC, Nalzawl, Lungsir clinic | Chakhang SC, Siata SC, Chhuarlung SC | New Serchhip SC, Chhiahtlang SC, Serchhip SC |
| 4 |  | 3 | Mauchar SC, Palsang SC, Tinghmun SC | Chhawlhhmun UHC, Luangmual SC, Chhawlhhmun SC | Mimbung PHC, Mimbung SC, Teikhang SC | Tumpui SC,Hmarveng Sc clinic,Parkkawn Sc clinic | Borapansury PHC, Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Diblibagh S/C, Puankhai S/C, Tuichawng S/C | Mamit SC, Dinthar clinic, Bazar Clinic | N.Saiha SC, Saihatlangkawn SC, N.Coloney Clinic | Sialhau SC, Keitum SC, Serchhip SC |
| 5 | June | 1 | Thingsulthliah PHC, Seling SC, Sesawng SC | Maubuang SC, Thiak SC | NE Khawdungsei PHC, Khawkawn SC, NE Khawdungsei SC | Vairengte CHC,Vairengte SC clinic,Vairengte Sc | Bungtlang PHC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Pangzawl PHC, Rawpui S/C, Pangzawl S/C, Thiltlang S/C | Zawlnuam PHC, Borai SC, Bungthuam SC | Tuipang PHC, Tuipang - L SC, Zawngling SC | Bungtlang SC, Hriangtlang SC, Thenzawl CHC |
| 6 |  | 3 | Baktawng SC, Khumtung SC, Tlungvel SC | Samlukhai SC, Hmuifang SC | Ngopa CHC, Ngopa SC, Kawlbem SC | Bilkhawthlir PHC,Bilkhawthlir SC,Bilkhawthlir SC Clinic | Longpuighat PHCM.Kawnpui SC, Vaseitlang SC, Devasora SC, Ajasora SC, Parva SC. | Hnahthial CHC, Hnahthial S/C, Tuipui D S/C, Leite S/C | Kanhmun SC, Thinghlun SC | Chapui SC, Mohre Clinic, Chheihlu | East Lungdar PHC, Leng SC, Sailulak SC |
| 7 | July | 1 | Darlawn PHC, Sawleng SC, Darlawn SC | Lungleng SC, Melthum SC | Bungzung PHC, Sazep SC, Vanzau SC | Kawnpui SC,Hortoki SC,Dilzau Village | Sangau PHC, Lungpher S PHC, , Cheural SC, Bualpui NG PHC, Vawmbuk SC & Lungzarhtum SC | Tawipui PHC, Mamte S/C, Thingfal S/C, Tawipui S S/C | Kawrtethawveng PHC, Tuidam SC, W. Bunghmun SC | Laki SC, Theiri Sc, Tuisih SC | East Lungdar SC, Mualcheng SC, Khawlailung SC |
| 8 |  | 3 | Sunluchhip Clinic, Chhchchhuahna Clinic | Mission Veng SC, Republic SC | Khawbung PHC, Zawlsei SC, Kuangthing SC | Tuithaveng SC,Rengtekawn SC,Thingdawl SC | DH Lawngtlai, Kawlchaw SC, Paithar SC, Mampui SC &Thingkah SC | Mualcheng S/C, Tawipui N S/C, Mualthuam S S/C | Kawrthah CHC, Rengdil SC, Zamuang SC | Tuipang - V SC, Serkawr SC, Theiva SC | Khawlailung PHC, Lungchhuan SC, N Vanlaiphai PHC |
| 9 | August | 1 | Khawruhlian PHC, Khawruhlian SC | Khatla SC, Bungkawn SC | Farkawn PHC, Khawkawn SC, Vaphai | Bairabi SC,Pangbalkawn Sc,Buhchangphai SC | Chawngte CHC, Hmunlai SC, Rualalung SC | Haulawng PHC, Hnahchang S/C, Haulawng S/C, Lalveng Clinic | Hriphaw SC, Saikhawthlir SC, Chuhvel SC | Tongkolong SC, Phura PHC, Phura SC | N Vanlaiphai SC, Lungkawlh SC, South Chawngtui SC |
| 10 |  | 3 | E Phaileng SC, Pehlawn Clinic, Kepran SC | Vaivakawn SC, Zotlang SC | Khawzawl PHC, Neihdawn SC, Chawngtlai SC | Bilkhawthlir SC,N.Chawnpui SC,Saiphai SC | Borapansury PHC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Mualthuam N S/C, Ramlaitui S/C, Sekhum Clininc | Marpara PHC, Silsuri SC | Vahai SC, Latawh SC, Zero SC | Thenzawl CHC, Thenzawl clinic, Thenzawl West SC |
| 11 | September | 1 | Phuaibuang PHC, Phuaibuang SC | Sakawrtuichhun SC, Maubawk SC | Kawlkulh PHC, Dulte SC, Pawlrang SC | Vairengte SC,Vairengte CHC,Phaisen SC | Bungtlang PHC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Chhipphir PHC, Zote S/C, Chhipphir S/C, Bualpui V S/C | Phuldungsei PHC, Pukzing SC | Meisatla SC, Old Saiha SC, College Veng SC | Kanan clinic, Buangpui SC, Neihloh clinic |
| 12 |  | 3 | Khawlian SC, Daido SC, NE Tlangnuam Clinic | Upper Republic SC, Dam Veng SC | Rabung PHC, Rabung SC, Khualen SC | Saiphai SC,Saipum Sc,N,Chawnpui SC | Longpuighat PHC M.Kawnpui SC, Vaseitlang SC, Devasora SC, Ajasora SC, Parva SC. | Lungsen PHC, Lungsen S/C, Rangte Clininc, Phairuangkai S/C | Kawnmawi clinic, Parvatui SC | Phura PHC, Lungpuk SC, Miepu SC | Kanghmun South SC, Ngentiang PHC, Lungpho SC |
| 13 | October | 1 | Suangpuilawn PHC, Suangpuilawn SC | Khatla SC, Bungkawn SC | Bulfekzawl SC, Dilkawn SC, Lianpui SC | Phainuam SC,Phaisen SC,thinglian Village | Sangau PHC, Lungpher S PHC, Cheural SC, Bualpui NG PHC, Vawmbuk SC & Lungzarhtum SC | Buarpui PHC, Sertre S/C, Sertlang S/C, Kawlhawk S/C | W.Phaileng PHC, Lallen SC | Tuipui Ferry SC, Romibok SC, Phalhrang SC | Thinglian SC, Rullam SC, Ngentiang PHC |
| 14 |  | 3 | Vanbawng SC, N Khawlek SC | Sialsuk PHC, Sailam SC, Samlukhai SC | Kelkawng SC, Khuangleng SC, Melbuk Clinic | N.Chawnpui Sc,Saiphai SC,Saipum SC | DH Lawngtlai, Kawlchaw SC, Paithar SC, Mampui SC &Thingkah SC | Buarpui PHC, Changpui S/C, Khawlek S/C, Dengsur Clinic | Damparengpui SC, Tupuibari SC, Rajiv Nagar clinic, | Chakhang PHC, Siata SC, Ainak | Chhingchhip PHC, Hmuntha SC, Hualtu SC |
| 15 | November | 1 | Phullen PHC, Phullen SC | Kanghmun PHC, Khawrihnim SC, West Lungdar SC | Hmunhmeltha SC, Ngur SC, Zote SC | Bairabi PHC,Phaisen SC | Chawngte CHC, , Hmunlai SC, Chawngte C SC, Chawngte P SC | Bunghmun PHC, Bunghmun S/C, Laisawral S/C, Sesawm S/C | Dampui SC, Rulpuihlim SC | Chhuarlung PHC, Niawhtlang SC, Lungbun SC | Hmuntha SC, Khawbel SC, Thentlang SC |
| 16 |  | 3 | Zawngin Clinic, Thanglailung SC | Sairang PHC, Mualkhang SC, West Serzawl SC | Zotlang SC, Ruantlang SC, Mualkawi Clinic | Lungmuat SC,Lungdai SC,Lungdai PHC | Borapansury PHC, Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Kawnpui S/C, Darngawn S/C, Thlengang S/C, Thenhlum S/C | Damdiai SC, Suarhliap SC | Chakhang SC, Siata SC, Chhuarlung SC | New Serchhip SC, Chhiahtlang SC, Chhingchhip SC |
| 17 | December | 1 | Ramhlun UHC, | Hlimen UHC, Melthum SC, Tlangnuam SC | Arro Clinic, Hmuncheng SC, Electric Clinic | Bukpui PHC,N.Hlimen SC,Bukpui SC | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Tlabung SDH, Nunsuri S/C, Tiperaghat S/C, Chawilung S/C | Kawrthah CHC, Rengdil SC, Zamuang SC | N.Saiha SC, Saihatlangkawn SC, N.Coloney Clinic | Sialhau SC, Keitum SC, Serchhip SC |
| 18 |  | 3 | Zemabawk SC, Zemabawk Clinic, Tuiraial SC | Tachhip SC, Lamchhip SC | Ngaizawl SC, Kawnzar Clinic, Khawzawl SC | N.Chawnpui SC,Saiphai SC,Saipum SC | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, Devasora SC, Ajasora SC, Parva SC. | Diblibagh S/C, Puankhai S/C, Tuichawng S/C | Hriphaw SC, Saikhawthlir SC | Tuipang PHC, Tuipang - L SC, Zawngling SC | Bungtlang SC, Hriangtlang SC, Thenzawl CHC |
| 19 | January | 1 | ITI UHC | Muallungthu SC, Aibawk SC | Sazep SC, Vanzau SC, Dungtlang SC | Bilkhawthlir SC,Phaisen Sc,Phainuam SC | Sangau PHC, Sangau SC Lungpher SC, Cheural SC, Bualpui NG PHC, Vawmbuk SC & Lungzarhtum SC | Pangzawl PHC, Rawpui S/C, Pangzawl S/C, Thiltlang S/C | Damparengpui SC, Tuipuibari SC, Rajiv Nagar clinic | Chapui SC, Mohre Clinic, Chheihlu | East Lungdar PHC, Leng SC, Sailulak SC |
| 20 |  | 3 | Bethlehem SC, Bethlehem Clinic, Venghlui SC | Lengpui SC, Sairang SC | Kawlkulh SC, Hliappui SC, Pawlrang SC | Kawnpui PHC,Kawnpui SC Clinic,Hortoki CS | DH Lawngtlai, , College veng SC, Lawngtlai I SC, Mampui SC | Hnahthial CHC, Hnahthial S/C, Tuipui D S/C, Leite S/C | Marpara PHC, Silsuri SC | Laki SC, Theiri Sc, Tuisih SC | East Lungdar SC, Mualcheng SC, Khawlailung SC |
| 21 | February | 1 | Sihphir SC, Sihphir VT Clinic, Durtlang N Clinic | Chhawlhhmun UHC, Luangmual SC, Chhawlhhmun SC | Tualcheng SC, Vaikhawtlang SC, Khuangphah SC | Bukpui SC,Bukpui PHC,N.Chaltlang SC | Chawngte CHC, Chawngte MC, Hmunlai SC, Chawngte C SC, Rualalung & Chawngte P SC | Vanlaiphai PHC, Muallianpui S/C, Darzo S/C, Vanlaiphai S/C | W.Phaileng PHC, Lallen SC, Kawnmawi clinic | Tuipang - V SC, Serkawr SC, Theiva SC | Khawlailung PHC, Lungchhuan SC, N Vanlaiphai PHC |
| 22 |  | 3 | Muthi Clinic, TNT Clinic, Thuampui SC | Maubuang SC, Thiak SC | Sialhawk SC, Riangtlei SC, Tlangpui SC | Diakkon SC,Thingdawl SC,Khuangpuilam Clinic | Borapansury PHC, Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Cherhlun PHC, Cherhlun S/C, Thingsai S/C, Bualpui H S/C | Mamit SC, Dinthar clinic, Bazar Clinic | Tongkolong SC, Phura PHC, Phura SC | N Vanlaiphai SC, Lungkawlh SC, South Chawngtui SC |
| 23 | March | 1 | Armed Veng, Ramthar Clinic, Chhinga Veng SC | Samlukhai SC, Hmuifang SC | Dulte SC, Kawlkulh SC, Kawlkulh PHC | Lungdai PHC,Lungdai SC,Zanlawn SC | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Tawipui PHC, Mamte S/C, Thingfal S/C, Tawipui S S/C | Phuldungsei PHC, Pukzing SC | Vahai SC, Latawh SC, Zero SC | Thenzawl CHC, Thenzawl clinic, Thenzawl West SC |
| 24 |  | 3 | Tuithiang Clinic, Bazar SC, Electric SC | Kanghmun SC, Hreicuk SC | Biate CHC, Riangtlei SC, Tlangmawi SC | Serkhan SC,Lungmuat SC,Nisapui SC | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, Devasora SC, Ajasora SC, Parva SC. | Mualcheng S/C, Tawipui N S/C, Mualthuam S S/C | Kanhmun SC, Borai SC, Thinghlun SC | Meisatla SC, Old Saiha SC, College Veng SC | Kanan clinic, Buangpui SC, Neihloh clinic |

| 3.DISTRICT MONITORING FIELD VISIT PLAN FOR DISTRICT PROGRAMME MANAGER FOR THE YEAR 2014 - 15 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S NO. | Month |  | Aizawl East | Aizawl West | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip |
| 1 | April | 1 | Thingsulthliah PHC, Thingsulthliah SC, | Aibawk PHC, Sateek SC, Phulpui SC | Khawzawl PHC, Ngaizawl SC, Darngawn SC | Vairengte CHC,Vairengte SC | Sangau PHC, Pangkhua SC, Rawlbuk SC & Sangau SC | Tawipui, Mamte, Thingfal, Thualthu | Zawlnuam PHC, Borai SC, Bungthuam SC | Chakhang PHC,Siata SC,Ainak | Chhingchhip PHC,Hmuntha SC,Hualtu SC |
| 2 |  | 2 | Baktawng SC, Khumtung SC, Tlungvel SC | Sialsuk PHC, Sailam SC, Samlukhai SC | Kawlkulh PHC, Kawlkulh SC, Dulte SC | Bairabi PHC,Pangbalkawn SC,Buhchangphai SC | Lungpher S PHC, Lungpher SC, Lungtian SC, Cheural SC & Vawmbuk SC | Mualcheng, Tawipui N, Tawipui S | Kanhmun SC,Thinghlun SC,New Eden SC | Chhuarlung PHC,Niawhtlang SC,Lungbun SC | Chhingchhip SC,Khawbel SC,Thentlang SC |
| 3 |  | 3 | Seling SC & Sesawng SC | Reiek PHC, Ailawng Sc, West Lungdar SC | Arro Clinic, Chawngtlai SC, Kawnzar Clinic | Bilkhawthlir PHC,Bilkhawthlir SC,Thinglian Village | Bualpui NG PHC, Siachangkawn SC, Bualpui SC & Lungzarhtum SC | S Vanlaiphai PHC, Darzo, Vanlaiphai, Muallianpui | Kawrtethawveng PHC,Tuidam SC,Bunghmun SC | Chakhang SC,Siata SC,Chhuarlung SC | New Serchhip SC,Chhiahtlang SC,Serchhip SC |
| 4 |  | 4 | Sakawrdai CHC & N. Vervek SC | Kanghmun PHC, Khawrihnim Sc, Lungdar SC | Electric Clinic, Neihdawn SC, Hmuncheng Clinic | Vairengte SC Clinic,Phainuam SC,Phaisen SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Leite , Tuipui D, Rotlang E | Kawrthah CHC,Rengdil SC,Zamuang SC | N.Saiha SC,Saihatlangkawn SC,N.Coloney Clinic | Sialhau SC,Keitum SC,Serchhip SC |
| 5 | May | 1 | Sakawrdai SC, Vaitin SC & Khawpuar Clinic | Lengpui PHC, Hmunpui SC, Lengte SC | Khawhai PHC, Vangtlang SC , Chalrang SC | Kawnpui PHC,Kawnpui SC | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Bunghmun, Bunghmun, Laisawral, Sesawm | W. Phaileng PHC,Kawnmawi clinic,Lallen SC | Tuipang PHC,Tuipang - L SC,Zawngling SC | Bungtlang SC,Hriangtlang SC,Thenzawl CHC |
| 6 |  | 2 | Zohmun SC, Palsang SC & Thingsat SC | Sairang PHC, Mualkhang Sc, West Serzawl Sc | Sialhawk PHC, Tlangmawi SC, Tlangpui SC | Bualpui SC,Bairabi PHC,Pangbalkawn SC | Chawngte CHC, Chawngte MC, Hmunlai SC, Chawngte C SC, Rualalung & Chawngte P SC | Kawnpui, Darngawn, Thlengang, Thenhlum | Tuipuibari SC,Damparengpui SC,Rajiv Nagar SC | Chapui SC,Mohre Clinic,Chheihlu | East Lungdar PHC,Leng SC,Sailulak SC |
| 7 |  | 3 | Tinghmun SC & Mauchar SC | Chawlhhmun UHC, | Biate CHC, Biate SC, Riangtlei SC | Bukpui PHC,Bukpui SC,N.Chaltlang SC | Borapansury PHC, Borapansury MC, Borapansury SC & Jarulsury SC | Buarpui PHC, Serte, Sertlangpui, Kawlhawk | Phuldungsei PHC,Pukzing SC,Parvatui SC | Laki SC,Theiri Sc,Tuisih SC | East Lungdar SC,Mualcheng SC,Khawlailung SC |
| 8 |  | 4 | Darlawn PHC, Darlawn SC & Sawleng SC | Luangmual SC, Chawlhhmun SC | Rabung PHC, Rabung SC, Khualen Clinic | Lungdai PHC,Lungdai SC,Serkhan SC | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Dengsur, Buarpui S/C, Khawlek S/C | Marpara PHC,Silsuri SC,Marpara S SC | Tuipang - V SC,Serkawr SC,Theiva SC | Khawlailung PHC,Lungchhuan SC,N Vanlaiphai PHC |
| 9 | June | 1 | Ratu SC & Sailutar Clinic | Maubuang Sc, Thiak Sc | Hnahlan PHC, Tualcheng SC, Vaikhawtlang SC | Bairabi PHC,Bairabi SC,Buhchangphai SC | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, | Hnahthial CHC, Hnahthial S/C, Thiltlang S/C, Tarpho S/C | Hriphaw SC,Saikhawthlir SC,Chuhvel SC | Tongkolong SC,Phura PHC,Phura SC | N Vanlaiphai SC,Lungkawlh SC,South Chawngtui SC |
| 10 |  | 2 | N. Serzawl SC, Sunhluchhip Clinic & Chhanchhuahna Clinic | Tachhip Sc, Lamchhip SC | Mimbung PHC, Teikhang SC, Mimbung SC | Kawnpui SC,Bualpui SC,Kawnpui SC Clinic | Devasora SC, Ajasora SC, Parva SC, & | Pangzawl PHC, Rawpui S/C, Pangzawl S/C | Damdiai SC,Suarhliap SC | Vahai SC,Latawh SC,Zero SC | Thenzawl CHC,Thenzawl clinic,Thenzawl West SC |
| 11 |  | 3 | Khawrulian PHC, Khawruhlian SC, Khanpui SC | Samlukhai Sc, Hmuifang SC | N.E Khawdungsei PHC, N.E Khawdungsei SC, Khawkawn SC | Bilkhawthlir SC,N.Chawnpui SC,Vairengte SC Clinic | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Theiriat S/C, Lunglawn S/C, Farmveng S/C, Salem S/C | Darlak SC,Nalzawl SC,Lungsir Clinic | Meisatla SC,Old Saiha SC,College Veng SC | Kanan clinic,Buangpui SC,Neihloh clinic |
| 12 |  | 4 | E. Phaileng SC, Pehlawn Clinic & Kepran SC | Muallungthu Sc, Aibawk Sc | Ngopa CHC, Ngopa SC, Kawlbem SC | Bilkhawthlir PHC,Saipum SC,Saiphai SC | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Luangmual S/C, Electrict S/C, Chanmari S/C | Mamit SC,Bazar Clinic,Dinthar Clinic | Phura PHC,Lungpuk SC,Miepu SC | Kanghmun South SC,Ngentiang PHC,Lungpho SC |
| 13 | July | 1 | Saitual SDH & Saitual SC | Kanghmun Sc, Hreichuk Sc | Bungzung PHC, Sazep SC, Vanzau SC | Lungdai PHC,Serkhan SC,Zanlawn SC | Sangau PHC, Pangkhua SC, Rawlbuk SC & Sangau SC | Cherhlun PHC, Cherhlun S/C, Thingsai S/C, New Ngharchhip S/C, Bualpui H S/C | Rawpuichhip PHC,Dapchhuah Clinic,Rulpuihlim SC | Tuipui Ferry SC,Romibok SC,Phalhrang SC | Thinglian SC,Rullam SC,Ngentiang PHC |
| 14 |  | 2 | Keifang SC, Rulchawm SC & Ruallung Clinic | Lengpui Sc, Sairang Sc | Khawbung PHC, Zawlsei SC, Khuangthing Sc | Kawnpui PHC,Khamrang SC,Kawnpui SC | Lungpher S PHC, Lungpher SC, Lungtian SC, Cheural SC & Vawmbuk SC | Pukpui S/C, Zotlang S/C, Zohnuai S/C, Serkawn Clinic | Tuahzawl SC,Dampui SC,Dapchhuah Clinic | Chakhang PHC,Siata SC,Ainak | Chhingchhip PHC,Hmuntha SC,Hualtu SC |
| 15 |  | 3 | Lenchim SC, Mualpheng Clinic & Maite SC | Falkawn Ref.Hopital, Kulikawn Hospital | Farkawn PHC, Khawkawn SC, Vaphai SC | Bairabi SC,Bairabi PHC,Pangbalkawn SC | Bualpui NG PHC, Siachangkawn SC, Bualpui SC & Lungzarhtum SC | Tlabung SDH, Zodin S/C, Nunsuri S/C, DIblibagh S/C, Tuichawng S/C | Zawlnuam,Borai,Bungthuam | Chhuarlung PHC,Niawhtlang SC,Lungbun SC | Hmuntha SC,Khawbel SC,Thentlang SC |
| 16 |  | 4 | Sihfa SC, Tualbung SC, Dilkhan Clinic | Melriat Sc, Hualngohmun Sc | Bulfekzawl SC, Khuangleng SC, Mualkawi Clinic | Bukpui PHC,N.Hlimen SC,N.Chaltlang SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Tiperaghat S/C, Chawilung S/C, Puankhai S/C | Kanhmun,Thinghlun,New Eden | Chakhang SC,Siata SC,Chhuarlung SC | New Serchhip SC,Chhiahtlang SC,Chhingchhip SC |
| 17 | August | 1 | Buhban SC & N. Lungpher Clinic |  | Khawzawl PHC, Neihdawn Sc, Chawngtlai SC | Bairabi PHC,Pangbalkawn SC,Buhchangphai SC | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Haulawng PHC, Haulawng S/C, Hnahchang S/C, Lalveng Clinic | Kawrtethawveng PHC,Tuidam SC,Bunghmun SC | N.Saiha SC,Saihatlangkawn SC,N.Coloney Clinic | Sialhau SC,Keitum SC,Serchhip SC |
| 18 |  | 2 | Phullen PHC & Phullen SC |  | Kawlkulh PHC , Hliappui SC, Pawlrang SC | Bukpui PHC,N.Hlimen SC,N,Chaltlang SC | Chawngte CHC, Chawngte MC, Hmunlai SC, Chawngte C SC, Rualalung & Chawngte P SC | Mualthuam N S/C, Ramlaitui S/C, Sekhum Clinic | Kawrthah CHC,Rengdil SC,Zamuang SC | Tuipang PHC,Tuipang - L SC,Zawngling SC | Bungtlang SC,Hriangtlang SC,Thenzawl CHC |
| 19 |  | 3 | Thanglailung SC & Zawngin Clinic |  | Zotlang Clinic, Ruantlang SC, Mualkawi clinic | Bilkhawthlir PHC,Saipum SC,Saiphai SC | Borapansury PHC, Borapansury MC, Borapansury SC & Jarulsury SC | Chhipphir PHC, Bualpui V S/C, Zote S/C, Chhipphir S/C | W. Phaileng PHC,Kawnmawi clinic,Lallen SC | Chapui SC,Mohre Clinic,Chheihlu | East Lungdar PHC,Leng SC,Sailulak SC |
| 20 |  | 4 | Suangpuilawn PHC & Suangpuilawn SC |  | Ngur Sc, Tlangsam SC, Hmunhmeltha SC | Kawnpui PHC,Kawnpui SC,Kawnpui SC clinic | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Venglai S/C, Venghlun S/C, Rahsiveng S/C, Hauruang S/C | Tuipuibari SC,Damparengpui SC,Rajiv Nagar SC | Laki SC,Theiri Sc,Tuisih SC | East Lungdar SC,Mualcheng SC,Khawlailung SC |
| 21 | September | 1 | Vanbawng SC & N. Khawlek SC | Lungleng SC, Melthum Sc | Zote SC, Zokhawthar SC, Sesih SC | Bilkhawthlir PHC,Saiphai SC,N.Chawnpui SC | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, | Tawipui, Mamte, Thingfal, Thualthu | Phuldungsei PHC,Pukzing SC,Parvatui SC | Tuipang - V SC,Serkawr SC,Theiva SC | Khawlailung PHC,Lungchhuan SC,N Vanlaiphai PHC |
| 22 |  | 2 | Phuaibuang PHC, Phuaibuang SC | Tlangnuam Sc, Salem Sc | Sazep SC, Vanzau SC, Dungtlang SC | Vairengte CHC,Saipum SC | Devasora SC, Ajasora SC, Parva SC, & | Mualcheng, Tawipui N, Tawipui S | Marpara PHC,Silsuri SC,Marpara S SC | Tongkolong SC,Phura PHC,Phura SC | N Vanlaiphai SC,Lungkawlh SC,South Chawngtui SC |
| 23 |  | 3 | Khawlian SC, N>E Tlangnuam Clinic, Daido SC | Mission Veng Sc, Republic Sc | Farkawn SC, Farkawn PHC, Vaphai SC | Bairabi PHC,Baairabi SC,Pangbalkawn SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | S Vanlaiphai PHC, Darzo, Vanlaiphai, Muallianpui | Hriphaw SC,Saikhawthlir SC,Chuhvel SC | Vahai SC,Latawh SC,Zero SC | Thenzawl CHC,Thenzawl clinic,Thenzawl West SC |
| 24 |  | 4 | Ramhlun UHC & ITI UHC | Venghnuai Sc, Kulikawn Sc | Samthang SC, Khuangthing SC, Khawbung PHC | Kawnpui PHC,Kawnpui SC,Hortoki SC | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Leite , Tuipui D, Rotlang E | Damdiai SC,Suarhliap SC | Meisatla SC,Old Saiha SC,College Veng SC | Kanan clinic,Buangpui SC,Neihloh clinic |
| 25 | October | 1 | Edenthar SC, Chanmari SC & Chanmari Clinic | Khatla Sc, Bungkawn Sc | Biate SC, Riangtlei SC, Tlangmawi clinic | Bukpui PHC,N.Hlimen SC,Bukpui SC | Sangau PHC, Pangkhua SC, Rawlbuk SC & Sangau SC | Bunghmun, Bunghmun, Laisawral, Sesawm | Darlak SC,Nalzawl SC,Lungsir Clinic | Phura PHC,Lungpuk SC,Miepu SC | Kanghmun South SC,Ngentiang PHC,Lungpho SC |
| 26 |  | 2 | Electric SC, Ramthar Clinic & Chhinga veng SC | Tuikual Sc, Dinthar Sc | Hnahlan SC, Vaikhawtlang SC, Tualcheng SC | Lungdai PHC,Zanlawn SC,Serkhan SC | Lungpher S PHC, Lungpher SC, Lungtian SC, Cheural SC & Vawmbuk SC | Kawnpui, Darngawn, Thlengang, Thenhlum | Mamit SC,Bazar Clinic,Dinthar Clinic | Tuipui Ferry SC,Romibok SC,Phalhrang SC | Thinglian SC,Rullam SC,Ngentiang PHC |
| 27 |  | 3 | Bazar SC, Zarkawt Clinic & Tuithiang Clinic | Vaivakawn Sc, Zotlang Sc | Dilkawn SC, Kelkang SC, Sesih SC | Kawnpui PHC,Bualpui SC,Kawnpui SC | Bualpui NG PHC, Siachangkawn SC, Bualpui SC & Lungzarhtum SC | Buarpui PHC, Serte, Sertlangpui, Kawlhawk | Rawpuichhip PHC,Dapchhuah Clinic,Rulpuihlim SC | Chakhang PHC,Siata SC,Ainak | Chhingchhip PHC,Hmuntha SC,Hualtu SC |
| 28 |  | 4 | Armed Veng SC, Venghlui SC, College veng Clinic | Luangmual Sc, Tanhril Sc | Venglai SC, Vengthlang SC, Kanan SC | Lungdai PHC,Lungdai SC,Lungmuat SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Dengsur, Buarpui S/C, Khawlek S/C | Tuahzawl SC,Dampui SC,Dapchhuah Clinic | Chhuarlung PHC,Niawhtlang SC,Lungbun SC | Hmuntha SC,Khawbel SC,Thentlang SC |
| 29 | November | 1 | Bethlehem SC, Bethlehem Clinic | Sakawrtuichhun, Maubawk Sc | Mimbung phc, Mimbung s.c, Teikhang sc | Bilkhawthlir SC,Tumpui SC,Bilkhawthlir SC Clinic | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Hnahthial CHC, Hnahthial S/C, Thiltlang S/C, Tarpho S/C | Zawlnuam,Borai,Bungthuam | Chakhang SC,Siata SC,Chhuarlung SC | New Serchhip SC,Chhiahtlang SC,Chhingchhip SC |
| 30 |  | 2 | Sihphir SC & Sihphur Clinic, | Lawipu Sc, Mission veng North Sc | N.E.K.D.S PHC, Khawkawn SC, Chiahpui Clinic | Diakkon SC,Salem SC clinic,Parkkawn linic | Chawngte CHC, Chawngte MC, Hmunlai SC, Chawngte C SC, Rualalung & Chawngte P SC | Pangzawl PHC, Rawpui S/C, Pangzawl S/C | Kanhmun,Thinghlun,New Eden | Chakhang PHC,Siata SC,Ainak | Sialhau SC,Keitum SC,Serchhip SC |
| 31 |  | 3 | Durtlang SC, Durtlang Mel 5 Clinic, Durtlang N Clinic | Upper Republic Sc, Dam Veng Sc | Ngopa CHC, Ngopa sc, Kawlbem sc | Hmar Veng Sc clinic,College veng clinic,Tuithaveng SC | Borapansury PHC, Borapansury MC, Borapansury SC & Jarulsury SC | Theiriat S/C, Lunglawn S/C, Farmveng S/C, Salem S/C | Kawrtethawveng PHC,Tuidam SC,Bunghmun SC | Chhuarlung PHC,Niawhtlang SC,Lungbun SC | Bungtlang SC,Hriangtlang SC,Thenzawl CHC |
| 32 |  | 4 | Tuirial SC, Zemabawk SC, Zemabawk Clinic | Sihhmui Sc, Rangvamual SC | Venglai sc, vengtlang sc, new champhai sc | Rengtekawn SC,Tuithaveng SC,Thingdawl SC | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Luangmual S/C, Electrict S/C, Chanmari S/C | Kawrthah CHC,Rengdil SC,Zamuang SC | Chakhang SC,Siata SC,Chhuarlung SC | East Lungdar PHC,Leng SC,Sailulak SC |
| 33 | December | 1 | Falkland Clinic, Thuampui Clinic, Zuangtui SC | Khatla Sc, Bungkawn Sc | Zotlang Clinic, Ruantlang SC, Mualkawi Clinic | Zanlawn SC,Lungmuat SC,Nisapui SC | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, | Cherhlun PHC, Cherhlun S/C, Thingsai S/C, New Ngharchhip S/C, Bualpui H S/C | Kawrthah CHC,Rengdil SC,Zamuang SC | N.Saiha SC,Saihatlangkawn SC,N.Coloney Clinic | East Lungdar SC,Mualcheng SC,Khawlailung SC |
| 34 |  | 2 | TNT Clinic & Muthi Clinic | CIVIL HOSPITAL | Dilkawn SC, Kelkang SC, Sesih SC | Lungdai PHC,Lungdai SC,Kawnpui Sc clinic | Devasora SC, Ajasora SC, Parva SC, & | Pukpui S/C, Zotlang S/C, Zohnuai S/C, Serkawn Clinic | W. Phaileng PHC,Kawnmawi clinic,Lallen SC | Tuipang PHC,Tuipang - L SC,Zawngling SC | Khawlailung PHC,Lungchhuan SC,N Vanlaiphai PHC |
| 35 |  | 3 | Chaltlang SC, Chaltlang N'Clinic, Laipuitlang Clinic | Aibawk PHC, Sateek SC, Phulpui SC | Kanan SC, Vengsang SC, Electric SC | Bukpui PHC,N.Chaltlang SC,N.Hlimen Sc | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Tlabung SDH, Zodin S/C, Nunsuri S/C, DIblibagh S/C, Tuichawng S/C | Tuipuibari SC,Damparengpui SC,Rajiv Nagar SC | Chapui SC,Mohre Clinic,Chheihlu | N Vanlaiphai SC,Lungkawlh SC,South Chawngtui SC |
| 36 |  | 4 | Bawngkawn SC & Bawngkawn S' Clinic | Sialsuk PHC, Sailam SC, Samlukhai SC | Venglai SC, Vengthlang SC, Tlangsam SC | Vairengte CHC,Vairengte SC,Vairengte SC Clinic | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Tiperaghat S/C, Chawilung S/C, Puankhai S/C | Phuldungsei PHC,Pukzing SC,Parvatui SC | Laki SC,Theiri Sc,Tuisih SC | Thenzawl CHC,Thenzawl clinic,Thenzawl West SC |
| 37 | January | 1 | Ramhlun SC, Ramhlun VT Clinic, Ramhlun S' Clinic | Reiek PHC, Ailawng Sc, West Lungdar SC | Neihdawn SC, Ngaizawl SC, Kawnzar Clinic | Bilkhawthlir PHC,Bilkhawthlir SC,Bilkhawthli SC clinic | Sangau PHC, Pangkhua SC, Rawlbuk SC & Sangau SC | Haulawng PHC, Haulawng S/C, Hnahchang S/C, Lalveng Clinic | Marpara PHC,Silsuri SC,Marpara S SC | Tuipang - V SC,Serkawr SC,Theiva SC | Kanan clinic,Buangpui SC,Neihloh clinic |
| 38 |  | 2 | Thingsulthliah PHC, Thingsulthliah SC, | Kanghmun PHC, Khawrihnim Sc, Lungdar SC | Mimbung SC, Teikhang SC, Hrianghmun SC | Vairengte SC clinic,Phaisen SC,Phainuam SC | Lungpher S PHC, Lungpher SC, Lungtian SC, Cheural SC & Vawmbuk SC | Mualthuam N S/C, Ramlaitui S/C Sekhum Clinic | Hriphaw SC,Saikhawthlir SC,Chuhvel SC | Tongkolong SC,Phura PHC,Phura SC | Kanghmun South SC,Ngentiang PHC,Lungpho SC |
| 39 |  | 3 | Baktawng SC, Khumtung SC, Tlungvel SC | Lengpui PHC, Hmunpui SC, Lengte SC | N.E.K.D.S PHC, Khawkawn sc, chiahpui clinic | Kawnpui PHC,Hortoki SC,Kawnpui SC | Bualpui NG PHC, Siachangkawn SC, Bualpui SC & Lungzarhtum SC | Chhipphir PHC, Bualpui V S/C, Zote S/C, Chhipphir S/C | Damdiai SC,Suarhliap SC | Vahai SC,Latawh SC,Zero SC | Thinglian SC,Rullam SC,Ngentiang PHC |
| 40 |  | 4 | Seling SC & Sesawng SC | Sairang PHC, Mualkhang Sc, West Serzawl Sc | Ngopa CHC, ngopa sc, kawlbem sc | Zanlawn SC,Serkhan SC,Bualpui SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Venglai S/C, Venghlun S/C, Rahsiveng S/C, Hauruang S/C | Darlak SC,Nalzawl SC,Lungsir Clinic | Meisatla SC,Old Saiha SC,College Veng SC | Chhingchhip PHC,Hmuntha SC,Hualtu SC |
| 41 | February | 1 | Sakawrdai CHC & N. Vervek SC | Chawlhhmun UHC, | Kawlkulh phc, Pawrang sc, Hliappui SC | Bairabi SC,Bairabi PHC,Pangbalkawn SC | Bungtlang PHC, Bungtlang MC, Bungtlang SC, Mampui SC, Khawmawi & Diltlang SC | Tawipui, Mamte, Thingfal, Thualthu | Mamit SC,Bazar Clinic,Dinthar Clinic | Phura PHC,Lungpuk SC,Miepu SC | Hmuntha SC,Khawbel SC,Thentlang SC |
| 42 |  | 2 | Sakawrdai SC, Vaitin SC & Khawpuar Clinic | Luangmual SC, Chawlhhmun SC | Rabung phc, Rabung sc, khualen clinin | Rengtekawn SC,Tuithaveng SC,tumpui SC | Chawngte CHC, Chawngte MC, Hmunlai SC, Chawngte C SC, Rualalung & Chawngte P SC | Mualcheng, Tawipui N, Tawipui S | Rawpuichhip PHC,Dapchhuah Clinic,Rulpuihlim SC | Tuipui Ferry SC,Romibok SC,Phalhrang SC | New Serchhip SC,Chhiahtlang SC,Chhingchhip SC |
| 43 |  | 3 | Zohmun SC, Palsang SC & Thingsat SC | Hlimen UHC, Melthum SC, Tlangnuam SC | Khawzaw phc, ARRO clinic, Electric clinic | Bairabi SC,Bairabi PHC,Pangbalkawn SC,Buhchangphai SC | Borapansury PHC, Borapansury MC, Borapansury SC & Jarulsury SC | S Vanlaiphai PHC, Darzo, Vanlaiphai, Muallianpui | Tuahzawl SC,Dampui SC,Dapchhuah Clinic | Chakhang PHC,Siata SC,Ainak | Sialhau SC,Keitum SC,Serchhip SC |
| 44 |  | 4 | Tinghmun SC & Mauchar SC | Maubuang Sc, Thiak Sc | Kawnzar clinic, Darngawn clinic, Khawzawl SC | Saiphai SC,Saipum SC,N.Chawnpui SC | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Leite , Tuipui D, Rotlang E | Zawlnuam,Borai,Bungthuam | Chhuarlung PHC,Niawhtlang SC,Lungbun SC | Bungtlang SC,Hriangtlang SC,Thenzawl CHC |
| 45 | March | 1 | Keifang SC, Rulchawm SC & Ruallung Clinic | Samlukhai Sc, Hmuifang SC | Sialhawk SC, Riangtlei SC, Tlangmawi SC | Kawnpui PHC,Kawnpui SC,Kawnpui SC clinic | Longpuighat PHC/MC, M.Kawnpui SC, Vaseitlang SC, | Bunghmun, Bunghmun, Laisawral, Sesawm | Kanhmun,Thinghlun,New Eden | Chakhang SC,Siata SC,Chhuarlung SC | East Lungdar PHC,Leng SC,Sailulak SC |
| 46 |  | 2 | Lenchim SC, Mualpheng Clinic & Maite SC | Muallungthu Sc, Aibawk Sc | Khawhai SC, New Chalrang SC, Chalrang SC | Bairabi SC,Pangbalkawn SC,Buhchangphai SC | Devasora SC, Ajasora SC, Parva SC, & | Kawnpui, Darngawn, Thlengang, Thenhlum | Kawrtethawveng PHC,Tuidam SC,Bunghmun SC | N.Saiha SC,Saihatlangkawn SC,N.Coloney Clinic | East Lungdar SC,Mualcheng SC,Khawlailung SC |
| 47 |  | 3 | Sihfa SC, Tualbung SC, Dilkhan Clinic | Kanghmun Sc, Hreichuk Sc | Hnahlan SC, Vaikhawtlang SC, Khuangphah SC | Bukpui SC,Bukpui PHC,N.Chaltlang SC | Lawngtlai MC, Kawlchaw SC, Paithar SC, College veng SC, Lawngtlai I SC &Thingkah SC | Buarpui PHC, Serte, Sertlangpui, Kawlhawk | Kawrthah CHC,Rengdil SC,Zamuang SC | Tuipang PHC,Tuipang - L SC,Zawngling SC | Khawlailung PHC,Lungchhuan SC,N Vanlaiphai PHC |
| 48 |  | 4 | Buhban SC & N. Lungpher Clinic | Lengpui Sc, Sairang Sc | Bulfekzawl SC, Hruaikawn SC, Khawbung N SC | Bairabi SC,Bairabi PHC,Buhchangphai Sc | Rualalung SC, Lungrang SC, Zehtet SC, Saizawh SC, & Ajasora SC | Dengsur, Buarpui S/C, Khawlek S/C | W. Phaileng PHC,Kawnmawi clinic,Lallen SC | Chapui SC,Mohre Clinic,Chheihlu | N Vanlaiphai SC,Lungkawlh SC,South Chawngtui SC |

4.  Medical Officer at SDH/CHC/PHC/UPHC will  be conducting a Supportive Supervision visit at least twice a month   to 2 weakm performing SCs/ANMs as per GOI guidelines.

5. LHV/CHO at Main Centre  will  be conducting a Supportive Supervision visit  every SC/SC Clinics  and attend all VHND  within their jurisdiction

Budget requirement is estimated as given below.

| Sr.No | Person responsible | Level | Frequency | Rate for POL, Vehicle hiring charges, Other mode of Transports, etc,. | DA | Amount |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mission Director | State | 2 times per month | @5400 per Visit X 2 times per month X 12 months = Rs.129600/- | @500/- per day X 4 days X 2 times per month X 12 months =Rs.48000/- | Rs. 177600/- |
| 2 | State Programme Manager | State |  | @5400 per Visit X 2 times per month X 12 months = Rs.129600/- | @500/- per day X 4 days X 2 times per month X 12 months =Rs. 48000/- | Rs.177600/- |
| 3 | Monitoring Officer/ Other designated Officer | State |  | @5400 per Visit X 2 times per month X 12 months = Rs.129600/- | @500/- per day X 4 days X 2 times per month X 12 months =Rs. 48000/- | Rs.177600/- |
| 4 | Chief Medical Officer | District | 2 times per month | @4320 per Visit X 2 times per month X 12 months X 9 district = Rs. 933120/- | @400/- per day X 4 days X 2 times per month X 12 months X 9 dist.=Rs. 345600/- | Rs. 1278720/- |
| 5 | Senior Medical Officer/ District Immunisation Officer/ Other Health Officer | District | 4 times per month | @4320 per Visit X 2 times per month X 12 months X 9 district = Rs. 933120/- | @400/- per day X 4 days X 2 times per month X 12 months X 9 dist.=Rs. 345600/- | Rs. 1278720/- |
| 6 | District Programme Manager | District |  | @2500 per Visit X 4 times per month X 12 months X 9 district = Rs. 1080000/- | @300/- per day X 2 days X 4 times per month X 12 months X 9 dist.=Rs. 259200/- | Rs. 1339200/- |
| 7 | Medical Officer | SDH/CHC/PHC/UPHC | 2 times per month | @750 per Visit X 2 times per month X 12 months X 76 SDH/CHC/PHC/UPHC = Rs. 13,68,000/- | @300/- per day X 2 days X 4 times per month X 76 SDH/CHC/PHC/UPHC =Rs. 729600/- | Rs. 2097600/- |
| 8 | LHV | Main Centre under SDH/CHC/PHC/UPHC | 4 times per month | @150 per Visit X 4times per month X 12 months X 81 Main Centre = Rs. 583200/- | @300/- per day X 3days X 4 times per month X 81 Main Centre =Rs. 2323800/- | Rs.2916000/- |
| 9 | TOTAL |  |  |  |  | Rs. 9443040/- |
| 10 | Contingencies @ Rs. 5/- % |  |  |  |  | Rs. 472152/- |
| 11 | GRAND TOTAL |  |  |  |  | Rs. 9915192/- |

(Rupees  Ninety Nine Lakhs Fifteen Thousand One Hundred and Ninety Two) only.