Annexure 1.

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

0. Existing Health Facilities in Mizoram

| S.No | DISTRICT | CHC/SDH | PHC | SC |
| --- | --- | --- | --- | --- |
| 1 | Aizawl | 4 | 11 | 91 |
| 2 | Lunglei | 2 | 9 | 70 |
| 3 | Saiha | 0 | 4 | 24 |
| 4 | Lawngtlai | 1 | 6 | 37 |
| 5 | Kolasib | 1 | 5 | 26 |
| 6 | Serchhip | 1 | 5 | 27 |
| 7 | Mamit | 1 | 7 | 33 |
| 8 | Champhai | 3 | 11 | 59 |
| Mizoram |  | 13 | 58 | 367 |

- Expansion Plan in Mizoram:

Table 1a: Plan for expansion of NPCDCS during 2013-2017

| Fin Year | State NCD Cell | District NCD Cell | District NCD Clinic | ICU/CCU/ CCC | CHC NCD Clinic | PHC coverage | Sub-Centre coverage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2013-14 | 1 | 2 | 2 | 0 | 0 | 0 | 0 |
| 2014-15 | 1 | 6 | 6 | 2 | 6 | 20 | 161 |
| 2015-16 | 1 | 7 | 7 | 2 | 9 | 40 | 275 |
| 2016-17 | 1 | 8 | 8 | 2 | 13 | 58 | 367 |

Table 1b: Plan for expansion with location of proposed New Facilities:

| Sl No | New Facility proposed | Existing in the beginning of FY | Addl Target during the FY | Total No of Cumu lative Target | Proposed Location of new facility |
| --- | --- | --- | --- | --- | --- |
|  | 2013-14 FY |  |  |  |  |
| 1 | State NCD Cell | 0 | 1 | 1 | Health Directorate |
| 2 | District NCD Cell | 0 | 2 | 2 | Aizawl & Lunglei districts |
| 3 | District NCD Clinic | 0 | 2 | 2 | - Civil Hospital Aizawl - Civil Hospital Lunglei |
| 4 | ICU/CCU/CCC | 0 | 0 | 0 |  |
| 5 | SDH/CHC NCD Clinics | 0 | 0 | 0 |  |
| 6 | PHC | 0 | 0 | 0 |  |
| 7 | Sub-Centre | 0 | 0 | 0 |  |
|  | 2014-15 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 2 | 4 | 6 | Serchhip dist., Kolasib dist., Saiha dist., & Lawngtlai dist. |
| 3 | District NCD Clinics | 2 | 4 | 6 | Serchhip dist., Kolasib dist., Saiha dist., & Lawngtlai dist. |
| 4 | ICU/CCU/CCC | 0 | 2 | 2 | - Civil Hospital Aizawl - Civil Hospital Lunglei |
| 5 | SDH/CHC NCD Clinics | 0 | 6 | 6 | - Aizawl District- Lengpui, Saitual, Sakawrdai, Thingsulthliah - Lunglei district – Hnahthial, Tlabung |
| 6 | PHCs | 0 | 20 | 20 | 20 PHCs under Aizawl & Lunglei |
| 7 | Sub-Centres |  | 161 | 161 | 161 Sub-Centres under Aizawl & Lunglei |
|  | 2015-16 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 6 | 1 | 7 | Mamit district |
| 3 | District NCD Clinic | 6 | 1 | 7 | Mamit district hospital |
| 4 | ICU/CCU/CCC | 2 | 0 | 2 |  |
| 5 | SDH/CHC NCD Clinic | 6 | 3 | 9 | 9 CHCs under Saiha (0), Lawngtlai (1), Serchhip (1) & Kolasib (1). |
| 6 | PHC | 20 | 20 | 40 | 20 PHCs under Saiha (4), Lawngtlai (6), Serchhip (5) & Kolasib (5). |
| 7 | Sub-Centres | 161 | 114 | 275 | 114 SCs under Saiha (24), Lawngtlai (37), Serchhip (27) & Kolasib (26). |
|  | 2016-17 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 7 | 1 | 8 | Champhai district |
| 3 | District NCD Clinic | 7 | 1 | 8 | Champhai District Hospital |
| 4 | ICU/CCU/CCC | 2 | 0 | 2 |  |
| 5 | CHC NCD Clinic | 9 | 4 | 13 | Champhai dist – Ngopa, Khawzawl, Biate Mamit dist - Kawrthah |
| 6 | PHC | 40 | 18 | 58 | 11 PHCs under Champhai dist 7 PHCs under Mamit dist |
| 7 | Sub-Centres | 275 | 92 | 367 | 59 SCs under Champhai dist 33 SCs under Mamit dist. |