Annexure 3

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

NPCDCS, Mizoram: TRAINING PLAN during 2014-15

Table 3a: No. of Contractual staff under NPCDCS & NPHCE, Mizoram, to be trained during 2014-2015

|  | No of facilities | Doctors | Nurses | Physiothe. | Counselor | Lab Tech | DEO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| State NCD Cell | 1 | 2 | 0 | 0 | 0 | 0 | 1 |
| Dist NCD Cells | 6 | 6 | 0 | 0 | 0 | 0 | 1 |
| Dist NCD Clinic | 6 | 6 | 12 | 6 | 6 | 6 | 6 |
| CCU | 2 | 2 | 8 | 0 | 0 | 0 | 0 |
| CHC Clinic | 6 | 6 | 6 | 0 | 6 | 6 | 6 |
| NPHCE staff | 2 | 4 | 12 | 2 + 4 (RW*) | 0 | 0 | 0 |
| Total No | 23 | 26 | 38 | 12 | 12 | 12 | 14 |

    - *RW = Rehabilitation Worker

Table 3b: No. of State’s permanent officers and staff to be trained under NPCDCS during 2014-15

| Facilities | No of Facilities | Doctors | GNM | ANM |
| --- | --- | --- | --- | --- |
| Dist Hospitals | 6 | 6 | 0 | 0 |
| CHC | 6 | 6 | 0 | 0 |
| PHC | 20 | 20 | 20 | 0 |
| SC | 161 | 0 | 0 | 161 |
| Total |  | 32 | 20 | 161 |

Table 3c: Detailed costing (Training)

| - Training at State /District level (NPCDCS & NPHCE Staff) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Category | No. of persons |  | Duration (days) | No of batches | Date | Unit cost per trainee (Rs) |  | Total cost (Rs) |
| Doctors | 26 |  | 15 | 1 | 2nd Qtr | 21059 |  | 5,47,534 |
| Nurses | 38 |  | 21 | 2 | 2nd & 3rd Qtr | 19978 |  | 7,59,164 |
| Physiotherapist | 12 |  | 15 | 1 | 2nd Qtr | 14893 |  | 1,78,716 |
| Counselor | 12 |  | 15 | 1 | 2nd Qtr | 14001 |  | 1,68,012 |
| Lab Tech | 12 |  | 5 | 1 | 2nd Qtr | 6862 |  | 82,344 |
| DEO | 14 |  | 5 | 1 | 2nd Qtr | 5549 |  | 77,686 |
| Total of A |  |  |  |  |  |  |  | 18,13,456 |
| B. Training at Central level |  |  |  |  |  |  |  |  |
| Programme Officers | 7 |  | 5 | - | As per schedule of MoHFW | 14602 |  | 1,02,214 |
| Finance Logistics Consultant | 7 |  | 3 | - |  | 16066 |  | 1,12,462 |
| Specialists | 2 |  | 15 | - |  | 33896 |  | 67,792 |
| Trainers | 10 |  | 3 | - |  | 15844 |  | 1,58,440 |
| DEO | 2 |  | 3 | - |  | 9059 |  | 18,118 |
| Total of B |  |  |  |  |  |  |  | 4,59,026 |
|  |  | - Training at State /District level (Health Dept officers and staff) |  |  |  |  |  |  |
| Doctors | 32 |  | 3 | 2 | 3rd Qtr | 4000 |  | 1,28,000 |
| Nurses | 40 |  | 3 | 2 | 3rd Qtr | 2880 |  | 57600 |
| ANM | 161 |  | 3 | 8 | 2nd.3rd &4th Qtr | 2880 |  | 463680 |
| Total of C |  |  |  |  |  |  |  | 649280 |
| Grand Total for Training (A+B+C) |  |  |  |  |  |  |  | 29,21,762 |

Per batch = 3532273/21 = 168200.00