| 6.2 EDLs finalised and drug formulary published and made available in all public health facilities, Overall procurement and logistics strategy in place. Detailed design and plan for rate contracting, regular stock up dates, indent management, warehousing, promotion of rational drug use, contingency funds with devolution of financial powers etc. in place. | EDL, procurement and logistic system as described in column 1, in place: Yes/No |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 6.3 Free drug availability | %Clients availing free drugs |  |  |  |  |
| - Timely roll out of RBSK |  |  |  |  |  |
| 7.1 RBSK roll –out plan in line GoI guidelines in place | Roll-out plan in place: yes/no |  |  |  |  |
| 7.2 RBSK teams recruited and trained | %HR recruitedfor RBSK %RBSK-HR trained |  |  |  |  |
| 7.3 Children (including children in anganwadis) screened | % Anganwadi children screened by RBSK teams % Targetschool children screened |  |  |  |  |
| 7.4 Empanelment of public and private secondary and tertiary facilities for referral | %Children referred to secondary facilities %Children referred to secondary facilities |  |  |  |  |
| - Adopting Clinical Establishment Act 2010 as per State’s/UT’s requirement, to regulate the quality and cost of health care in different public and private health facilities |  |  |  |  |  |
| 8.1 Adoption of Clinical Establishment Act 2010 or similar Act | Actin place: yes/no | Yes | Yes |  |  |
| 8.2 Rules and regulations framed for Clinical Establishment Act 2010 | Rules and regulations framed: yes/no | No | Framing of rules & regulation is in process |  |  |
| 8.3 Institutional /regulatory framework set-up | Regulatory framework set –up: Yes/No | No | Is in process |  |  |
| 8.4 Capacity building of programme management staff/others involved in implementation of Clinical Establishment Act underway | %Training completed against the target | Nil | 70% | 80% | 90% |
| - Increase in State annual health budget |  |  |  |  |  |