PROGRAMME IMPLEMENTATION PLAN 2014-15 FOR IMPLEMENTATION OF

PRE CONCEPTION & PRE NATAL DIAGNOSTIC TECHNIQUE (PC & PNDT) ACT, 1994,  MIZORAM

PROGRAMME IMPLEMENTATION PLAN 2014-15

FOR THE IMPLEMENTATION OF PC & PNDT ACT, 1994 IN THE STATE OF MIZORAM

STATUTORY BODIES

The Statutory Bodies namely the State Supervisory Board, State Appropriate Authority, State Advisory Committee was constituted on 12th September, 2011. These Statutory Bodies will be reconstituted by 12th September, 2014.

The District Appropriate Authority was constituted on 25th July, 2013. The District Advisory Committee will be constituted in the near future.

The meetings of the State Supervisory Board will be convened once in every 6 month as per the recent guidelines. The meetings of the State Advisory Committee will be convened 6 times in a year. The meetings of District Advisory Committee will be convened 6 times in a year.

SETTING UP OF STATE PNDT CELL

The State PNDT cell has not been set up. Hence proposal for setting up of the state PNDT cell is as follows :

- Human resources :

- Consultant 		– 1 post

- Programme Assistant 	– 1 post

- Data Entry Operator 	– 1 post

- Legal expert 		–

The budget proposed for the above human resources is as given below :

| Sl.No. | Designation | No. of Post | Salary per Month | Amount requested |
| --- | --- | --- | --- | --- |
| 1. | Consultant | 1 | Rs 50,000/- | Rs 6,00,000/- |
| 2. | Programme Assistant | 1 | Rs 20,000/- | Rs 2,40,000/- |
| 3. | Data Entry Operator | 1 | Rs 12,000/- | Rs 1,44,000/- * |
| 4. | Legal expert |  |  | Rs 2,00,000/- ** |
|  |  |  | TOTAL | Rs 11,84,000/- |

*The post of one Data Entry Operator was already approved in 2012-13 and already in place. This is proposed for continuation in the year 2014-15.

The budget proposed for salary of contractual staff is reflected in FMR code A.7.2.1.

**A lump sum of Rs 2,00,000/- is proposed for Legal expert. Till date the State Appropriate Authority have not received any complaint and no case have been filed. The lump sum amount of Rs 2 lakhs proposed maybe kept and utilized as and when the need arises for consultation of legal expert.

The budget proposed for engagement of Legal expert is reflected in FMR code A.7.2.2.

REQUIREMENT FOR SETTING UP OF STATE PNDT CELL

| Sl.No. | Particulars | Rate | Amount proposed |
| --- | --- | --- | --- |
| 1. | Computer with accessories | Rs 35,000/- | Rs 35,000/- |
| 2. | Office Table x 2 | Rs 15,000/- | Rs 30,000/- |
| 3. | Office Chair x2 | Rs 3,500/- | Rs 7,000/- |
| 4. | Steel Almirah x 2 | Rs 14,300/- | Rs 28,600/- |
| 5. | Computer Table | Rs 6,400/- | Rs 6,400/- |
| 6. | Computer Chair | Rs 4,800/- | Rs 4,800/- |
| 7. | Office expenditure | Rs 1,50,000/- | Rs 1,50,000/- |
|  |  | TOTAL | Rs 2,61,800 |

The budget proposed for setting up of State PNDT cell is reflected in FMR code A.7.1

The term of reference (TOR) of the above Human Resources proposed newly is as given below :

- Job Title		: 	Consultant

Qualification	: 	1) MBBS degree from institution recognised by Medical

Council of India.

2) Must have completed compulsory internship.

Job requirement/

Responsibility	:	1) Preparing Programme Implementation Plan

2) Organizing State Level Review Meetings and Orientation

Workshop

3) Organizing training programmes.

4) Visiting districts to monitor.

5) Any other job assigned by concerned officers.

Remuneration	:	Rs 50,000/- per month (consolidated)

- Job Title		:	Programme Assistant

Qualification	:	1) Graduate in any stream

2) Knowledge and experience in office work desirable

3) Computer knowledge desirable

Job requirement	:	1) Assistance to Consultant in all his job responsibilities.

2) Correspondence with districts.

3) Assistant in organising review meetings and official tours.

4) Maintenance of files and correspondence.

5) Assistance in preparation of reports.

6) Any other job assigned as per programme need.

Remuneration	:	Rs 20,000/- per month (consolidated)

SETTING UP OF STATE INSPECTION AND MONITORING COMMITTEE (SIMC)

The State Inspection and Monitoring Committee (SIMC) as already been set up. This has to be revised as some of the members of the SIMC are not in position due to transfer of posting place. This will be revised in the coming near future.

MAPPING FOR FACILITIES REGISTERED UNDER PC & PNDT ACT

Mapping of registered ultrasound centres in Mizoram have not been done so far. Mapping for facilities registered under PC & PNDT Act in Mizoram is proposed to be carried out in the 2nd quarter of the year 2014-15. Financial requirement for mapping is estimated approximately at Rs 1.50 lakh. This is reflected in FMR code A.7.2.3.

REVIEW MEETINGS

- The review meeting of the State Supervisory Board will be convened once in 6 months. As the number of registrations are few and there is no other financial source, the expenditure for the review meeting is proposed at Rs 30,000/- per meeting. The total cost of the meeting in 2014-15 is Rs 60,000/- only. This is reflected in FMR code A.7.2.4.

- The review meeting of the State Advisory Committee to be convened 6 times in a year. The expenditure for the review meeting is proposed at Rs 20,000/- per meeting. The total cost of the meeting in 2014-15 is Rs 1.20 lakh only. This is reflected in FMR code A.7.2.5.

- The review meeting of District Advisory Committee will be convened 6 times in a year. The expenditure for the review meeting is proposed at Rs 5,000/- per meeting. The cost of 6 meetings in 2014-15 is Rs 30,000/- per district. The total cost for review meeting of DAC is Rs 2.40 lakh only. This is reflected in FMR code A.7.2.6.

MEDICAL AUDIT

The Medical Audit will be conducted once in a year. Medical Audit of Aizawl District will be conducted by State Appropriate Authority or any officers detailed by the State Appropriate Authority. The expenditure for Medical Audit is proposed at Rs 19,000/- only. This is reflected in FMR code A.7.2.7.

The Medical Audit of other districts will be conducted once in a year. Medical Audit of other districts will be conducted by State Appropriate Authority / District Appropriate Authority or any officers detailed for the purpose. The expenditure is proposed at Rs 40,000/- only. This is reflected in FMR code A.7.2.8.

INSPECTION OF ULTRASOUND CENTRES

Two inspections is proposed for the year 2014-15. It is proposed that the first inspection of all the ultrasound centres will be carried out from the state level. The inspection maybe carried out by the State Appropriate Authority or any officers detailed for the purpose. The expenditure for the first inspection is proposed at Rs 54,000/- only.

The second inspection will be carried out at the district level. This will be conducted by District Appropriate Authority or any officers detailed for the purpose. The expenditure for the second inspection is proposed at Rs 54,000/- only.

The budget proposal for inspections is reflected in FMR code A.7.2.9.

TRAINING

Two training programmes will be undertaken in 2014-15.

Training at State Level: 1st Training will be conducted in the 2nd quarter. The participants for the training are State Supervisory Board, State Advisory Committee, State Appropriate Authority and Judiciaries. The expenditure proposed for the said training is at Rs 30,000/- only.

2nd training will be conducted in the 3rd quarter. The participants for the training are Gynaecologists, Radiologists, Sonologists and owner of Ultrasound centres. The expenditure proposed for the said training is at Rs 30,000/- only.

The expenditure of above two trainings at the state level is reflected in FMR code A.9.9.1.

Training at District Level : 1st training will be conducted in the 2nd quarter.  The participants for the training are District Appropriate Authority, District Advisory Committee and Judiciaries. The expenditure proposed for the training is at Rs 5,000/- per district. The total expenditure for training is at Rs 40,000/- only.

2nd training will be conducted in the 3rd quarter. The participants for the training are Gynaecologists, Radiologists, Sonologists and owner of Ultrasound centres. The expenditure proposed for the said training is at Rs 5,000/- per district. The total expenditure for training is Rs 40,000/- only.

The expenditure of above two trainings at the district level is reflected in FMR code A.9.9.1.

MOBILITY SUPPORT

Mobility support is for conducting training at the state and district level, and for inspection of ultrasound centres. The amount for mobility support is kept at Rs 2,00,000/- only. This is reflected in FMR code A.7.3.

IEC / BCC / IPC PLAN

- Hoardings : Hoardings will be placed at the strategic location in the ultrasound centre and at the footend of the ultrasound bed. There are 47 ultrasound machine which has been registered. The old ones are to be replaced by new hoardings. The expenditure for one hoarding is estimated at Rs 1,500/-. The total number of new hoardings to be made is 100. The total expenditure for the hoarding is Rs 1,50,000/- only.

- Advertisement : To create awareness to the public advertisements in newspapers, magazine, etc. @ Rs 3,000/- per advertisement. 50 numbers of advertisements is proposed for the year 2014-15. Total expenditure for advertisement is Rs 1,50,000/- only.

- TV spots : To create awareness to the public it is proposed to telecast the PNDT programme in the TV scroll. The estimated cost for TV scroll per day is Rs 700/-. This will be telecast in Doordharshan Kendra at least for 7 days in 2014-15. Total cost for TV spots is Rs 4,900/- only.

- All India Radio : To create awareness to the public it is proposed to broadcast the PNDT programme in the All India Radio, Aizawl. The estimated cost for broadcast per day is Rs 300/-. This will be broadcast in AIR, Aizawl at least for 7 days in 2014-15. Total cost for TV spots is Rs 2,100/- only.

- IPC : To create awareness among the young generations and marriagable age, it is proposed to conduct seminars among College students, youth groups like YMA, KTP, SAY, etc. Six seminars will be conducted in the year 2014-15. Cost of conducting one seminar is Rs 20,000/-. The total cost of 6 seminars is Rs 1,20,000/- only.

- Translation and Printing of PC & PNDT Act in local vernacular (Mizo Language) : The PC & PNDT Act is not yet translated and printed in Mizo Language. Therefore it is essential to translate and print in Mizo Language. The amount proposed for the above is Rs 1.00 lakh only.

The total amount under IEC / BCC / IPC is Rs 5,57,000/- only. This is reflected in FMR code B.10.3.50

The total estimated budget for the implementation of PC & PNDT Act, 1994 in the state of Mizoram for the year 2014-15 is Rs 30,79,800/- only.

BUDGET SUMMARY FOR PNDT FOR THE STATE OF MIZORAM PIP 2014-2015

Rs in lakh

| FMR Code | Component | Physical Target | Fund Requested |
| --- | --- | --- | --- |
| 1. | State Level |  |  |
| A.7.2.1 A.7.2.2 | - Consultant @Rs 50,000/month - Programme Assistant @ Rs 20,000/ month - DEO @ Rs 12,000/month - Legal Expert | 1 1 1 1 | 6.00 2.40 1.44 2.00 |
| A.7.1 | Computer with accessories @ Rs 35,000/ | 1 | 0.35 |
|  | Office table @Rs 15,000/- | 2 | 0.30 |
|  | Office chair @Rs 3,500/- | 2 | 0.07 |
|  | Steel Almirah @Rs 14,300/- | 2 | 0.286 |
|  | Computer table @Rs 6,400/- | 1 | 0.064 |
|  | Computer chair @Rs 4,800/- | 1 | 0.048 |
|  | Office expenditure @Rs 1.5 lakh | - | 1.50 |
| A.7.2.3 A.7.2.4 A.7.2.5 A.7.2.7 A.7.2.9 | Mapping of ultrasound centres | - | 1.50 |
|  | Review meeting of State SSB @Rs 30,000/- | 2 | 0.60 |
|  | Review meeting of SAC @Rs 20,000/- | 6 | 1.20 |
|  | Medical audit of Aizawl District | 1 | 0.19 |
|  | Inspection of all ultrasound centre | 1 | 0.54 |
| A.9.9 | Training – State Level @Rs 30,000/- | 2 | 0.60 |
| A.7.3 | Mobility support | - | 2.00 |
| B.10.3.5 | IEC/SEC/IPC Plan/Translation | - | 5.57 |
|  | Total |  | 26.658 |
| 2. | District level (8 Districts) |  |  |
| A.7.2.6 | Review meeting of DAC @Rs 5,000/- per meeting | 48 | 2.40 |
| A.7.2.8 | Medical Audit @Rs 5,000/- per district | 8 | 0.40 |
| A.7.2.9 | 2nd inspection of Ultrasound centre | 8 | 0.54 |
| A.9.9 | Training at District Level @ Rs 5,000/- per training | 16 | 0.80 |
|  | Total |  | 4.14 |

Grand Total of fund requested                    Rs 30.798 lakh

BUDGET SUMMARY FOR PNDT FOR THE STATE OF MIZORAM PIP 2015-2016

Rs in lakh

| FMR Code | Component | Physical Target | Fund Requested |
| --- | --- | --- | --- |
| 1. | State Level |  |  |
| A.7.2.1 A.7.2.2 | - Consultant @Rs 50,000/month - Programme Assistant @ Rs 20,000/ month - DEO @ Rs 12,000/month - Legal Expert | 1 1 1 1 | 6.00 2.40 1.44 2.00 |
| A.7.1 | Office expenditure @Rs 1.5 lakh | - | 1.50 |
| A.7.2.4 A.7.2.5 A.7.2.7 A.7.2.9 | Review meeting of State SSB @Rs 30,000/- | 2 | 0.60 |
|  | Review meeting of SAC @Rs 20,000/- | 6 | 1.20 |
|  | Medical audit of Aizawl District | 1 | 0.19 |
|  | Inspection of all ultrasound centre | 1 | 0.54 |
| A.9.9 | Training – State Level @Rs 30,000/- | 2 | 0.60 |
| A.7.3 | Mobility support | - | 2.00 |
| B.10.3.5 | IEC/SEC/IPC Plan | - | 4.57 |
|  | Total |  | 23.04 |
| 2. | District level (8 Districts) |  |  |
| A.7.2.6 | Review meeting of DAC @Rs 5,000/- per meeting | 48 | 2.40 |
| A.7.2.8 | Medical Audit @Rs 5,000/- per district | 8 | 0.40 |
| A.7.2.9 | 2nd & 3rd inspection of Ultrasound centre | 16 | 1.08 |
| A.9.9 | Training at District Level @ Rs 5,000/- per training | 16 | 0.80 |
|  | Total |  | 4.68 |

Grand Total of fund requested                    Rs 27.72 lakh

BUDGET SUMMARY FOR PNDT FOR THE STATE OF MIZORAM PIP 2016-2017

Rs in lakh

| FMR Code | Component | Physical Target | Fund Requested |
| --- | --- | --- | --- |
| 1. | State Level |  |  |
| A.7.2.1 A.7.2.2 | - Consultant @Rs 55,000/month with 10% increment | 1 | 6.60 |
|  | - Programme Assistant @ Rs 22,000/ month with 10% increment | 1 | 2.64 |
|  | - DEO @ Rs 13,200/month with 10% increment | 1 | 1.584 |
|  | - Legal Expert | 1 | 2.00 |
| A.7.1 | Office expenditure @Rs 1.5 lakh | - | 1.50 |
| A.7.2.4 A.7.2.5 A.7.2.7 A.7.2.9 | Review meeting of State SSB @Rs 30,000/- | 2 | 0.60 |
|  | Review meeting of SAC @Rs 20,000/- | 6 | 1.20 |
|  | Medical audit of Aizawl District | 1 | 0.19 |
|  | Inspection of all ultrasound centre | 1 | 0.54 |
| A.9.9 | Training – State Level @Rs 30,000/- | 2 | 0.60 |
| A.7.3 | Mobility support | - | 2.00 |
| B.10.3.5 | IEC/SEC/IPC Plan | - | 4.57 |
|  | Total |  | 24.024 |
| 2. | District level (8 Districts) |  |  |
| A.7.2.6 | Review meeting of DAC @Rs 5,000/- per meeting | 48 | 2.40 |
| A.7.2.8 | Medical Audit @Rs 5,000/- per district | 8 | 0.40 |
| A.7.2.9 | 2nd & 3rd inspection of Ultrasound centre | 16 | 1.08 |
| A.9.9 | Training at District Level @ Rs 5,000/- per training | 16 | 0.80 |
|  | Total |  | 4.68 |

Grand Total of fund requested                    Rs 28.704 lakh