Annexure 1.

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

0. Existing Health Facilities in Mizoram

| S.No | DISTRICT | CHC/SDH | PHC | SC |
| --- | --- | --- | --- | --- |
| 1 | Aizawl West | 0 | 6 | 37 |
| 2 | Aizawl East | 3 | 6 | 54 |
| 3 | Lunglei | 2 | 9 | 70 |
| 4 | Saiha | 0 | 4 | 24 |
| 5 | Lawngtlai | 1 | 6 | 37 |
| 6 | Kolasib | 1 | 5 | 26 |
| 7 | Serchhip | 1 | 5 | 27 |
| 8 | Mamit | 1 | 7 | 33 |
| 9 | Champhai | 3 | 11 | 59 |
| Mizoram |  | 12 | 59 | 367 |

- Expansion Plan in Mizoram:

Table 1a: Plan for expansion of NPCDCS during 2013-2017

| Fin Year | State NCD Cell | District NCD Cell | District NCD Clinic | ICU/CCU/ CCC | CHC NCD Clinic | PHC coverage | Sub-Centre coverage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2013-14 | 1 | 2 | 2 | 0 | 0 | 0 | 0 |
| 2014-15 | 1 | 6 | 6 | 2 | 5 | 21 | 161 |
| 2015-16 | 1 | 7 | 7 | 2 | 8 | 41 | 275 |
| 2016-17 | 1 | 8 | 8 | 2 | 12 | 59 | 367 |

Table 1b: Plan for expansion with location of proposed New Facilities:

| Sl No | New Facility proposed | Existing in the beginning of FY | Addl Target during the FY | Total No of Cumulative Target | Proposed Location of new facility |
| --- | --- | --- | --- | --- | --- |
|  | 2013-14 FY |  |  |  |  |
| 1 | State NCD Cell | 0 | 1 | 1 | Health Directorate |
| 2 | District NCD Cell | 0 | 2 | 2 | Aizawl & Lunglei districts |
| 3 | District NCD Clinic | 0 | 2 | 2 | - Civil Hospital Aizawl - Civil Hospital Lunglei |
| 4 | ICU/CCU/CCC | 0 | 0 | 0 |  |
| 5 | SDH/CHC NCD Clinics | 0 | 0 | 0 |  |
| 6 | PHC | 0 | 0 | 0 |  |
| 7 | Sub-Centre | 0 | 0 | 0 |  |
|  | 2014-15 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 2 | 4 | 6 | Serchhip dist., Kolasib dist., Saiha dist., & Lawngtlai dist. |
| 3 | District NCD Clinics | 2 | 4 | 6 | Serchhip dist., Kolasib dist., Saiha dist., & Lawngtlai dist. |
| 4 | ICU/CCU/CCC | 0 | 2 | 2 | - Civil Hospital Aizawl - Civil Hospital Lunglei |
| 5 | SDH/CHC NCD Clinics | 0 | 5 | 5 | - Aizawl District-Saitual, Sakawrdai&Kulikawn - Lunglei district – Hnahthial, Tlabung |
| 6 | PHCs | 0 | 21 | 21 | 21 PHCs under Aizawl & Lunglei |
| 7 | Sub-Centres |  | 161 | 161 | 161 Sub-Centres under Aizawl & Lunglei |
|  | 2015-16 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 6 | 1 | 7 | Mamit district |
| 3 | District NCD Clinic | 6 | 1 | 7 | Mamit district hospital |
| 4 | ICU/CCU/CCC | 2 | 0 | 2 |  |
| 5 | SDH/CHC NCD Clinic | 5 | 3 | 8 | 8 CHCs under Saiha (0), Lawngtlai (1), Serchhip (1) & Kolasib (1). |
| 6 | PHC | 21 | 20 | 41 | 21 PHCs under Saiha (4), Lawngtlai (6), Serchhip (5) & Kolasib (5). |
| 7 | Sub-Centres | 161 | 114 | 275 | 114 SCs under Saiha (24), Lawngtlai (37), Serchhip (27) & Kolasib (26). |
|  | 2016-17 FY |  |  |  |  |
| 1 | State NCD Cell | 1 | 0 | 1 |  |
| 2 | District NCD Cell | 7 | 1 | 8 | Champhai district |
| 3 | District NCD Clinic | 7 | 1 | 8 | Champhai District Hospital |
| 4 | ICU/CCU/CCC | 2 | 0 | 2 |  |
| 5 | CHC NCD Clinic | 8 | 4 | 12 | Champhai dist – Ngopa, Khawzawl, Biate Mamit dist - Kawrthah |
| 6 | PHC | 41 | 18 | 59 | 11 PHCs under Champhai dist 7 PHCs under Mamit dist |
| 7 | Sub-Centres | 275 | 92 | 367 | 59 SCs under Champhai dist 33 SCs under Mamit dist. |

Annexure 2.

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

IEC PLAN with Budget during 2014-2015 FY:

Table 2a: State NCD Cell IEC Plan & Budget

|  | IEC Plan & Budget for State NCD Cell | Amount (in lakhs) |
| --- | --- | --- |
| - Mass Media |  |  |
| TV Spots | Developing 4 TV Spots = 4x 0.25 = 1.0 | 1.0 |
|  | Broadcasting at DDK@Rs 600/ min x 100 | 0.6 |
|  | Broadcasting at 2 local channels @ Rs 400/min x 200 | 0.8 |
| Radio Jingles | Developing 2 Jingles = 2x Rs 10000 | 0.2 |
|  | Broadcasting @ Rs 400x 100 | 0.4 |
| Print media | Advertisements @ Rs 3000 x 50 | 1.5 |
| 2. Printing | Leaflets = 2@ Rs5 x 10,000 | 1.0 |
|  | Registers, Formats, Referral cards | 1.0 |
| 3. Mid Media | Signages = 28 nos. @ Rs 5000 | 1.4 |
|  | Hoardings @ 35,000 x 6 nos. | 2.1 |
|  | Total State NCD Cell budget | 10.0 |

Table 2b: District NCD Cell:  IEC Plan & Budget

|  | IEC Plan & Budget for District NCD Cell | Amount (in lakhs |
| --- | --- | --- |
| - Mass Media |  |  |
| TV Spots | Broadcasting at DDK@Rs 600/ min x 100 | 0.6 |
|  | Broadcasting at 2 local channels @ Rs 400/min x 200 | 0.8 |
| Radio Jingles | Broadcasting @ Rs 400x 100 | 0.4 |
| Print media | Advertisements @ Rs 3000 x 50 | 1.5 |
| 2. Printing | Leaflets = 2@ Rs5 x 10,000 | 1.0 |
| 3. Mid Media | Hoardings @ 35,000 x 2 nos | 0.7 |
|  | Total (1 District NCD Cell IEC budget) | 5.0 |
|  | Total budget for 5 District NCD Cells (5 lakh x5 nos) | 25.0 |

Total IEC Budget for State NCD Cell & 5 District NCD Cells =					35.0 lakhs

- Other IEC Activities during 2014-15:

The following activities are proposed -

| Sl no |  | Activity Proposed | Amount (in lakh) |
| --- | --- | --- | --- |
| 1 | World Cancer Day Observation | 6.0 |
|  | - State level – 2.5 lakhs |  |
|  | - District level: 7 districts x 0.5 lakh each = 3.5 lakh |  |
| 2 | Competitions – essay writing/short film making : | 5.0 |
| 3 | Partnership with FBOs & NGOs - Churches and NGOs working in the field of NCDs in various districts will be involved for IPC at various levels: Rs 3000 x 50 IPCs x 10 FBOs/NGOs = Rs 15.0 lakh | 15.0 |
| 4 | Sensitization Workshops - @ Rs 5000 x 40 legislators = Rs.2.0 lakhs - @ Rs 2500 x 40 YMA leaders= Rs 1.0 lakh - @ Rs 2500x40 FBO leaders = Rs 1.0 lakh | 4.0 |
| 5 | Inter Personal Communications (IPC) - NCD Awareness campaign will be conducted at various schools, colleges, communities to generate awareness on NCD and to promote Healthy Lifestyle - @ Rs 4000 x 100 = Rs 4.0 lakhs | 4.0 |
|  | Total amount proposed for State Innovations | 34.0 |

Annexure 3

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

NPCDCS, Mizoram: TRAINING PLAN during 2014-15

Table 3a: No. of Contractual staff under NPCDCS & NPHCE, Mizoram, to be trained during 2014-2015

|  | No of facilities | Doctors | Nurses | Physiothe. | Counselor | Lab Tech | DEO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| State NCD Cell | 1 | 2 | 0 | 0 | 0 | 0 | 1 |
| Dist NCD Cells | 6 | 6 | 0 | 0 | 0 | 0 | 1 |
| Dist NCD Clinic | 6 | 6 | 12 | 6 | 6 | 6 | 6 |
| CCU | 2 | 2 | 8 | 0 | 0 | 0 | 0 |
| CHC Clinic | 5 | 5 | 5 | 0 | 5 | 5 | 5 |
| NPHCE staff | 2 | 4 | 12 | 2 + 4 (RW*) | 0 | 0 | 0 |
| Total No | 22 | 25 | 37 | 12 | 11 | 11 | 13 |

    - *RW = Rehabilitation Worker

Table 3b: No. of State’s permanent officers and staff to be trained under NPCDCS during 2014-15

| Facilities | No of Facilities | Doctors | GNM | ANM |
| --- | --- | --- | --- | --- |
| Dist Hospitals | 6 | 6 | 0 | 0 |
| CHC | 5 | 5 | 0 | 0 |
| PHC | 20 | 20 | 20 | 0 |
| SC | 161 | 0 | 0 | 161 |
| Total |  | 31 | 20 | 161 |

Table 3c: Detailed costing (Training)

| - Training at State /District level (NPCDCS & NPHCE Staff) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Category | No. of persons |  | Duration (days) | No of batches | Date | Unit cost per trainee (Rs) |  | Total cost (Rs) |
| Doctors | 25 |  | 15 | 1 | 2ndQtr | 21059 |  | 5,26,475 |
| Nurses | 37 |  | 21 | 2 | 2nd& 3rdQtr | 19978 |  | 7,39,186 |
| Physiotherapist | 12 |  | 15 | 1 | 2ndQtr | 14893 |  | 1,78,716 |
| Counselor | 11 |  | 15 | 1 | 2ndQtr | 14001 |  | 1,54,011 |
| Lab Tech | 11 |  | 5 | 1 | 2ndQtr | 6862 |  | 75,482 |
| DEO | 13 |  | 5 | 1 | 2ndQtr | 5549 |  | 72,137 |
| Total of A |  |  |  |  |  |  |  | 17,46,007 |
| B. Training at Central level |  |  |  |  |  |  |  |  |
| Programme Officers | 7 |  | 5 | - | As per schedule of MoHFW | 14602 |  | 1,02,214 |
| Finance Logistics Consultant | 7 |  | 3 | - |  | 16066 |  | 1,12,462 |
| Specialists | 2 |  | 15 | - |  | 33896 |  | 67,792 |
| Trainers | 10 |  | 3 | - |  | 15844 |  | 1,58,440 |
| DEO | 2 |  | 3 | - |  | 9059 |  | 18,118 |
| Total of B |  |  |  |  |  |  |  | 4,59,026 |
|  |  | - Training at State /District level (Health Dept officers and staff) |  |  |  |  |  |  |
| Doctors | 31 |  | 3 | 2 | 3rdQtr | 4000 |  | 1,24,000 |
| Nurses | 21 |  | 3 | 2 | 3rdQtr | 2880 |  | 60480 |
| ANM | 161 |  | 3 | 8 | 2nd.3rd&4thQtr | 2880 |  | 463680 |
| Total of C |  |  |  |  |  |  |  | 6,48,160 |
| Grand Total for Training (A+B+C) |  |  |  |  |  |  |  | 28,53,193 |

Annexure 4

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

Outreach plan

Outreach will be conducted periodically by State NCD Cell and all 6 District NCD Cells. Resource persons will be pooled from NCD Cells, District Hospitals, NCD Clinics and TCCC. It is envisaged to have 12 outreach programmes per NCD Cell. The cost of one outreach has been calculated @ Rs.20, 000/- per camp.

Break-up of One Outreach Camp:

| Sl No | Item | Amount (Rs) |
| --- | --- | --- |
| 1 | POL/Vehicle: | Rs.3000.00 |
| 2 | Site preparation: | Rs 2000.00 |
| 3 | Consumables, including basic medicines: | Rs 2000.00 |
| 4 | Honorarium: Doctors @ Rs 500 x 4 = 2000 | Rs 2000.00 |
| 5 | Honorarium: Supporting staff @ Rs 250x4 = 1000 | Rs 1000.00 |
| 6 | Fooding/Refreshment: 10 x Rs 300 = Rs 3000.00 | Rs 3000.00 |
| 7 | Documentation – hoardings, registration cards, photography | Rs 3000.00 |
| 8 | Hall hiring charge: | Rs 2000.00 |
| 9 | Publicity: | Rs 2000.00 |
|  | Total per Outreach Camp | Rs 20000.00 |
|  | Grand Total: 7 NCD Cells x 12 Camps each @ Rs 0.2 lakh | Rs 16,80,000.00 |

Annexure 5

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF CANCER, DIABETES, CARDIOVASCULAR DISEASES AND STROKE (NPCDCS): MIZORAM: PIP FOR 2014-2015

| Sl No | Item | Amount (Rs) |
| --- | --- | --- |
| 1 | POL/Vehicle: | Rs. 8000.00 |
| 4 | Lodging: @ Rs. 800 x 4 days x 2 persons | Rs 6400.00 |
| 6 | Fooding/Refreshment: @ Rs 300 x 4 days x 4 persons | Rs 4800.00 |
|  | Total per Supervisory visit | Rs 19,200.00 |
|  | Grand Total: 6 districts x 4 times/year x Rs. 19,200 per visit | Rs. 4,60,800 |