PROJECT IMPLEMENTATION PLAN

FOR THE YEAR

2014     -    2015

NATIONAL LEPROSY ERADICATION

CONTROL PROGRAMME

(NLEP)

NLEP CELL

DIRECTORATE OF HEALTH SERVICES

MIZORAM : AIZAWL

- SITUATION   ANALYSIS

STRENGTH:-

The strength of NLEP in Mizoram during the past year had been the intensive tours of the SLO and SMO in various districts of Mizoram. During these tours, sensitization of the programme at the grass root level i.e. the ASHA’s , Health Workers ,Health Supervisors and Non-medical Supervisors  had been done, due to which case detection by ASHA’s had greatly improved as compared to previous years. Also, the overall new case detection had doubled as compared to the previous years(i.e. from 18 during the previous year to 34 in the current year till date) , which is also a result of these active tour programmes and ASHA sensitizations.

WEAKNESS:-

The main weakness of the programme had been the difficulty in trying to immobilize migrant populations of Mizoram, regarding treatment completion of MDT as they form a major part of the State’s case load.

THREATS:-

It had come to the SLO’s notice that, some border areas of Mizoram had been infiltrated with cases from neighboring states. This problem could pose as a threat for insurgence of new cases in these areas. Hence, we had conducted active search of these cases and had given MDT to those identified.

NEW INITIATIVES PROPOSED:-

- To conduct training at different Medical institutions  of the State like Nursing colleges, Health Worker school etc. To conduct training for all the newly recruited 88 doctors within this coming year.

- To hire PMW on contractual basis, in the high endemic regions of the State.In Mizoram, Lawngtlai district has been recorded as a high endemic district with ANCDR of 9.3 per 100,000 population in 2012-2013, and ANCDR of 23 per 100,000 during 2013-2014.

- To conduct review meetings with the PMW’s of the state at the State capital on quarterly basis for better functioning of the programme and and to conduct training for newly recruited PMW’s  and to conduct re-orientation training for the already existing 8 PMW’s

- PERFORMANCE UNDER NLEP.

| S.No. | Indicators | 2008 -09 | 2009 -10 | 2010 -11 | 2011-12 | 2012-13 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | No. of new cases detected (ANCDR/100,000) | 23 (2%) | 10 (0.9%) | 21 (1.9%) | 17 (1.5%) | 18 (1.6%) |
| 2. | No. of cases on record at year end (PR/10,000) | 17 (0.15%) | 19 (0.17%) | 20 (0.18%) | 18 (0.16%) | 27 (0.24%) |
| 3. | No. of Grade II disability among new cases (%) | 0 | 0 | 0 | 0 | 0 |
| 4. | Treatment Completion Rate | MB- 75% PB-80% | MB-70% PB-75% | MB- 77% PB- 66% | MB-81% PB-68% | MB-61% PB-75% |
| 5. | Reconstructive Surgery conducted | 0 | 0 | 0 | 0 | 0 |
| Total |  |  |  | - |  |  |

Current Scenario - 2013 April till 2014 January.

Total New case= 34                                          ANCDR = 3%

Current No. of case on record = 46               PR = 0.41%

- NLEP Annual Plan for the year 2014-15

- Case detection and Management

  - Special activities – 209 districts

Special activities in high endemic districts where ANCDR is more than 10 per 100,000 population. This activity was completed in 209 high endemic districts during 2012-13 and need to be planned for Active Search again during the current year, as per the PIP for 12th. Plan.

In Mizoram, out of the 34 new cases detected during 2013-2014 January, 28 cases are from one district alone, which is Lawngtlai District. Hence, the ANCDR may be calculated as follows:-

No. of new cases detected = 28

Population of Lawngtlai district = 1,17,894

ANCDR = 23 per 100,000 population.

| Special activities in high endemic district | No. of Block | Unit cost per Block (Rs.) | Amount for districts (Rupees) |
| --- | --- | --- | --- |
| Special activities In High endemic district - Capacity building of staff - Awareness drive - Enhanced - monitoring and supervision - Validation of MB and child cases | 2 | 1,00,000 | 2,00,000 |

  - (A) Intensive Case Detection Drive – 440 districts

Special activities in high endemic blocks of low endemic districts was carried out during the year 2013-14 by all the States and UTs. Any such block  that were left out during 2013-14 should be planned to be covered during 2014-15.

| Special activities in high endemic blocks (Of low endemic district) | No. of Block with ANCDR >10/100,000 | Unit cost per Block (Rs.) | Amount for State/UT (Rupees) |
| --- | --- | --- | --- |
| Special activities - House to house visit by search team of ASHA, AWW and PRI members for suspecting cases - Confirmation of suspects by team of MO PHC and NMS/PMW - Intensive IEC activity prior to house visit | 2 | 2 x 1,00,000 | 2,00,000 |

  - Services in Urban Areas

To be calculated for State/UT based on identified urban areas located.

| S.No | Category of urban area | Number | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. 2. 3. | Township Medium city –I Medium city – II Mega city | 3 1 | 3 x 1,14,000 1 x 2,40,000 4,72,000 5,60,000 | 3,42,000 2,40,000 |
| Total |  |  |  | 7,20,000 |

- Though the population of the state capital of Mizoram (Aizawl) is only upto 4 lakhs, it may be regarded as Medium city-I as it is a state capital. Besides Aizawl City, Lunglei, Champhai, Lawngtlai are proposed to be included as Township.

  - ASHA Involvement

Under this result based initiative following two activities need to be planned district wise -

Performance based incentive to ASHA and sensitisation to new ASHA.

| S. NO | No. of ASHA activity | Number | Unit Cost per person (Rs.) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Sensitization of New ASHA | 250 | 100 | 25,000 |
| 2 | Incentive to ASHA (Proposed Rate) | Case diagnosis Treatment MB PB | 250 X 40 600 X 40 400 X 40 | 10,000 24,000 16,000 |
|  | - |  |  |  |
|  |  | - | - | 75,000 |

  - Multidrug Therapy

To be supplied to the States/UTs by the centre, not to be budgeted by State/UT.

  - Materials & Supplies

To be calculated for State/UT according to the number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Supportive Drugs & dressings | 9 | 9 X 40,000 | 3,60,000 |
| 2. | Laboratory reagents and equipments | 9 | 9 X 8,000 | 72,000 |
| 3. | Printing works |  | 9 X 20,000 | 1,80,000 |
| Total |  | - | 9 X 68,000 | 6,12,000 |

  - Services through NGO & other Agencies

To be calculated at State level on the basis of NGO involved through SET Schemes.

| S. No. | Name of NGO under SET Scheme | Unit cost per NGO (Rupees) | Amount (Rupees) |
| --- | --- | --- | --- |
| 1 | YMA/MHIP | 1,80,000 X 5 | 9,00,000 |
| Total |  |  |  |

Fund requirement for each NGO should be separately worked out as per their work liability. The requirement must be actual for each NGO as per agreed contract.

  - Operational Research

This activity will be organised from the Central Level. However, States are often involved in Operational Research as a Partner with WHO, ILEP, ICMR and other research organizations with fund support from such organizations. Such details may be included under the Additional ties proposed separately in the plan.

- Disability Prevention and Medical Rehabilitation (DPMR)

  - DPMR

Activities to be planned are-

DPMR services – To be calculated for each district

| S.No | Item | No. required | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. 2. 3. 4. | MCR footwear Aids & appliance Welfare allowances for RCS patient RCS reimbursement to Govt. Institutions | 5 X 2 pairs 5 5 5 | 300 X 5 17,000 8000 At Institute – 5000/- At camps – 10,000/- | 1,500 85,000 45,000 25,000 50,000 |
| Total |  | - | - | 2,06,500 |

Actual number of persons district wise with insensitive feet should be attached.

Detailed plan of RCS in camps also to be indicated as an attachment.

- Information. Education and Communication (IEC/BCC)

- To specifically cover clients, Health providers, influencers and the masses.

State/UT IEC plan will be drawn up in the Annual Plan under the following heads:

| S.No | Medium | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Mass Media (TV, Radio Press) | 9 | 9 X 39,000 | 3,51,000 |
| 2. | Outdoor Media | 9 | 9 X 23,000 | 2,07,000 |
| 3. | Rural Media | 9 | 9 X 31,000 | 2,79,000 |
| 4. | Advocacy meeting | 9 | 9 X 5000 | 45,000 |
| Total |  |  | 9 X 98,000 | 8,82,000 |

*The State Leprosy Officer will be able to distribute the total funds on the basis of actual requirements of each district keeping adequate funds at State level under Mass Media and Advocacy meetings.

- Human Resources and Capacity building

  - Capacity building

- Calculated for each district –

| S.No | Type of training (Category to be mentioned as per need) | No. to be trained in the District | No. of course for 30 persons | Unit cost* per course (Rs.) | Amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1. | Medical Officer | 30 | 1 | 1 x 74,500 | 74,500 |
| 2. | Health supervisor and Health worker training | 100 | 3 | 3 x50,400 | 1,51,200 |
| 3. | PMW training | 9 | 1 | 1 x10,000 | 10,000 |
| 4. | ASHA training | 107 | 4 | 4 x40,000 | 1,60,000 |
| Total |  | 246 | 9 | - | 3,95,700 |

*Unit cost  calculated as per State NRHM norm fixed for all health programmes

- Calculation for State/UT

| S.No | Type of training | Total no. to be trained in the State/UT | No. of course for 30 persons | Unit cost per course (Rs.) | Total amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1. | District level Training from Table - A | 246 | 9 | - | 3,95,700 |
| Total |  | 246 | 9 | - | 3,95,700 |

  - Human Resource on contract in States/UTs

    - Contractual staff at State level

| S.No | Category | No. of posts | Unit cost * per month | Cost per year (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Surveillance Medical Officer | 1 | 60,000 | 7,20,000 |
| 2. | BFO Cum Admn. Officer | 1 | 40,000 | 4,80,000 |
| 3. | Admn. Asstt. | 1 | 22,000 | 2,64,000 |
| 4. | DEO | 1 | 25,000 | 3,00,000 |
| 5. | Driver | 1 | 15,000 | 1,80,000 |
| Total |  | 5 | 1,62,000 | 19,44,000 |

*The salaries are calculated based on salary of vertical health programmes and NRHM. It may kindly be noted that the salary of DEO was approved at Rs 20,000 for two consecutive financial years from 2012-13 and was paid as much. However, in this year’s PIP guidelines it was reduced to Rs 12,000 again which the state presume to be clerical error as it is considered unlikely to reduce the salary without due cause.

    - District Leprosy Societies

As, Mizoram is a small state, under NLEP, the S.L.O and S.M.O are able to tour even the most remote areas of the State, hence hiring of District  leprosy consultant and Physiotherapist is not required for the state at this time.

    - Special Provision for selected States/UTs

Not applicable for the State

    - High endemic Blocks

Special provision for providing one Para Medical Worker on contractual basis for leprosy supervision, monitoring and programme implementation in high endemic blocks and urban areas of identified high endemic districts, have been approved during the 12th Plan period. The proposal is  as below-

| S.No | Category of post | No. of high endemic blocks/Urban areas identified | Unit cost per month (Rs.) | Unit cost per year (Rs.) | Total cost (Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1. | Paramedical Worker in Block/PHC | 2 | 16,000 x 2 | 1,92,000 x2 | 3,84,000 |
| 2. | Paramedical Worker in urban areas | - | - | - | - |
| Total |  |  |  |  | 3,84,000 |

In Mizoram, out of the 34 new cases detected during 2013-2014 January, 28 cases are from one district alone, which is Lawngtlai District. Hence, the ANCDR may be calculated as follows:-

No. of new cases detected = 28

Population of Lawngtlai district = 1,17,894

ANCDR = 23 per 100,000 population.

In Lawngtlai District, there are two blocks which are identified as high endemic blocks during 2013- 2014 January. These two blocks are 1. Chawngte Block   2. Lawngtlai Block(Bungtlang South area). Hence hiring of PMW  is requested for these two blocks.

- Programme Management

  - Travel Cost

Travel cost and Review Meetings

| S.No. | Activity | No. of unit (State/District) | Unit cost (Rupees) | Total (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Travel cost for contractual persons at State level (Tick one of these) | >5-9 distt. | 60,000 x 5 | 3,00,000 |
| 2. | Travel cost for contractual persons at district level | - | - | - |
| Total |  | - | - | 3,00,000 |

  - Review meetings

| S.No. | Activity | No. of unit (State/District) | Unit cost (Rupees) | Total (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | State level Review meetings (Quarterly) | 9 | 9 X 50,000 | 4,50,000 |
| Total |  | - | - | 4,50,000 |

  - Office operation and maintenance

This may be calculated for State/UT according to number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Rent, Telephone, Electricity, P&T charges, Miscellaneous District | 9 | 9 x 35000 | 3,15,000 |
| 2. | State Leprosy Cell | 1 | 1 x 75000 | 75,000 |
| 3. | Office Equipment Maintenance cost State Leprosy Cell | 1 | 1 x 50,000 | 50,000 |
| Total |  |  |  | 4,40,000 |

  - Consumables

This may be calculated for State/UT according to number of districts

| S.No | Stationery Items | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | District | 9 | 9 x 30000 | 2,70,000 |
| 2 | State Leprosy Cell | 1 | 1 x1,00,000 | 1,00,000 |
|  | Total |  |  | 3,70,000 |

  - Mobility support - Vehicle Hiring and POL/Maintenance

| S.No | Item | No. of districts | No. of Vehicle | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- |
| 1 | District Leprosy Unit | 9 | 1 | 150000 | 13,50,000 |
| 2 | State Leprosy Cell | 1 | 2 | 200000 | 4,00,000 |
|  | Total | 9 | 3 | 3,50,000 | 17,50,000 |

- Additionality in Annual Plan

- NRHM

Details of activities with justification for which funds under additionality are proposed and agreed by the State NRHM may be indicated.

- WHO, ILEP, ICMR and Other Organizations

Project activities planned to be carried out with such other partner organizations with justification indicating budget may be shown separately for each organization.

NOTE : 	A summary of the State/UT budget proposal will be indicated in the attached Format.

--X--

Format for submitting budget proposal under NLEP for 2014-15

(Rs. in lakhs)

| Sl. No. | Name of District | Functional head wise budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Case detection & Management |  |  |  |  |  | DPMR | IEC/BCC | Human Resources & Capacity building |  | Programme Management |  |  |  | Total Budget |
|  |  |  |  |  |  |  |  |  |  | Training | Human Resources | Travel cost | Review meeting | Office Expenses & Consumable | Mobility support |  |
|  |  | ASHA | Special Activities (ICDD) | Urban | Material & Supplies | NGO | Operational Research |  |  |  |  |  |  |  |  |  |
| 1 | Aizawl East |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| 2 | Aizawl West |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| 3 | Champhai |  |  | 1.14 |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 4.27 |
| 4 | Kolasib |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| 5 | Mamit |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| 6 | Serchhip |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| 7 | Lunglei |  |  | 1.14 |  |  |  |  | 0.98 |  | 1.92 |  |  | 0.65 | 1.5 | 6.19 |
| 8 | Lawngtlai |  | 2.00 | 1.14 |  |  | 2.00 |  | 0.98 |  | 1.92 |  |  | 0.65 | 1.5 | 10.19 |
| 9 | Saiha |  |  |  |  |  |  |  | 0.98 |  |  |  |  | 0.65 | 1.5 | 3.13 |
| A- Total of District |  |  | 2.00 | 3.42 |  |  | 2.00 |  | 8.82 |  | 3.84 |  |  | 5.85 | 13.5 | 39.43 |
| B- State HQ Cell |  |  | 0.75 | 2.40 | 6.12 | 9.00 |  | 2.06 |  | 3.95 | 19.44 | 3.00 | 4.50 | 2.25 | 4.00 | 57.47 |
| Grand total (A+B) |  |  | 2.75 | 5.82 | 6.12 | 9.00 | 2.00 | 2.06 | 8.82 | 3.95 | 23.28 | 3.00 | 4.50 | 8.10 | 17.50 | 96.90 |

Additionality

| Organization | Project details | Total Budget |
| --- | --- | --- |
| NRHM |  |  |
| WHO |  |  |
| ILEP |  |  |
| Other Organization (Specify) |  |  |
| Total |  |  |