SKILL ASSESSMENT PLAN, ENHANCEMENT TRAINING PLAN AND ESTABLISHMENT OF SKILL LABORATORY PLAN

Skill laboratory for Skill base Training  for HR   will be set up in the State  as per Govt. of India Operational Guidelines.

In the 1st Phrase (i.e. 2014-15) Skill Labs will set up at Aizawl and Lunglei district only.

Secondly, in the 2nd phrase during 2015-16, it will be targeted at 4 district, namely, Champhai, Lawngtlai, kolasib and Mamit district.

Thirdly, in the 3dr phrase during 2016-17, it will be set up at another remaining district such as, Saiha and Serchhip district.

These two District have  H/W/ANM  Training School which  are well equip with  other requisite and will be extended for establishment of Skill Labs. Besides, the Training Schools  have Hostel which are convenient for accommodation of the Training participants. As the establishment  of Skill labs  premises,  these two Training School are located nearby of District Hospital of Aizawl and Lunglei district.

Institutional Set up

- State Nodal Officer : Principal, Aizawl ANM Training School will be appointed as State Nodal Officer.

- District Nodal Officer : Each District Principal, Each District ANM/Training school Nursing College will be appointed for District  Nodal Officer. If there is no such Training School/college,  Medical Superitendent  of District Hospital will be appointed for District  Nodal Officer.

- As per guidelines, Each Skill Labs will be comprises of the following Staff.

- MBBS preferably Lady Medical Officer	1 no.

- BSc/Post Graduate Nursing			3 no.

- Training coordinators				1 no.

- Data Entry Operator				1 no.

- IV Grade					1 no.

Establishment of Skill Labs

Skill labs will be set up as per GOI guidelines, therefore, categorized requirement are listed as below.

- Infrastructure development

Civil works/Furniture/Wood work	/renovation/Electrical work with power backup by 5 KVAgenerator/water supply and other ancillary requirement  for skill lab including seminar room and office set up (New MCH wing have built-in skill lab and seminar room etc. so no separate budgeting is required for skills lab in these MCH wing for civil works).

- Mannequins & Equipement (as per specification)

- (1)	Consumable & supplies

Teaching –learning material (2 Computers, 2 Laptops, 1 LCD projector, 1 screen, 1 printer cum Fax cum photocopier, etc.)

(2)	POL for Generator – Diesel @ 10 litres per day

(3)	Stationeries – Register, Paper and other materials like printer cum Fax cum photocopier ink.

4.	Annual Maintenance of Equipments, Mannequins, Generators, etc

Assessment Plan

- 307  nos.  of  HR  (32 -MOs/ 96-SNs/ 9 – ANMs + 138 - ANMs of sc conducting delivery / 32 Lab. Tech)  from  all Delivery points and Sub Centre conducting Delivery  will be assessed.

- Assessment  and Training  for  all facilities  under   Pilot District selecting two districts, namely Lawngtlai and Saiha district will be conducted from 3rd  quarter of 2014-15.

- Thirdly,  assessment and Training  for  all facilities  other than Facilities under Lawngtlai and Saiha District  will be started  from 2015-16 onwards .

Enhancement Training Plan

- After having assessment of such mentioned  HR,  enhancement training  188  nos.  of  HR  (32 -MOs/ 96-SNs/28 - ANMs/ 32 Lab. Tech=188) of  delivery points + 5% of Sub Centre  will be conducted during  4th quarter of 2014-15.

- Enhancement Training  for  all facilities  under  4  High Priority  District selecting namely Lawngtlai, Lunglei, Mamit  and Saiha district will be conducted from 3rd  - 4th quarter of 2014-15.

- Regular Pre- Services and Post Service assessment and training for all HR and  newly  recruited HR  under State and NHM  will be conducted  from 2015-16 onwards.

- CALENDAR

( 1 )	District-wise Assessment Calendar

| Sl.No | Name of District | Total Assessment / Training Load | No of Batch ( 30 per batch) | No of days needed for assessment/Training | Venue of assessment/Training | Dates/Period assessment/Training |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | District – DPs + 5% SCs | 307 nos. of HR (32 -MOs/ 96-SNs/ 9 – ANMs + 138 - ANMs of sc conducting delivery / 32 Lab. Tech) 10 batches | 10 | 20 | DHs - Aizawl Lunglei, Kolasib district and Christian Hospital Serkawn, Lunglei | 2nd Quarter,2014-15 |
| 2 | Lawngtlai (Pilot District) | 64 nos. of HR (3 -MOs/ 9-SNs/ 39 – ANMs /3 lab tech | 2 | 4 | DH – Lunglei district | 3rd Quarter 2014-15 |
| 3 | Saiha (Pilot District) | 55 nos. of HR (4 -MOs/ 12-SNs/ 26 – ANMs /4lab tech | 2 | 4 | DH – Lunglei district | 3rd Quarter 2014-15 |
| 4 | Aizawl East | 75 nos. of HR (2 -MOs/ 6-SNs/ 65 – ANMs /2 lab tech | 3 | 6 | DH - Aizawl West district. | 2nd Quarter 2015-16 |
| 5 | Aizawl West | 87 nos. of HR (7 -MOs/21-SNs/ 52 – ANMs /7lab tech | 3 | 6 | DH - Aizawl West district. | 3rd Quarter 2015-16 |
| 6 | Champhai | 77 nos. of HR (9 -MOs/27-SNs/ 42 – ANMs /9lab tech | 3 | 6 | DH - Aizawl West district. | 3rd Quarter 2015-16 |
| 7 | Kolasib | 53 nos. of HR (6 -MOs/18-SNs/ 23 – ANMs /6 lab tech | 2 | 4 | DH Kolasib District | 4th Quarter 2014-15 |
| 8 | Lunglei | 115 nos. of HR (10 -MOs/30-SNs/ 65 – ANMs /10 lab tech | 4 | 8 | DH Lunglei District | 2nd Quarter 2015-16 |
| 9 | Mamit | 54 nos. of HR (5 -MOs/15-SNs/ 29 – ANMs /5 lab tech | 2 | 4 | DH Aizawl West District | 4th Quarter 2015-16 |
| 10 | Serchhip | 36 nos. of HR (3 -MOs/9-SNs/ 21 – ANMs /3 lab tech | 1 | 2 | Serkawn Christian Hospital, Lunglei District | 2nd Quarter 2015-16 |
| 11 | State | 836 nos. of HR (79 -MOs/237-SNs/ 435 – ANMs /79 lab tech | 28 batches | 56 days | DHs - Aizawl Lunglei, Kolasib district and Christian Hospital Serkawn, Lunglei |  |

(2)	District-wise competency enhancement Training Calendar

| Sl.No | Name of District | Total Assessment / Training Load | No of Batch ( 16 per batch) | No of days needed for assessment/Training | Venue of assessment/Training | Dates/Period assessment/Training |
| --- | --- | --- | --- | --- | --- | --- |
|  | District – DPs + 5% SCs | 307 nos. of HR (32 -MOs/ 96-SNs/ 9 – ANMs + 138 - ANMs of sc conducting delivery / 32 Lab. Tech) 10 batches | 20 | 120 | DHs - Aizawl Lunglei, Kolasib district and Christian Hospital Serkawn, Lunglei | 3 &4th Quarter, 2014-15 |
| 1 | Lawngtlai (Pilot District) | 64 nos. of HR (3 -MOs/ 9-SNs/ 39 – ANMs /3 lab tech | 4 | 24 | Skill Lab, Lunglei district | 4th Quarter 2014-15 |
| 2 | Saiha (Pilot District) | 55 nos. of HR (4 -MOs/ 12-SNs/ 26 – ANMs /4lab tech | 3 | 18 | Skill Lab, Lunglei district | 3rd Quarter 2014-15 |
| 3 | Aizawl East | 75 nos. of HR (2 -MOs/ 6-SNs/ 65 – ANMs /2 lab tech | 5 | 30 | Skill Lab, ANM Training School, Aizawl | 4th Quarter 2015-16 |
| 4 | Aizawl West | 87 nos. of HR (7 -MOs/21-SNs/ 52 – ANMs /7lab tech | 6 | 36 | Skill Lab, ANM Training School, Aizawl | 4th Quarter 2015-16 |
| 5 | Champhai | 77 nos. of HR (9 -MOs/27-SNs/ 42 – ANMs /9lab tech | 5 | 30 | District Skill lab, Champhai Dist. | 1st quarter 2016-17 |
| 6 | Kolasib | 53 nos. of HR (6 -MOs/18-SNs/ 23 – ANMs /6 lab tech | 3 | 18 | DH Kolasib District | 4th Quarter 2014-15 |
| 7 | Lunglei | 115 nos. of HR (10 -MOs/30-SNs/ 65 – ANMs /10 lab tech | 7 | 42 | Skill Lab, Lunglei district, Aizawl | 3rd & 4th Quarter 2015-16 |
| 8 | Mamit | 54 nos. of HR (5 -MOs/15-SNs/ 29 – ANMs /5 lab tech | 3 | 18 | Skill Lab, ANM Training School, Aizawl | 4th Quarter 2014-15 |
| 9 | Serchhip | 36 nos. of HR (3 -MOs/9-SNs/ 21 – ANMs /3 lab tech | 2 | 12 | Serkawn Christian Hospital, Lunglei District | 2nd Quarter 2015-16 |
| 10 | State | 529 nos. of HR (47 -MOs/141-SNs/297 – ANMs /47 lab tech | 33 batches | 198 days | DHs - Aizawl Lunglei, Kolasib district and Christian Hospital Serkawn, Lunglei |  |

- ASSESSMENT PLAN for 2014-15

( 1 )	ASSESSMENT PLAN FOR DELIVERY POINTS, 5 % OF SUB CENTRE AND  SUB CENTRE CONDUCTING DELIVERY

| Sl.No | Name of District | Total Assessment / Training Load | No of Batch ( 30 per batch) | No of days needed for assessment/Training | Venue of assessment/Training | Dates/Period assessment/Training |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | District – DPs + 5% SCs | 307 nos. of HR (32 -MOs/ 96-SNs/ 9 – ANMs + 138 - ANMs of sc conducting delivery / 32 Lab. Tech) 10 batches | 10 | 20 | DHs - Aizawl Lunglei, Kolasib district and Christian Hospital Serkawn, Lunglei | 2nd Quarter,2014-15 |

No of Participants : 307  nos.  of  HR  (32 -MOs/ 96-SNs/ 147 ANMs (9 – ANMs + 138 - ANMs of sc conducting delivery )/ 32 Lab. Tech) , 10 batches

Budget estimation

| Sl.No | Fund requirement (TA/DA/Others) | Amount (in Rs.) |
| --- | --- | --- |
| 1 | DA for 27 ANM/SN@ Rs. 300/- per head for 2 days | 16200 |
| 2 | DA for 3 MOs@ Rs.500/- per head for 2 days | 3000 |
| 3 | TA for 27 ANM/SN/Lab Tech @ Rs. 700 (to and fro) per head | 18900 |
| 4 | TA- POL for 3 MOs @ Rs. 3000 (to and fro) per head | 9000 |
| 5 | Lunch & Tea for the Trainee Rs.250 x 30 participants x 2days | 15000 |
|  | Sub Total | 62100 |
| 6 | 10 % for Contingency (Teaching Material, Course Material & MIS Expenses) | 6210 |
|  | TOTAL | 68,310 |

Under delivery Points + 5 %  Sub Centre + Sub Centre conducting delivery,  HR assessment have been planned  for  10 batches of 307  nos.  of  HR  (32 -MOs/ 96-SNs/ 147 ANMs (9 – ANMs + 138 - ANMs of sc conducting delivery )/ 32 Lab. Tech). Fund requirement  is estimated as above, Rs. 89,100/- per assessment training. Total fund requirement  for delivery Points + 5 %  Sub Centre + Sub Centre conducting delivery is Rs. 6,83,100/-.

( 2 )	ASSESSMENT PLAN FOR PILOT DISTRICT UNDER LAWNGTLAI AND SAIHA DISTRICT

| Sl.No | Name of District | Total Assessment / Training Load | No of Batch ( 30 per batch) | No of days needed for assessment/Training | Venue of assessment/Training | Dates/Period assessment/Training |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Lawngtlai (Pilot District) | 64 nos. of HR (3 -MOs/ 9-SNs/ 39 – ANMs /3 lab tech | 2 | 4 | DH – Lunglei district | 3rd Quarter 2014-15 |
| 2 | Saiha (Pilot District) | 55 nos. of HR (4 -MOs/ 12-SNs/ 26 – ANMs /4lab tech | 2 | 4 | DH – Lunglei district | 3rd Quarter 2014-15 |

No of Participants : 119  nos.  of  HR  (7 -MOs/ 21-SNs/ 65 ANMs / 7 Lab. Tech , 4 batches

Budget estimation

| Sl.No | Fund requirement (TA/DA/Others) | Amount (in Rs.) |
| --- | --- | --- |
| 1 | DA for 28 ANM/SN@ Rs. 300/- per head for 2 days | 16800 |
| 2 | DA for 2 MOs@ Rs.500/- per head for 2 days | 3000 |
| 3 | TA for 28 ANM/SN/Lab Tech @ Rs. 700 (to and fro) per head | 19600 |
| 4 | TA- POL for 2 MOs @ Rs. 3000 (to and fro) per head | 6000 |
| 5 | Lunch & Tea for the Trainee Rs.250 x 30 participants x 2days | 15000 |
|  | Sub Total | 60400 |
| 6 | 10 % for Contingency (Teaching Material, Course Material & MIS Expenses) | 6040 |
|  | TOTAL | 66,440 |

Under Pilot district,  HR assessment have been planned  for  4 batches of 119  nos.  of  HR  (7 -MOs/ 21-SNs/ 65 ANMs / 7 Lab. Tech. Fund requirement  is estimated as above, Rs. 88,000/- per assessment training. Total fund requirement  is Rs. 2,65,760/-

( 3 ) ASSESSMENT PLAN FOR OTHER HP  DISTRICT LUNGLEI AND MAMIT DISTRICT

( a) Lunglei

3. KNOWLEDGE AND SKILL ENHANCEMENT TRAINING PLAN for 2014-15

( 1 )	 Knowledge and Skills enhancement Training  Plan for HR for  DPs + 5% SCs and SC  conducting delivery during 3rd & 4th Quarter  of 2014-15.

No of Participants : 307  nos.  of  HR  (32 -MOs/ 96-SNs/ 147 ANMs (9 – ANMs + 138 - ANMs of SC  conducting delivery )/ 32 Lab. Tech) ,

No of batch : 10 batches

Time : 3rd - 4th Quarter,2014-15

Budget estimation

| Sl.No | Fund requirement (TA/DA/Others) | Amount (in Rs.) |
| --- | --- | --- |
| 1 | DA for 14 ANM/SN/Lab Tech @ Rs. 400/- per head for 6 days | 33600 |
| 2 | DA for 2 MOs@ Rs.700/- per head for 6 days | 8400 |
| 3 | TA for 14 ANM/SN/Lab Tech @ Rs. 700 (to and fro) per head | 9800 |
| 4 | TA- POL for 2 MOs @ Rs. 3000 (to and fro) per head | 6000 |
| 5 | Lunch & Tea for the Trainee Rs.250 x 16 participants x 6 days | 24000 |
|  | Sub Total | 81800 |
| 6 | 10 % for Contingency (Teaching Material, Course Material & MIS Expenses) | 8180 |
|  | TOTAL | 89,980 |

- Delivery Points + 5 %  Sub Centre + Sub Centre conducting delivery,  HR assessment have been planned  for  20 batches of 307  nos.  of  HR  (32 -MOs/ 96-SNs/ 147 ANMs (9 – ANMs + 138 - ANMs of sc conducting delivery )/ 32 Lab. Tech). Fund requirement  is estimated for  Rs. 89,980/- per batch of assessment training. Total fund requirement  for 20 batches of delivery Points + 5 %  Sub Centre + Sub Centre conducting delivery is Rs. 17,99,600/-

- Enhancement Training of 53  nos.  of  HR  (6 -MOs/18-SNs/ 23 – ANMs /6 lab tech under Kolasib District also will be conducted during 4th quarter,2014-15. Fund requirement  is estimated for  Rs. 89,980/- per batch of assessment training. Total fund requirement  for 3 batches is estimated  Rs. 2,69,940/-

- Enhancement Training of 53  nos.  of  HR  (6 -MOs/18-SNs/ 23 – ANMs /6 lab tech under HP District Lawngtlai, Lunglei, Mamit and Saiha also  will be conducted during 3rd and 4th quarter,2014-15. Fund requirement  is estimated for  Rs. 89,980/- per batch of assessment training. Total fund requirement  for 3 batches is estimated  Rs. /-

Budget Requirement for 2014-15

| Sl.No | Particulars | No | Rate (in Rs.) | Amount (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Infrastructure |  |  |  |
|  | Civil works/Furniture/Wood work /renovation/Electrical work with power backup by 5 KVAgenerator/water supply and other ancillary requirement for skill lab including seminar room and office set up (New MCH wing have built-in skill lab and seminar room etc. so no separate budgeting is required for skills lab in these MCH wing for civil works). | 2 | 20,00,000 | 40,00,000 |
| 2 | Mannequins & Equiptment (as per specification) | 2 | 15,00,000 | 30,00,000 |
| 3 | 1) Consumable & supplies |  |  |  |
|  | Teaching –learning material (2 Computers, 2 Laptops, 1 LCD projector, 1 screen, 1 printer cum Fax cum photocopier, etc.) | 2 | 3,00,000 | 6,00,000 |
|  | 2)POL for Generator – Diesel @ 10 litres per day | 2 | 1,72,800 | 3,45,600 |
|  | 3)Stationeries – Register, Paper and other materials like printer cum Fax cum photocopier ink. | 2 | 50,000 | 1,00,000 |
| 4 | Annual Maintenance of Equipments, Mannequins, Generators, etc | 2 | 40,000 | 80,000 |
| 5 | Human resources |  |  |  |
|  | 1. MBBS preferably Lady Medical Officer | 2 | 66,000 | 7,92,000 |
|  | 2. BSc/Post Graduate Nursing | 2 | 46000 | 5,52,000 |
|  | 3. Training coordinators | 2 | 25000 | 3,00,000 |
|  | 4. Data Entry Operator | 2 | 17800 | 213600 |
|  | 5. IV Grade | 2 | 8000 | 96000 |
| 6 | Competency Assessment of skill for SNs/ANMs/Lab tech | 14 batches | 67,776 | 10,84,416 |
| 7 | Training for enhancement of Skill for HR at Delivery points, 12 batches. | 41 batches | 89,980 | 3689180 |
| 8 | Monthly visit of Mentoring Group for 6 months | 6 months | 50000 | 3,00,000 |
|  | TOTAL |  |  | 1,57,81,980 |