Back ground information required for approval of State PIP 2014-2015

FMR Code-B1: ASHA Programme

State PIP 2014-2015 focuses on equipping the ASHAs with the crucial HBNC Kit needs and filling the gap where more ASHAs and ASHA Mobilizers are needed in the State. The NIOS certification for the ASHAs will be prioritized from 2015-2016 State PIP onward. The state has intentionally decided to go ahead with this step by step process of equipping the ASHAs adequately and then with refresher trainings and experiences in the field work, come up with the certification.

With high ASHA drop out and replacement rate, the state has decided to prepone the NIOS Certification for the next year. Therefore, this current State PIP, 2014-2015 (ASHA Programme) focusses on building the ASHA structure and re integrating the administrative structure and activating the available and existing systems to empower the ASHAs.

Status of ASHA Selection in Mizoram:

ASHA Annexure-I

| *POPULATION | ASHA REQUIRED as per POPULATION | ASHA MOBILIZER | ASHA ENGAGED | ASHA SHORTFALL. TARGET-2014-2015. |
| --- | --- | --- | --- | --- |
| Rural population | Rural Areas |  | Rural Areas | Rural Areas |
| 782276 | 1204 | 121 | 842 | 362 |
| Urban Population | Urban Areas |  | Urban Areas | Urban Areas |
| 333321 | 334 | 17 | 145 | 189 |
| *1115597 | 1538 | 138 | 987 | 551 |
| Rural HPD POPU. | Rural HPD areas |  | HPD Rural | HPD Rural |
| 356004 | 548 | 55 | 455 | 93 |
| Rural NHPD POPU. | Rural NHPD |  | NHPD Rural | NHPD Rural |
| 426272 | 656 | 66 | 387 | 269 |
| Urban HPD | Urban HPD Areas |  | Urban HPD | Urban HPD |
| 62800 | 63 | 3 | 41 | 22 |
| Urban NHPD | Urban NHPD Areas |  | Urban NHPD | Urban NHPD |
| 270521 | 271 | 14 | 104 | 167 |
| *1115597 | 1538 | 138 | 987 | 551 |

*Source: Mizoram State latest HMIS Report, 2013-2014

The population data is derived from the HMIS report, Mizoram 2013-2014 and as advised by the HMS Manager. The 2011 census population (1091014) used for the 2013-2014 was a PROVISIONAL data. Therefore, a more realistic population data (*1115597, State HMIS 2013-2014) needs to be used for the estimation of the need of number of ASHAs to actually work at the village level. As per the 2013-2014 State PIP there was a shortfall of 103 ASHAs based on the 2011 census population report of 1091014. However, considering the population gap between the provisional 2011 census and the State HMIS data for 2013-2014, an actual representation of the State population became more valid in the estimates for the ASHA status.

Considering the population difference in the two data source, the need for a more field based data (HMIS) is being used. This has resulted in the vast difference in the increasing need for the number of ASHAs in the State.

District-wise ASHA Status (Rural & Urban, HPD & NHPD) Distribution.

| Sl.No | DISTRICT | POPULATION | ASHA REQUIRED as per Population | No OF EXISTING ASHA | SHORTFALL OF ASHA | DISTRICT | TOTAL DISTRICT SHORTFALL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East (Rural) | 92007 | 142 | 47 | 95 | Aizawl East | 173 |
|  | Aizawl East (Urban) | 155079 | 155 | 77 | 78 |  |  |
| 2 | Aizawl West (Rural) | 50662 | 78 | 62 | 16 | Aizawl West | 75 |
|  | Aizawl West (Urban) | 115442 | 116 | 57 | 59 |  |  |
| 3 | Champhai | 136270 | 208 | 122 | 86 | Champhai | 86 |
| 4 | Kolasib | 83363 | 127 | 71 | 56 | Kolasib | 56 |
| 5 | Lawngtlai | 131671 | 203 | 174 | 29 | Lawngtlai | 29 |
| 6 | Lunglei (Rural) | 88528 | 137 | 144 | -7 | Lunglei | 15 |
|  | Lunglei (Urban) | 62800 | 63 | 41 | 22 |  |  |
| 7 | Mamit | 76333 | 118 | 66 | 52 | Mamit | 52 |
| 8 | Saiha District | 59472 | 92 | 71 | 21 | Saiha | 21 |
| 9 | Serchhip District | 63970 | 99 | 55 | 44 | Serchhip | 44 |
| TOTAL |  | 1115597 | 1538 | 987 | 551 |  | 551 |

The rural and urban population has been calculated as per the approval for the Urban Health Mission in the State. Aizawl and Lunglei Districts are the only two sites where the UHM is beong approved in Mizoram. Therefore, all the rest of the districts are categorized as RURAL. The Urban population, therefore includes the district headquarters of Aizawl East District, Aizawl West District and Lunglei District. This further points to the fact that except the headquarter district/town, all other villages and blocks are still considered and counted as RURAL as per the table shown above. Sl.No.1,2 and 6 have  proportionate distribution of the Urban and Rural population. This is further divided into the need for the number of ASHAs in the State.

All villages have ASHAs in place. However, due to the expansion of population, a village is likely to increase the number of Village Council for better administration. As the presence of an ASHA is based on the number of Village Council, the need for an increase in the number of ASHAs and ASHA Mobilizers is realized lately. A rough estimates showed that there are at least 114 ASHAs covering more than 1500 population.

As a result, there are ASHAs in the rural areas who cover 2-3 sparsely populated areas. Here, home visits becomes extremely difficult for the ASHAs especially during the monsoon due to heavy rains, landslides and absence of transportation due to slippery muddy roads.

The ASHA Mobilizers who are responsible for the regular supportive supervisory visits finds it more difficult to conduct the task. An ASHA Mobilizer in the so called “Urban Areas” covers from 15-41 ASHAs. Lunglei and Aizawl East and West are the URBAN areas considered. However, the reality is that more than 85% of these areas are hilly and difficult to reach areas. The ASHA functionality of the state clearly identifies that the poor performance areas are the DIFFICULT AREAS. Which means that the ASHA Mobilizers are unable to efficiently reach the entire areas. The supportive supervision visits conducted by RRC-NE Staff have also confirmed the situations. Therefore, in the light of what is happening and the need to scale up the supportive supervision visits by the Mobilizers, the state have proposed for the increase in the number of the ASHA Mobilizers from the existing 66 ASHA Mobilizers (placed in each PHCs, Main Centre and SDH of the Districts) to an additional of 72 Mobilizers as per the population distribution shown in the table provided above.

ASHA Annexure II

Status of ASHA Training:

| Sl.No | MODULES | CUMULATIVE ACHIEVEMENT (Since Inception till date) | PROPOSES NUMBER TO BE TRAINED IN 2013-2014 |
| --- | --- | --- | --- |
| 1 | Module 1 | 987 | 0 |
| 2 | Module 2 | 987 | 0 |
| 3 | Module 3 | 987 | 0 |
| 4 | Module 4 | 987 | 0 |
| 5 | Module 5 | 987 | 0 |
| 6 | Module 6&7 Round-1 | 987 | 0 |
| 7 | Module 6&7 Round-2 | 987 | 0 |
| 8 | Module 6&7 Round-3 | 987 | 0 |
| 9 | Module 6&7 Round-4 | 0 | 1538 |
| OTHER ASHA TRAININGS: |  |  |  |
| Sl.No | MODULES/TRAINING ACTIVITY | CUMULATIVE ACHIEVEMENT (Since Inception till date) | PROPOSES NUMBER TO BE TRAINED IN 2013-2014 |
| 1 | Special Medical Skill Enhancement Training for ASHAs | 0 | 1676 |
| 2 | Induction Training (Integrated module 1-5) | 0 | 726 |
| 3 | Coordinator and Mobilizers on Facilitator Hand Book | 0 | 147 |
| 4 | Refresher Training on District TOT, Mod.6&7 | 0 | 18 |
| 5 | Refresher Training on Functionality Report | 0 | 147 |

ASHAs in the State have undergone training from Module 1-4, 5 and Module 6-7 (1-3 Round) till 2013-2014 financial year. However, the number of ASHA drop out was captured late in 2013-2014. This ASHA Drop out amounted to 13% of the total 987 ASHAs in the State. In as much, though there was a 13% drop out, there was no vacuum left. All ASHA Drop outs were immediately replaced, however, without trainings till November, 2013. The ground reality can be a different scenario in spite of the reported 13% drop out. This means that apart from the official report of 13 % drop out, more drop out and replacements are expected at the field level. The supervisory and monitoring visits by the RRC-NE staff have pointed the same. As a result, the trainings and refreshers training needs to be inclusive of a maximum coverage for skill enhancement.

It may be noted that since Mizoram is a hilly and difficult state, the ratio of 1 ASHA per 1000 population has been redefined to meet the state specific need as:

- Rural Areas	: 1 ASHA for every 650 population (State specific need/adjustment)

- Urban Areas	: 1 ASHA for every 1000 population (as per guideline).

(Please refer to the table in Annexure I for the Urban and Rural Distribution)

Rural Area coverage by an ASHA is being reduced from the general 1000 population to 650 due to the sparse distribution of population (Mizoram Population density is 40p/Sq.Km). This issue had been put up with NHSRC and due consent have been discussed in Review Meetings.

Module 6&7 Round 4 is being proposed again (was approved in 2013-2014 ROP) because the approved amount in the State PIP-2013-2014 was utilized to conduct a REFRESHER TRAINING for the ASHAs with the consent and suggestion from NHSRC (discussed and consented on 29-30 Nov.2013 Review Meeting at Guwahati). A letter regarding the fund utilization for Refresher Training and the need for approval for 2014-2015 are stated in the letter sent to the Ms. Anuradha Gupta, MD, New Delhi, vide even no. No.B.11011/3/2013-NRHM (SPMSU) 162, dated 4/12/2013, with a copy marked to-

- Dr. Baishya, Director, RRC-NE, Guwahati, Assam.

- Ms. Preeti Pant, Director, North East Division, NRHM, New Delhi.

- Dr. Sundararaman, Executive Director, NHSRC, New Delhi.

- Dr. Rajani Ved, Advisor, Community Process, NHSRC, New Delhi.

- File copy, (Community Process/ASHA), NRHM, Mizoram.

FMR Code B1.1.1 SELECTION AND TRAINING OF ASHA

FMR Code B1.1.1.1 (Integrated Induction Training on Module 1-5)

| Sl.No | DISTRICT | New ASHAs | New Mobilizers | DROP OUT /REPLACEMENTS | TOTAL TRAINEES | BATCH | AMOUNT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East District (Rural) | 95 | 12 | 12 | 119 | 5 | 932000 |
|  | Aizawl East District (Urban) | 78 | 4 | 6 | 88 | 3 | 559200 |
| 2 | Aizawl West District (Rural) | 16 | 2 | 10 | 28 | 1 | 186400 |
|  | Aizawl West District (Urban) | 59 | 6 | 16 | 81 | 3 | 559200 |
| 3 | Champhai District | 86 | 8 | 6 | 100 | 3 | 559200 |
| 4 | Kolasib District | 56 | 6 | 4 | 66 | 2 | 372800 |
| 5 | Lawngtlai District | 29 | 15 | 8 | 52 | 1 | 186400 |
| 6 | Lunglei District (Rural) | -7 | 3 | 7 | 3 | 1 | 186400 |
|  | Lunglei District (Urban) | 22 | 2 | 12 | 36 | 1 | 186400 |
| 7 | Mamit District | 52 | 4 | 9 | 65 | 2 | 372800 |
| 8 | Saiha District | 21 | 5 | 11 | 32 | 1 | 186400 |
| 9 | Serchhip District | 44 | 5 | 2 | 56 | 2 | 372800 |
| TOTAL |  | 551 | 72 | 103 | 726 | 25 | 4660000 |

As per the State HMIS population report 2013-2014, the table above is the representation of the number of ASHAs existing, required and needing training. Out of the existing 987 ASHAs in the State, an additional of 551 ASHAs are needed and out of the existing 66 Mobilizers, 72 needed induction training. This training need is as per the requirement suggested by the Ministry in the improved State PIP 2014-2017 guidelines for the Community Process whereby a 15 days integrated training from Module 1-5 for all new ASHAs and Mobilizers.

There are 551 new ASHAs proposed against the existing 987. More so, an additional of 103 ASHA Drop outs/replaced are also included for the training. This makes the total number of ASHA more than the actual new ASHA proposed to 654 trainees.

The trainees are divided into batch (1 Batch= 30 trainees). Here, an average of Rs.186400/- per batch is estimated for this proposed training inclusive of their TA and DA and training materials and the Trainers cost altogether. Therefore the total amount for the integrated Induction training for 654 new ASHAs and 72 New Mobilizers constituting of 25 batches for 8 days training each is the total sum amount of Rs.46,60,000/- only (Rupees. Forty Six Lakhs and Sixty Thousand only).

Please note that the cost per ASHA or batch is more than the Module 6&7 training as the number of days, here, in this induction training is 8 days (double the number of days as in the Module 6&7)

FMR Code B1.1.1.2 (ASHA Training on Module VI & VII Round-4)

| Sl.No | AREAS | DISTRICT | ASHA REQUIRED as per Population | BATCH | RATE |
| --- | --- | --- | --- | --- | --- |
| 1 | NHPD RURAL | Aizawl East District (Rural) | 142 | 5 | 586000 |
|  | NHPD URBAN | Aizawl East District (Urban) | 155 | 6 | 703200 |
| 2 | NHPD RURAL | Aizawl West District (Rural) | 78 | 3 | 351600 |
|  | NHPD URBAN | Aizawl West District (Urban) | 116 | 4 | 468800 |
| 3 | NHPD RURAL | Champhai District | 208 | 7 | 820400 |
| 4 | NHPD RURAL | Kolasib District | 127 | 4 | 468800 |
| 5 | HPD | Lawngtlai District | 203 | 7 | 820400 |
| 6 |  | Lunglei District (Rural) | 137 | 5 | 586000 |
|  |  | Lunglei District (Urban) | 63 | 2 | 234400 |
| 7 |  | Mamit District | 118 | 4 | 468800 |
| 8 |  | Saiha District | 92 | 3 | 351600 |
| 9 | NHPD RURAL | Serchhip District | 99 | 3 | 351600 |
| TOTAL |  |  | 1538 | 53 | 6211600 |

As was mentioned earlier, the approved budget in the State ROP 2013-2014 for Round IV of Module 6&7 had been used for a REFRESHER TRAINING with the suggestion incorporated from NHSRC. Module 6&7 Round 4 is being proposed again (was approved in 2013-2014 ROP) because the approved amount in the State PIP-2013-2014 was utilized to conduct a REFRESHER TRAINING for the ASHAs with the consent and suggestion from NHSRC (discussed and consented on 29-30 Nov.2013 Review Meeting at Guwahati). A letter regarding the fund utilization for Refresher Training and the need for approval for 2014-2015 are stated in the letter sent to the Anuradha Gupta vide even no. No.B.11011/3/2013-NRHM (SPMSU) 162, dated 4/12/2013, with a copy marked to-

- Dr. Baishya, Director, RRC-NE, Guwahati, Assam.

- Ms. Preeti Pant, Director, North East Division, NRHM, New Delhi.

- Dr. Sundararaman, Executive Director, NHSRC, New Delhi.

- Dr. Rajani Ved, Advisor, Community Process, NHSRC, New Delhi.

- File copy, (Community Process/ASHA), NRHM, Mizoram.

The training will be conducted at the PHC or main Centre areas wise. This will enable better accessibility for the ASHAs and promote better attendance. The District and State Trainers will be the trainers. The training will be for a period of 4 days each in each districts. The table shows the detailed training budget cost. It has been estimated that a sum of Rs.3400/- per ASHA is being estimated. This comes to a sum total of Rs.117200 /- per batch consisting of 30 trainees each for 4 days each. A total of 53 batches is calculated which amounts to a total sum amount of Rs.62,11,600 /- only (Rupees. Sixty Two Lakhs Eleven Thousand and Six Hundred only)

FMR Code B1.1.1.3 SUPPLEMENTARY TRAINING FOR ASHAs:

FMR Code B1.1.1.4.1 (ASHA Mobilizers and Coordinators on Facilitators Hand Book)

| DISTRICT | COORDINATORS | MOBILIZER | TOTAL TRAINEES | BATCH | AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Aizawl East District (Rural) | 1 | 14 | 23 | 1 | 112800 |
| Aizawl East District (Urban) |  | 8 |  |  |  |
| Aizawl West District (Rural) | 1 | 8 | 15 | 1 | 112800 |
| Aizawl West District (Urban) |  | 6 |  |  |  |
| Champhai District | 1 | 21 | 22 |  |  |
| Kolasib District | 1 | 13 | 14 | 1 | 112800 |
| Lawngtlai District | 1 | 20 | 21 |  |  |
| Lunglei District (Rural) | 1 | 14 | 18 | 1 | 112800 |
| Lunglei District (Urban) |  | 3 |  |  |  |
| Mamit District | 1 | 12 | 13 |  |  |
| Saiha District | 1 | 9 | 10 | 1 | 112800 |
| Serchhip District | 1 | 10 | 11 |  |  |
| TOTAL | 9 | 138 | 147 | 5 | 564000 |

The need for strengthening the ASHA Mobilizers and the ASHA Coordinators at the District and the PHC level is crucial for the effective management for the ASHAs in the community level. This management is link to the thorough knowledge of the ASHA Facilitator’s Handbook. Training on this handbook will enable the ASHA Coordinator and Mobilizers to effectively engage themselves and increase the ASHA performance. The ASHA Mobilizers and Coordinators have not been trained efficiently in the management level. Their training on module 6&7 does not fully prepare them in the management skills and knowledge of the administrative process in the ASHA Programme.

Thus, as per the HMIS population, 138 ASHA Mobilizers are required in Mizoram as against the existing 66 ASHA Mobilizers. This is calculated on the basis of 1 ASHA Mobilizer for every 20 ASHAs in the Urban areas and 1 ASHA Mobilizer for every 10 ASHAs in Rural Areas. This is a state specific requirement to minimize the coverage population for rural areas due to sparse population distribution and difficult coverage. The poor functionality score for the ASHAs is directly responsible for the efficient coverage of the Mobilizers amongst their ASHAs within their catchment areas. Thus, increase in the number of ASHA Mobilizers from the existing 66 to 138 will strengthen the field monitoring and supervisory support for the ASHA and improve their performances. Therefore a total number of 9 ASHA Coordinators and 138 ASHA Mobilizers across the 9 Districts are being proposed to be trained. This reflects to the state of Rs.3380 per trainees and a sum amount of Rs.112800/- per batch consisting of 30 trainees. Thus, a total sum amount of Rs.5,64,000/- (Rupees. Five Lakhs and Sixty Four Thousand only) for the entire training cost inclusive of TA and DA, Trainers’ cost and training materials altogether.

FMR Code B1.1.1.4.2 (District ToT Refresher Training)

| Sl.No | ACTIVITIES | COST/ITEMS | REMARKS |
| --- | --- | --- | --- |
| 1 | Number of Mobilizers and Coordinators to be trained | 9 Coordinators + 9 DPM+5 State Trainers | 23 Trainers/attendees. |
| 2 | Number of Batches required @ 30 per batch | 1 batch | An average of 30 persons per batch as per guidelines. |
| 3 | Costing details per batch - | 138500 |  |
| 4 | Duration, | 5 days |  |
| 5 | TA,/DA, | 72000 | TA Rs.1500 (both ways) x 18 + DA Rs.500x 18 x5 |
| 6 | Venue,/accommodation, | 5000 | Hall rent Rs.1000 per day x 5 days |
| 7 | Resource person’s honorarium | 25000 | Rs.1000 x 5 Trainers x 5days |
| 8 | officials | 12500 | DA Rs.500x 5officialsx 5 days |
| 9 | Refreshments | 19000 | Rs.100X1 batch+ 5 trainers+3 officialsX5 days=19000 |
| 10 | Training material etc | 5000 | Rs.200 x 25 (supporting staffs included) |
| 11 | Total cost | 119500 | Rs.138500 x 1 batch |

The State has only 3 State Trainers. The existing District Programme Managers (9 in numbers) are the district trainers. However, with the number of ASHAs in each district, 1 District trainer is too less to conduct an effective training. Therefore, the ASHA Coordinators (9 in numbers) are also envisaged to be trained as District Trainers. Therefore, a total of 18 District Trainers to be given a ToT training for efficient training Programme at the district level. The State has proposed for the inclusion of two additional trainers from the Chakma speaking community in the western belt of Lunglei and Lawngtlai districts (Tlabung and Chawngte). Thus, including the existing 3 state trainers, there will be a total of 23 trainers (both state trainers and district trainers) along with other supporting staffs; which makes it to 1 batch of 30 participants. The training will be conducted at Aizawl for better infrastructure and management efficiency and to adhere to the quality of the training quality.

A total of Rs.138500/- (Rupees. One Lakh Thirty Eight Thousand and Five Hundred only) is calculated for the said training.

FMR Code B1.1.2. PROCUREMENT OF ASHA DRUG KIT

FMR Code B1.1.2.1 (New ASHA Drug Kits)

| Sr. No. | Name of Drugs in Drug Kit as per Guidelines for Community Processes and HBNC guidelines | QUANTITY |
| --- | --- | --- |
| 1 | Tab Paracetamol 500mg | 10 Strips (100 Tabs) |
| 2 | G.V. Paint | 1 Piece |
| 3 | Life- bouy Soap | 1 Piece |
| 4 | Provident Ointment 15gm tube | 1 Tube |
| 5 | Cotton Absorbent roll of 100gm | 1 roll |
| 6 | Bandage, 4cmx 4 meters | 10 rolls |
| 7 | Co-trimoxazole Suspension | 10 bottles |
| 8 | Tetracycline 250mg | 5 strips (50 caps) |
| 9 | ORS | 20 Sachets |

The above ASHA Drug Kit is the requirement for new proposed (551) and the Dropout/ replacements (103) ASHAs; together a total of 654 ASHAs New Kits are required for these new ASHAs to be fully functional. The list of Drug Kit is as per the entitlement of the ASHAs in the guidelines. The rates thereof are as per the State Procurement allowance. The rates as provided is estimated at Rs.718 per ASHA per Drug Kit.

| Sl.No | ITEMS | REQUIREMENT | COST | REMARKS |
| --- | --- | --- | --- | --- |
| 1 | Number of ASHA with Drug Kits | 987 | NA | Even though 987 ASHAs are recorded to have the Drug Kit, 103 drop out/replacements are without the essential ASHA Drug Kit. The rate of drop out/replacements rate is not static. It will rise and fall. Therefore a 10% allowance is requested as additional support to meet the unexpected future drop out, |
| 2 | No. of New Drug Kits required and unit cost details | 654 | 719400 | 103 ASHAs replacing drop out are without Drug Kit along with 551 new ASHAs required. (Rs.1000*X654 ASHA=Rs.654000).+ 10% extra for unforseen drop out=Rs.65400 = Rs.719400 *as per the latest MoH allowance. |

As per the provision of Rs.1000 per ASHA for the new ASHA Drug Kit, a sum amount of Rs.654000 (Rupees. Six Lakhs Fifty Four Thousand only) is being estimated. However, the State feels the need for the preparation to meet an unforeseen further ASHA Drop out and Replacements calls for a security of a 10% (Rs.65400/-)additional requests. It is necessary to ensure that the ASHAs be well equipped with the Drug Kit in case of drop out and replacement. Thus a total amount of Rs.719400 (Rupees. Seven Lakhs Nineteen Thousand and Four Hundred only) is being estimated for the procurement of new ASHA Drug Kit for 654 ASHAs.

FMR Code B1.1.2.3 PROCUREMENT OF ASHA HBNC KIT

FMR Code B1.1.2.3.1 New HBNC Kits.

Out of the 987 ASHAs in the State, 103 ASHAs are drop out/replacement is being reported as on November, 2013. The field reality is expected to be more than the reported figure. These drop out ASHAs are replaced with new ASHAs however they have no HBNC Kits at all. More so, 551 new ASHAs have been proposed and are expected to be appointed from 2014-2015. As per the 2011 Census (1115597), the total ASHA required is 1538 (Urban:1 ASHA per 1000 population. Rural: 1 ASHA per 650 (modified as per State specific need). Only 987 ASHAs are currently in existence and functioning. A total of 551 ASHAs shortfall is calculated as per the latest need. Therefore, the State has proposed and will appoint the remaining 551 ASHAs to fill the requirement. As such, HBNC Kit for the new ASHAs will be required. 650 ASHAs for the rural areas is calculated due to the sparse distribution of population in the hilly areas/rural place where a village has a population of hardly 600-700 people. In some cases there are people even less than 500 population in a village. Therefore, an average of 650 is calculated for such difficult areas. This issue for state specific issue is acknowledged by NHSRC (Review Meeting in Guwahati, 2013).

Therefore, the table below shows a detail calculation of the need and cost of HBNC kit. New HBNC Kit (103 drop out/replacements + 551 new ASHAs= 654 ASHA)Procurement cost amounts to a total sum of Rs.35,54490 and the Replenishment need of HBNC Kit for the currently existing ASHAs (987 existing ASHAs-103 replacements getting new HBNC=884 ASHAs) amount to a sum total of Rs.48,04,540 respectively.

| Sl.No | ITEMS | REQUIREMENT | COST | REMARKS |
| --- | --- | --- | --- | --- |
| 1 | Number of ASHA with HBNC Kits | 987 | NIL | Even though all the existing ASHAs are having HBNC kits, they need major replacements. Procurement was made in 2010.It is observed that all the ASHAs have to be provided with the new HBNC kit. |
| 2 | No. of New HBNC Kits required and unit cost details | 654 | 3554490 | HBNC Kit Requirement: 1. Mucus Extractor=@ Rs.40/- 2. Flip Chart=@ Rs.395/- 3. Digital Thermometer=@ Rs.200/- 4. Digital Wrist watch=@ Rs.500/- 5. Baby Wrapping Blanket=@ Rs.200/- 6. Umbrella=@ Rs.200/- 7. Torch Light=@ Rs.150/- 8. ASHA Carry Bag=@ Rs.250/- 9.ASHA Uniform=@ Rs.500/- 10.ASHA ID Card=@ Rs.50/- 11.Rain Coat=@ Rs.500/- 12. Baby Weighing Scale=@Rs.450/- 13. B.P. Apparatus (Digital) @ Rs2000/- ------------------------------------------- Total = Rs.5435/- per ASHA. (Rs.5435X654 ASHA=Rs.3554490/- |
| 3 | No. of HBNC Kits to be replenished and unit cost details | 884 | 4804540 | REPLACEMENTS OF USED/OLD (non-functional due to wear and tear of 3 years usage) 1. Mucus Extractor=@ Rs.40/- 2. Flip Chart=@ Rs.395/- 3. Digital Thermometer=@ Rs.200/- 4. Digital Wrist watch=@ Rs.500/- 5. Baby Wrapping Blanket=@ Rs.200/- 6. Umbrella=@ Rs.200/- 7. Torch Light=@ Rs.150/- 8. ASHA Carry Bag=@ Rs.250/- 9.ASHA Uniform=@ Rs.500/- 10.ASHA ID Card=@ Rs.50/- 11.Rain Coat=@ Rs.500/- 12. Baby Weighing Scale=@Rs.450 13. B.P. Apparatus (Digital) @ Rs2000/- ------------------------------------------------------------ TOTAL= Rs.5435/- (Rs.5435 X 884 ASHAs=Rs.4804540/- |

103 ASHAs are drop out/replacement therefore they have no HBNC Kits. More so, 551 new ASHAs to be appointed from 2014. As per the 2011 Census (1115597), the total ASHA required is 1538 (Urban:1 ASHA per 1000 population. Rural: 1 ASHA per 650* population). Only 987 are currently in existence. 551 shortfall is calculated. Therefore, the State will appoint the remaining 551 ASHAs to fill the requirement. As such, HBNC Kit for the new ASHAs will be required. * 650 for rural areas is calculated due to the sparse distribution of population in the hilly areas/rural place where a village has a population of hardly 600-700 people. In some cases even less than 500 population. Therefore, an average of 650 is calculated for such difficult areas. This issue for state specific issue is acknowledged by NHSRC (Review Meeting in Guwahati, 2013).

Therefore, based on the calculations mentioned above, 654 new ASHAs are in need of new HBNC Kit amounting to a total sum of Rs.35,54,490/- (Rupees. Thirty Five Lakhs, Fifty Four Thousand, Four Hundred and Ninety only). Similarly, there are 884 ASHAs needing Replenishment of the HBNC Kit due to wear and tear of the KIT they received way back in 2010. This amounts to a total sum of Rs.48,04,540/- (Rupees. Forty Eight Lakhs, Four Thousand, Five Hundred and Forty only).

FMR Code B1.1.3 PERFORMANCE INCENTIVE/OTHER INCENTIVE TO ASHAs (IF ANY)

| ACTIVITY | NUMBER | COST | REMARKS/DETAILS |
| --- | --- | --- | --- |
| Best ASHA District Level | 9 | 27000 | 9 ASHAs x Rs.3000 =27000) |
| Best Mobiliser District Level | 9 | 27000 | 9 ASHAs x Rs.3000 =27000) |
| Best ASHA State Level | 1 | 4000 | 1 ASHA x Rs.4000) |
| Best Mobiliser State Level | 1 | 4000 | (1 Mobiliser x Rs.4000) |
| Best Coordinator State Level | 1 | 4000 | ( 1 Coordinator x Rs.4000) |
| ASHA Awards | 21 | 66,000 |  |

With the ASHA DAY Observation to be organized in all districts, it becomes very appropriate and convenient as well as relevant to award the best performing ASHAs in the respective districts. This awarding of the ASHAs is a tool for encouraging the ASHAs to do well in their respective community. This is the ultimate outcome of the monthly meeting held at the PHC, the quarterly review meeting, the contributing elements provided by the AGRC and the AMG as a whole. The award will be a signal to all the ASHAs and the district officials that the ASHA Programme is being held accounted for and that everybody’s contribution is being measured. This will enable a sense of recognition and appreciation by the ASHAs. All this is for the positive and development of the ASHA Programme. Similar to the ASHA’s performance, the role and activity of the ASHA Mobilizers and the Coordinators will also be measured and monitored and awarded.

Therefore, the State proposes the total amount of Rs.66,000/- (Rupees. Sixty Six Thousand only) towards the awards for the best performing ASHAs, Mobilizers and Coordinators of the State.

FMR Code B1.1.3.2 HOME BASED NEW BORN CARE INCENTIVE FOR ASHA

FMR Code B1.1.3.6 OTHER (SUPPORT PROVISIONS TO ASHA SUCH AS UNIFORMS, DIARY, ASHA GHAR ETC)

Included in the HBNC Kit. May be considered as an important need and on a priority basis. Without these basic equipment (HBNC Kit), the ASHAs cannot be expected to function effectively and efficiently. Therefore the need for these equipment is paramount.

FMR Code B1.1.3.6.1 Monthly Meeting of ASHAs and ASHA Mobilizers at the PHC/MC level.

| ASHA Monthly Meeting : At PHC Level (Monthly) |  |  |
| --- | --- | --- |
|  | Details | Remarks |
| Number of ASHAs and ASHA Mobilizers expected to attend the meeting | 1538 ASHAs + 138 Mobilisers = 1676 |  |
| Number of Batches required @ 30 per batch | 55 | Meeting will be conducted by mobilisers at their own PHC level |
| Costing details per batch - | 19300 |  |
| Duration, | 1 day |  |
| TA,/DA, | 15000 | TA Rs.200 (Updown) x 30 members + 3 officials + DA Rs 300x 30 x 1 day |
| Refreshment | 3300 | 100x 30 members + 3 officials x 1 day. |
| Venue,/accommodation, | 1000 | Hall rent Rs 1000 per day x 1 days |
| Total cost | 12,738,000.00 | Rs.19300 x 55 batch x 12 months |

As per the table provided above, the State is proposing the monthly meeting of the ASHAs and the ASHA Mobilizers at their respective PHC/Main Centre in every district. This monthly meeting is necessary to regularly enable a continuous supervisory support by the Mobilizers. This will enhance the performance of the ASHAs and enable a better and efficient administration. This is also a monitoring tool whereby the Mobilizer will be able to strengthen the functioning of the ASHAs and report the real time field scenario to the State Office for a prompt action and feed back to the Ministry at the national level.

Time and over, it has been brought to the State notice that the interaction between the ASHA and the Mobilizer is not satisfactory. The Quarterly review Meeting is too seldom and from this year, the State proposes to have a more rigorous and consistent monthly meeting. The State will internally improvised a CONTINUED COMPREHENSIVE EDUCATION (CCE) for the ASHAs and the Mobilizers during these monthly meetings. This CCE is a concept derived from the CME classes. Therefore, basic health care topics will be imparted to the AHSAs and the Mobilizers by the available medical staffs of the concerned PHC and the Main Centre or the SDH apart from the regular meeting and discussions.

The calculated activities amount to a sum amount of Rs.19300 per Batch. Thus, a meeting on a monthly basis means 12 meetings in a year. Therefore a total amount of Rs.1,27,38,000/- (Rupees. One Crore, Twenty Seven Lakhs, Thirty Eight Thousand only).

FMR Code B1.1.3.6.2 Quarterly Review Meeting of ASHA Coordinators at State Level

| ASHA Coordinator Quarterly Review Meeting : At State level (Quarterly) |  |  |
| --- | --- | --- |
|  | Details | Remarks |
| Number of ASHAs and ASHA Mobilizers expected to attend the meeting | 9 coordinators, 9 CMOs and 9 DPMs |  |
| Number of Batches required @ 30 per batch | 1 | Meeting will be conducted at State level |
| Costing details per batch - | 51200 |  |
| Duration, | 1 day |  |
| TA,/DA, | 48000 | TA Rs. 1000 (Updown) x 27 members + 5 officials + DA Rs 500x 27 x 1 day |
| Refreshment | 3200 | 100x 32 members |
| Venue,/accommodation, | 1000 | Hall rent Rs. 1000 per day x 1 days |
| Total cost | 204,800.00 | Rs.51200 x 1 batch x 4 quarters |

As a continuum of supervisory support for the ASHAs, the state proposes a Quarterly review Meeting of the ASHA Coordinators in consultation with the District level officials consisting of the DPM and the CMO of the respective Districts in the State. This quarterly review meeting will form an important platform for the Coordinator in particular to raise the concerns of the ASHA at the district level. This quarterly meeting will be a follow up of the monthly ASHA meeting at the PHC level. In other words, the ASHA Mobilizers will submit reports of the monthly meeting to the ASHA Coordinator. This reports will be compiled by the coordinator and shall make a presentation.

This is a crucial activity to strengthen the ASHA Programme. It is an activity to remind the ASHA, ASHA Mobilizers, ASHA Coordinators and the Medical Officers and Chief Medical Officers that the ASHA Programme is being driven towards a goal and that the community level activities of the ASHA needs to be well documented.

FMR Code B1.1.3.6.3 Observation of ASHA CONFERENCE/DAY.

| ASHA Day Observation : At District Level ( yearly) |  |  |
| --- | --- | --- |
|  | Details | Remarks |
| Number of ASHAs and ASHA Mobilizers expected to attend the meeting/ Day | 1538 ASHAs + 138 Mobilisers = 1676 + 9 Coordinators + 9 DPMs + 9 CMOs +27 Officials + 20 invitees= 1750 |  |
| Number of Batches required @ 195 per batch | 9 | Day will be observed at District level ( 1 batch per District) |
| Costing details per batch | 352000 |  |
| Duration, | 1 day |  |
| TA,/DA, | 156000 | TA Rs. 500 (Updown) x 195 members + DA Rs 300x 195 x 1 day |
| Refreshment | 195000 | 100x 195members |
| Venue,/accommodation, | 1000 | Hall rent Rs 1000 per day x 1 days |
| Total cost | 3,168,000.00 | Rs. 352000 x 9 Districts |

ASHA CONFERENCE/DAY is an important social gathering for the ASHAs in the state. Mizoram being a strongly community bonded state, highly considers a mass gathering. Therefore, this annual ASHA DAY is an apt activity to bolster and strengthened the ASHA Programme.

The state strongly feels the need to give importance to this annual ASHA DAY observation. Therefore a two phased ASHA DAY is being proposed- one at the District Level and one at the State level. A two phased ASHA DAY is being proposed because, the district level ASHA DAY Observation will enable maximum ASHA Participation at the district level. This will be a selection and screening phase for the best performing ASHA in the respective district.

The best selected ASHA from the respective 9 districts will be called at the State level along with the DPMs, ASHA Coordinator and other prominent personnel. The Health Minister, Health Secretary, DHS Officers, CBOs, NGOs, partners and the Media will be summoned to sensitize the role and contribution of ASHAs. Awards will be given to the ASHAs and felicitated as role models for other ASHAs.

Thus, a total sum of Rs.31,68,000/- (Rupees. Thirty One Lakh and Sixty Eight Thousand only) for the ASHA DAY Observation at the District Level.

FMR Code B1.1.3.6.4 ASHA Data Base Printing.

| EXPENDITURE | QUANTITY | RATE | AMOUNT |
| --- | --- | --- | --- |
| ASHA Data Base Register | 30 | 500 | 15000 |

Printing of the ASHA Data Base is needed as it is necessary for all ASHA Mentoring Group members to have a copy in order to easily access the ASHAs as and when required (as per the suggestions of RRC Regional Coordinator on the 8th AMG Meeting). The data base also needed to be put in the hard copy for easy reference in the office and to share it to CBO partners and other officials. Hard cover binding and presentable colored cover is the requirement. A total of Rs.15,000 (Rupees Fifteen Thousand only)

| Printings of Home Based Newborn Care (HBNC) form |  |  |  |
| --- | --- | --- | --- |
| Total No. of Books required | 21768( copies) | Rs. 10/- | Calculated by taking the average of live births for the past 3 years(2011-14) =21768 |
| Total |  | Rs.217680 | Total No. of Books 21768 x Rs. 10/- |

The State had printed HBNC Format in February 2014 from the Mission Flexi Pool of the then NRHM because the ASHA Programme did not have approval in the ROP. This printing of the HBNC Format was estimated as- 5 HBNC format per ASHA and was calculated to last for at least 1 quarter as a maximum time period. With the introduction of the HBNC Incentives for the ASHAs from the month of March, 2014, the HBNC formats have been used appropriately and the demand is more than anticipated.

Therefore, the state proposes for the re printing of the HBNC format for the use of the ASHAs for the financial year  2014-2015. As is mentioned in the tabulated box above, the average number of Live Births is the baseline for the number of HBNC formats needed. Thus, a total amount of Rs.21,680/- (Rupees. Twenty One Thousand Six Hundred and Eighty only) is proposed for the reprinting of the HBNC format for use by the ASHAs.

FMR Code B1.1.3.6.5 ASHA enrolment for Class 10 &12 in Open School.

| Costing Details of Open School: Details budget of ASHA who are interested for higher studies |  |  |
| --- | --- | --- |
|  | Details | Remarks |
| Number of ASHAs to be enrolled | 115 | 97 for Class X & 18 for Cl- XII |
| Costing details per head for Cl-X | 5800 | Admission fee Rs 1200 + Tuition fee Rs 3600 (300x12) + Exam fee Rs. 1000 |
| Total | 562600 | Rs 5800 x 97 |
| Costing details per head for Cl-XII | 6100 | Admission fee Rs 1500 + Tuition fee Rs 3600 (300x12) + Exam fee Rs. 100 |
| Total | 109800 | Rs. 6100 x 18 |

The State is proposing a career path for the eligible and willing ASHAs. Eligible and willing meaning that most of the ASHAs are above their 30s. So, for those ASHAs who are interested in continuing their education will be given an opportunity to enroll for Class 10 and Class 12 respectively. Those who have not passed class 10 will be enroll in the National Indira Gandhi Open School (NIOS) for class 10. And for those ASHAs who have passed class 10 and wants to move ahead will be admitted to class 12. This initiative is being implemented by the state to help the ASHAs move up in their career and also help in the retention of the ASHAs. The state is planning further to help induct these educated ASHAs to Health Workers and Nurses in the future. Enrolment in the NIOS for 10th and 12th standard is the first step in this endeavor. NIOS sub centers are outsourced to private educational institutions in the state. As such, the cost involves varies. With this proposal, the state will meet all expenses for the ASHAs to complete their education.

As provided in the table above, the cost may differs from centre to centre. The sum total that the state proposes as the first phase of enrolment for the ASHAs in the NIOS for class 10 and 12 is a total sum amount of Rs.1,90,800/- (Rupees. One Lakh, Ninety Thousand and Eight Hundred only)

FMR Code B1.1.5 ASHA RESOURCE CENTRE/ASHA MENTORING GROUP

FMR Code B1.1.5.1 ASHA Mentoring Group.

| Meeting of ASHA Mentoring Group (AMG) |  |  |  |
| --- | --- | --- | --- |
|  | Number | Amount | Remarks |
| Cost per meeting |  | 24400 |  |
| No. of Members | 30 |  |  |
| No. of meetings to be held | 4 ( Quarterly) |  |  |
| Hall Rent | 700 | 2800 | Hall rent Rs 700 x 4 times |
| DA | 500 /head | 15000 | DA Rs 500 x 30 members |
| Logistic | 100 | 3000 | Logistics ( Note Book, Pen, File…etc) Rs. 100 x 30 |
| Refreshment | 120 | 3600 | Refreshment ( Lunch, Morning and evening tea, tec…) Rs 120 x 30 |
| Grand Total |  | 97600 | Rs. 24400 x 4 meeting ( Quarterly) |

The State ASHA Mentoring Group (AMG) Meeting is scheduled for every quarter of the year. The AMG members have been reformed to 15 exclusive members. The AMG meeting will discuss and share opinions on improving the ASHA Programme with the Mission Directors and give reports and suggestions of their field visit to the ASHAs. More so, the MAG will also be a committee to address the ASHA Grievances at the State level (this will be generated from the district level ASHA Grievance Redressal Committee (AGRC) resolutions (if there are cases to be dealt at the State level).

A sum total of Rs.97600 (Rupees. Ninety Seven Thousand and Six Hundred only) towards AMG Quarterly Meeting expenses is being proposed by the State.

FMR Code B1.1.5.2 ASHA Grievance Redressal Committee Office.

| ASHA Grievance Redressal Committee |  |  |  |
| --- | --- | --- | --- |
| items | Number | Rate | Remarks |
| Landline Telephone | 9 | 500 | Rs.500x 9districts x 12 months=54000 |
| Register/ Record Book | 9 | 200 | Rs. 200x9 districts=1800 |
| Post Box | 9 | 500 | Rs.500x 9 Districts=4500 |
| Total Amount | Rs. 60300 |  |  |

As pert the guidelines, ASHA Programme, ASHA Grievance Redressal Committee (AGRC) have been formed in all 9 districts in September 2013. However, there is no secretary, no office and no infrastructure or support for the cell to fully function as there was no financial approval. The AGRC is supposed to address the ASHA grievances on a quarterly basis. The formation of infrastructure support and a full time secretary (as per the requirement) is needed to maintain efficiency of the committee. The monthly honorarium/pay for the full time secretary is included in the HR section. A total of Rs.76500 (Rupees Seventy Six Thousand and Five Hundred only). This is the recommendation and advice/suggestions from NHSRC.

The land line telephone, register book full time secretary and the post box are laid down as per the guideline provided by the ministry. A total sum of Rs.500 is an estimated cost for the bills and maintenance of the telephone, including the connection cost.

It is really important for the AGRC to be functional with the above details available. The Monthly meetings and the Quarterly review meeting and the AGRC cell are all part of a system. Therefore, their roles are intertwined and thus, failure of one system will result to an entire system break down. Therefore, it is necessary for the complete set up of a system and thus the approval for the same.

PRINTING OF ASHA DIARY

| ASHA Diary | 1538 | Rs.38450 | 25 per Diary (1538 x25=38450) |
| --- | --- | --- | --- |

Due to the high rate of ASHA drop out and replacements, the demand for the ASHA Diary is high. Moreover, it is necessary for the State to retain stocks of the ASHA Diary for use when the demand is made. Approval for the proposed amount for the ASHA Diary will enable an efficient management of the ASHA activities and meeting the need for supply of ASHA Diary. The first supply of ASHA Diary was made in 2012. With constant use, the booklet is easily used up. As a result, the need to replenish them all and also retain some extras for unforeseen demand due to lose and drop outs.

Special Medical Skills Enhancement Training for ASHAs:

| Costing Details of trainings : Medical Skill enhancement for 1538 ASHA for 3 Days and 138 Mobilisers for 3 days - PHC and District Level |  |  |
| --- | --- | --- |
|  | Details | Remarks |
| Number of ASHAs and ASHA Mobilizers to be trained | 1538 ASHAs + 138 Mobilisers = 1676 |  |
| Number of Batches required @ 30 per batch | 56 batch |  |
| Costing details per batch - | 108200 |  |
| Duration, | 4 days |  |
| TA,/DA, | 57000 | TA Rs. 700 (Updown) x 30 + DA Rs 300x 30 x 4 days |
| Venue,/accommodation, | 4000 | Hall rent Rs 1000 per day x 4 days |
| Resource person’s honorarium | 20000 | Rs. 1000 x 5 Trainers x 4days |
| officials | 6000 | DA Rs. 500 x 3 officials x 4 days |
| Refreshment | 15200 | Rs. 100x30 trainees s + 5 trainers + 3 officials x 4 days = 15200 |
| Training material etc | 6000 | Rs. 200 x 30 (2 supporting staff included) |
| Total cost | 6,059,200.00 | Rs. 108200 x 56 batch |

High Priority Districts like Lunglei, Lawngtlai, Saiha and Mamit have experienced an even number of health workers distribution in certain pockets of blocks. The health workers post are not regularly maintained and that is a concern. The ASHA is trained in Module 1-7, however, it is not sufficient for the ASHA to effectively tackle the immediate need emerging due to the absence of appropriate medical personnel. This has resulted to the increasing chance to a fatal situation and even contributed to the high MMR and IMR in rural areas. Technically this proposal may not sound right. But the need for training the ASHAs in the interiors of the rural areas is a request that comes from the field level. The District Programme Managers and the concerned medical officers are also suggesting the same as there is no other options. Even without training, it is usually the ASHAs who are in the frontline of such situation. Therefore, training the ASHAs in contemporary life saving skills and imparting a specialized set of training to empower them to even cater to the needs of an emergency could save lives unexpected situation.

The need for this specialized skill training is most compelling in the HPD. This doesn’t mean that the NHPD does not require the training. The ASHAs in the NHPD do need such updated trainings. A NHP doesn’t mean that it is a well-oiled functioning health facility. There are rural areas not easily reached either by vehicle or by foot. Such places do need special attention irrespective of whether they are HPD or NHPD. Therefore, the state proposed such training for the entire ASHA population as shown in the tabulated financial costings.