Community Action for Health, Mizoram

Background Information: The Mizoram State Health Society (MSHS) has launched Community Based Planning and Monitoring (CBPM)/ Community Action for Health (CAH) Programme in Mizoram on the 5th February 2014 under the State Health Mission by Mr Lal Thanzara,  Hon’ble  Minister,  Health & Family Welfare Dept. Mizoram.

Prior to the launching of CAH the State Nodal Officer for Community Monitoring was notified and the State Mentoring Group committee were formed and notified by the Government of Mizoram. As shown in Table -1, RKS were formed in District Hospital, Sub-divisional Hospital, CHC and PHC way back 2005- 2006, 2007-2008 respectively. VHSNCs were formed and in place. All RKS were trained twice and all VHSNCs were trained once in Mizoram.

Table 1: Showing RKS and existing VHSNCs per District

| Sl.No | District | DH | SDH | CHC | PHC | SC | SC / Clinic | VHSNC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl E | 0 | 0 | 2 | 6 | 54 | 30 | 115 |
| 2 | Aizawl W | 1 | 2 | 0 | 6 | 40 | 27 | 87 |
| 3 | Kolasib | 1 | 0 | 1 | 5 | 29 | 8 | 48 |
| 4 | Mamit | 1 | 0 | 1 | 7 | 30 | 4 | 62 |
| 5 | Serchhip | 1 | 0 | 1 | 5 | 26 | 3 | 41 |
| 6 | Champhai | 1 | 0 | 2 | 11 | 59 | 21 | 102 |
| 7 | Lunglei | 1 | 1 | 1 | 9 | 71 | 15 | 123 |
| 8 | Saiha | 1 | 0 | 0 | 4 | 24 | 11 | 72 |
| 9 | Lawngtlai | 1 | 0 | 1 | 4 | 37 | 12 | 165 |
|  | Total | 8 | 3 | 9 | 57 | 370 | 131 | 815 |

At present the state has 830 villages officially. The government of Mizoram is planning to constitute 15 more VHSNC to cover all the villages.

Goal: Develop and strengthen community involvement in accountability, planning and action mechanisms and processes to improve access and utilization of health services under NHM.

Objective of CAH:

- To provide regular and systematic information about community needs.

- To provide feedback according to the locally developed yardsticks/parameters as well as on some key indicators.

- To provide feedback on the status of fulfillment of entitlements, functioning of various levels of public health system,

- To identify gaps/ deficiencies in services and level of community satisfaction.

- To increase the community sense of involvement and participation to improve responsive functioning of the public health system.

Strategies: The strategies for implementing CAH component are as below:

- Constitution of State Mentoring Group on Community Monitoring for Community Action for Health (SMGCM) A SMG on CM for Community Action is constituted for providing advisory support to the State for implementing CBPM/CAH. The SMGCM is chaired by the Mission Director, NHM, Health and Family Welfare Dept and comprises of senior officials from the State Health Society/ Departments of Health and Family Welfare, Prominent Citizen, Human Rights Activist, Department of Social welfare and NGO representatives. Representatives from the national level AGCA will also be included as SMGCM members. SMGCA members will be oriented to the CBMP processes as implemented in the pilot phase and in other states. The SMGCA would constitute need based working groups on areas such as adaptation of training manuals, tools and guidelines.

- Formation and Strengthening of Planning and Monitoring Committee:

The process of Community Action for Health would be initiated by organizing sensitization meetings at the district and at the grassroots level for key stakeholders from the Health, ICDS, PHE departments. These meetings would help in developing an understanding among the stakeholders on the CAH program and seeking their support in the implementation process. This would be followed by constitution and orientation of Planning and Monitoring Committees at the districts  level. These committees would include:

- District Health Planning and Monitoring Committee (DPMC)

- Village Health Planning and Monitoring Committee (VPMC/VHSNCs)

The members of DPMC would include Local council members of the area especially members of its Health Committee, officials of Health and ICDS departments, Representatives of VPMCs with annual rotation, representatives of RKSs and representatives of NGOs/CBOs. Similarly, the members of VPMCs would include Village council representatives, representatives of VHSNCs of the concerned area, representatives of health and ICDS departments and representatives of NGOs/CBOs. The meetings of these committees at the district level would be organised by the implementing partners on a quarterly basis.

- VHSNC Trainings: The VHSNC members will be trained by using cascading model which will be organised through SPMU capacity building/ Training section. Initially, State level Master Trainers (MTs) will be trained on VHSNC guidelines who in turn will train District level Master Trainers. These district level Master Trainers will then train VHSNC members at the Primary Health Center (PHC) and grassroots level. The training will be imparted in two phases. The first phase will be of one day duration at Grass root level and second phase will be of two day duration at PHC level.

- RKS Training: As mentioned above Members of RKS were trained on RKS guidelines being developed by MoHFW which was later adopted by the state. At the state level, a team of Master trainers from SPMU, NGOs will be trained, which in turn will train RKS members at District or CHC/PHC level. The training for RKS members on community process will be organized in the coming year.

- Mentoring of VHSNCs and initiation of CAH processes

Post training, mentoring of VHSNCs will be done in partnership with local NGOs/ CBOs. Since the training of VHSNCs and RKS members is an intensive process so it is expected that process of intensive mentoring will start in coming planning cycle FY- 2015-16. In each district, one CHC would be adopted for initiating intensive CAH processes, involving mentoring of VHSNCs, collection of community feedback on functioning of health services (both at community and facility level), sharing of feedback with service providers for corrective action. These sites would be used as learning and experimentation on community approaches. Cross visits for service providers, VHSNCs and village council members would be organized in these sites for promoting learning and action.

- Involvement of  Village Council and Local council

The village council members are integral to the successful implementation of this component so there involvement would be ensured at different levels. These representatives would be members of VHSNCs, Village Planning and Monitoring Committees, District Planning and Monitoring Committees and Rogi Kalyan Samities. They would be the key initiators of process in terms of setting agenda through platforms like MHIP and MAS, assessing service delivery and identifying gaps through involvement in community enquiry process and flagging issues to higher levels. The local NGOs would be working with them through the process.

Scale of Implementation:

In the first two months Serchhip district was selected for the pilot project; then and there the programme was role out in 1 PHC (with its 6 VHSNCs) & 1 CHC (with its 7 VHSNCs) and their jurisdiction respectively. Coverage will be CHC, PHC and 13 VHSNCs, the pilot project will last till May 2014 that is for 3 months. Fund allocation for the year 2013-2014 was Rs 18.4 lakhs, fund utilized so far was Rs 4.4 lakhs. Details are as follows:

Table 2: Scale of Implementation

| SI No | District | District Hospital | Sub Divisional Hospital | CHC | PHC | SC/ Clinics | VHSNCs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Serchhip | 1 | 0 | 1 | 5 | 26+3 | 41 |
| 2 | Lunglei | 1 | 1 | 1 | 9 | 71+15 | 123 |
| 3 | Lawngtlai | 1 | 0 | 1 | 4 | 37+12 | 165 |
| 4 | Mamit | 1 | 0 | 1 | 7 | 30+4 | 62 |
| 5 | Kolasib | 1 | 0 | 1 | 5 | 29+8 | 48 |
| 6 | Aizawl W | 1 | 2 | 0 | 6 | 40+27 | 87 |
| 7 | Aizawl E | 0 | 0 | 2 | 6 | 54+ 30 | 115 |
| 8 | Champhai | 1 | 0 | 2 | 11 | 59+21 | 102 |
| 9 | Saiha | 1 | 0 | 0 | 4 | 24+11 | 72 |
|  | Total | 8 | 3 | 9 | 57 | 501 | 815 |

Activity details:

The following activities are being proposed to be undertaken:

Constitution of State Mentoring Group on Community Monitoring (SMGCM)

State Health Society constitutes SMGCM as an advisory body to provide oversight to the CAH component. The orientation of members of SMGCM will be organized by the AGCA. The committee will meet on quarterly basis to oversee the process and provide overall guidance. Three meetings are planned for SMGCM in this FY. In addition, the SMGCM would constitute need based working groups on areas such as adaptation of training manuals, tools and guidelines. Costs for four meetings have been factored in the budget.

Appointment of a State Nodal Officer

As of now the State of Mizoram has only one staff that is the State Nodal Officer for CM, appointed from the state government under NHM. Though the State Mentoring Group for Community Action has been formed and the Nodal Agency NGOs have been selected the state is in dire need of office staff for analyzing the reports and return of the activities of community monitoring as well as the community and the NGOs. The incumbent would undertake the following tasks;

a) organize SMGCM and working group meetings;

b) undertake state and district planning processes;

c) facilitate processes for selection and capacity building of NGOs

d) coordinate with SPMU on capacity building plans and

e) programme and financial reporting.

Community Processes/ ASHA Support structure at  Various level

The Community Support structure is proposed as per the ‘Guidelines of Community Process’ in the table below. The work template for initiating/strengthening Interventions on Community Action for Health (CAH) along with the estimated budget of activities is shown below for approval.

Review of VHSNCs and RKS

The AGCA would undertake a rapid review of functioning of selected RKS and VHSNCs in three selected district. Findings emerging the review would guide steps for strengthening the committees, including their capacity building planning.

Sensitization of district and block officials

District and CHC/ PHC level officials from Health, Social Welfare Department, Village council and Public Health Engineering would be oriented on the objectives, processes and systems concerning CAH. Orientation for 20- 30 officials is planned in each district.

Selection of nodal NGOs\

A mapping exercise will be undertaken to identify potential NGOs and CBOs who have the capacity and experience to implement component in the designated districts. The AGCA would provide need based support in developing the NGO selection tools. Subsequently, a field appraisal of shortlisted agencies will be undertaken by a committee to identify potential agencies. In the current FY, selected NGOs will support in training of VHSNC in their respective districts. Subsequently, they would mentor VHSNCs and undertake capacity building of RKS.

Formation and strengthening of Planning and Monitoring Committees:

In FY 2014-15, the implementing partners would Coordinate formation of DPMCs and VPMCs in their respective districts. After formation, at least one meeting of these committees would be organised. The process of formation and strengthening of these committees would be bottom up one as the members of lower committees would be the members of higher ones. The VPMCs have representatives of VHSNCs and similarly, the DPMCs have representation from BPMCs.

Training of VHSNCs

Trainings will be organised through cascading model. SPMU will be the nodal organisation for organising ToTs at State and district level, whereas NGOs will manage trainings at block and village level. There will be three stages of this process as given below:

1)  State ToT- The AGCA will train a pool of around 10- 20 Master Trainers from SPMU. The initial training would be organized for duration of two days. The MTs would in turn orients the District Trainers and subsequently assesses the quality of VHSNC training roll out.

2)  District ToT- In each district, a pool of around 10 district MTs would be created to facilitate trainings of VHSNC (including AWW, VC members and SHGs). One batch of training of the DTs would be organized at the state/ regional level.

3)  Training of VHSNC- As per the National VHSNC Guidelines, the training of VHSNC members would be done in two phases a) one day orientation meeting of all VHSNC members at GP level b) a 2 day structured training of 5 members per VHSNC at the PHC level. In the first phase, as mentioned above, 329 VHSNCs are proposed to be trained. The initial orientation has been planned for 15 persons (VHSNC and community representatives) in each GP. The subsequent training would be organized for a duration of two days duration at the GP or PHC level.

In the first year of 2014-15 three districts of table 2, Scale of implementation serial no 1-3 will be targeted first. Later in 2015-16 from the same table serial no 4-6 will be projected. Then the last three serial no that is the 7-9 will be targeted in 2016-17

BUDGET  FOR COMMUNITY  PROCESSES / ASHA  SUPPORT STRUCTURE AT VARIOUS LEVEL

Table 1

| FMR Code | Activities | Unit Cost | Physical Target | Total Project Cost | Amount Proposed (in lakhs) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B.15.1 |  |  |  |  | 2014-15 | 2015-16 | 2016-17 |
|  | At The State Level |  |  |  |  |  |  |
| 1 | Programme Manager VHSNC & CP | 45,000 | 12 | 540000 | 5.40 |  |  |
| 2 | Consultant Documentation & Communication | 35,000 | 12 | 420000 | 4.20 |  |  |
| 3 | Accounts Assistant Salary | 15,000 | 12 | 180000 | 1.80 |  |  |
| 4 | Statistical/ Data Assistant | 15,000 | 12 | 180000 | 1.80 |  |  |
| 5 | Office Attendant | 8,000 | 12 | 96000 | 0.96 |  |  |
| 6 | Driver | 9,500 | 12 | 114000 | 1.14 |  |  |
| 7 | Overhead Charges @ 5% |  |  | 76500 | 0.77 |  |  |
|  | Sub Total 1 |  |  | 1606500 | 16.07 |  |  |
|  | Admin Expenses |  |  |  |  |  |  |
| 1 | Office Expenses on Telephone, photocopy, Stationery | 30,000 | 12 | 360000 | 3.60 |  |  |
| 2 | Monitoring and Supervision/documentation, Workshops, seminars and review meetings | 600,000 |  | 600000 | 6.00 |  |  |
| 3 | Overhead charges @ 5% |  |  | 48000 | 0.48 |  |  |
|  | Sub Total 2 |  |  | 1008000 | 10.08 |  |  |
|  | Total at State Level |  |  | 2614500 | 26.15 |  |  |
|  | At The District Level (DPMSU) |  |  |  |  |  |  |
| 1 | District Community Mobiliser | 30,000*3 | 12 | 1080000 | 10.80 |  |  |
| 2 | District Data Assistant | 15,000*3 | 12 | 540000 | 5.40 |  |  |
| 3 | Office Contingencies | 3,000*3 | 12 | 108000 | 1.08 |  |  |
| 4 | TA/DA for monitoring visits and collection of information. (Telephone, fax, computer, stationaries etc to be used for DPMU) | At Rs 500 per visit for minimum ten visits in a month = 5000 per month | 5000*3*12 | 180000 | 1.80 |  |  |
| Sub Total 3 |  |  |  | 828000 | 8.28 |  |  |
| Grand Total (1+2+3) |  |  |  | 3442500 | 34.43 |  |  |

Table 2:

| FMR Code | State Level Activities | Unit Cost | Physical Target | Total Project Cost | Amount Proposed (in lakhs) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B.15.1.1 |  |  |  |  | 2014-15 | 2015-16 | 2016-17 |
| 1 | Mobility support of State Nodal Officer within the state NHM (buying of Vehicle) | 774798 | 1 | 774798 | 7.75 |  |  |
| 2 | Visioning and Planning meeting to develop detailed implementation plans | 150000 | 1 | 150000 | 1.50 |  |  |
| 3 | Strengthening of the State Mentoring Group on Community Action (SMGCA) | 0 | 0 | 0 | 0.00 |  |  |
| 4 | Constitution/Expansion of the SMGCA | 0 | 0 | 0 | 0.00 |  |  |
| 5 | Quarterly Meetings of SMGCA | 50000 | 4 | 200000 | 2.00 |  |  |
| 6 | Constitution/Expansion of working groups for development/ adaptation of guidelines, manual and tools etc. | 10000 | 4 | 40000 | 0.40 |  |  |
| 7 | Organizing Working Groups meetings | 45000 | 4 | 180000 | 1.80 |  |  |
| 8 | Mapping exercise to identify potential agencies to support implementation of CAH interventions | 25000 | 3 | 75000 | 0.75 |  |  |
| 9 | Selection of State Facilitating Agencies ( NGOs/ CBOs) – designing the selection criteria, desk and field review, contracting etc | 30000 | 1 | 30000 | 0.30 |  |  |
| 10 | Adaptation/ simplification of training modules, manuals and tools | 95000 | 1 | 95000 | 0.95 |  |  |
| 11 | Development and printing of IEC materials – health entitlements and service gurantees, VHSNC, RKS etc | 250000 | 1 | 250000 | 2.50 |  |  |

| 12 | Orientation of training institutions such as ASHA resource Center, MPW school etc on CAH processes | 45000 | 1 | 45000 | 0.45 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13 | Training of trainers to facilitate large scale training of VHSNC, RKS and PRI members | 55000 | 3 | 330000 | 3.30 |  |  |
| 14 | Issuing necessary Govt. orders for re-constitution of VHSNC ( as per the revised National Guidelines) | 0 | 0 | 0 | 0.00 |  |  |
| 15 | Review meetings of district level implementing partners (preferably on quarterly basis) | 47500 | 3 | 142500 | 1.43 |  |  |
| 16 | Development and Publication of reports, newsletters etc | 25*5000 | 4 | 500000 | 5.00 |  |  |
| 17 | Include - Facilitation cost of State Nodal Agency | 25,000 | 12 | 300000 | 3.00 |  |  |
|  | Sub Total |  |  | 3112298 | 31.12 |  |  |

Table 3:

| FMR Code | District Level Activities | Unit Cost | Physical Target | Total Project Cost | Amount Proposed (in lakhs) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B.15.1.2 |  |  |  |  | 2014-15 | 2015-16 | 2016-17 |
| 1 | Strengthening of Planning and Monitoring Committees at District level | 35000 | 3 | 105000 | 1.05 |  |  |
| a | Constitution/ Expansion Planning and Monitoring Committees at District level | 0 | 0 | 0 | 0.00 |  |  |
| b | Orientation of Planning and Monitoring Committees | 45000 | 3 | 135000 | 1.35 |  |  |
| c | Quarterly Meetings of Planning and Monitoring Committees at District level | 25000 | 3*3 | 225000 | 2.25 |  |  |
| 2 | Training of Trainers for VHSNC and RKS training | 825 | 60 | 49500 | 0.50 |  |  |
| 3 | Formation/ Strengthening of District Grievance Red-ressal Committee | 1500 | 3 | 4500 | 0.05 |  |  |
| 4 | Training for VHSNC members |  |  |  | 0.00 |  |  |
| a | Orientation of VHSNC members at community level (1 day at community level) | 250*20 | 329 | 1645000 | 16.45 |  |  |
| b | Training of selected VHSNC members at village/local level (2 days) | 250*5*2 | 329 | 822500 | 8.23 |  |  |
| c | Review / mentoring meetings of VHSNC members (preferably biannual basis) | 17000 | 2 | 34000 | 0.34 |  |  |
| d | Orientation of ASHA and Anganwadi Workers on roles and responsibilities of VHSNC (1 day in clusters at PHC/ Sector level) | 230 | 329*2 | 151340 | 1.51 |  |  |
| 5 | Orientation Training of RKS Members | 29300 | 25 | 732500 | 7.33 |  |  |

| 6 | Compilation and analysis of community level enquiry and facility survey reports (at least on a bi-annual basis) | 12000 | 2 | 24000 | 0.24 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7 | Workshops for service providers on CAH | 64000 | 1 | 64000 | 0.64 |  |  |
| 8 | Organizing periodic Public Hearing (Jan Sawaads) | 100 | 329 | 32900 | 0.33 |  |  |
| 9 | Follow up on action taken regarding issues identified at the Public Hearing | 100000 | 1 | 100000 | 1.00 |  |  |
| 10 | Include – Facilitation cost of district Nodal Agency | 79465 | 12 | 953580 | 9.54 |  |  |
|  | Sub Total |  |  | 5078820 | 50.79 |  |  |

Table 4:

| FMR Code | Village/Community Level Activities | Unit Cost | Physical Target | Total Project Cost | Amount Proposed (in lakhs) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B.15.1.3 |  |  |  |  | 2014-15 | 2015-16 | 2016-17 |
| 1 | Reconstitution/ Expansion of VHSNC as per National Guidelines | 0 | 0 | 0 | 0.00 |  |  |
| 2 | Organizing shows to create awareness on health entitlements | 1000 | 329 | 329000 | 3.29 |  |  |
| 3 | Wall writings on health entitlements and service guarantees | 1000 | 329 | 329000 | 3.29 |  |  |
| 4 | Monitoring of services provided during Village Health Sanitation Nutrition days | 800 | 110 | 88000 | 0.88 |  |  |
| 5 | Community level enquiry and preparation of village level report cards facility, health facility card (preferably on a quarterly basis) | 200 | 329 | 65800 | 0.66 |  |  |
| 6 | Sharing of village reports cards, health facility cards (preferably on a quarterly basis) | 200 | 25 | 5000 | 0.05 |  |  |
| 7 | Meetings with ASHAs, ANMs and Village council members to discuss issues on health coverage, access and other implementation issues emerging from community enquiry and facility surveys | 200 | 845 | 169000 | 1.69 |  |  |
| 8 | Facilitate development of village health action plan (on annual basis) | 500 | 845 | 422500 | 4.23 |  |  |
|  | Sub Total |  |  | 1408300 | 14.08 |  |  |

| Sl no | Activities | Total Project Cost (Rs) | Amount Proposed (in lakhs) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2014-15 | 2015-16 | 2016-17 |
| 1 | Budget for Community Processes/ ASHA Supports structure at State and District level | 3442500 | 34.43 |  |  |
| 2 | A. State Level Activities | 3112298 | 31.12 |  |  |
| 3 | B. District Level Activities | 5078820 | 50.79 |  |  |
| 4 | C. Village/Community Level Activities | 1408300 | 14.08 |  |  |
|  | Grand Total | 13041918 | 130.42 |  |  |