HPD Specific Plans in Budget Sheet

Performance Based Incentives for 4 HPDs- Lunglei, Lawngtlai, Saiha & Mamit

- Incentive for Line listing of severely anaemic pregnant mothers: FMR Code A.1.5.1

It is an established fact that anaemia is the commonest indirect cause of Maternal Deaths globally. This also stands true in the HPDs where anaemia is misunderstood and the symptoms neglected. This is also due to socio-economic factors as pregnant women go to work in the farms until close to the EDD. If the Health Workers involved in Ante natal check-ups are incentivised and provide quality ANCs, deaths and complications of anaemia can be averted

| Estimated severely anaemic pregnant women in 4 HPDs 2014-15 | Incentive for ANM for line listing and follow up | Total estimated incentive for 2014-15 |
| --- | --- | --- |
| 351 | Rs 100/- | Rs 35100/- |

- Incentive for identification and referral of high risk pregnancies: FMR Code A.1.5.3

7% of the total ANC are estimated to have High risk pregnancies. In order to detect these, meticulous history taking, competency and assured referral services are essential. ANMs need to be skilled and patient to elicit proper history to detect Bad Obstetric History, Post LSCS and pay serious attention to the complaints of the mother. They should also be able to recognize the danger signs from the examinations and tests performed at the Sub Centre level and refer accordingly

| Estimated pregnant women in 4 HPDs to have High Risk in 2014-15 | Incentive for ANM to detect and refer High Risk pregnancies | Total estimated incentives for 2014-15 |
| --- | --- | --- |
| 93 | Rs 1000/- | Rs 93000/- |

- Incentive for EmOC Team at District Hospital FRUs: FMR Code A.1.5.4

Delay in receiving appropriate care at the facility is one of the deterrents of people approaching public hospitals. Timely intervention saves both the life of mother and child. EmOC Teams if available and render C-sections of more than 10 a month, provided 20% of the total deliveries are C-sections are entitled for an incentive of Rs 3000/- in order to enable women to have access to comprehensive emergency obstetric care.

| Total C-Sections in HPDs in 2013-14 | Estimated increase in providing Emergency C Sections | Estimated incentives for EmOC Team |
| --- | --- | --- |
| 218 | 120 | Rs 294000/- |

- ANM incentive for conducting Home Deliveries in notified villages: FMR Code A.1.5.7

Women living in areas that are isolated and difficult to access have to resort to home deliveries as situation does not permit them to access facility care. Services of trained personnel are also unavailable leading to unattended risks exposing them to higher morbidity and mortality. In order to render skilled birth attendant services in areas where home deliveries are high

| Expected Home deliveries in notified villages 2014-15 | Incentive for ANM | Estimated incentive for ANM |
| --- | --- | --- |
| 597 | Rs 1000/- | Rs 597000/- |

Maternal & Child Health

New Born Care Corners: FMR Code B.5.6.3

In order to strengthen Delivery Points of all levels in the 4 HPDs, it has been proposed to equip them with NBCC. In addition, strengthening all SCs across the HPDs to provide essential care is also planned. 71 such facilities have been proposed to be equipped with NBCC (65 SCs and 6 PHCs). These PHCs either do not have NBCC or are using indigenous Radiant Warmers as stop-gap arrangement.

Moreover, since there is a lack of equipment and accessories mandatory for NBCC in many centres, many new born babies who could have been treated at the centre are therefore referred to other facilities, and have to face difficulties in transportation due to bad roads especially during rainy season which in turn leads to higher mortality rate

Establishment Cost @ Rs 105000/- x 71 = Rs 7455000 /-

Back Up electricity - solar plate @ Rs 20000/- x 71 = Rs 1420000 /-

Total Cost – Rs 8875000 /-

Time to Care approach: FMR Code A.8 & A.1.5

Rationale for proposing 2 ANMs in SCs catering to notified villages: Villages that are >30 minutes’ walk distance (1 hour to and fro) are identified in all HPDs. Home Deliveries are high in these areas. As per HMIS 2013-14 up to March, there were a total of 1831 home deliveries in the 4 HPDs and out of these, only 597 (33%) were attended by SBA. This is also due to poor communication and as a result assured referrals are not available. Situational analysis suggests that manpower strengthening in these areas would be the solution. List of notified villages are attached. Even though the mileage depicted may seem less, considering the geographical terrain and the fact that the roads are seasonal, it is proposed under FMR Code A.8 to deploy 2 ANMs in the SCs catering to these villages, incentives for Skilled Birth Attendants for Home Deliveries have been proposed as per guidelines under A.1.5

Special Schemes for transportation: FMR Code A.1.5.6

Provision for special referral transportation for pregnant women and sick infants:

The 4 HPDs have villages that are >30 minutes’ walk. List of notified villages is attached. Plan is to utilize the already available resources like locally made stretcher (palki-type) @ Rs 100/- per km to the nearest road head. This for the present situation is the only solution for assured referral services for pregnant mothers and sick infants.

For HPD PIP\Lawngtlai.docx

For HPD PIP\Lunglei district Notified village.docx

For HPD PIP\Mamit district Notified village.docx

For HPD PIP\Saiha Dist.Village without SC.xlsx

Comprehensive Abortion Care: FMR Code A.1.5.9

Upon Gap Analysis, it was found that Comprehensive Abortion Care services are being provided only at District Hospitals, and there are 2 reported Maternal deaths following unsafe abortions. In order to satisfy this unmet need it needs to be ensured that all Medical Officers at PHCs are trained in CAC and equipment like MVA/EVA, appropriate forceps and drugs (Misoprostol, antibiotics, analgesics) including sterilization equipment are readily available. IEC and IPC are very essential to alter the Health Seeking Behaviour in the community. In Lawngtlai District, among the Chakma population, women prefer to undergo multiple MTPs instead of contraceptive use. Massive efforts need to be pitched in in order to change the attitude of the community regarding the lower risk of contraceptive use over multiple MTPs. For this it is proposed to translate and print IEC materials in the local language (Chakma), strengthen VHNDs, campaigns in schools addressing adolescents and mobilise community and Faith based organizations

Birth Waiting Homes: A.1.5.10 & .1.5.11

Women living in riverine areas that are accessible only by boats or in villages connected with fair weather roads face difficulty in accessing timely and appropriate health care, resorting to unsafe home deliveries and services of quacks. In order to alleviate this situation, birth waiting homes have been proposed in identified facilities catering to these villages so that pregnant mothers can wait for their deliveries once their EDD is known.

| District | Facility | Unit Cost | Strength |
| --- | --- | --- | --- |
| Lawngtlai | District Hospital | Rs 1000000/- | 5 bedded |
|  | Chawngte CHC | Rs 1000000/- | 5 bedded |
|  | Bungtlang PHC | Rs 800000/- | 3 bedded |
| Lunglei | District Hospital | Rs 1000000/- | 5 bedded |
|  | Tlabung | Rs 1000000/- | 5 bedded |
| Saiha | District Hospital | Rs 1000000/- | 5 bedded |
|  | Phura PHC | Rs 800000/- | 3 bedded |
| Mamit | District Hospital | Rs 1000000/- | 5 bedded |
|  | Kawrthah CHC | Rs 800000/- | 3 bedded |
|  | Total Cost | Rs 62400000/- |  |

Maternal & Infant Death Review: FMR Code A.1.4 & A.2.8

For conducting regular Infant and Maternal Death Review in all the 9 districts to analyse the incidence and cause of death and to take corrective measures - within the facility, identify gaps in programme implementation resulting in deaths and issues in accessing appropriate health care.

In Mizoram, since the incidence of Maternal Deaths is more sporadic than Infant Death which occurs every day across the State, Death Reviews of both Infant and Maternal Deaths are done together

| Maternal Deaths in 2013-14 | Incentive for ASHA in reporting | Incentive for audit team | TA for deceased family | Total budgeted for 2014-15 |
| --- | --- | --- | --- | --- |
| 16 | Rs 200/- | Rs 750/- @ Rs 250/- per member | Rs 200/- | Rs 1150x16=Rs 18400/- |

| Infant Deaths in 2013-14 | No of Infant Deaths in Facility | Incentive for ANM in reporting Facility Deaths | Incentive for audit team | TA for deceased family | Total budgeted for 2014-15 |
| --- | --- | --- | --- | --- | --- |
| 758 | 531 | Rs 200/- | Rs 750/- @ Rs 250/- per member | Rs 200/- | Rs 1150x531=Rs 610650/- |
| Infant Deaths in 2013-14 | No of Infant Deaths reported from Community | Incentive for Asha in reporting Home Deaths | Incentive for audit team | TA for deceased family | Total budgeted for 2014-15 |
| 758 | 227 | Rs 100/- | Rs 750/- @ Rs 250/- per member | Rs 200/- | Rs 1050x227=Rs 238350/- |
|  |  |  |  | Total | Rs 849000/- |

RTI/STI:  FMR Code A.1.5.9

Since awareness regarding RTI/STI below the PHC level is quite low and the number of RTI/STI patients identified and their partners counselled at SC level is practically nil for the year 2013-14. For better case identification and treatment of RTI/STI has been proposed to be undertaken at the district level for all the 4 HPDs and is to be conducted by the personnel who were already trained in RTI/STI

Cost of sensitization workshop for Female Health Workers in 4 HPDs:

| District | Components | Rate /day (Rs) | No. of days | No. of participants | Amount |
| --- | --- | --- | --- | --- | --- |
| Lawngtlai | TA/DA & Working Lunch | Rs 1000/- | 1 day | 42 | Rs 42000/- |
| Lunglei |  | Rs 1000/- | I day | 81 | Rs 81000/- |
| Mamit |  | Rs 1000/- | I day | 24 | Rs 24000/- |
| Saiha |  | Rs 1000/- | 1 day | 39 | Rs 39000/- |

Total Cost:  Rs 186000/-

My Safe Motherhood Booklet: FMR Code A.3.5.5.5

Even though ANC is improving in numbers, quality is still a concern. Many mothers who come for ANC especially primi gravida need to be educated on birth preparedness. Communication skills itself also need to be developed. In addition to skills, non- local Health Workers working in areas under the 4 HPDs need to have working knowledge of the language of the ethnic people groups. It is found that Ante natal clinics are mere entering of names, cursory examinations, Hb test and TT Injections. In order for ANCs to be more holistic, health education on locally available food, hygiene, rest and awareness on danger signs are mandatory. It is proposed to translate My Safe Motherhood Booklet into the language of the Chakma, Mara and Bru, in colour at the estimated cost of Rs 40/- per booklet. The pictorial presentations make it easy to remember and certain modifications shall be made while translating to make it local specific

Total estimated pregnancies in 2014-15: 25000

Printing of My Safe Motherhood Booklet @ Rs 40/- per copy

Total cost – Rs 1000000/-

MCH Wing: FMR Code B4.1.5

MCH Wing has been proposed for all the 4 HPDs to provide the best possible care during pregnancy, delivery and post partum period. To ensure these services, we will need a team of dedicated service providers, equipment, and construction of new infrastructures and renovation of the existing ones. Identified needs have been proposed accordingly

Estimated cost for infrastructure:

New construction for Mamit – Rs 75 lakhs

Renovation for Lunglei – Rs 2000000/-

Renovation for Lawngtlai – Rs 4701000/-

Renovation for Saiha – Rs 4740000/-

Note: Please refer to MH Annexure XIV

Estimates for MCH Wing for 4 HPDs:

| Sl. No. | Equipment | Number | Unit Cost in Rs | Total Cost in Rs |
| --- | --- | --- | --- | --- |
| 1 | Footstep | 20 | 1395 | 27900 |
| 2 | Suction Machine (Manual & Electrically operated) | 8 | 11378 | 91024 |
| 3 | Stethoscope & BP Instrument | 8 | 0386 | 24688 |
| 4 | Digital Weighing Machine | 8 | 1200 | 9600 |
| 5 | Radiant Warmer with stabilizer | 4 | 50500 | 202000 |
| 6 | Delivery Tray 30cm x 25cm | 10 | 341 | 3410 |
| 7 | Episiotomy Tray 27.5cm x 22cm | 10 | 236 | 2360 |
| 8 | MVA Tray 25cm x 20cm | 10 | 223 | 2230 |
| 9 | Mackintosh | 20 | 74 | 1480 |
| 10 | Kelly’s Pad | 10 | 388 | 3880 |
| 11 | Dressing Drum (6 sizes) | 4 | 338300 | 1353200 |
| 12 | Thermometer | 20 | 50 | 1000 |
| 13 | Mattress 6ft x 3ft | 102 | 4120 | 420240 |
| 14 | Pillow & Cover | 102 | 307 | 31314 |
| 15 | Bed Sheet | 102 | 250 | 25500 |
| 16 | Bed Cover | 102 | 248 | 25296 |
| 17 | IV Drip Stand | 1400 | 30 | 42000 |
| 18 | Screen Partition | 4 | 2800 | 11200 |
| 19 | Pulse Oxymeter | 4 | 42000 | 168000 |
| 20 | Delivery Kit for HIV +ve women | 20 | 208 | 4160 |
| 21 | OT Table | 1 | 348448 | 348448 |
| 22 | Wheel Chair | 8 | 6990 | 55920 |
| 23 | Infant Feeding Tube | 100 | 7 | 700 |
|  |  |  | Total | Rs 2855550/- |

The above rates are taken from the State DHME approved rates. Estimates for the following could not be done as they were not in the list:

- Labour mattress – 4 Nos

- Wall mounted thermometer – 4 Nos

- Equipment for adult resuscitation kit – 4 Nos

- Equipment for neonatal resuscitation kit – 4 Nos

- Oxygen cylinder – 8 Nos

- Hub cutter – 4 Nos

- Puncture proof container

- Kelly’s Placental Forceps for PPIUCD: 57 for SC, 8 for DH, 9 for CHC in the 4 HPDs

Inter sectoral Convergence: FMR Code B14.1

Health Systems strengthening and universal and equitable health coverage cannot be achieved by Health Sector alone. It needs strong and active liaising with other line departments. For reviewing activities and progress made over the months, it has been planned to hold bi annual review meetings at the State and District levels. Such review meetings under the Chairmanship of DCs at District Level and Health Secretary at State Level shall help in addressing the gaps and plan for way forward.

| Number of Review Meetings proposed | Total Estimated for State | Total Estimated for per District (9 Districts) | Total for State | Total for Districts |
| --- | --- | --- | --- | --- |
| 2 | Rs 300000/- per meeting | Rs 25000/- per meeting | Rs 600000/- | Rs 450000/- |

IMEP: FMR Code B16.1.4.1

Staffs at Health Facilities have been trained and practise segregation but disposal is an issue in almost all facilities in the State. The first line is to make available colour coded bags in all facilities and staff trained in the subject. Number of bags required is planned for 1 bag of each colour utilized per day

| No. of Facilities in the State | Number of bags required per day (1 colour) | Number of bags required per day | Estimated cost @ 3 bags | Total estimated cost for 2014-15 |
| --- | --- | --- | --- | --- |
| 480 | 1370 | 4110 | Rs 3/- | Rs 4500450 /- |

It has been found on gap analysis and routine field monitoring that Sharps pits especially at the Sub Centres need re-construction. Either they were filled up or poorly constructed that the safety covers and locks are damaged. It is estimated that for 2014-15, 10 new pits need to be constructed @ Rs 5000/- per pit

| No of facilities needing new pits | Estimated cost per pit | Total cost |
| --- | --- | --- |
| 10 | Rs 5000/- | Rs 50000/- |

Incinerators have been installed at the District Hospitals but they are not fully functional and some need major renovations.

| No of incinerators for repair | Estimated cost per unit | Total cost |
| --- | --- | --- |
| 3 | Rs 50000/- | Rs 150000/- |