EXECUTIVE SUMMARY:

Mizoram is one of the smallest and most backward states in the country. The entire state of Mizoram is tribal dominated Area, hilly terrain characteri zed by poor transport and communication facilities. More than 90% of the population follows Christianity. Although, the population of cities/towns in the state may be less than cities in other big states but the  towns and cities are recognizing rapid expansions due to large scale migration from rural to urban areas in search of works, education and other opportunities. It may also be noted that migration from neighboring States – Assam, Manipur and Tripura and neighboring countries Myanmar & Bangladesh is also contributing a lot in the rapid increase of urban population.  In Mizoram, urban population as per Census 2011 stands at 52.11% (571771) which is 29.64% more than the last decade.

The National Rural Health Mission (NRHM) was launched in 2005 which make opportunity for the rural population to access health facilities and better health Care services. There have been little efforts in provisions of health care services for the urban poor community especially those who are dwelling in the outskirt of the city and towns. Since 2003-04 Urban Health Scheme has been taken up as one of the RCH Programmes covering two major Townships which is observed as not enough to meet the increasing demand of health care needs. It is necessary to address the health of urban poor in proportion to the growth of population.

The launch of National Urban Health Mission is much appreciated and anticipated while considering the health concerns of urban community. It will envisage systematical approach to provide integrated and sustainable health care service delivery for Primary, Secondary and Tertiary sectors in the urban areas of the State with focus on poor slums and other vulnerable groups.

OBJECTIVES:

Provision of integrated and sustainable Primary Health Care to promote the health Status of urban poor community/ low income neighborhoods, particularly those who are dwelling in the outskirt of the cities, towns and vulnerable sections, KFAs

URBAN PUBLIC HEALTH CENTRES:

As already mentioned, Urban Health has been taken up as one of the scheme under RCH/NRHM in two major city/town viz. Aizawl (capital city) and Lunglei township ( 2nd biggest town) since 2004. 4 UHCs and 1 UHC have been established with 5 beds each in Aizawl and Lunglei respectively and these UHCs are providing round the clock services. In 2013-14 NUHM ROP 2(two) new UPHC in Aizawl City and 1 (One) new UPHC in Lunglei Town was approved and the total number of UPHC with the existing centres comes to 8 (eight) numbers. As per guidelines of NUHM PIP, as the setting up of UPHC are to be phased out, no new UPHC was proposed during 2014-15. Out of these 8 approved UPHCs two UPHCs namely ITI UPHC and Sihphir UPHC are on Government buildings, and the remaining six (6) UPHCs are functioning on rented buildings. Construction of three new UPHC is proposed during the current year at Chawlhhmun, Hlimen and Sazaikawn during the year 2014-15. As approved by Government of India, these UPHCs is intended to be equipped to function as rural/normal PHCs in order to effectively address the urban poor population by providing primary, secondary etc health services. Meanwhile provision of outreach services/session has also been provided through these UHCs. From the past experience, it has been considered that functioning of UHCs as PHC is very effective to promote the health status of poor community especially those who are living in the outskirt of the cities. Major services provided through UHCs are as summarized below:

- Provision of OPD & IPD services for general patients

- Conducting Deliveries

- Management of minor injuries/First Aid Services

- Referral to higher facilities as necessary

- Outreach service / Home visits for early detection of pregnancy by ANM & ASHA.

- Counselling of mother for fully immunization

- Provision of services related to Vector Born diseases

- FP Services – Distribution of condoms and oral pills

In order to provide integrated better health care service to the vulnerable groups (KFA) dwelling in the KFAs cities and town, launching of NUHM is worth mentioning. Therefore the State Planning Team proposed to extent Urban Health in all the district capitals. As envisaged in the guidelines NUHM would have high focus in the State of Mizoram in addition to the existing services as mentioned

- Urban poor living in listed and unlisted areas/slums or BPL & AAY families

- Other vulnerable population - daily laborers such as working at stone quarries, beggars, sex workers and other temporary migrants.

- Public health thrust on sanitation, clean drinking water, vector control etc.

- Strengthening of public health capacity of urban local bodies and NGOs.

- Strengthening of infrastructure.

In order to achieve the above , establishment of UPHC has been proposed . It has been planned that all the proposed UPHC will provide round the clock services like other PHCs, Health Care services like OPD, IPD , ANC, PNC, Institutional deliveries, Immunization services etc. And all the local bodies/local authorities/NGOs have agreed to donate a plot of land for establishment of all selected sites for UPHCs (Agreements attached). City/Town wise number of proposals for establishment of UPHC are as below:

| Name of District capitals | No of UPHC proposed |
| --- | --- |
| Aizawl ( State Capital) | 6 |
| Lunglei | 2 |

PROPOSAL FOR ESTABLISHMENT OF URBAN PUBLIC HEALTH CENTRES IN MIZORAM

AIZAWL:

Introduction: Aizawl is the biggest city in Mizoram and also the Capital of the State.  The city is located in the northern part of Mizoram. It has a population of 2,29,714 as per 2001 census and 2,93,416 as per 2011 census exhibiting a rise of 27.73% over the last decade. Urban population comprises 77.4% in Aizawl District.  The population density in 2011 is 234/Sq.km. It is also the centre of all important offices, State Assembly house and civil Secretariat. Aizawl city occupies an area of 457 Sq.km.

Geography: Aizawl is located north of the Tropic of Cancer in the northern part of Mizoram. It is situated on a ridge 1,132 metres above sea level with Tlawng river valley to its west and the Tuirial River to the east. Aizawl has a mild, sub-tropical climate due to its location and elevation. In the summer the temperature ranges from 20-30 degrees Celsius, and in the winter 11-21 degrees C.

Administration: The Aizawl Municipal Council (AMC) is in charge of civic Administration of Aizawl City. It was formed in 2010 with 19 members. Administered by Council Chairman, Vice Chairman and three Executive Members. The AMC consists of 19 members representing 19 Wards of the City of Aizawl. One- thirds of the total members is reserved for women. The tenure of the Council is five years. There is a Ward Committee in every ward. The Ward Committee consists of a Chairman, who is an elected Counselor from the Wards, and two each from Local Councils within the Ward. There is also 78 Local Councils in Aizawl City with a term of 3 years.

Economy: Around 40% of families are basically depending on Government Job as it is the Capital of Mizoram. The rest are mainly Merchants, Cultivators, Daily Labourers and Hawkers etc.

Transport: Aizawl is connected by road with Silchar (District Capital of Cachar, Assam) through National Highway 54, with Agartala through National Highway 40 and with Imphal through National Highway 150. Aizawl is also connected by Air through Lengpui Airport which is situated nearby Aizawl City. As for Railway, It is connected by Rail road up to Bairabi town, Kolasib District (Assam Border).

GIS MAPPING OF DIFFERENT LOCALITIES IN AIZAWL CITY WITH POPULATION DETAILS (As per census 2011)

| Sl.no | Name of Ward | Ward no. | No. of House | Total Population | Total Male | Total Female | Location |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sihphir | 1 | 1,349 | 6,528 | 3,268 | 3,260 | 23° 49' 25''N | 92° 44' 10" |
| 2 | Selesih | 2 | 188 | 882 | 425 | 457 | 23°48'07"N | 92°44'00"E |
| 3 | Durtlang Vengthar | 3 | 341 | 1,756 | 949 | 807 | 23°47'18"N | 92°4349"E |
| 4 | Durtlang | 4 | 812 | 4,019 | 1,965 | 2,054 | 23°46'34"N | 92°4352"E |
| 5 | Durtlang Leitan | 5 | 923 | 4,598 | 2,300 | 2,298 | 23°45'59"N | 92°4429"E |
| 6 | Bawngkawn Chhimveng | 6 | 468 | 2,237 | 1,077 | 1,160 | 23°45'23"E | 92°44'02"E |
| 7 | Bawngkawn | 7 | 1,367 | 6,407 | 3,166 | 3,241 | 23°45'21"N | 92°44'01"E |
| 8 | Zemabawk | 8 | 2,022 | 9983 | 5,193 | 4,790 | 23°44'12"N | 92°45'13"E |
| 9 | Falkland | 9 | 234 | 1342 | 771 | 571 | 23°44'14"N | 92°44'50"E |
| 10 | Thuampui | 10 | 887 | 4,021 | 1996 | 2025 | 23°44'50"N | 92°44'27"E |
| 11 | Zemabawk North | 11 | 639 | 3,119 | 1541 | 1578 | 23°44'06"N | 92°45'02"E |
| 12 | Zuangtui | 12 | 854 | 3,912 | 1991 | 1921 | 23°45'11"N | 92°44'43"E |
| 13 | Muanna Veng | 13 | 241 | 2,023 | 1197 | 826 | 23°45'18"N | 92°44'52"E |
| 14 | Edenthar | 14 | 624 | 2,845 | 1394 | 1451 | 23°44'59"N | 92°43'25"E |
| 15 | Chaltlang | 15 | 2018 | 10,632 | 5,246 | 5,386 | 23°45'02"N | 92°43'40"E |
| 16 | Laipuitlang | 16 | 409 | 1,979 | 899 | 1,080 | 23°44'39"N | 92°43'27"E |
| 17 | Ramhlun North | 17 | 1,357 | 6,428 | 3,107 | 3,321 | 23°44'54"N | 92°43'47"E |
| 18 | Ramhlun Venglai | 18 | 622 | 3,073 | 1,489 | 1,584 | 23°44'35"N | 92°43'37"E |
| 19 | Ramhlun Vengthar | 19 | 597 | 3,006 | 1,452 | 1,554 | 23°44'38"N | 92°43'51"E |
| 20 | Ramhlun Sport Complex | 20 | 210 | 1,013 | 499 | 514 | 23°44'28"N | 92°43'51"E |
| 21 | Ramhlun South | 21 | 1,343 | 6,424 | 3,100 | 3,324 | 23°44'25"N | 92°43'40"E |
| 22 | Ramthar Veng | 22 | 1,029 | 5,258 | 2,582 | 2,676 | 23°44'20"N | 92°43'37"E |
| 23 | Ramthar North | 23 | 375 | 1,928 | 951 | 977 | 23°44'21"N | 92°43'55"E |
| 24 | Aizawl Venglai | 24 | 526 | 2,505 | 1,171 | 1,334 | 23°43'53"N | 92°43'24"E |
| 25 | Electric veng | 25 | 1262 | 6,165 | 3,001 | 3,164 | 23°44'11"N | 92°4320"E |
| 26 | Dawrpui | 26 | 755 | 3,660 | 1,853 | 1,807 | 23°43'51"N | 92°43'11"E |
| 27 | Saron Veng | 27 | 675 | 3,030 | 1,519 | 1,511 | 23°43'49"N | 92°43'22"E |
| 28 | Chhinga Veng | 28 | 1,585 | 7,629 | 3,665 | 3,964 | 23°43'59"N | 92°43'20"E |
| 29 | Armed Veng North | 29 | 833 | 4,083 | 1,965 | 2,118 | 23°44'04"N | 92°43'41"E |
| 30 | Armed Veng South | 30 | 957 | 4,847 | 2,385 | 2,462 | 23°43'54"N | 92°43'48"E |
| 31 | Chite | 31 | 100 | 497 | 271 | 226 | 23°44'04"N | 92°44'08"E |
| 32 | Tuithiang | 32 | 443 | 2,133 | 1,040 | 1,093 | 23°43'44"N | 92°43'32"E |
| 33 | Bethlehem | 33 | 977 | 4,846 | 2,354 | 2,492 | 23°43'37"N | 92°43'33"E |
| 34 | Bethlehem Vengthlang | 34 | 1,460 | 7,467 | 3,648 | 3,819 | 23 43' 43" N | 92 43' 38"E |
| 35 | College Veng | 35 | 611 | 2,904 | 1,398 | 1,506 | 23°43'14"N | 92°44'04"E |
| 36 | ITI Veng | 36 | 899 | 4,440 | 2,197 | 2,243 | 23°43'04"N | 92°44'15"E |
| 37 | Venghlui | 37 | 1,034 | 4,744 | 2,359 | 2,385 | 23°43'22"N | 92°43'29"E |
| 38 | Republic | 38 | 878 | 4,159 | 2,024 | 2,135 | 23 43' 11"N | 92 43' 27"E |
| 39 | Upper Republic | 39 | 544 | 2,644 | 1,266 | 1,378 | 23°43'05"N | 92°43'23"E |
| 40 | Dam Veng | 40 | 309 | 1,345 | 648 | 697 | 23°42'48"N | 92°43'36"E |
| 41 | Salem Veng | 41 | 845 | 4,134 | 2,016 | 2,118 | 23°42'39"N | 92°43'47"E |
| 42 | Venghnuai | 42 | 439 | 2,092 | 1,008 | 1,084 | 23°42'42"N | 92°43'36"E |
| 43 | Republic Vengthlang | 43 | 492 | 2,412 | 1,154 | 1,258 | 23 43' 16."N | 92 43' 28."E |
| 44 | Mission Veng | 44 | 1,757 | 7,596 | 3,636 | 3,960 | 23°42'55"N | 92°43'17"E |
| 45 | Thakthing | 45 | 282 | 1,297 | 617 | 680 | 23°42'41"N | 92°43'26"E |
| 46 | Kulikawn | 46 | 1,091 | 4,978 | 2,406 | 2,572 | 23°42'22"N | 92°43'16"E |
| 47 | Tlangnuam | 47 | 839 | 4,008 | 2,018 | 1,990 | 23°42'13"N | 92°42'24"E |
| 48 | Melthum | 48 | 241 | 1,110 | 584 | 526 | 23°41'11"N | 92°43'22"E |
| 49 | Saikhamakawn | 49 | 317 | 1,463 | 727 | 736 | 23°41'45"N | 92°43'21"E |
| 50 | Hlimen | 50 | 564 | 2,733 | 1,404 | 1,329 | 23°41'02"N | 92°42'57"E |
| 51 | Mission Vengthlang | 51 | 1,006 | 4,876 | 2,375 | 2,501 | 23°42'49"N | 92°42'49"E |
| 52 | Khatla | 52 | 1,391 | 6,248 | 3,147 | 3,101 | 23°43'23"N | 92°42'50"E |
| 53 | Khatla South | 53 | 742 | 3,727 | 1,993 | 1,734 | 23°43'02"N | 92°43'08"E |
| 54 | Bungkawn Nursery | 54 | 523 | 2,734 | 1,344 | 1,390 | 23°43'05"N | 92°42'45"E |
| 55 | Bungkawn | 55 | 1,047 | 4,955 | 2,378 | 2,577 | 23°43'23"N | 92°42'29"E |
| 56 | Bungkawn Vengthar | 56 | 522 | 2,346 | 1,158 | 1,188 | 23°43'31"N | 92°42'34"E |
| 57 | Maubawk | 57 | 815 | 4,120 | 1,980 | 2,140 | 23°43'18"N | 92°41'52"E |
| 58 | Lawipu | 58 | 168 | 760 | 384 | 376 | 23°43'24"N | 92°41'20"E |
| 59 | Tuikual South | 59 | 1,206 | 5,768 | 2,969 | 2,799 | 23°4331"N | 92°43'11"E |
| 60 | Tuikual North | 60 | 983 | 4702 | 2,302 | 2,400 | 23°43'43"N | 92°43'03"E |
| 61 | Dinthar | 61 | 1227 | 6,157 | 2,982 | 3,175 | 23°43'51"N | 92°42'51"E |
| 62 | Dawrpui Vengthar | 62 | 848 | 4,095 | 2,054 | 2,041 | 23°44'04"N | 92°42'59"E |
| 63 | Vaivakawn | 63 | 854 | 3,996 | 1,952 | 2,044 | 23°44'17"N | 92°42'43"E |
| 64 | Kanan Veng | 64 | 713 | 3,572 | 1,686 | 1,886 | 23°43'53"N | 92°42'24"E |
| 65 | Chawnpui | 65 | 822 | 3,965 | 1,862 | 2,103 | 23°44'03"N | 92°42'14"E |
| 66 | Zonuam | 66 | 556 | 2,647 | 1,330 | 1,317 | 23°44'08"N | 92°41'43"E |
| 67 | Zotlang | 67 | 614 | 3,018 | 1,451 | 1,567 | 23°44'18"N | 92°42'29"E |
| 68 | Luangmual | 68 | 1,082 | 5,466 | 2,905 | 2,561 | 23°44'32"N | 92°42'07"E |
| 69 | Govt.Complex | 69 | 421 | 1913 | 941 | 972 | 23°43'40"N | 92°41'41"E |
| 70 | Tanhril | 70 | 566 | 2,930 | 1,417 | 1,513 | 23 44' 34"N | 92 40' 43"E |
| 71 | Sakawrtuichhun | 71 | 284 | 1,425 | 755 | 670 | 23°45'30"N | 92°40'39"E |
| 72 | Zarkawt | 72 | 514 | 2,620 | 1,208 | 1,412 | 23°44'12"N | 92°43'08"E |
| 73 | Chanmari | 73 | 1,262 | 5,626 | 2,808 | 2,818 | 23°44'26"N | 92°43'17"E |
| 74 | Chanmari West | 74 | 1,316 | 6,302 | 3,098 | 3,204 | 23°44'45"N | 92°43'06"E |
| 75 | Hunthar | 75 | 564 | 2,680 | 1,300 | 1,380 | 23°44'35"N | 92°42'58"E |
| 76 | Rangvamual | 76 | 331 | 1,342 | 645 | 697 | 23°45'43"N | 92°40'51"E |
| 77 | Chawlhhmun | 77 | 634 | 3,092 | 1,597 | 1,495 | 23°44'29"N | 92°41'34"E |
|  | Total |  | 60,635 | 2,93,416 | 1,44,913 | 1,48,503 |  |  |

PROPOSED LOCATIONS FOR ESTABLISHMENT OF UPHC IN AIZAWL TOWN

ITI :

Urban Health Centre in ITI locality was established in 2004 under Reproductive and Child Health Programme.  It is situated in the eastern part of Aizawl City. The UHC building and staff quarters (25 nos) were constructed by the state government through loan taken from NABARD with an expenditure of Rs 127.50 lakhs and Rs.339.06 lakhs respectively. The population coverage by the UHC is around 28,535 with 5,829 households. The UHC covers 6 wards as per 2011 census which are depicted in the map provided herewith. They were Ward nos: 33, 34, 35, 36 , 37 and 41. Therefore, it has been considered that ITI UHC is appropriate to be converted into UPHC as it is addressing many health issues of its catering population. The renovation and up gradation of the building is on going from the fund approved for renovation during 2013-14 and will be finished soon and is much appreciated. The staff quarters with this UPHC were in poor condition and will be proposed for renovation in the coming years.

Chawlhhmun:

Chawlhhmun UHC was established in 2004 under RCH Programme and is situated in the western part of Aizawl City and is catering a large number of low income neighborhoods. When the Plan for NUHM has been formulated, convergence with urban local bodies has been initiated and frequent joint committees were conducted with Health Department delegates and Urban local bodies. After careful deliberations, the Urban Local Bodies agreed to donate a plot of land for construction of UPHC along with site for staff quarters (copy of the same enclosed for ready reference). The catering population is estimated to be around 11436 (Ward No. 66, 70, 71, 76 & 77) with a total household 2371 households as it is difficult to ascertain the exact figure as the area has a floating/migrating population. Currently the UHC is running in a rented house which barely meet the requirement. As the Local Council has donated a plot of land in a suitable location and the construction of the UPHC building is given priority so that the UPHC may function as desired. The community including the invulnerable population are depending on the service of this UPHC as they are lying many kilometers away from the nearest primary health facilities. The abstract cost for construction of new UPHC building amounting to Rs 75.00 lakhs is appended annexure -3

Hlimen UHC:

Hlimen UHC was like the other UHC established in 2004 to address primary health care delivery to the poor population dwelling in the southern part of the City. This UHC is running in a rented house since the inception. The urban local body has accepted to donate a plot of land for establishment of the UPHC (copy of the same enclosed for ready reference). This UPHC covers ward No. 47,48,49,50 with a population of 9314 and 1961 households.  Like other UHC, up gradation in terms of facilities – furniture, equipment etc. is done from funds allocated during 2013-14. Apart from the designated ward, this UPHC is currently catering the nearby hamlets and villages. The building currently occupied for the UPHC is rented and the owner are trying to sell the building, it is understood that the procurement of the building is not allowed under the mission, if the owner managed to sell the building, it is very likely that it will not be available for rent anymore. The said building is the only available building around the area suitable for establishment of UPHC. Hence, the construction of the building is needed immediately an may be approved during 2014-2015. The abstract cost amounting to Rs 75 lakhs is appended at annexure -3 (page no-42)

ZEMABAWK (Ramhlun UHC):

The existing UHC established at Ramhlun locality is functioning in a rented building, is being proposed to be shifted at Zemabawk locality, as the Local Council in this area is unable to donate land. It is considered that shifting of UHC/UPHC will capture more vulnerable population. Zemabawk is located in the northeastern part of Aizawl city. There are no health facilities in this area except cancer hospital and sub-centres. The area has a large concentration of migrating population as well as low income neighborhoods. The proposed UPHC will cater a large number of KFAs which is indicated in the map provided herewith. The nearest Health service delivery point from this area is located at 2 kms away. The expected number of population to be covered by UPHC is 24,400 with households of 4,877. As per GIS mapping it covers Ward No 8,9,10,11,12,13. The local authority has agreed to donate a vast area for construction of UPHC and quarters (Copy of the same enclosed for reference). The current UPHC building occupied for the UPHC is not satisfactory in term of space and location and there is no option to seek for another building. The construction of the building will be proposed later.

SIHPHIR:

Sihphir, an outskirt of Aizawl City has been proposed for establishment of Urban PHC, the Government of Mizoram had intended to establish a PHC but due to financial constrains failed to establish the same. After careful consideration, as the State Government has already constructed buildings for establishment of PHC, the building is available for establishment of UPHC subject to availability of funds from Government of India. There is also space for construction of Staff quarters inside the compound. Therefore the state Planning team proposed creation of UPHC in this area.  The estimated population to be covered is around 13,185 covering ward No. 1, 2, 3& 4 with a households of 2,690. This building is not occupied till date and need renovation and up gradation. The cost of this building is Rs.57.15 lakhs.The renovation of the building has already been started from the fund approved during 2013-14 and will be occupied for the new approved UPHC anytime soon.

LAWIPU:

Lawipu, a locality in Aizawl City is one of the most targeted area under NUHM being located in an isolated area and will cater the most vulnerable population in the city. The State Government also make efforts to promote the living conditions of the poor neighborhood through Slum Housing scheme under JnNURM etc. The State government has created a housing complex in this locality that will be able to accommodate around 400 households. In addition to this, the area has wide areas of stone quarries with a resident population engaged in the stone quarries comprising of foreign laborers and immigrants who are deprived of proper health care. It is estimated to cover Ward No.54, 55, 56, 57 & 58 as per GIS mapping. The target population is 14,915 with households of 3,075. In order to address the health care needs of the targeted population it is imperative that at least one UPHC be established in this area and the approval for the establishment of UPHC is very much appreciated. Also there is a PHE Pump House in the area for the whole Aizawl City where a number of Government quarters for the employees are constructed and occupied. As such all these Government employees will be able to avail this centre. The UPHC will be functioning in a rented building for which arrangement has already been made. As it is understood that fund is limited under the mission and phasing out of the construction is encouraged, the construction of the building will be proposed in the following year(s).

Lunglei City/ town:

Introduction:

Lunglei the 2nd biggest city after Aizawl in Mizoram is located in the south-central part of the State. Lunglei is situated at a distance of 235 km from Aizawl City. Lunglei was the Capital South of Lushai (Mizo) Hill District for 10 years from 1888, as was Aizawl for the North Hill Districts. Lunglei has had an importance till partition of India as it had direct access to Chittagong, a big city in Bangladesh which made Lunglei the Commercial and Education Centre. As per Census 2011, the population of Lunglei is 57011 which is a rise of 20.39% the last decade.

Geography: Lunglei is located at 22.88 N 92.73E; it has an average elevation of 722 metres (2368 feet)

Administration:

Lunglei Town is divided into four (4) constituencies which include the surrounding villages and is divided into 23 sub-wards under population census 2011. The Administration of Lunglei Town is indirectly managed from the State Government.  Sometimes back, the Govt. of Mizoram constituted Lunglei High Power Committee (LHPC) to look after and manage development of Lunglei Town. All the development Programme either from the State or GOI have been routed through LHPC.

Economy:

25% of the total households are depending on Government services, the rest are depending on mainly agriculture and non-regular income like trading, daily wage laborers, hawkers, peddlers etc.

GIS MAPPING OF DIFFERENT LOCALITIES IN LUNGLEI WITH POPULATION DETAILS (As per census 2011)

| Sl.no | Name of Ward | Ward no. | No of House | Total Population | Total Male | Total Female | Location |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hauruang | 1 | 250 | 1,159 | 556 | 603 | 22°52'27" | 92°43'03" |
| 2 | Rahsi Veng | 2 | 791 | 3,759 | 1,869 | 1,890 | 22°53'20" | 92°44'39" |
| 3 | Venghlun | 3 | 401 | 1,988 | 939 | 1,049 | 22°53'34" | 92°44'35" |
| 4 | Venglai | 4 | 712 | 3,237 | 1,636 | 1,601 | 22°53'25" | 92°44'48" |
| 5 | Electric Veng | 5 | 879 | 4,505 | 2,215 | 2,290 | 22°53'22" | 92°45'01" |
| 6 | Bazar | 6 | 968 | 4,622 | 2,323 | 2,299 | 22°53'46" | 92°45'20" |
| 7 | College Veng | 7 | 261 | 1,228 | 601 | 627 | 22°53'39" | 92°45'00" |
| 8 | Sazaikawn | 8 | 95 | 551 | 316 | 235 | 22°53′08″ | 92°43′57″ |
| 9 | Zohnuai | 9 | 306 | 1,520 | 743 | 777 | 22°53'58" | 92°45'55" |
| 10 | Serkawn | 10 | 558 | 2,762 | 1,343 | 1,419 | 22°54'26" | 92°45'43" |
| 11 | Zotlang | 11 | 516 | 2,891 | 1,735 | 1,156 | 22°54'55" | 92°45'21" |
| 12 | Pukpui | 12 | 526 | 2,958 | 1,943 | 1,015 | 22°56'01" | 92°45'24" |
| 13 | Chanmari | 13 | 1,082 | 5,391 | 2,755 | 2,636 | 22°53'00" | 92°45'01" |
| 14 | Farm Veng | 14 | 382 | 1,837 | 932 | 905 | 22°53'06" | 92°45'17" |
| 15 | Salem | 15 | 345 | 1,669 | 818 | 851 | 22°52'28" | 92°45'21" |
| 16 | Ramthar | 16 | 750 | 3,604 | 1,820 | 1,784 | 22°52'48" | 92°45'25" |
| 17 | Lunglawn | 17 | 812 | 4,108 | 2,349 | 1,759 | 22°52'09" | 92°45'29" |
| 18 | Luangmual | 18 | 389 | 1,865 | 949 | 916 | 22°51'37" | 92°45'28" |
| 19 | Sethlun | 19 | 179 | 880 | 420 | 460 | 22°52'02" | 92°46'01" |
| 20 | Theiriat | 20 | 389 | 1,988 | 974 | 1,014 | 22°51'51" | 92°47'11" |
| 21 | Hrangchalkawn | 21 | 157 | 723 | 361 | 362 | 22°50'59" | 92°47'50" |
| 22 | Lungpuizawl | 22 | 150 | 600 | 318 | 282 | 22°50'55" | 92°48'26" |
| 23 | Zobawk | 23 | 693 | 3,166 | 1,559 | 1,607 | 22°51'22" | 92°49'31" |
|  | Total |  | 11,591 | 57,011 | 29,474 | 27,537 |  |  |

PROPOSED LOCATIONS FOR ESTABLISHMENT OF UPHC IN LUNGLEI TOWN

LUNGLEI TOWN:

HRANGCHALKAWN UPHC:

This UHC was established along with UHCs established in Aizawl City in 2004. The location was chosen as it lies in as strategically suitable place which can cater the population of the outskirt of Lunglei town as well as peri-urban areas with the nearby villages. It is therefore, the approval to upgrade this UHC to UPHC is much appreciated. It covers around 7,357 population, with total households of 1568 and covering ward no: 19, 20, 21, 22 & 23. The services provided through this UHC are as mentioned in the previous chapter. The local authority donated a land for construction of UPHC (Copy of the same enclosed for ready reference.) The construction of new building will be proposed in the next financial year.

SAZAIKAWN UPHC:

Saizaikawn is located in the western part of the Lunglei Town. It  covers 3 localities and 5 catering villages, the estimated population to be covered is around 15,580(excluding the villages) with households of 3,316 in the ward no.3, 4, 5, 6, 7 & 8. The local Authority donated a land for construction of UPHC (copy of the same enclosed for ready reference.) As approved in the PIP of 2014-15, the UPHC will be functioning in a rented house, but it may please be noted that a suitable building large enough to house all the facilities expected in an UPHC is hard to come by and the building currently rented for the UPHC (the only available building in the vicinity) is too small to meet all the requirements and hence construction of a new building in the land donated by the Local Council is proposed. The abstract cost for construction of new UPHC building amounting to Rs 75.00 lakhs is enclosed in annexure -4 (Page no-47)

Activities under NUHM:

Major activities to be undertaken under NUHM are as summarized below:

- Provision of ANC, INC, PNC, conducting deliveries in the UPHCs.

- RTI/STI Services in convergence with SACs

- Child Health -Immunization services, promotion of early breast feeding, management of child hood illnesses etc.

- Counselling on MH, CH, FP, ARSH & Prevention from HIV/AIDS

- First Aid treatment

- Referral to FRUs / Higher facilities as necessary.

- Orientation of MAS and make them functional as per guidelines.

- Creating mentoring groups/ support structures for MAS/ ASHA through NGOs/CBOs

- Outreach Sessions as per guidelines

- Convergence with community organizations, Urban Local Bodies and other health  determinants – Clean water supply, sanitation, nutrition, health care, education skill development etc.

- Convergence with other health programmes such as RNTCP, NVBDCP, NPCB, IDSP etc and other department – PHE, UD&PA, SWD, and School Health etc.

- Capacity building of stake holders – ULBs, Medical and paramedic staff, community levels structures.

- Wide range of IEC/BCC activities.

- Community Monitoring

- Implement JSY & JSSK as per guidelines.

MAHILA AROGYA SAMITIS:

As envisaged in the guidelines, Mahila Arogya Samitis are formed to participate in community mobilization for the successful implementation of NUHM. The Accredited Social Health Activists will be entrusted as Leader of MAS wherever applicable. The orientation of these MAS has been completed.

| Proposed UPHC | No of approx population cover | No of approx households | No of MAS formed |
| --- | --- | --- | --- |
| Aizawl City |  |  |  |
| Hlimen UPHC | 9,314 | 1,961 | 2 |
| Chawlhhmun UPHC | 11,436 | 2,371 | 3 |
| Zemabawk UPHC | 24,400 | 4,877 | 5 |
| ITI UPHC | 28,535 | 5,829 | 5 |
| Sihphir UPHC | 13,185 | 2,690 | 4 |
| Lawipu UPHC | 14,915 | 3,075 | 3 |
| Lunglei Town |  |  |  |
| Hrangchalkawn | 7,357 | 1,568 | 3 |
| Sazaikawn | 15,580 | 3,316 | 4 |
| Total | 1,24,722 | 25,687 | 29 |

IEC/BCC : Detailed Activities

| IEC /BCC (Budgetted for 8 UPHCs) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl.No | Category | Nos | Rate (Rs) | Amount |
| 1 | Orientation Campaigns to Public and stakeholders | 20 | 20,000 | 4,00,000 |
| 2 | IPC sessions to MAS etc | 320 | 2,500 | 8,00,000 |
| 3 | Awareness Campaign among NGO/CBO/ Government Department and Target Groups | 20 | 20,000 | 4,00,000 |
| 4 | Printing of Leaflets | 1,00,000 | 3 | 3,00,000 |
| 5 | Preparation of TV spots in local language | 2 | 2,00,000 | 4,00,000 |
| 6 | Printing of UPHC posters | 5,000 | 40 | 2,00,000 |
| 7 | Telecasting of TV spots in local channels | 250 | 1,000 | 2,50,000 |
| 10 | Display Advertisement to local papers | 200 | 3,000 | 6,00,000 |
| 11 | Wall writing at all levels | 100 | 3,500 | 3,50,000 |
| 12 | Printing of stickers | 10,000 | 10 | 1,00,000 |
| 13 | Erection of Hoardings at strategic locations within the area of approved UPHC ( Aizawl City and Lunglei Town) | 50 | 10,000 | 5,00,000 |
| 14 | Healthy Mother’ Healthy Infant’ Competition at UPHC level once in a year | 8 | 5000 | 40,000 |
|  | Total |  |  | 43,40,000 |

| OPERATING COST SUPPORT FOR RUNNING UPHC (OTHER THAN UNTIED GRANTS AND CONSUMABLES - 8 NOS ) |  |  |
| --- | --- | --- |
| (Major items of equipment to be procured are listed out below, other requirement if any will be provided from the fund available under State / NRHM) |  |  |
| Sl.No | Materials | Quantity Required |
| 1 | Steel bed for in patients | 32 |
| 2 | Ward Bedside Locker | 32 |
| 3 | Instrument Table | 8 |
| 4 | Generator/inverter | 8 |
| 5 | Refrigerator / Deep Freezers | 8 |
| 6 | Shadowless OT light | 8 |
| 7 | Labour Tables | 8 |
| 8 | OT Tables | 8 |
| 9 | Revolving chair | 8 |
| 10 | Instrumental Cabinet | 16 |
| 11 | Suction Machine | 8 |
| 12 | kidney Tray | 16 |
| 13 | Examination Table | 8 |
| 14 | Foot Step | 16 |
| 15 | Infant warmer | 8 |
| 16 | Stethoscope | 8 |
| 17 | BP Apparatus normal | 16 |
| 18 | BP Apparatus with Pedestal | 8 |
| 19 | Baby cot | 16 |
| 20 | Revolving stool | 8 |
| 21 | Glucometer | 10 |
| 22 | Oxygen administration machine | 10 |
| 23 | antrior Vaginal wall retraction | 20 |
| 24 | Bowl for antiseptic solution | 10 |
| 25 | Mucus Extractor with suction machine | 10 |
| 26 | Sponge holding forcep Bowl for anti septic | 10 |
| 27 | Instrument tray | 10 |
| 28 | Head light | 10 |
| 29 | Ear speculum | 10 |
| 30 | Nebulizer | 10 |
| 31 | Mattress | 40 |
| 32 | Pillow with cover | 40 |
| 33 | Blanket | 40 |
| 34 | Bed sheet | 40 |
| 35 | Towel | 20 |
| 36 | Tongue depressor | 10 |
| 37 | Thermometer | 10 |
| 38 | Hub cuter | 10 |
| 39 | Needle destroyer | 10 |
| 40 | IV Stand | 10 |
| 41 | Mackintosh | 40 |
| 42 | Kelley's pad | 20 |
| 43 | Glass ware | as per need |
| 44 | Height measuring scale | 10 |
| 45 | Baby Weighing Scale | 10 |
| 46 | Forceps and Scissors | as per need |
| 47 | Adult Weighing Scale | 10 |
| 48 | Binocular Microscope | 10 |
|  | Other Requirements |  |
| 1 | Full Computer sets | 10 |
| 2 | Office/ UPHC tables | 40 |
| 3 | Office / UPHC chairs | 40 |
| 4 | Computer tables | 10 |
| 5 | Computer chairs | 10 |
| 6 | Steel Almirah | 10 |
| 7 | Installation of Solar Water heaters | 10 |
| 8 | Purchase of Water storage tanks 10,000 lit ( Sintex) | 10 |
| 9 | Carpet & Parda |  |
| 10 | Floor tiling of Labour room* |  |
| 11 | Repairing of Plumbing * |  |
| 12 | Installation of running water* |  |
| 13 | Upgradation of electrification* |  |
| 14 | Wood waiting Benches for OPD |  |

| List of General Medicines and Consumables for UPHC (8 nos) for 2014-15 |  |
| --- | --- |
| Sl.No | Name of Drugs |
| 1 | Lignocaine gel 2% w/w (30gm tube) |
| 2 | Tab. Paracetamol 500mg |
| 3 | Tab. Dexamethasone .5mg |
| 4 | Cap. Phenytoin Sodium 100mg |
| 5 | Cap. Amoxycillin 500mg |
| 6 | Amoxicillin anhydrous 500 mg + Clavulanic acid 125mg |
| 7 | Tab. Ciprofloxacin 500mg |
| 8 | Oint. Benzoic acid(6%)+Salicylic acid (3%) |
| 9 | Calamine Lotion |
| 10 | Tab. Nitrofurantoin 100mg |
| 11 | Tab. Atenolol 50mg |
| 12 | Tab. Enalapril Maleate 5mg |
| 13 | Tab. Enalapril Maleate 10mg |
| 14 | Inj. Furosemide 20mg/2ml |
| 15 | Inj. Mannitol IP20%w/v |
| 16 | Tab. Ranitidine 150mg |
| 17 | Tab. Famotidine 20mg |
| 18 | Cap. Omeprazole 20mg |
| 19 | Inj. Metoclopramide 10mg/2ml |
| 20 | ORS powder |
| 21 | Tab. Norfloxacin + Tinidazole IP |
| 22 | Inj. Vit. B Complex |
| 23 | Tab. IFA (100+0.5) large |
| 24 | Tab. Calcium Carbonate 500mg |
| 25 | Inj. Adrenaline 1mg/ml |
| 26 | Tab. Albendazole 400mg |
| 27 | Clotrimozole Cream IP 2 % w/w |
| 28 | Silver Sulphadiazaine cream USJP 1% w/w |
| 29 | Theophyline and Etofylline Inj. (anhydrous Thephyuline 50.6 mg Etofylline 169.4mg) |
| 30 | Theophylline and Etiohphlline tab |
| 31 | Salbutamol Suplhate tab IP 4 mg |
| 32 | Syp. Paracetamol 125mg/5ml |
| 33 | Inj. Paracetamol 150mg/ml |
| 34 | Inj. Phenearmine Maleate 22.75mg/ml |
| 35 | Cap. Ampicillin 250mg |
| 36 | Inj. Ampicillin 250mg/vial |
| 37 | Inj. Benzyly Penicillin 12 lacs unit (LA 12) |
| 38 | Cap. Amoxycillin 250mg |
| 39 | Amoxycillin Dry Syp. 125mg/5ml |
| 40 | Tab. Amoxicillin Dispersable USP 125 mg |
| 41 | Amoxicillin anhydrous 250 mg + Clavulanic acid 125 mg |
| 42 | Inj. Gentamicin 40mg/ml |
| 43 | Tab. Trimethoprin+Sulphadoxine(20+100) Ped |
| 44 | Tab. Ciprofloxacin 250mg |
| 45 | Inj. Amikacin 100mg/2ml |
| 46 | Tab. Azithromycin 250mg |
| 47 | Azithromycin 100 mg/5ml Syp |
| 48 | Oint. Miconazole 2% |
| 49 | Povidone Iodine Solution 5% |
| 50 | Oint. Povidone Iodine 5% |
| 51 | Oint. Silver Sulphadiazine 1% w/w |
| 52 | Oint. Clotrimoxazole 2%w/w |
| 53 | Metronidazole susp 60 ml |
| 54 | Syp. Domperidone |
| 55 | Gentamycin eye drop .3%w/v |
| 56 | Gentamycin ear drop .3%w/v |
| 57 | Inj. Theophylline+Etophylline 2ml |
| 58 | Inj. Dextrose 5% (10ml) |
| 59 | Inj. Dextrose 10% (10ml) |
| 60 | Inj. Electrolyte P |
| 61 | Inj. Electrolyte M |
| 62 | Tab. Vitamin B Complex |
| 63 | Vit. A Solution |
| 64 | Tab. Ascorbic acid 100mg |
| 65 | Tab. IFA (20+100mg) small |
| 66 | Albendazole Susp. 200mg/5ml |
| 67 | Cough syrup |
| 68 | Co-Trimoxazole Oral Suspension IP each 5 ml contains Trimethoprim 40mg sulphamethoxazole |
| 69 | Cotrimoxazole Tab.IP (Paediatric) (Tremethoprim 40mg) |
| 70 | Silver Sulphadiazaine cream USJP 1% w/w |
| 71 | Plasma Expander Infusion |
| 72 | Benedicts Solution (qualitative) 500ml |
| 73 | Anti A Blood grouping serum USP 10 ml vial |

Programme Management:

The Governing Body and Executive Committees of the State Health Mission (NRHM) already formed are re-notified for the implementation of State Urban Health Mission. Secretary in charge of Urban Development and Housing Department are included in the Governing Body and Executive Committees, as desired by GoI, Minister in-charge of Urban Development and Housing Department will also be included later. Copies of order for formation of Governing Body and Executive Committee enclosed for reference. At the district level, expansion of District Health Society is not required as per guidelines except Lunglei District where the Urban Development Officer is  included in the committee of District Health Society.

State Level:

Mission Director, NRHM is redesignated as Mission Director of National Health Mission. Joint  Mission Director is be appointed for NHM to assist Mission Director, NHM as and when necessary. As experienced during the implementation of NRHM, the implementation of various schemes cannot go smoothly as desired due to the absence of a subordinate officer to assist  Mission Director. Mission Director is frequently engaged on tour for different official purposes in and out of the state. Therefore it is considered that the role of Addl. MD is very significant to implement the programme as per plan. As considered necessary, a Nodal Officer is designated to take initiative for the implementation of all schemes under NUHM. Mission Director and Nodal Officer are engaged from the State Services.  Although, most of the staff proposed during 2013-14 were not approved, it is felt necessary that the following contractual staff exclusively for Urban Health Cell in the SPMU be approved to facilitate execution / implementation of various schemes under NUHM as the work load of the existing staff under NRHM is already overloaded.

Proposed Contractual Staff at State Level:

| Sl.No | Name of Post | No. of Post | Monthly Remuneration (Rs.) | Budget 2014-15 (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | State Programme Manager | 1 | 40,000 /- | 2,40,000/- |
| 2 | State Finance Manager | 1 | 40,000/- | 2,40,000/- |
| 3 | State MIS Manager | 1 | 40,000/- | 2,40,000/- |
| 4 | State M&E/Health Consultant | 1 | 40,000/- | 2,40,000/- |
| 5 | DEO | 1 | 15,000/- | 90,000/- |
| 6 | Accounts Clerk cum Office Asst. | 1 | 15,000/- | 90,000/- |
| 7 | Support Staff | 1 | 8,000/- | 48,000/- |
|  | Total | 7 |  | 11,88,000/- |

Minister, Health & FW Department

STATE LEVEL ORGANOGRAM OF NATIONAL URBAN HEALTH MISSION, MIZORAM

Secretary,                      Health & FW Department

Mission Director

National Health Mission

Addl. Mission Director,

National Urban Health Mission

Nodal Officer, NUHM

State Programme Manager

State M&E/Health Consultant

State Finance Manager

State MIS Manager

D.E.O

Account cum Office Assistant

District Level:

At the district level formation of separate Programme Management Unit for UHM is considered not required for the time being. The existing PMU under NRHM will manage the programme as it is estimated that there is no heavy work to execute. Therefore recruitment of contractual staff has not been proposed as well.

UPHC Level:

Under plan approval of 2013-14, the post of Accounts Clerk cum Office Assistants   only is approved. However, the service of DEOs will be indispensable as they are expected to handle the HMIS and may kindly be approved:

| Sl.No | Name of Post | No. of Post | Monthly Remuneration (Rs.) | Budget 2014-15 |
| --- | --- | --- | --- | --- |
| 1 | Accounts Clerk cum Office Asst | 8 | 12,500 /- | 12,00,000/- |
| 2 | DEO | 8 | 12,500/- | 12,00,000/- |
|  | Total | 16 |  | 24,00,000/- |

Other Human Resources:

The proposed 8 UPHCs will be made functional as Rural PHCs. They will provide round the clock services in addition to outreach session. The proposal is based on salary of same post at normal area proposed under NRHM for 2014-15, If the proposal of RCH is approved, It is assumed that all the technical staff under NUHM, especially Medical Officers are likely to shift to NRHM as there are many available post. No of Post (as per NUHM PIP approval 2013-14) and  remuneration proposed   for 2014-15 are tabulated below:

| Sl.No | Name of Post | No. of Post | Monthly Remuneration (Rs.) | Budget 2014-15 |
| --- | --- | --- | --- | --- |
| 1 | Medical Officer ( Full Time) | 8 | 54,000 | 51,84,000 |
| 2 | Staff Nurses (3 each) | 25 | 16,200 | 48,60,000 |
| 3 | Lab Technicians (Certificate) | 10 | 16,200 | 19,44,000 |
| 4 | ANMs | 19 | 13,635 | 31,08,780 |
| 5 | Helper /Sweeper (1 each) for each UPHCs | 19 | 8,000 | 18,24,000 |
|  | Total | 100 |  | 1,69,20,780 |

ANNEX 1

STATE NUHM PIP (2014-15)

ANNEX 1a

- State Profile :

Mizoram is a mountainous region which became the 23rd State of the Indian Union in February, 1987. It was one of the districts of Assam till 1973 when it became a Union Territory, sandwiched between Myanmar in the east and south and Bangladesh in the west, Mizoram occupies an area of great strategic importance in the north-eastern corner of India. It has a total of 722 Km international boundary with Myanmar and Bangladesh. As a sequel of the signing of the Historic Memorandum of Settlement between the Government of India and the Mizo National Front in 1986, Mizoram was granted Statehood on February 20, 1987 as per Statehood Act of 1986 and Mizoram became the 23rd State of the Indian Union.

The Capital of Mizoram is Aizawl. The Mizoram State Legislative Assembly has 40 seats. Mizoram is now represented at the Parliamentary by two Members, one in the Lok Sabha and the other in the Rajya Sabha. Mizoram is divided into 8 Administrative Districts and 9 Districts under the health Administration namely:-

1) Aizawl (Aizawl East and Aizawl West under Health Department)

2) Champhai

3) Kolasib

4) Mamit

5) Serchhip

6) Lunglei

7) Lawngtlai

8) Saiha.

POPULATION TREND IN MIZORAM (1951-2011)

| Sl.No | Year | No.of Towns | Total Population | Urban | Rural | % of Urban |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1951 | 1 | 196,202 | 6,956 | 189,246 | 3.55 |
| 2 | 1961 | 1 | 266,063 | 14,257 | 251,806 | 5.36 |
| 3 | 1971 | 2 | 332,390 | 37,759 | 294,631 | 11.36 |
| 4 | 1981 | 6 | 493,757 | 121,814 | 371,943 | 24.67 |
| 5 | 1991 | 22 | 689,756 | 317,946 | 371,810 | 46.10 |
| 6 | 2001 | 23 | 888,573 | 441,006 | 447,567 | 49.63 |
| 7 | 2011 | 23 | 1,097,206 | 571,771 | 525,435 | 52.11 |

Population Trend Chart

Table 1: Demographic Profile (based on 2011 census)

| Total Population (In lakhs) | 10,97,206 |
| --- | --- |
| Urban Population (In lakhs) | 5,71,771 |
| Urban Population as percentage of total population | 52.11% |
| Urban slum population (in lakhs) | NA |
| Slum population as percentage of urban population | NA |
| Number of Metro cities | Nil |
| Number of Million + cities (> 10 lakh population) | Nil |
| Number of cities with 1 to 10 lakh population | 1 |
| Number of towns with less than 1 lakh but more than 50 thousand population | 1 |
| Number of State HQs/District HQs which have less that 50 thousand population but are covered under NUHM | 6 |

Table 2: Health indicators

|  | Total (State Data) | Urban | Urban Poor (wherever available) |
| --- | --- | --- | --- |
| Infant Mortality Rate | 34 (SRS 2011) | NA | NA |
| Under-five Mortality Rate |  | NA | NA |
| Maternal Mortality Ratio | 61 (HMIS 2012-13) | NA | NA |
| Total Fertility Rate | 2.9 (NFHS-3) | NA | NA |
| Full Immunization (percentage) | 79.8 (HMIS 2012-13) | NA | NA |
| Number of SAM children identified (ICDS data) | 916 (ICDS data) | NA | NA |
| Annual Blood Examination Rate (ABER) for malaria | 17.67 (HMIS 2012-13) | NA | NA |
| Annual Parasite Index (API) | 8.68 (HMIS 2012-13) | NA | NA |
| Dengue Case Fatality Rate | 0 | NA | NA |
| Annual New Smear Positive case detection rate | 68% (HMIS 2012-13) | NA | NA |
| Treatment success rate among new smear positive cases | 88% (HMIS 2012-13) | NA | NA |
| Leprosy Prevalence Rate | 0.68 (HMIS 2012-13) | NA | NA |
| No. of outbreaks reported under IDSP in past year | 4 (HMIS 2013-14) | NA | NA |

Note : Data not available for Urban and Urban Poor.

Table 3: Details of cities/towns to be covered under NUHM as per 2011 census

| Name of the city/town | Type(state capital /district headquarters/other) | Population as per 2011 census | No. of slums | Slum population | Whether covered under JnNURM, BSUP, IDSMT |
| --- | --- | --- | --- | --- | --- |
| Aizawl | State Capital | 2,93,416 | NA | NA | Yes |
| Lunglei | District HQ | 57,011 | NA | NA | Yes |

Table 4: Details of cities/towns taken up for NUHM implementation in 2014-15

| Sl. No. | Name of City/Town | Type (state capital /district headquarters /other) | Population | Slum population | Implementing Authority (City/ Dist. Health Society) | Development Partner , if any |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl | State Capital | 2,93,416 | NA | State / District Health Society | UD&PA, School Education PHE, Social Welfare, Aizawl Municipal Council, Local Council |
| 2 | Lunglei | District HQ | 57,011 | NA | District Health Society | UD&PA, School Education PHE, Social Welfare, Village Council |

Table 5: State’s Allocation under Urban RCH Component under NRHM-RCH Flexible Pool:

| FMR Code | Activity | Amount Approved in 2012-13 (Rs in Lakhs) | Amount Approved in 2013-14 (Rs in Lakhs) |
| --- | --- | --- | --- |
| A.5 | URBAN RCH (focus on Urban slums) |  |  |
| A.5.1 | Identification of urban areas / mapping of urban slums and planning |  |  |
| A.5.2 | HR for urban health including doctors, ANMs, Lab techs |  |  |
| A.5.2.1 | Doctors/Mos |  |  |
| A.5.2.2 | Specialist |  |  |
| A.5.2.3 | Dentists |  |  |
| A.5.2.4 | ANM |  |  |
| A.5.2.5 | Staff Nurse |  |  |
| A.5.2.6 | LHV |  |  |
| A.5.2.7 | LT |  |  |
| A.5.2.8 | Pharmacists |  |  |
| A.5.2.9 | Radiographers |  |  |
| A.5.2.10 | OT Technician |  |  |
| A.5.2.11 | Support staff | 18.98 | 9.49 |
| A.5.2.12 | Others (pl specify) |  |  |
| A.5.3 | Operating expenses for UHP and UHC | 12.00 | 12.00 |
| A.5.4 | Outreach activities |  |  |
| A.5.5 | Others (pl specify) | 0.10 |  |
| A.5.5.1 | Infrastructure support for Urban areas |  |  |
|  | TOTAL | 31.08 | 21.49 |

Table 6: State’s Allocation under Infrastructure Maintenance (Treasury Route) head of NRHM

| FMR Code | Activity | Amount Approved in 2012-13 (Rs in Lakhs) | Amount Approved in 2013-14 (Rs in Lakhs) |
| --- | --- | --- | --- |
|  | Infrastructure Maintenance |  |  |
| 1. | Urban Family Welfare Centres (UFWCs) | 25.79 | 31.99 |
| 2. | Urban Revamping Scheme (Health Posts) |  |  |
|  | Total | 25.79 | 31.99 |

ANNEX 1b

STATE LEVEL INDICATORS & TARGETS

| Processes & Inputs |  |  |  |
| --- | --- | --- | --- |
| Indicators | Baseline number | Number Proposed (2014-15) | Number Achieved (2014-15) |
| - Number of Mahila Arogya Samiti (MAS) formed * | 0 | 29 | - |
| - Number of MAS members trained * | 0 | 282 | - |
| - Number of Accredited Social Health Activists (ASHAs) selected and trained * | 0 |  | - |
| - Number of ANMs recruited* | 0 | Nil |  |
| - Number of UPHCs made operational * | 0 | 5 |  |
| - Number of UCHCs made operational * | 0 | Nil |  |
| - No. of RKS created at UPHC and UCHC * | 0 | Nil |  |
| - Number of city PMUs established (personnel recruited and office space provided) * | 0 | Nil |  |
| - Number of cities covered under NUHM* | 0 | 2 |  |
| - Population covered under NUHM* | 0 | 74,869 (population in the cluster areas of UPHC) |  |
| - No. of slums covered under NUHM* | 0 | 36 ( Localities in the cluster areas of UPHC)) |  |
| - Slum population covered under NUHM* | 0 | 143140 (Population in the cluster areas of UPHC) |  |
| - Other vulnerable population covered under NUHM* | 0 | NA |  |

* Year 2013-14 being the baseline year, the indicators for these NUHM components would be zero.

ANNEX 1c

SUMMARY OF STATE NUHM BUDGET (2014-15)

| Name of the State: MIZORAM |  |  |  |
| --- | --- | --- | --- |
| FMR Code | Budget Head | Budget | % total budget |
|  |  | (Rs. Lakhs) |  |
| 1 | Planning & Mapping | 6.00 | 0.73 |
| 2 | Programme Management | 35.88 | 4.37 |
| 3 | Training & Capacity Building | 2.90 | 0.35 |
| 4 | Strengthening of Health Services |  |  |
| 4.a | Human Resource | 193.21 | 23.54 |
| 4.b | Infrastructure | 225.00 | 27.43 |
| 4.c | Untied grants | 20.00 | 2.45 |
| 4.d | Procurement (drugs and consumable) | 100.00 | 12.19 |
| 4.e | Other services | 232.14 | 28.29 |
| 5 | Regulation & Quality Assurance |  |  |
| 6 | Community Processes | 1.45 | 0.17 |
| 7 | Innovative Actions & PPP |  |  |
| 8 | Monitoring & Evaluation | 4.00 | 0.48 |
|  | TOTAL | 820.58 | 100.00 |

ANNEX 1d

DETAILED STATE NUHM BUDGET (2014-15)

| FMR Code | Budget Head | Physical Target (No.) | Unit cost* (Rs.) | Budget | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | (Rs. Lakhs) |  |
| 1 | Planning & Mapping |  |  |  |  |
| 1.1 | Metro cities | No. of cities | Rs.15 lakhs |  |  |
| 1.1.1 | Mapping |  |  |  |  |
| 1.1.2 | Data gathering (secondary/primary) |  |  |  |  |
| 1.1.3 | Any Other |  |  |  |  |
| 1.2 | Million+ cities | No. of cities | Rs.10 lakhs |  |  |
| 1.2.1 | Mapping |  |  |  |  |
| 1.2.2 | Data gathering (secondary/primary) |  |  |  |  |
| 1.2.3 | Any Other |  |  |  |  |
| 1.3 | Cities (1 lakh to 10 lakh population) | No. of cities | Rs.5 lakhs |  |  |
| 1.3.1 | Mapping |  |  |  |  |
| 1.3.2 | Data gathering (secondary/primary) |  |  |  |  |
| 1.3.3 | Any Other |  |  |  |  |
| 1.4 | Towns (50,000 to 1 lakh population) | No. of cities | Rs.2 lakhs | 6.00 | For 3 new towns to be included in 2015-16 PIP. Planning and Mapping is required during 2014-15 |
| 1.4.1 | Mapping |  |  |  |  |
| 1.4.2 | Data gathering (secondary/primary) |  |  |  |  |
| 1.4.3 | Any Other |  |  |  |  |
| 2 | Programme Management |  |  |  |  |
| 2.1 | State PMU |  |  |  |  |
| 2.1.1 | Human Resources | 7 | Rs.1.98 lakhs / Month | 11.88 | List of staff and remuneration proposed is given in page no- |
| 2.1.2 | Mobility support | 1 |  | 3.00 | @Rs 25000 p.m. |
| 2.1.3 | Office Expenses | 1 | Rs.1 lakh / month | 12 .00 | Proposed at 2013-14 rate approval |
| 2.2 | District PMU |  |  |  |  |
| 2.2.1 | Human Resources |  |  |  | Existing staff under NRHM will manage programme at Dist levels |
| 2.2.2 | Mobility support | 3 | Rs.05 p.m | 1.80 | Current 3 Districts to be covered under NUHM namely: Undivided Aizawl District( Aizawl East District, Aizawl West) District and Lunglei District ( 8 UPHC in all) |
| 2.2.3 | Office Expenses | 3 | Rs.0.2 p.m | 7.20 | Proposed for 3 districts |
| 2.3 | City PMU |  |  |  | No separate City PMU |
| 2.3.1 | Human Resources |  |  |  |  |
| 2.3.2 | Mobility support |  |  |  |  |
| 2.3.3 | Office Expenses |  |  |  |  |
| 3 | Training & Capacity Building |  |  |  |  |
| 3.1 | Orientation of Urban Local Bodies (ULB) | No. of ULBs | Rs.5 lakhs for metros, Rs.3 lakhs for million+ cities, Rs.1 lakh for other cities above 1 lakh and Rs.0.5 lakhs for smaller towns below 1 lakh |  | Already done for ULB to be covered during 2014-15 |
| 3.2 | Training of ANM/paramedical staff | 12 | Maximum Rs.5000 per ANM (for entire training package) | 0.60 | Proposed for 12 remaining ANMs already approved. |
| 3.3 | Training of Medical Officers | 5 | Maximum Rs.10,000 per MO (for entire training package) | 0.50 | Proposed 5 remaining M.O already approved. |
| 3.4 | Orientation of Specialists | May be taken up in the subsequent years |  |  |  |
| 3.5 | Orientation of MAS | No. of MAS | Maximum Rs.10,000 per MAS (for entire training package) |  | Already done for approved 8 UPHC |
| 3.6 | Selection & Training of ASHA | No. of ASHA | Maximum Rs.10,000 per ASHA (for entire training package) |  | Selection of ASHA solely for NUHM is not yet done. |
| 3.7 | Other Trainings/Orientations | No. of Training -2 Nos of Participants - 18 | Rs 10,000 | 1.80 | Training of 8 Accounts Clerk and 8 DEO and 2 Consultants |
| 4 | Strengthening of Health Services |  |  |  |  |
| 4.a | Human Resource |  |  |  |  |
| 4.b | Infrastructure |  |  |  |  |
| 4.c | Untied grants |  |  |  |  |
| 4.d | Procurement (drugs and consumable) |  |  |  |  |
| 4.e | Other services |  |  |  |  |
| 4.1 | Outreach services/camps/UHNDs |  |  |  |  |
| 4.1.1 | UHNDs | 60 | Maximum Rs.10,000 per UHND/camp | 6.00 | Proposed in addition to 48 outreach camp already approved for 2013-14 |
| 4.1.2 | Special outreach camps in slums/ vulnerable areas | 32 | Rs 10,000 per UHND | 3.20 | Proposed for 1 UHND for every quarter for 8 UPHC |
| 4.2 | ANM/LHV |  |  |  |  |
| 4.2.1 | Salary support for ANM/LHV | 19 | Proposed as per NRHM budget proposal for 2014-15 i.e, Rs 13,635 | 31.09 | Nos proposed is as per NUHM PIP approval of 2013-14 |
| 4.2.2 | Mobility support for ANM/LHV | 19 | Rs.500 pm | 1.14 | As per norms |
| 4.3 | Urban PHC (UPHC) |  |  |  |  |
| 4.3.1 | Renovation/up-gradation of existing facility to UPHC | No. of UPHCs | Rs.10 lakhs per UPHC |  |  |
| 4.3.2 | Building of new UPHC | 3 | Rs 75 lakhs per UPHC | 225 | Details provided in annexure-3&4 |
| 4.3.3 | Operating cost support for running UPHC (other than untied grants and medicines & consumables) | 8 | Rs.20 lakhs per year per UPHC | 160.00 | Purchase of equipments, Major hospital appliances, Furniture, Minor modifications of buildings etc |
| 4.3.3.1 | Human Resource (8 Accounts Clerk cum Office Asst & 8 DEO) | 16 | Rs. 12,500 p.m | 24.00 | They will be posted at UPHCs to look after A/C and HMIS under supervision of MO .Details given on page- |
| 4.3.3.1.1 | MO salary | 8 | Rs.54,000 p.m | 51.84 | Proposed in line with NRHM budget proposal for 2014-15 |
| 4.3.3.1.2 | Salary of paramedical & nursing staff (Staff Nurse/ Lab Technician/ Pharmacist/ Other) | 25 Staff Nurses & 10 Lab. tech | Rs.16,200 p.m | 68.04 | Proposed in line with NRHM budget proposal for 2014-15 |
| 4.3.3.1.3 | Salary of support staff (non clinical staff) | Helpers / Sweeper 19 nos | 8,000 | 18.24 | As per reasonable rates in the state |
| 4.3.3.1.4 | Public Health Manager |  |  |  |  |
| 4.3.3.1.5 | Office Expenses | 8 | Rs 50,000 p.a. | 4.00 | As per norms |
| 4.3.3.2 | Others |  |  |  |  |
| 4.3.4 | Untied grants to UPHC | 8 | Rs.2.50 lakhs per year per UPHC | 20.00 | As per norms |
| 4.3.5 | Medicines & Consumables for UPHC | 8 | Rs.12.50 lakhs per year per UPHC | 100.00 | As per norms |
| 4.3.5.1 | Emergency drugs |  |  |  |  |
| 4.3.5.2 | Others (e.g. hiring of premises/ mobile PHC) | 6 | Rs.0.2 p.m | 14.40 | 6 out of 8 UPHCs established in hired buildings |
| 4.4 | Urban CHC (UCHC) |  |  |  |  |
| 4.4.1 | Capital cost support for new UCHC | May be taken up in the subsequent years |  |  |  |
| 4.4.2 | Human Resource |  |  |  |  |
| 4.4.2.1 |  |  |  |  |  |
| 4.4.2.2 |  |  |  |  |  |
| 4.4.3 | Untied grants for UCHC | No. of UCHC/urban referral hospitals | Rs.5 lakhs per year per hospital |  |  |
| 4.4.4 | Medicines & Consumables for UCHC |  |  |  |  |
| 4.5 | School Health Program |  |  |  |  |
| 4.5.1 | Human Resource |  |  |  |  |
| 4.5.2 | Other School Health services |  |  |  |  |
| 4.6 | IEC/BCC | Details given in write-up | As per need | 43.40 | Details of activities given in page no-15 |
| 5 | Regulation & Quality Assurance | May be taken up in the subsequent years |  |  |  |
| 6 | Community Processes |  |  |  |  |
| 6.1 | MAS/community groups | 29 | Rs.5000 per year per MAS | 1.45 |  |
| 6.2 | ASHA (urban) | No. of ASHA | Approx. Rs.2000 pm per ASHA |  | Not budgetted due to non availability of guidel ines during planning process. |
| 6.3 | NGO support for community processes | No. of NGOs engaged | As per need |  |  |
| 7 | Innovative Actions & PPP |  | As per need |  |  |
| 8 | Monitoring & Evaluation |  |  |  |  |
| 8.1 | Baseline/end line surveys | 8 | Rs.50,000 per UPHC | 4.00 | Monitoring through field visits, Review meetings etc,. This may be given priority as it is especially important during the initial period. |
| 8.2 | Research Studies in Urban Public Health |  |  |  |  |
| 8.3 | IT based monitoring initiatives |  |  |  |  |
|  | TOTAL |  |  | 820.58 |  |

* The unit costs given here are indicative. The States/UTs have adjusted  these unit costs as per local conditions and prevailing rates.

ANNEX 2

CRITERIA FOR SELF-APPRAISAL OF NUHM PIP

| S.no. | Criteria | Remark [yes (Y), or no (N)] |
| --- | --- | --- |
| 1 | Has the State NUHM PIP been reviewed in detail by a single person (preferably Secretary/MD) to ensure internal consistency? If yes, by whom? | Yes, by M.D |
| 2 | Has the state ensured that there is no double budgeting for the NUHM PIP under any head? Has the State ensured that there is no duplication of budget between NRHM and NUHM? | Yes |
| 3 | Has a chartered accountant/finance manager reviewed the budget in detail? | Yes |
| 4 | Is the urban health cell within State Programme Management Unit in place and functional? | No |
| 5 | Has the PIP been approved by the State Health Society ? | Yes |
| 6 | Have City Health Plan s (where applicable) been shared with the concerned ULBs ? | Yes |
| 7 | Have the government orders for enlarging the ambit of the State Health Mission and Society and constitution of City Urban Health Mission/ Society been issued? | Yes |

ANNEX  3

- CITY PROFILE

Name of the City:  AIZAWL

Status of the city: State Capital

Table 1: Demographic Profile

| Total Population of city (in lakhs) | 2.93 |
| --- | --- |
| Slum Population (in lakhs) | NA |
| Slum Population as percentage of urban population | NA |
| Number of Notified Slums | NA |
| Number of slums not notified | NA |
| No. of Slum Households | NA |
| No. of slums covered under slum improvement programme (BSUP,IDSMT,etc.) | NA |
| Number of slums where households have individual water connections* | NA |
| Number of slums connected to sewerage network* | NA |
| Number of slums having a Primary school | NA |
| No. of slums having AWC | NA |
| No. of slums having primary health care facility | NA |

- Indicate source of data wherever available (e.g. AHS , NFHS-3 , etc.)

- State may also mention if data is unavailable

Table 2: Health/Morbidity Profile of the City:

The data may be collected from the leading public hospitals in the city and based on IDSP.

| Sl. No. | Name of Disease/ cause of morbidity (e.g. COPD, trauma, cardiovascular disease etc.) | Number of cases admitted in 2012 |
| --- | --- | --- |
| 1. | Injuries and Trauma | 1743 |
| 2. | Self inflicted injuries/suicide | 4 |
| 3. | Cardiovascular Disease | 242 |
| 4. | Cancer (Breast cancer) | 33 |
| 5. | Cancer (cervical cancer) | 29 |
| 6. | Cancer (other types) | 133 |
| 7. | Mental health and depression | 44 |
| 8. | Chronic Obstructive Pulmonary Disease (COPD) | 204 |
| 9. | Malaria | 106 |
| 10. | Dengue |  |
| 11. | Infectious fever (like H1N1, avian influenza, etc.) |  |
| 12. | TB | 115 |
| 13. | MDR TB |  |
| 14. | Diarrhea and gastroenteritis | 322 |
| 15. | Jaundice/Hepatitis | 461 |
| 16. | Skin diseases | 162 |
| 17. | Severely Acute Malnourishment (SAM) |  |
| 18. | Iron deficiency disorder | 2 |
| 19. | Others |  |

Data: Civil Hospital Aizawl

Table 3: Listing of Slums

Listing and Mapping of slums

A mapping of the listed and unlisted slums, vulnerable populations as well as public health facilities catering to the slums may be done for each city in the following format:

| Sl.no | Ward no. | Name of the slum/KFA | Population | Quality of housing (kutcha/pucca/mixed) | Quality of sanitation (IHL,community toilets, OD) | Status of water supply (Piped, Hand pumps, open wells, none) | Location and distance of nearest AWC | Location and distance of nearest Primary School | Location and distance of nearest Primary Health Centre/UHP/UFWC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 47, 48, 49,50 | Hlimen | 9,314 | Kutcha/Mixed | Average | Piped/Hand Pump | NA | NA | NA |
| 2 | 33, 34, 35, 36, 37, 41 | ITI | 28535 | Kutcha/Mixed | Average | Piped/Hand pump | NA | NA | NA |
| 3 | 66, 70, 71, 76, 77 | Chawlhhmun | 11436 | Kutcha/Mixed | Average | Piped/Hand Pump | NA | NA | NA |
| 4 | 8, 9, 10, 11, 12, 13 | Zemabawk | 24400 | Kutcha/Mixed | Average | Piped/Hand pump | NA | NA | NA |
| 5 | 1, 2, 3, 4 | Sihphir | 13185 | Kutcha/Mixed | Average | Piped/Hand Pump | NA | NA | NA |
| 6 | 54, 55, 56, 57, 58 | Lawipu | 14916 | Kutcha/Mixed | Average | Piped/Hand pump | NA | NA | NA |

Table 4: Overview of existing public health facilities

- To list all kinds of hospitals, , maternity homes, dispensaries run by ULBs and state health department, including public facilities managed through PPP

- While listing the Urban Family Welfare Centres (UFWC) and Urban Health Posts (UHPs) the category of UFWC (Type I, II, II) and UHP (Type A, B, C, D) may be specified along with the details of Human Resources in position.

| Sl. No. | Name & type of facility (DH, Maternity Home, CHC, other ref. hospital UFWC, UHP PHC,Dispensary etc.) | Managing Authority (Municipal Council, State Health Department, facilities functioning on PPP basis) | Location of Health facility | Population covered by the facility | Services provided | Human Resources available – list type and number of HR available i.e. ANM, LT, SN, MOs, Specialists etc. | No. and type of equipment available: X-ray machine, USG, autoclave etc. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Civil Hospital Aizawl | State Govt. | Dawrpui | 2,93,413 | General | ANM-3, LT-25, SN-80, M.O-32, Spst-72 | X-ray – 1 USG – 3 Autoclave- 3 |
| 2 | Kulikawn Hospital | State Govt. | Kulikawn | Cannot be determined | General | ANM-2, LT-5, SN-16, M.O-5, Spst-6 | X-ray – 1 USG – 3 Autoclave-2 |
| 3 | Cancer Hospital | State Govt. | Zemabawk |  | Cancer | ANM-Nil, LT-Nil, SN-10, M.O-2, Spst-7 | X-ray – 1 USG – 1 Autoclave- 1 |
| 4 | Synod Hospital | Private | Durtlang |  | General |  |  |
| 5 | Greenwood Hospital | Private | Bawngkawn |  | General |  |  |
| 6 | Bethesda Hospital | Private | Bawngkawn |  | General |  |  |
| 7 | Nazareth Hospital | Private | Ramhlun North |  | General |  |  |
| 8 | Grace Nursing Home | Private | Zarkawt |  | General |  |  |
| 9 | New Life Hospital | Private | Chanmari |  | General |  |  |
| 10 | Vaivenga Hospital | Private | Dawrpui |  | General |  |  |
| 11 | Seventh Day Hospital | Private | Vaivakawn |  | General |  |  |
| 12 | Aizawl Hospital | Private | Mission Veng |  | General |  |  |
| 13 | B.N.Hospital | Private | Kulikawn |  | General |  |  |
| 14 | Alpha Hospital | Private | Kulikawn |  | General |  |  |

| COST APPRAISAL FOR THE WORK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| "CONSTRUCTION OF URBAN PUBLIC HEALTH CENTRE AT CHAWLHHMUN |  |  |  |  |  |  |  |
| UNDER NATIONAL URBAN HEALTH MISSION, MIZORAM" |  |  |  |  |  |  |  |
| Sl.No | Description | Unit | Qty. | Rates |  | Amount |  |
| 1 | Civil works |  |  |  |  |  |  |
| 1.1 | Ground Floor | Sqm | 126.56 | ` | 22,000.00 | ` | 2,784,320.00 |
| 1.2 | First Floor | Sqm | 126.56 | ` | 22,000.00 | ` | 2,784,320.00 |
| Civil of civil works (total of 1) = |  |  |  |  |  | ` | 5,568,640.00 |
| 2 | Services |  |  |  |  |  |  |
| 3.1 | Internal Water Supply and Sanitary Installations (% means percentage of building cost) |  |  |  | 10% | ` | 556,864.00 |
| 3.2 | External Service Connection for Water Supply |  |  |  | 5% | ` | 278,432.00 |
| 3.3 | R.C.C. Water Tank | litre | 20,000.00 | ` | 20.00 | ` | 400,000.00 |
| 3.4 | Internal Electrification |  |  |  | 13% | ` | 696,080.00 |
| 3 | Cost of services (total of 2) = |  |  |  |  | ` | 1,931,376.00 |
| 4 | Total (total 1+total 2) = |  |  |  |  | ` | 7,500,016.00 |
|  | GRAND TOTAL |  |  |  |  | ` | 7,500,016.00 |
|  |  |  |  |  | SAY = | ` | 7,500,000.00 |
|  | (Rupees Seventy Five Lakh )only |  |  |  |  |  |  |

| COST APPRAISAL FOR THE WORK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| "CONSTRUCTION OF URBAN PUBLIC HEALTH CENTRE AT HLIMEN |  |  |  |  |  |  |  |
| UNDER NATIONAL URBAN HEALTH MISSION, MIZORAM" |  |  |  |  |  |  |  |
| Sl.No | Description | Unit | Qty. | Rates |  | Amount |  |
| 1 | Civil works |  |  |  |  |  |  |
| 1.1 | Ground Floor | Sqm | 126.56 | ` | 22,000.00 | ` | 2,784,320.00 |
| 1.2 | First Floor | Sqm | 126.56 | ` | 22,000.00 | ` | 2,784,320.00 |
| Civil of civil works (total of 1) = |  |  |  |  |  | ` | 5,568,640.00 |
| 2 | Services |  |  |  |  |  |  |
| 3.1 | Internal Water Supply and Sanitary Installations (% means percentage of building cost) |  |  |  | 10% | ` | 556,864.00 |
| 3.2 | External Service Connection for Water Supply |  |  |  | 5% | ` | 278,432.00 |
| 3.3 | R.C.C. Water Tank | litre | 20,000.00 | ` | 20.00 | ` | 400,000.00 |
| 3.4 | Internal Electrification |  |  |  | 13% | ` | 696,080.00 |
| 3 | Cost of services (total of 2) = |  |  |  |  | ` | 1,931,376.00 |
| 4 | Total (total 1+total 2) = |  |  |  |  | ` | 7,500,016.00 |
|  | GRAND TOTAL |  |  |  |  | ` | 7,500,016.00 |
|  |  |  |  |  | SAY = | ` | 7,500,000.00 |
|  | (Rupees Seventy Five Lakh )only |  |  |  |  |  |  |

ANNEX 4

- CITY PROFILE

Name of the City:  LUNGLEI

Status of the city: District Capital

Table 1: Demographic Profile

| Total Population of city (in lakhs) | 0.57 |
| --- | --- |
| Slum Population (in lakhs) | NA |
| Slum Population as percentage of urban population | NA |
| Number of Notified Slums | NA |
| Number of slums not notified | NA |
| No. of Slum Households | NA |
| No. of slums covered under slum improvement programme (BSUP,IDSMT,etc.) | NA |
| Number of slums where households have individual water connections* | NA |
| Number of slums connected to sewerage network* | NA |
| Number of slums having a Primary school | NA |
| No. of slums having AWC | NA |
| No. of slums having primary health care facility | NA |

- Indicate source of data wherever available (e.g. AHS , NFHS-3 , etc.)

- State may also mention if data is unavailable

Table 2: Health/Morbidity Profile of the City:

The data may be collected from the leading public hospitals in the city and based on IDSP.

| Sl. No. | Name of Disease/ cause of morbidity (e.g. COPD, trauma, cardiovascular disease etc.) | Number of cases admitted in 2012 |
| --- | --- | --- |
| 1. | Injuries and Trauma | 37 |
| 2. | Self inflicted injuries/suicide | - |
| 3. | Cardiovascular Disease | 23 |
| 4. | Cancer (Breast cancer) | 2 |
| 5. | Cancer (cervical cancer) | - |
| 6. | Cancer (other types) | 28 |
| 7. | Mental health and depression | - |
| 8. | Chronic Obstructive Pulmonary Disease (COPD) | 25 |
| 9. | Malaria | 661 |
| 10. | Dengue | - |
| 11. | Infectious fever (like H1N1, avian influenza, etc.) | - |
| 12. | TB | 24 |
| 13. | MDR TB | - |
| 14. | Diarrhea and gastroenteritis | 323 |
| 15. | Jaundice/Hepatitis | 8 |
| 16. | Skin diseases | 21 |
| 17. | Severely Acute Malnourishment (SAM) | - |
| 18. | Iron deficiency disorder | - |
| 19. | Others | 8034 |

Data : Civil Hospital, Lunglei

Table 3: Listing of Slums

Listing and Mapping of slums

A mapping of the listed and unlisted slums, vulnerable populations as well as public health facilities catering to the slums may be done for each city in the following format:

| Sl.no | Ward no. | Name of the slum/KFA | Population | Quality of housing (kutcha/pucca/mixed) | Quality of sanitation (IHL,community toilets, OD) | Status of water supply (Piped, Hand pumps, open wells, none) | Location and distance of nearest AWC | Location and distance of nearest Primary School | Location and distance of nearest Primary Health Centre/UHP/UFWC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 19, 20, 21, 22, 23 | Hrangchalkawn | 7357 | Kutcha/Mixed | Average | Piped/Hand Pump | NA | NA | NA |
| 2 | 3,4,5,6,7,8 | Sazaikawn | 15580 | Kutcha/Mixed | Average | Piped/Hand pump | NA | NA | NA |

Table 4: Overview of existing public health facilities

- To list all kinds of hospitals, , maternity homes, dispensaries run by ULBs and state health department, including public facilities managed through PPP

- While listing the Urban Family Welfare Centres (UFWC) and Urban Health Posts (UHPs) the category of UFWC (Type I, II, II) and UHP (Type A, B, C, D) may be specified along with the details of Human Resources in position.

| Sl. No. | Name & type of facility (DH, Maternity Home, CHC, other ref. hospital UFWC, UHP PHC,Dispensary etc.) | Managing Authority (Municipal Council, State Health Department, facilities functioning on PPP basis) | Location of Health facility | Population covered by the facility | Services provided | Human Resources available – list type and number of HR available i.e. ANM, LT, SN, MOs, Specialists etc. | No. and type of equipment available: X-ray machine, USG, autoclave etc. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Civil Hospital | State Govt. | Chanmari | 57,011 |  | ANM-4, LT-4, SN-41, M.O-9, Spst-15 | X-ray – 1 USG – 1 Autoclave- 2 |
| 2 | Christian Hospital | Private | Serkawn | Cannot be determined |  |  |  |
| 3 | Hope Hospital | Private | Chanmari |  |  |  |  |
| 4 | Faith Hospital | Private | Chanmari |  |  |  |  |

| 1. | District Hospital | State Govt. | Vengsang | 32,734 | General | ANM-1, LT-2, SN-21, M.O-5, Spst-5 | X-ray – 1 USG – 1 Autoclave- 1 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2. | D.M.Hospital | Private | Vengthlang | Cannot be determined | General |  |  |
| 3 | Med Aim Hospital | Private | Zotlang |  | General |  |  |

| COST APPRAISAL FOR THE WORK |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| "CONSTRUCTION OF URBAN PUBLIC HEALTH CENTRE AT SAZAIKAWN |  |  |  |  |  |  |  |
| UNDER NATIONAL URBAN HEALTH CENTRE, MIZORAM" |  |  |  |  |  |  |  |
| Sl.No | Description | Unit | Qty. | Rates |  | Amount |  |
| 1 | Civil works |  |  |  |  |  |  |
| 1.1 | Ground Floor | Sqm | 121.12 | ` | 22,000.00 | ` | 2,664,640.00 |
| 1.2 | First Floor | Sqm | 121.12 | ` | 22,000.00 | ` | 2,664,640.00 |
|  | Civil of civil works (total of 1) = |  |  |  |  |  | 5,329,280.00 |
|  | Add Cost Index 4.5% for Lunglei Div.(PWD) |  |  |  |  | ` | 239,817.60 |
| Cost of Civil of civil works (total of 2) = |  |  |  |  |  | ` | 5,569,097.60 |
| 2 | Services |  |  |  |  |  |  |
| 3.1 | Internal Water Supply and Sanitary Installations (% means percentage of building cost) |  |  |  | 10% | ` | 556,909.76 |
| 3.2 | External Service Connection for Water Supply |  |  |  | 5% | ` | 278,454.88 |
| 3.3 | R.C.C. Water Tank | litre | 20,000.00 | ` | 20.00 | ` | 400,000.00 |
| 3.4 | Internal Electrification |  |  |  | 13% | ` | 696,137.20 |
| 3 | Cost of services (total of 3) = |  |  |  |  | ` | 1,931,501.84 |
| 4 | Total (total 2+total 3) = |  |  |  |  | ` | 7,500,599.44 |
|  | GRAND TOTAL |  |  |  |  | ` | 7,500,599.44 |
|  |  |  |  |  | SAY = | ` | 7,500,000.00 |
|  | (Rupees Seventy Five Lakh )only |  |  |  |  |  |  |