PROJECT IMPLEMENTATION PLAN

FOR THE YEAR

2014     -    2015

NATIONAL LEPROSY ERADICATION

CONTROL PROGRAMME

(NLEP)

NLEP CELL

DIRECTORATE OF HEALTH SERVICES

MIZORAM : AIZAWL

- Situation analysis:-

STRENGTH:-

The strength of NLEP in Mizoram during the past year had been the active participation of ASHA’s due to  intensive tours of the SLO and SMO in various districts of Mizoram. During these tours, sensitization of the programme at the grass root level i.e. the ASHA’s , Health Workers ,Health Supervisors and Non-medical Supervisors  had been done, due to which case detection by ASHA’s had greatly improved as compared to previous years. Also, the overall new case detection had doubled as compared to the previous years(i.e. from 18 during the previous year to 39 in  2014) , which is also a result of these active tour programmes and ASHA sensitizations.

WEAKNESS:-

The main weakness of the programme had been the difficulty in trying to immobilize migrant populations of Mizoram, regarding treatment completion of MDT as they form a major part of the State’s case load.

THREATS:-

It had come to the SLO’s notice that, some border areas of Mizoram had been infiltrated with cases from neighboring states. This problem could pose as a threat for insurgence of new cases in these areas. Hence, we had conducted active search of these cases and had given MDT to those identified.

NEW INITIATIVES PROPOSED:-

- To conduct training at different Medical institutions  of the State like Nursing colleges, Health Worker school etc. To conduct training for all the newly recruited 88 doctors within this coming year.

- To hire PMW on contractual basis, in the high endemic regions of the State.In Mizoram, Lawngtlai district has been recorded as a high endemic district with ANCDR of 9.3 per 100,000 population in 2012-2013, and ANCDR of 23 per 100,000 during 2013-2014.

- To conduct review meetings with the PMW’s of the state at the State capital on quarterly basis for better functioning of the programme and and to conduct training for newly recruited PMW’s  and to conduct re-orientation training for the already existing 8 PMW’s

II.    PERFORMANCE UNDER NLEP.

| S.No. | Indicators | 2008 -09 | 2009 -10 | 2010 -11 | 2011-12 | 2012-13 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | No. of new cases detected (ANCDR/100,000) | 23 (2%) | 10 (0.9%) | 21 (1.9%) | 17 (1.5%) | 18 (1.6%) |
| 2. | No. of cases on record at year end (PR/10,000) | 17 (0.15%) | 19 (0.17%) | 20 (0.18%) | 18 (0.16%) | 27 (0.24%) |
| 3. | No. of Grade II disability among new cases (%) | 0 | 0 | 0 | 0 | 0 |
| 4. | Treatment Completion Rate | MB- 75% PB-80% | MB-70% PB-75% | MB- 77% PB- 66% | MB-81% PB-68% | MB-61% PB-75% |
| 5. | Reconstructive Surgery conducted | 0 | 0 | 0 | 0 | 0 |
| Total |  |  |  | - |  |  |

III. NLEP annual plan for the year 2014-2015

1.   Improved early case detection

Under this result based initiative following two activities need to be planned district wise

1.1. Incentive to ASHA

| S.NO | No. of ASHA activity | Number | Unit cost per person (rs.) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Incentive to ASHA | Case diagnosis Treatment completion MB PB | 250 x 40 600 x 40 400 x 40 | 10,000 24,000 16,000 |
| Total |  | - | - | 50,000 |

1.1 a. Sensitization of ASHA

| S.NO | No. of ASHA activity | Number | Unit cost per person (rs.) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Sensitization of ASHA | 250 | 100 | 25,000 |
| Total |  | - | - | 25,000 |

  - Specific plan for high endemic districts

Special activities in high endemic districts where ANCDR is more than 10 per 100,000 population. This activity was completed in 209 high endemic districts during 2012-13 and need to be planned for Active Search again during the current year, as per the PIP for 12th. Plan.

In Mizoram, out of the 39 new cases detected during 2013-2014 March , 32 cases are from

one district alone, which is Lawngtlai District. Hence, the ANCDR may be calculated as

follows:-

No. of new cases detected in Lawngtlai district = 32

Population of Lawngtlai district                          = 1,17,894

ANCDR                                                              = 25.62  per 100,000 population.

| Special activities in high endemic district | No. of Block | Unit cost per Block (Rs.) | Amount for districts (Rupees) |
| --- | --- | --- | --- |
| Special activities In High endemic district - Capacity building of staff - Awareness drive - Enhanced - monitoring and supervision - Validation of MB and child cases | For one district | 2,00,000 | 2,00,000 |

2.     Improved case management:-

2.1   DPMR services (MCR footwear, Aids and appliances, welfare allowance to BPL

patients)

| S.No | Item | No. required | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. 2. 3. | MCR footwear Aids & appliance Welfare allowances for BPL patient | 5 X 2 pairs 5 15 | 300 X 5 17,000 8000 | 1,500 85,000 1,20,000 |
| Total |  | - | - | 2,06,500 |

2.2    Urban Leprosy Control

| S.No | Category of urban area | Number | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. 2. 3. | Township Medium city –I Medium city – II Mega city | 3 1 - | 3 x 1,14,000 1 x 2,40,000 - | 3,42,000 2,40,000 - |
| Total |  |  |  | 5,82,000 |

- Though the population of the state capital of Mizoram (Aizawl) is only upto 4 lakhs, it may be regarded as Medium city-I as it is a state capital. Besides Aizawl City, Lunglei, Champhai, Lawngtlai are proposed to be included as Township.

2.3. Materials and supplies

2.3 i. Supportive drugs, Lab reagents & equipments and printing works

To be calculated for State/UT according to the number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Supportive Drugs & dressings | 9 | 9 X 40,000 | 3,60,000 |
| 2. | Laboratory reagents and equipments | 9 | 9 X 8,000 | 72,000 |
| 3. | Printing works | 9 | 9 X 20,000 | 1,80,000 |
| Total |  | - | 9 X 68,000 | 6,12,000 |

2.4     NGO -  SET SCHEME

To be calculated at State  level  on the basis of NGO involved through SET Schemes.

| No. of NGO under SET Scheme | Unit cost per NGO (Rupees) | Amount (Rupees) |
| --- | --- | --- |
| 5 (YMA/MHIP) | 1,80,000 x 5 | 9,00,000.00 |

3.Stigma reduced

Objective of the communication plan will be -

- To develop effective communication vis-a-vis the target audiences and take on the task of
effectively delivering the same.

- To complement and support the detection and treatment services being provided through
the General Health Care System, making it more acceptable to the community.

- To strive to remove stigma surrounding leprosy and prevent discrimination against
leprosy affected persons.

•	To specifically cover clients, Health providers, influencers and the masses.
State/UT IEC plan will be drawn up in the Annual Plan under the following heads:

3.1          Mass media, Outdoor media, Rural media, Advocacy media

| S.No | Medium | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Mass Media (TV, Radio Press) | 9 | 9 X 39,000 | 3,51,000 |
| 2 | Outdoor Media | 9 | 9 X 23,000 | 2,07,000 |
| 3 | Rural Media | 9 | 9 X 31,000 | 2,79,000 |
| 4 | Advocacy meeting | 9 | 9 X 5000 | 45,000 |
| Total |  |  | 9 X 98,000 | 8,82,000 |

*The State Leprosy Officer will be able to distribute the total funds on the basis of actual requirements of each district keeping adequate funds at State level under Mass Media and Advocacy meetings.

4.   Development of Leprosy Expertise sustained

| S.No | Type of training | No. to be trained in the District | No. of course for 30 persons | Unit cost per course (Rs.) | Amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1 | Training of new MO | 30 | 1 | 1 x 74,500 | 74,500 |
| 2 | Refresher training of MO | - | - |  | - |
| 3 | Training to new H.S/H.W | 100 | 3 | 3 x 50,400 | 1,51,200 |
| 4 | Other training - Physiotherapist | 9 | 1 | 1 x 35,000 | 35,000 |
| 5 | Training to Lab. Tech | 9 | 1 | 1 x 35,000 | 35,000 |
| 6. | Management training to district nucleus team | 100 | 1 | 1 x 1,00,000 | 1,00,000 |
| Total |  |  |  |  | 3,95,700 |

5.	Monitoring. Supervision and Evaluation system improved

5.1        Travel cost and Review meeting

| S.No | Activity |  |  | No. unit (State/district) |  | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Travel expenses- contractual staff at State level. |  |  | >5-9 |  | 5 x 60,000 | 3,00,000 |
| 2 | Travel expenses – contractual staff at District level. |  |  | - |  | - | - |
| 3 | Review meetings |  |  | 9 |  | 9 x 50,000 | 4,50,000 |
|  | TOTAL |  |  |  |  |  | 7,50,000 |

5.2. Office operation and maintenance

This may be calculated for State/UT according to number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Office operation – State Cell |  | 1 x 75,000 | 75,000 |
| 2. | Offi`ce operation – District cell |  | 9 x 35,000 | 3,15,000 |
| 3 | Office equipment maintenance - State |  | 1 x 50,000 | 50,000 |
| Total |  |  |  | 4,40,000 |

5.3. Consumables

This may be calculated for State/UT according to number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1. 2 | State cell | 1 1 | 1,00,000 | 1,00,000 50,000 |
| 2. | District cell | 9 | 9 x 30,000 | 2,70,000 |
|  | Total |  |  | 3,70,000 |

5.4. Vehicle Hiring and POL/Maintenance

| S.No | Item | No. of districts | No. of Vehicle | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- |
| 1 | State Cell |  | 2 | 2,00,000 | 4,00,000 |
| 2 | District Cell | 9 | 1 | 1,50,000 | 13,50,000 |
|  | Total |  | 3 |  | 17,50,000 |

6.   Programme Management ensured

6.1. Contractual staff at State level - as per existing strength

| S.No | Category | No. of posts | Unit cost * per month | Cost per year (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Surveillance Medical Officer | 1 | 54,000 | 6,48,000 |
| 2 | BFO Cum Admn. Officer | 1 | 34,500 | 4,14,000 |
| 3 | Administrative Assistant | 1 | 18,400 | 2,20,000 |
| 4 | DEO | 1 | 23,000 | 2,76,000 |
| 5 | Driver | 1 | 12,650 | 1,51,800 |
| Total |  | 5 | 1,34,550 | 17,09,800 |

*The salary proposed is with 15% increment except for salary of SMO where it is proposed as per proposal of Medical Officers under National Health Mission Mizoram.

6.2. Contractual staff at District and block level

| S.No | Category | No. of posts | Unit cost * per month | Cost per year (Rupees) |
| --- | --- | --- | --- | --- |
| 1. | Driver | - | - | - |
| 2. | Contractual staff in selected states, NMS |  | - | - |
| Total |  | - | - | - |

7.     Others

7.1  Travel expenses for regular staff for specific programme/training need, awards etc.

| S.No | Activity |  |  | District |  | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Travel expenses for regular staff for specific programme/ training need, awards etc |  |  | 9 |  | 9 x 64,835 | 5,83,515 |
|  | TOTAL |  |  |  |  |  | 5,83,515 |

Grand total = Rs. 94,56,515