STATE VECTOR BORNE DISEASE CONTROL PROGRAMME, Mizoram

PIP for inclusion in NRHM for the year 2014-2015

INTRODUCTION:

The SVBDCP, Mizoram is very grateful to the Central Government for assisting the State financially and materially in the control of vector borne diseases especially Malaria. Much has been accomplished through the aid and guidance provided. Although the indigenous malaria disease incidence and death rate are declining, there still remain much to be done. Malaria still remains a major public health problem in the state. Beside indigenous Malaria, Dengue and Japanese Encephalitis posses a potential threat to the State. Dengue Control Programme was initiated during 2012-2013 and cases have been detected in the approved Sentinel Surveillance Hospital i.e Civil Hospital, Aizawl, although, no fatality case have been reported. As Culex Mosquitoes are prevalent in the state, there is also every possibility of Acute Encephalitis Syndrome / Japanese Encephalitis (JE) occurrence in the State. Lack of diagnostic kit in the State seems to be curtaining the disease prevalence as there is a recorded case of two patients succumbing to J.E in the state, which was recognised after referral to outside of the State. It is, therefore, felt the need to make and strengthen the strategies in combating the dreadful diseases and reduce the burden on health and economic development of the thousands affected by these vector borne diseases.

The Salient points on Malaria and Dengue in Mizoram are as follows:

| YEAR | MALARIA |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | ABER | SPR | Pf% | API | Death |
| 2010 | 33.74 | 4.70 | 92.42 | 15.85 | 31 |
| 2011 | 17.41 | 4.93 | 94.49 | 8.58 | 30 |
| 2012 | 14.29 | 5.87 | 95.49 | 8.38 | 25 |
| 2013 | 20.88 | 5.11 | 88.02 | 10.67 | 21 |

| YEAR | DENGUE |  |  |
| --- | --- | --- | --- |
|  | Suspected Case | Positive | Death |
| 2011 | NIL | NIL | NIL |
| 2012 | 90 | 6 | NIL |
| 2013 | 96 | 7 | NIL |

STRATEGIC PLAN FOR MALARIA CONTROL IN INDIA (2012-2017)

MISSION :

To reduce the morbidity and mortality due to malaria and improving the quality of life, thereby contributing to health and alleviation of poverty in the country.

GOALS :

- Screening all fever cases suspected for malaria (60% through quality microscopy and 40% by Rapid Diagnostic Test).

- Treating all P. falciparum cases with full course of effective ACT and primaquine and all P. vivax cases with 3 days chloroquine and 14 days primaquine.

- Equipping all Health Institutions ( PHC level and above), especially in high-risk areas, with microscopy facility and RDT for emergency use and injectable artemisinin derivatives.

- Strengthening all District and Sub-District Hospitals in malaria endemic areas as per IPHS with facilities for management of severe malaria cases.

OBJECTIVE :

To achieve by the end of 2017, an API of < 1 per 1000 Population at National Level.

OUTCOME INDICATORS :

- At least 80% of those suffering from malaria get correct, affordable, appropriate and complete treatment within 24 hours of reporting to the health system by the year 2017.

- At least 80% of those at high risk of malaria get protected by effective preventive measures such as ITN/LLIN or IRS by 2017.

- At least 10% of the population in high-risk areas is surveyed annually (Annual Blood Examination Rate >10%).

IMPACT INDICATORS :

- To bring down annual incidence of malaria to less than 1 per 1000 population at National level by 2017.

- At least 50% reduction in mortality due to malaria by the year 2017, taking 2010 level as baseline.

ACHIEVEMENTS OF MIZORAM STATE ON MALARIA CONTROL PROGRAMME

| YEAR | MALARIA |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2009 | 17.52 | 9.59 | 119 |
| 2010 | 33.74 | 15.85 | 31 |
| 2011 | 17.41 | 8.58 | 30 |
| 2012 | 14.29 | 8.38 | 25 |
| 2013 | 20.88 | 10.67 | 21 |

MIZORAM STATE GOALS AND TARGETS FOR THE 12TH FIVE YEAR PLAN :

| Year | STATE GOALS FOR THE 12TH FIVE YEAR PLAN |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012-2013 | >16.5% | < 5 | < 22 |
| 2013-2014 | >18% | < 4 | < 16 |
| 2014-2015 | >19.5% | < 3 | < 11 |
| 2015-2016 | >21% | < 2 | < 8 |
| 2016-2017 | >22.5% | < 1 | < 5 |

Considering the high incidence of Malaria in Mizoram, especially with Malaria Pf rate of over 95.09 %, the SVBDCP, Mizoram, is of the opinion that blanket coverage of DDT spray, distribution of LLINs and impregnation of bed nets in the whole state is pertinent. Example can be cited for the same on how 4 years back DDT spray was not undertaken in few areas where API was less than 2.  Consequently, it was found out that Malaria incidence increased to a great extent in the following years in those unsprayed areas.

Apart from DDT spray, it is felt that much of the Malaria cases and the few fatalities which was witnessed during 2013 could have been prevented with the distribution of LLINs and impregnation of local bed nets as majority of the inhabitants of areas with high API do not own bed nets or have impregnated bed nets. Due to non supply of K-Othrine (Deltamethrin 2.5%) for impregnation of bed nets and distribution of LLINs, it was witnessed that the API still remains very high in spite of improved IRS coverage in many endemic regions. Hence LLINs distribution and provision for impregnation of bed nets are crucial to the State and is regarded to be one of the major factors in preventing deaths due to Malaria. Provision for impregnation of bed nets is essential as majority of the population prefers to use their own bed nets which have their tailoring of choice over distributed LLINs.

After careful analysis of the State situation and performance, the yearly API target set during the 12th Five Year Plan was found not feasible and far fetched. All the while keeping the State Goals in mind, yearly revised targets set are as below:

| Year | ABER | API | MORTALITY |
| --- | --- | --- | --- |
| 2014-2015 | > 23% | < 9.5 | <18 |
| 2015-2016 | >23.5% | < 9 | < 15 |
| 2016-2017 | > 24% | < 8 | <10 |

OBJECTIVES AND TARGETS OF DENGUE CONTROL PROGRAMME:

OBJECTIVES : Following are the specific objectives of the Mid Term Plan

- To reduce the incidence of Dengue and Chikungunya and to bring down the disease burden.

- To reduce the case fatality rate due to Dengue.

TARGETS :

- Dengue cases fatality rate to below 1%.

- Functional Sentinel Surveillance Hospital in all endemic districts/towns/cities.

- Functional Rapid Diagnostic Response team in all endemic districts/towns/cities.

By the latter part of 2012, Dengue and Chikungunya Control Programme was implemented in the State. Civil Hospital, Aizawl was identified as Sentinel Surveillance Hospital for Dengue. Random Sampling was done from the OPD patients and 6 cases were found to be positive for Dengue infection in the year 2012 and & cases in the year 2013.

Due to delayed release of funds in 2012 (as well as unreleased of funds) for Dengue and Malaria in the second instalment, the State faced problems in procurement of Dengue NS1 antigen test kit. The IgM MAC ELISA test kit (96 test) received from NIV Pune was used up within a short period of time and the State could not proceed further in diagnosing Dengue during 2012-2013.

It is also felt necessary to increase the number of Sentinel Surveillance sites to have better coverage of the population at risk. Keeping in mind the high percentage of patient attendance in Private Hospitals of the State, setting up of additional Sentinel Surveillance sites at Civil Hospital, Lunglei  in the southern part of Mizoram is proposed.

STATUS OF MIZORAM FOR DENGUE IS AS FOLLOWS:

| Year | Suspected Cases | Positive Cases | Deaths |
| --- | --- | --- | --- |
| 2012 | 90 | 6 | Nil |
| 2013 | 96 | 7 | Nil |

Note – 5 cases were detected in the year 2010 from Private Hospital before programme was implemented in the State.

EXECUTIVE SUMMARY

The disease situation in Mizoram State is as follows:

| Year | Malaria Cases | Malaria Deaths | Dengue Cases | Dengue Deaths | Chikungunya Cases | AES/ JE Cases | AES/ JE Deaths | Kala-azar Cases | Kala-azar Deaths | Micro-filaria Rate % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 | 9883 | 25 | 6 | Nil | Nil | Nil | Nil | Nil | Nil | Nil |
| 2013 | 11408 | 21 | 7 | Nil | Nil | Nil | Nil | Nil | Nil | Nil |

In the State, Malaria is still a major public health problem till date. 13 cases of Dengue were identified during 2012 & 2013. In the Medical History of Mizoram, it was reported that two persons had succumbed to Japanese Encephalitis and it was known only after their blood Sample was sent outside the State for Confirmation. The actual prevalence of the disease cannot be estimated as yet.

Malaria is endemic (API>2) in 5 districts (out of 9) namely :

- Mamit District

- Kolasib District

- Lunglei District

- Lawngtlai District and

- Saiha District

The requirement for programme implementation has been indicated in detail and summary is indicated below:

| Disease | Unspent Balance as on -----January, 2014 in lakhs | Committed expenditure for 2013-14 in lakhs | Cash assistance required from NVBDCP for 2014-15 in lakhs | State resources |
| --- | --- | --- | --- | --- |
| Malaria : |  |  |  |  |
| - Domestic Budget Support | 44.19 | 184 | 642.23 |  |
| - World bank fund for project states | Nil | Nil | Nil |  |
| - GFATM for Project states | 278.83 | 382 | 413.48 |  |
| Dengue (from Domestic Budget) | 1.35 | 20 | 60.73 |  |
| Chikungunya (from Domestic Budget) | Nil | Nil |  |  |
| AES including JE (from Domestic Budget) | Nil | Nil |  |  |
| Filaria (from Domestic Budget) | Nil | Nil | Nil |  |
| Kala-azar (from Domestic Budget) | Nil | Nil | Nil |  |
| Kala-azar (World Bank Project assistance) | Nil | Nil | Nil |  |
| Total | 324.37 | 586 | 1055.71 |  |

ANNUAL ACTION PLAN/PIP 2014 – 2015

- Demographic Profile of Mizoram :

Population of the State :

| Infrastructure | Number |
| --- | --- |
| District | 9 |
| CHCs | 12 |
| PHCs | 57 |
| UHCs | 5 |
| HSCs | 370 |
| Health Clinics | 130 |
| ASHAs | 987 |
| Villages | 925 |

- Inaccessible/ Hard to reach villages :

Mizoram is a highly terrain State with many hard to reach villages and villages inaccessible by road, especially during monsoon. The following are the list of inaccessible/hard to reach villages, District-wise:-

| Sl.No | Name of District | No of hard to reach Villages |
| --- | --- | --- |
| 1 | Aizawl East | 18 |
| 2 | Aizawl West | 0 |
| 3 | Champhai | 6 |
| 4 | Kolasib | 4 |
| 5 | Lawngtlai | 35 |
| 6 | Lunglei | 34 |
| 7 | Mamit | 12 |
| 8 | Saiha | 0 |
| 9 | Serchhip | 0 |
|  | Total | 109 |

- District-wise status of Manpower (Sanctioned and Vacant):

- Regular Post :

| Sl.No | Regular Post | Required | Sanctioned | In position | Vacant |
| --- | --- | --- | --- | --- | --- |
| 1 | District Malaria Officer/ District VBD Control Officer | 9 | 0 | 9 designated as DMO | 0 |
| 2 | District Filaria Officer | 0 | 0 | 0 | 0 |
| 3 | Asst Malaria Officer/ VBD Officer | 6 | 3 | 3 | 0 |
| 4 | Medical Officer | 0 | 0 | 0 | 0 |
| 5 | Senior Malaria Inspector | 0 | 0 | 0 | 0 |
| 6 | Malaria Inspector | 10 | 10 | 10 | 0 |
| 7 | Multi Purpose Health Supervisor | 171 | 171 | 119 | 52 |
|  | Regular Post | Required | Sanctioned | In position | Vacant |
| 8 | Multi Purpose Health Asst or Multipurpose Worker | 770 | 770 | 559 | 211 |
| 9 | Lab Tech. | 67 | 67 | 62 | 5 |

- Contractual Post:-

| Sl.no | Post | In Position | Proposed | Remarks |
| --- | --- | --- | --- | --- |
| 1 | MPW regular | Nil | Nil | Financed by State or NRHM |
| 2 | MPW (Male) Contract under NVBDCP | Nil. (terminated by GoI on 1st April, 2014) | 109 | There are 109 inaccessible villages in the State. So 109 MPWs are required to be financed by GoI. |
| 3 | Laboratory Technician | 10 | 30 | 10 are financed under GFATM, Proposed additional 20 under NVBDCP,GOI |
| 4 | Consultant (District Level & State Level) | 14( 5 in State & 9 in District) | Nil | Financed by GFATM |
| 5 | Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor(MTS) | 16 | 27 | There are 27 Malaria Units in the State. Additional 11 MTS are required which are to be financed by NVBDCP |
| 6 | Project Monitor unit staff both at State and District Level | (a) SSH :- M.O.- 2 (b) State :- i. Stat. Asst – 1 ii. Sect. Asst – 2 (c) District :- Sect. Asst cum DEO – 9 | Nil | Financed by GFATM |

- Special emphasis needs to be paid to Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor. The State requires an additional 11 MTS as there are 11 Malaria Units/Blocks in the State which are not covered by MTS. These areas show higher API. Thus the proposed 11 additional posts for MTS is very crucial to boost the Malaria Programme Control in the State.

- MALARIA :

Target :  During the 12th Plan period, the proposed target is as below :

ABER > 10%, API<1 per thousand population (during 12th plan, the objective is to bring down annual incidence of malaria cases to less than 1 per 1000 population at national level by 2017 and its monitoring at district level).

The target and goals set by the State is as follows:

| Year | STATE GOALS FOR THE 12TH FIVE YEAR PLAN |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012-2013 | >16.5% | < 5 | < 22 |
| 2013-2014 | >18% | < 4 | < 16 |
| 2014-2015 | >19.5% | < 3 | < 11 |
| 2015-2016 | >21% | < 2 | < 8 |
| 2016-2017 | >22.5% | < 1 | < 5 |

After careful analysis of the State situation and performance, the yearly API target set during the 12th Five year plan was found not feasible and far fetched. All the while keeping the State Goals in mind, yearly target is set for the year 2014-2015 as below :

| Year | ABER | API | MORTALITY |
| --- | --- | --- | --- |
| 2014-2015 | > 23% | < 9.5 | <18 |

Achievement during the year 2012&2013 :

| YEAR | MALARIA |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012 | 14.29 | 8.38 | 25 |
| 2013 | 20.88 | 10.67 | 21 |

- Epidemiological Data  :

- District-wise  2012 :-

| District | Person Examined |  | Positive | Pf | No of Deaths | ABER | API | Pf% | SPR | SFR | Total BE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |  |
| Aizawl East | 19353 | 9387 | 137 | 122 | 0 | 8.27 | 0.59 | 89.05 | 0.71 | 0.63 | 19325 |
| Aizawl West | 20637 | 9008 | 219 | 196 | 9 | 13.32 | 1.41 | 89.50 | 1.06 | 0.95 | 20637 |
| Champhai | 17301 | 7331 | 96 | 82 | 1 | 6.75 | 0.37 | 85.42 | 0.55 | 0.47 | 17301 |
| Kolasib | 18547 | 8865 | 329 | 306 | 1 | 22.68 | 4.02 | 93.01 | 1.77 | 1.65 | 18547 |
| Lawngtlai | 29272 | 17865 | 5034 | 4911 | 7 | 24.05 | 41.36 | 97.56 | 17.2 | 16.78 | 29272 |
| Lunglei | 31368 | 12276 | 3042 | 2833 | 3 | 21.31 | 20.67 | 93.13 | 9.70 | 9.03 | 31368 |
| Mamit | 16584 | 5927 | 774 | 759 | 1 | 25.46 | 11.88 | 98.06 | 4.67 | 4.58 | 16584 |
| Saiha | 7966 | 3394 | 182 | 163 | 1 | 13.83 | 3.16 | 89.56 | 2.28 | 2.05 | 7966 |
| Serchhip | 7421 | 4285 | 70 | 65 | 2 | 12.28 | 1.16 | 92.86 | 0.94 | 0.88 | 7421 |
| Total / Average | 168421 | 78338 | 9883 | 9437 | 25 | 14.29 | 8.38 | 95.49 | 5.87 | 5.60 | 168421 |

- District wise 2013 :

| District | Person Examined |  | Positive | Pf | No of Deaths | ABER | API | Pf% | SPR | SFR | Total BE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |  |
| Aizawl East | 39387 | 17317 | 232 | 177 | 0 | 16.73 | 0.94 | 76.29 | 0.56 | 0.43 | 56704 |
| Aizawl West | 31504 | 13017 | 312 | 231 | 2 | 22.49 | 1.94 | 74.04 | 0.86 | 0.64 | 44521 |
| Champhai | 14331 | 9357 | 92 | 70 | 1 | 10.65 | 0.68 | 76.09 | 0.64 | 0.49 | 23688 |
| Kolasib | 18182 | 9497 | 312 | 276 | 3 | 21.96 | 3.81 | 88.46 | 1.74 | 1.54 | 27679 |
| Lawngtlai | 24580 | 19039 | 4619 | 4081 | 1 | 21.51 | 35.96 | 88.35 | 16.72 | 14.77 | 43619 |
| Lunglei | 47130 | 22544 | 3972 | 3508 | 1 | 32.66 | 26.01 | 88.32 | 7.96 | 7.03 | 69674 |
| Mamit | 19904 | 10010 | 1649 | 1574 | 8 | 28.41 | 22.28 | 95.45 | 7.84 | 7.48 | 29914 |
| Saiha | 6488 | 6173 | 488 | 368 | 2 | 20.26 | 8.47 | 75.41 | 4.18 | 3.15 | 12661 |
| Serchhip | 9721 | 5661 | 71 | 55 | 3 | 15.43 | 1.12 | 77.46 | 0.73 | 0.56 | 15382 |
| Total / Average | 211227 | 112615 | 11747 | 10340 | 21 | 20.88 | 10.67 | 88.02 | 5.11 | 4.50 | 323842 |

- District in the State categorized based on their API (2013) :

| Sl. No | Name Of District | API (Descending Order) |
| --- | --- | --- |
| 1 | Lawngtlai | 35.96 |
| 2 | Lunglei | 26.01 |
| 3 | Mamit | 22.28 |
| 4 | Saiha | 8.47 |
| 5 | Kolasib | 3.81 |
| 6 | Aizawl West | 1.94 |
| 7 | Serchhip | 1.12 |
| 8 | Aizawl East | 0.94 |
| 9 | Champhai | 0.64 |

Mizoram State falls into Category 3 :- State with more than 1 API with either all the districts with more than 1 API or few districts with less than 1 API and few with more than 1 API.

- Urban Malaria Scheme

At present, Urban Malaria Scheme(UMS) has not yet been implemented in any of the cities/ towns of the State. Lunglei town fits the criteria for implementation of UMS i.e. population of > 40,000 and API of >2.

With a population of over 50,000 and API of 6.11 in 2013, Malaria is still a major health problem in Lunglei town. Lunglei is the most populated town in the State. Decreased acceptance of IRS inspite of IEC/BCC undertakings seems to be one of the reasons behind a consistently high API in the town. Further, numerous mosquito breeding pockets due to faulty drainage system in the town and the climatic conditions experienced in the region favours the prevalence of indigenous malaria in the town.

| Name of Town | Population (2011) | API (2013) | ABER (2013) | Total Malaria Case positive |
| --- | --- | --- | --- | --- |
| Lunglei | 49,871 | 6.11 | 12.95 | 305 |

Apart from Malaria, the abundance of other vectors namely Culex and Aedes Mosquitoes in the town and peripheral bordering areas poses a serious threat of harbouring other diseases viz Dengue, Chikungunia and Japanese Encephalitis. Hence, implementing the Urban Malaria Scheme for the town is a much needed strategy for achieving the goals and target set in the 12th Five Year Plan.

(i). Proposal for Initiation of Urban Malaria Scheme for 2014-2015:

Lunglei town is proposed for UMS initiation during the year 2014-2015.

Status of Lunglei Town as on January 2014:-

| UMS Town | Populat-ion* | Town Area (Sq Kms) | Quantity of unpolluted water (Linear metres) | Quantity of Polluted water (Linear Metres) | Person examined during 2013 | Total Malaria Cases 2013 | Total number of deaths |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lunglei | 49,871 | 55 sq Kms | 1150 metres | 6000 metres | 6462 | 305 | 1 |

*Population taken from 2011 census.

(ii). Requirements for 2014-2015

- Larvicides and Pyrethrum requirements ;

| UMS town | Total Population (2011) | Larvicides Required |  |  |  | For Space Spray |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | For Polluted waters (Bacillus thuringiensis israelensis (Bti) – H-14 WP @Rs 950 per litre) |  | For Non- Polluted Waters (Temephos 50% EC @ Rs 600 per litre) |  | Pyrethrum Extract 2% @ Rs 1200/- per litre |  |
|  |  | Quantity Required (Litres) | Fund Required (Rs) | Quantity required (Litres) | Fund Required (Rs) | Quantity Required (Litres) | Fund Required (Rs) |
| Lunglei | 49,871 | 1500 | 14,25,000/- | 600 | 3,60,000/- | 300 | 3,60,000/- |
| Total fund required |  | 21,45,000/- |  |  |  |  |  |

- Estimated Fund Requirements under UMS for 2014-2015:

- For setting of UMS in Lunglei ,the proposed strategy and resources required are as follows:

- UMS will be attached to Malaria Control Programme of the District.

- Provision for recruiting a Biologist, shall be made with a monthly salary of Rs 30,000/-.

- An additional insect collector shall be attached to UMS from the District Entomological Surveillance Units (which is proposed for 2014-2015).

- Water treatment with larvicides(Temephos 50% EC and Bti H-14 WP) shall be undertaken after every 7 days (unpolluted) and 14 days (polluted) from last treatment for each water body/collection/drain. This shall be carried out for 6 months a year (during high rainfall months).

- Space spraying with Pyrethrum 2% shall be undertaken only in case of malaria outbreaks.

- Field workers shall be hired on daily wage basis for 20 days a month with a wage of Rs 300/- per day

- The Technician of State Entomological Surveillance Unit shall be attached.

Fund requirement for setting up UMS in Lunglei Town and operational expenses for the year 2014-2015 is as follows:

|  | Particulars |  | Quantity | Unit Cost (Rs) | Fund Required (per annum) |
| --- | --- | --- | --- | --- | --- |
| 1. | Human Resources |  |  |  |  |
|  | i. | Biologist | 1 | 30,000/- pm | 3,60,000/- |
|  | ii. | Field Workers | 6 | 300/- per day for 120 days | 2,16 ,000/- |
|  | iii. | Insect Collectors | 1 | - | Mentioned under Entomological Surveillance Unit |
|  | iv. | Technicians | 1 | - | Will be covered by the Technician of State Entomological Surveillance Unit |
|  | Total |  |  |  | 5,76,000/- |
| 2. | Anti-Larva Measures |  |  |  |  |
|  | i. | Temephos 50% EC | 600 Litres | 600/- | 3,60,000/- |
|  | ii. | Bti H-14WP | 1500 Litres | 950/- | 14,25,000/- |
|  | iii. | Pyrethrum Extract 2% | 100 Litres | 1400/- | 3,60,000/- |
|  | Total |  |  |  | 21,45,000/- |
| 3 | Others |  |  |  |  |
|  | i. | Training | 1 | 2,00,000/- | 2,00,000/- |
|  | ii. | Mobility and operational cost |  | 7,00,000/- | 7,00,000/- |
|  | ii. | Modification of Rooms and Store room | 1 | 6,00,000/- | 6,00,000/- |
|  | ii. | Equipments eg hand compression sprayer, protective gears etc |  | 3,00,000/- | 3,00,000/- |
|  | iii. | Contingencies |  | 5,00,000/- | 5,00,000/- |
|  | Total |  |  |  | 23,00,000/- |
| Total Estimated Fund Requirement for 2014-2015 (1+2+3) |  |  |  |  | 50,21,000/- |

The proposed timeline for setting up UMS centre in Lunglei is as follows :

- UMS Centre is proposed to be established during the 1st quarter of 2014-2015. Room shall be rented due to non availability of room in District VBDCP centre in Lunglei.

- Biologist, Fieldworkers and Insect Collectors will be recruited during the 2nd quarter of 2014-2015.

- Training shall be conducted in the 2nd quarter, within a month of recruitment.

- Field workers shall be employed for 120 days a year, with a wage of Rs 300/- per working day.

- Insect collectors proposed under Entomological Surveillance Units shall be incorporated in UMS.

- Technical supervision shall be covered by State Entomological Surveillance Unit Technician.

- Larvicides, equipments and other necessaries shall be procured during the 2nd quarter to ensure UMS will be operational by 3rd quarter of 2014-2015.

- Entomological Surveillance :

The State Entomologist, unfortunately, expired in the year 2008. Because of financial constraints, the State Entomologist post is still vacant and yet to be filled up even though candidates are available. The importance of Entomological Surveillance is very much recognized by the State for the Control of Vector Borne Diseases. For revival of the Entomological Surveillance Programme in the State, an entomologist is indispensable.

Setting up a State Entomological Surveillance Unit is proposed along with District Entomological Surveillance units to strengthen the ongoing control of vector borne diseases and will be a huge factor in achieving our goals and targets of the 12th Five Year Plan. As of present, the state does not have an Entomological Surveillance Unit.

The formulated plan for Entomological Surveillance in the State:\

- Setting up an Entomological Surveillance Unit at State level headed by State Entomologist. The State Entomologist (new post) shall be attached to State Vector Borne Disease Control Programme, Mizoram, with a monthly salary of Rs 40,000/- per month.

- District Entomological Surveillance Units which will include one Insect Collector (new post) for each District (9 Districts) and an additional Insect Collector which is to be attached to the proposed UMS of Lunglei Town.

- One Entomological Technician, shall be posted in the State Entomological Surveillance Unit with monthly salary of Rs 30,000/-.

- Entomological Surveillance shall be conducted throughout the year and necessary research carried out.

Following are the estimated requirements for the State Entomological Surveillance :

| No of Entomological Units : 10 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1. | State Entomological Surveillance Unit : 1 |  |  |  |  |
|  | 2. | District Entomological Surveillance Unit : 9 |  |  |  |  |
|  | a. | Human Resources |  | Quantity | Unit Cost (Rs) Per Month | Fund Required for a year |
|  |  | i. | State Entomologist | 1 | 40,000/- | 4,20,000/- |
|  |  | ii. | Technician | 1 | 25,000/- | 3,00,000/- |
|  |  | iii. | Insect Collectors | 10 (one for UMS) | 8,000/- | 9,60,000/- |
|  |  |  | Total |  |  | 16,80,000/- |
|  | b. | Operational cost |  |  |  |  |
|  |  | i. | Trainings for Insect Collectors |  |  | 5,00,000/- |
|  |  | ii. | Modification of Rooms |  |  | 6,00,000/- |
|  |  | iii. | Operational Research for vector prevalence in high focus(endemic) districts |  |  | 5,00,000/- |
|  |  | iv. | Hiring of Vehicles (Mobility) |  |  | 8,00,000/- |
|  |  | v. | Equipments eg Insect collecting kits, light trap, collecting jar, insect nets, light microscope, susceptibility test tubes, insecticide impregnated papers etc including office expenses |  |  | 10,00,000/- |
|  |  | vi. | Contingencies |  |  | 5,00,000/- |
|  |  | Total |  |  |  | 38,40,000/- |
|  | Grand Total |  |  |  |  | 56,04,000/- |

Proposed timeline for setting up Entomological Surveillance Units are as follows :

- Modification of rooms and recruitment of Human Resources during the 1st quarter of 2014-2015. Rooms will have to be rented as there is no space available in the SVBDCP Centre.

- Necessary training within a month of recruitment, during the 1st quarter.

- 10 insect collectors, one for each district (9 Districts) with additional one insect collector to be attached with UMS (Lunglei Town)

- Procurement of equipments and necessaries during the 2nd quarter so that Entomological Surveillance can be carried out by end of 2nd quarter 2014-2015.

F.1.1 Malaria

F.1.1.a :	Contractual Payments :

- F.1.1.a.i : Multipurpose Worker (Male) Contractual :-

- There had been 75 contractual Multipurpose Workers (Male) till 31st March 2014, in the State provided by NVBDCP, GoI with remuneration of Rs. 6000/- per month. However, these MPWs were terminated by NVBDCP from 1st April, 2014.

- Of the total 921 villages in the State, 109 are classified as hard to reach village especially during monsoon. These MPWs are posted in the hard to reach villages, which do not have sub-centre or are far from nearest medical facility centre.

- Malaria incidence is high and case fatality is higher among the inhabitants of these villages. Hence MPWs(Male) are indispensible and plays an important field role in the control of Malaria deaths and economic loss through early diagnosis and prompt treatment. 34 villages of the state still needs to be covered.

- With the current remuneration of Rs 6000/-, it is very difficult to acquire and retain a committed worker. It is therefore proposed that remuneration be increased to Rs 8100/- per month i.e by 35%. After their induction in SVBDCP, Mizoram in 2010, the mortality cases was reduced by 73.95% in 2010 (39 deaths) as compared to 2009 (119 deaths). This reflects their importance to the State.

Current MPWs(Male) and their place of posting are as below:

| Sl,no | District | No of MPWs | No of hard to reach Villages | Additional MPWs Required | SC with API >2 | Funds Required |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Aizawl East | 3 | 18 | 3 | 1 | 5,83,200/- |
| 2. | Aizawl West | 5 | 0 | 0 | 2 | 4,86,000/- |
| 3. | Champhai | 6 | 6 | 0 | Nil | 5,83,200/- |
| 4. | Kolasib | 12 | 4 | 0 | 13 | 11,66,400/- |
| 5. | Lawngtlai | 10 | 35 | 14 | 29 | 23,32,800/- |
| 6. | Lunglei | 12 | 34 | 17 | 81 | 28,18,800/- |
| 7. | Mamit | 12 | 12 | 0 | 21 | 11,66,400/- |
| 8. | Saiha | 5 | 0 | 0 | 14 | 4,86,000/- |
| 9. | Serchhip | 10 | 0 | 0 | Nil | 9,72,000/- |
| Total |  | 75 | 109 | 34 | 161 | 105,94,800/- |

With respect to the above situation, the state would require an additional 34 MPWs(Male) to cover all the inaccessible villages of the State, to have the effective work force required to reach our goals and targets of achieving API of less than 1 per 1000. Since API is highest among the Districts with more hard to reach villages priority be given to these villages in. Since they are indispensible to the State, in the interest of the public, reconsideration of financial support is necessary.

- F.1.1.a.ii :	Lab Technicians :- 						NIL

- F.1.1.a.iii :	VBD Technical Supervisor :-				NIL

- F.1.1.a.iv :	District VBD Consultant :-					NIL

- F.1.1.a.v :	State Consultant (non-project States), :-			NIL

M&E Consultant,

VBD Consultant.(preferably Entomologist )		NIL

F.1.1.b :	ASHA Incentives :-

    - ASHAs play a vital role in prompt diagnosis and treatment of malaria cases. Although they are ‘passive’ workers, due to the cultural practices, they function as ‘active’ workers on many occasions. Their contribution to Annual Blood Slide Examination/ RDT is huge and amounts to over 30% in some districts.

The approximate fund requirements for ASHA incentives are as follows:

| Sl no | Activity | Rate | No of ASHAs | Amount | Funds Required |
| --- | --- | --- | --- | --- | --- |
| 1 | Total blood examined during 2013 (50% of total blood examined in the State ) | 15/- | 987 | 114909 | 17,23,635/- |
| 2 | Total number of malaria positive case (30% of total malaria positive case in the State) | 75/- | 987 | 3524 | 2,64,300/- |
| 3 | Total number of Cases Referred (15% of all Malaria pf Cases) | 300/- | 987 | 1551 | 4,65,300/- |
| 4 | Contingencies |  |  |  | 2,00,000/- |
| Total Fund required under DBS for ASHA Incentives |  |  |  |  | 26,53,235/- |

Note :- ASHAs contribution is calculated and recommended to be above 30%.
Due to continuous training of ASHAs, the total number of blood examination performed by ASHAs is expected to increase in the following years.
Data taken from 2013

Note - Incentives for distribution of LLINs @ Rs 10/- per bed net is funded under GFATM

F.1.1.c :	Operational Cost :

- F.1.1.c.i : Spray Wages :-

- The State currently employs 334 Spray men. As blanket coverage of DDT spray throughout the State is favoured, an additional 16 spray men is proposed. Considering price hike of essential commodities, decreased compliance and acceptance on DDT usage and the risk spray men are exposed to, an increase in spray wage to Rs 250/- per working day (minimum unskilled labour wage of state) from the existing wage of Rs 170 per working day is proposed as a necessity to attract committed and effective spray men.

- A total of 120 days of spray undertaking which is divided into 2 rounds, March & April consist the first round and June & July the second round will be carried out.

| Sl no | No of spray men | No of spraying days | Spray wage per day | Total fund required |
| --- | --- | --- | --- | --- |
| Round 1 | 350 | 60 | 250 | 5250000/- |
| Round 2 | 350 | 60 | 250 | 5250000/- |
| Total |  | 120 |  | 105,00,000/- |

- F.1.1.c.ii : Operational cost for IRS :-

- New Hand Compression Pumps (HC Pumps) with pressure gauze:

After detailed study on low IRS acceptance, the major factor for low acceptance of IRS in Urban and Semi-urban areas was primarily related to the spray quality. Families who are economically more privileged have their walls painted. Those homes do not accept IRS due to the fact that DDT spraying leaves much streaking on the painted walls and thus spoils their interior decoration. Inadequate experience in application of spraying technique by the spray team is an added factor to the streaking of walls apart from the shortcomings of our current HC pumps. The reasons are as follows :

- The current HC Pumps used for DDT spraying do not have an inbuilt pressure gauze. Although spray teams are taught to frequently measure the discharge rate from nozzle, it is impractical to constantly measure the pressure from discharge rate as much homes needs to be covered. Thus the prescribed pressure is often neglected. This results in DDT sprayed to be in excess of how much the wall could adsorb which then leads to trickling of DDT suspensions and thus streaking the walls. Thus the pressure needs to be constantly monitored so that the right amount of DDT suspension is released per second to prevent excess or inadequate discharge rate. As frequent manual measurement of pressure is burdensome, not accurate enough and not very practical in the actual field, HC pumps with inbuilt pressure gauge is needed to improve the spray quality.

- When the correct distance for spraying is not maintained in addition to the correct amount of time used for one swipe, which is usually due to lack of sufficient training days for spray men so that by experience and practise, they master the correct distance and duration to be maintained, overlapping of DDT spray occurs which results in DDT suspension to trickle and thus streaking the walls.

With regards to these factors, a HC pumps with inbuilt pressure gauge is needed so as to minimise the streaking of walls. There is no other realistic alternative but to improve the spray quality by minimising streaking of DDT spray if we want to improve the IRS acceptance in the urban and semi-urban areas. Improving IEC/BCC for these areas will not improve the IRS acceptance if emphasis on spray quality is not made. This issue is prominent in the urban and sub-urban areas. Earlier strategies were focussed on spray coverage while spray quality was not given much priority. Since the importance of spray quality has been recognized, focus needs to be shifted to improving spray quality which will eventually improve the IRS acceptance. So, the Backpack Sprayer with pressure gauge will initially be used for urban and semi-urban areas. IEC/BCC undertakings can still improve IRS in the rural areas.

Hence, the requirement for procurement of Backpack Sprayers with pressure gauge (HC pumps) is as follows :

| Sl.No | Particulars | Amount | Rate (Rs) | Total fund required |
| --- | --- | --- | --- | --- |
| 1 | New Backpack Sprayers with Pressure Gauge (HC Pumps) | 120 | 11,000/- | 13,20,000/- |

- Spray parts and repair cost :

As mentioned earlier on the importance of spray quality, sufficient spare parts needs to be available to the spray team so as not to compromise on the spray quality and thus reducing the IRS acceptance. This is very crucial as one poor spray quality due to insufficiency of spare parts e.g. faulty nozzles, can lead to non acceptance of IRS by many in the sensitive urban and semi-urban areas. This leads to non-acceptance of IRS in the subsequent years. Thus, each spray team should have sufficient spare parts as they have to travel to remote villages.

Moreover, repairing of HC pumps is constantly required and must be done as soon as possible each time to minimise the delay in IRS coverage as per plan.  This delay should be kept at minimum because the number of HC pump is limited and a halt in their work would be a big problem in each field of planning involving IRS operation. Some defects cannot be repaired by the spray team and requires the help of a mechanics. Hence, the repair mechanic must be well equipped with sufficient spare parts and transportation be provided for repair works during ongoing spraying in remote and hard to reach villages. The fund required for procurement of spare parts and  TA/DA of mechanics for repairs of HC pumps are as follows :

| Sl No | Particulars | Approximate fund required (Rs) |
| --- | --- | --- |
| 1 | Purchase of Spare parts | 5,00,000/- |
| 2 | TA/DA for HC Pump repairs | 4,00,000/- |
| Total Fund required |  | 9,00,000/- |

- Distribution of DDT within the state :

Each District requirement of fund for vehicle hiring for DDT dropping differs according to the terrain, road conditions and distance to be covered. The requirements for DDT dropping are as follows:

| Sl.No | District | No of Villages | No of Sub Centres/Clinics | Fund required for DDT dropping (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 116 | 55 | 1,70,000/- |
| 2 | Aizawl West | 93 | 40 | 1,70,000/- |
| 3 | Champhai | 102 | 59 | 2,00,000/- |
| 4 | Lunglei | 185 | 71 | 2,50,000/- |
| 5 | Lawngtlai | 181 | 37 | 2,00,000/- |
| 6 | Kolasib | 48 | 28 | 1,00,000/- |
| 7 | Mamit | 74 | 30 | 1,80,000/- |
| 8 | Saiha | 81 | 24 | 1,80,000/- |
| 9 | Serchhip | 41 | 26 | 1,00,000/- |
| 10 | State to District HQ | 9 District HQ |  | 5,00,000/- |
| Total fund required for DDT dropping for 2014-2015 |  |  |  | 20,50,000/- |

- Transportation of spray teams :

Transportation of Spray teams to their spraying destination is necessary and must be aided from the SVBDCP. As the spray wages are less, the spray team cannot be expected to hire their own vehicle. The State government cannot provide vehicles for the transportation of Spray Men hence fund allocations need to be made as some of the villages are very far from towns/PHCs with no daily vehicle services. In some areas, boats have to be hired to reach the villages. Transportation problems faced by the spray men are the biggest reason why attrition rate is very high, almost above 95%. This necessitate the recruitment of previously inexperienced persons as spray men each year, and thus progress cannot be made regarding improvement in spray quality which eventually lowers the IRS acceptance inspite of much progress in IEC/BCC components.

Hence, to retain a dedicated and experienced spray men, apart from increase in their daily wages, their transportation needs to be provided to minimise their expenditure. The morale of spray men would definitively be boosted resulting in attrition rate to fall, which will eventually leads to improved IRS acceptance via improved spray quality.

The transportation cost for spray team differs with Districts in relation to number of villages, conditions of roads and distance needed to be covered. The fund required for transportation of spray teams are :

| Sl.No | District | No of Villages | No of Sub Centres/Clinics | Fund required for transportation of spray teams (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 116 | 55 | 2,00,000/- |
| 2 | Aizawl West | 93 | 40 | 1,80,000/- |
| 3 | Champhai | 102 | 59 | 2,00,000/- |
| 4 | Lunglei | 185 | 71 | 2,70,000/- |
| 5 | Lawngtlai | 181 | 37 | 3,25,000/- |
| 6 | Kolasib | 48 | 28 | 1,50,000/- |
| 7 | Mamit | 74 | 30 | 2,00,000/- |
| 8 | Saiha | 81 | 24 | 2,40,000/- |
| 9 | Serchhip | 41 | 26 | 1,20,000/- |
| Total fund required for transportation of Spray Teams for 2014-2015 |  |  |  | 18,85,000/- |

- Equipments including personal protections :

The equipments required by the spray teams are :

| Sl no | Item | Quantity | Cost (Rs) | Fund required (Rs) |
| --- | --- | --- | --- | --- |
| 1. | Buckets with measurements | 1000 | 250/- | 2,50,000/- |
| 2. | Mugs with measurements | 1000 | 75 | 75,000/- |
| 3. | Long sleeve Rubber gloves | 700 | 250/- | 1,75,000/- |
| 4. | Face Masks | 1000 | 100 | 1,00,000/- |
| 5. | Towels | 1000 | 150 | 15,00,000/- |
| 6. | Soaps | 20000 | 10 | 2,00,000/- |
| 7. | Filtering cloth | 3000 | 50 | 1,50,000 |
| 8 | Goggles | 400 | 350 | 1,40,000/- |
| 9 | Pens | 1000 | 5 | 5000 |
| 10 | Printed Spray reporting book | 1500 | 35 | 52,500 |
| 11 | Plastic DDT carrying bags | 800 | 30 | 24,000/- |
| 12 | Miscellaneous |  |  | 2,00,000/- |
| Total Fund required for IRS equipments for 2014-2015 |  |  |  | 15,21,500/- |

Total operational cost for IRS :

| Sl No | Particulars | Fund required (Rs) |
| --- | --- | --- |
| 1 | Backpack sprayer (HC Pumps) with pressure gauge | 13,20,000/- |
| 2 | Spray Parts and repair cost | 9,00,000/- |
| 3 | DDT dropping | 20,50,000/- |
| 4 | Transportation of Spray Teams | 18,85,000/- |
| 5 | Equipments including personal protection | 15,21,500/- |
| 6 | Miscellaneous | 4,00,000/- |
| Total fund required for Operational IRS for 2014-2015 |  | 80,76,500/- |

- F.1.1.c.iii :- Impregnation of bed nets for North East Sates :

    - As unavailability of Deltamethrin 2.5% for impregnation of bed nets of the inhabitants of highly malaria endemic areas is one of the major contributors to the high Malaria cases and fatalities, it is, therefore, of utmost importance to address this problem. Supply of Deltamethrin 2.5% for impregnation of bed nets cannot be neglected again.

    - The State does not have Entomological Surveillance Unit. Although DDT resistance have not been officially declared, recent incidence of high API in regions with good coverage of IRS suggests the need for research into the effectiveness of DDT.

    - The total bed nets to be impregnated are estimated at 250000 nos. The acceptance of using impregnated bed nets is higher than DDT spraying or LLINs. This can be attributed to personal preference for own design, size and colour of bed nets.

    - Estimated requirement for impregnation of bed nets is as follows :

| Sl no | Activities | Quantity | Rate (Rs) | Fund required |
| --- | --- | --- | --- | --- |
| 1 | Incentives for impregnation of bed nets by NGOs/FBOs | 2,50,000 Bed Nets | 10/- per net | 25,00,000/- |
| 2 | Deltamethrin 2.5% | 2500 litres* | 1800/- per Litre | 45,00,000/- |
| Total Fund required for impregnation of bed nets |  |  |  | 70,00,000/- |

*The estimated requirement of 10ml Deltamethrine 2.5% per single sized bed net is made.

F.1.1.d :	Monitoring, Evaluation & Supervision & Epidemic Preparedness including mobility & NAMMIS and MPW monitoring incentives.

- Monitoring, Evaluation & Supervision :-

Funds required for Monitoring, Evaluation, Supervision and Epidemic Preparedness including mobility and NAMMIS under DBS are as follows :

| Sl no | Post | No of post | No of days for Field visits per month | Approximate cost per day including TA/DA (Rs) | Fund Required (Yearly) |
| --- | --- | --- | --- | --- | --- |
| 1 | SPO | 1 | 2 | 5000/- | 1,20,000/- |
| 2 | Dy Director(Malaria) | 1 | 2 | 5000/- | 1,20,000/- |
| 3 | DMOs/CMOs | 9 | 2 | 3000/- | 6,48,000/- |
| 4 | M&E Consultant | 1 | 6 | 4,500/- | 3,24,000/- |
| 5 | State Public Health Consultant | 1 | 6 | 4,500/- | 3,24,000/- |
| 6 | IEC/BCC Consultant | 1 | 6 | 4,500/- | 3,24,000/- |
| 7 | Finance Consultant | 1 | 6 | 4,500/- | 3,24,000/- |
| 8 | PSCM Consultant | 1 | 6 | 4,500/- | 3,24,000/- |
| 9 | NAMMIS | 1 | 3 | 4,500/- | 1,62,000/- |
| 10 | Printing of reports etc |  |  |  | 25,00,000/- |
| 11 | Epidemic Preparedness including Rapid Response Team |  |  |  | 2,00,000/- |
| Total |  |  |  |  | 53,70,000/- |

F.1.1.e :	IEC/BCC :-

- As evident from the last few years, progress in IEC/BCC is largely reflected in the State Malaria Control Programme progress. The IEC/BCC activities undertaken have huge impact in the State especially in the urban and sub-urban areas. However much greater effort needs to be put into the sub-urban and rural areas where API continues to be very high. Remembering that IEC/BCC is a continual process, giving more efforts in the regions with high API and at the same time, continuing the activities in the improved areas is the strategy the State plans to adopt.

- Upon scrutiny, it was realised that the goal of the 12th five year plan of attaining an API of less than 1 per 1000 population largely depends on IEC/BCC progress factor. Hence, utmost importance needs to be given to this Sector in Malaria Control Programme.

- Many new activities are proposed for the 2014 -2015. These activities were not possible in the previous years due to shortage of Human Resources in the IEC/BCC sector. One of the biggest factors hampering the progress of the Programme for Control of Malaria seems to be lack of awareness and low living conditions of the inhabitants of endemic region. Hence, much IEC/BCC activities need to be undertaken.

- Here are the list of activities proposed for the year 2014-2015 along with financial requirements:

| Sl no | Activities | Proposed number of Activities to be undertaken | Rate (Rs) | Fund required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Awareness Campaign to NGOs | 150 | 2500/- | 3,75,000/- |
| 2 | Banner Hoardings | 160 (one each for SC with API > 2) | 5,000/- | 8,00,000/- |
| 3 | Quiz Competition | 9 (one for each district) | 80,000/- | 7,20,000/- |
| 4 | Awareness at Sports Competition | 15 (3 for each district with API >2) | 4000/- | 60,000/- |
| 5 | Advocacy with NGOs/FBOs | 5 | 2500/- | 12,500/- |
| 6 | Speech deliveries to Churches | 20 | 1500/- | 30,000/- |
| 7 | Workshop on Sensitization of Health Staffs | 9 (One for each District) | 4000/- | 36,000/- |
| 8 | Campaign cum Mass Blood testing | 4 (for Endemic regions with API > 20) | 10000/- | 40,000/- |
| 9 | Radio talk/ jingle | 5 (one for each district with API >2) | 2500/- | 12,500/- |
| 10 | TV Scroll Advertisement | For 6 months in two major channels of the State | 15500/- per month per channel | 1,86,000/- |
| 11 | TV Spot Advertisements | For 6 months in local channels in highly endemic regions | 20,000/- per month | 6,00,000/- |
| 12 | Malaria Clinics | 4 clinics during high transmission period in areas with API > 10 | 20,000/- | 80,000/- |
| 13 | Projector awareness | 3 shows each in the 5 endemic districts | 10000/- | 1,50,000/- |
| 14 | Organizing local sports competition in high endemic areas | 5 (one for each malaria endemic district) | 50,000/- | 2,50,000/- |
| 15 | Organizing Essay competitions | 2 competitions for each endemic district with 1 for school | 25,000/- | 2,50,000/- |
| 16 | Organizing short video clip competition | Twice for the whole state | 50,000/- | 1,00,000/- |
| 17 | Sponsorship of Local TV shows | Sponsorship deal with 3 Major Local TV shows | 2,00,000/- | 6,00,000/- |
| Total Fund Required under IEC/BCC for 2014-2015 |  |  |  | 43,02,000/- |

F.1.1.f :	PPP/NGO and Inter-sectoral Convergence :-

- Community participation and inter-sectoral coordination is essential for the success of any Health Programme. It is indeed the effective approach of Primary Health Care. NGOs in Mizoram are particularly very influential on the public. As majority of the population are Christians, private partnership with Church Based Organizations is a must to boost the Malaria Control Programme in the State.

- For the convenience of administration, monitoring and supervision, the Church Based Organizations can be divided into 2 zones.

- Northern Zone : Covering 6 districts viz Champhai, Serchhip, Aizawl East, Aizawl West, Mamit and Kolasib.

- Southern Zone : Covering 3 districts viz Lunglei, Lawngtlai and Saiha.

- Apart from the Church Based Organizations, YMA (Young Mizo Association), the largest NGO in the State which literally includes approximately more than 98%  of the age group of 14 years and above of the whole population in the State. Central YMA governs the branch YMAs which spans every village of Mizoram. It is a social organization and partnering with it is a must to improve the awareness, health education and reduction of breeding grounds of mosquitoes in and around the human habitats. It would be a huge mistake to neglect the NGOs, particularly the YMA in our strive to control Malaria and allied.

The PPP with Church Based Organization and YMA will include :

- Sanitation drive and Environmental management

- Awareness Campaign

- Provision of Outreach Services

- Provision and Promotion of insecticides treated bed nets and treatment of community owned bed nets

- Health Education with the objective of individuals to be self-reliant in matters of health.

With regards to the above mentioned proposed PPP with CBOs and NGOs, the funding required is as follows,

| Sl No | Public Private Partnership | Estimated fund required (Rs) | Activities to be performed |
| --- | --- | --- | --- |
| 1 | Church Based Organization, - Northern Zone - Southern Zone | 10,00,000/- 7,00,000/- | - Sanitation Drive and Environment Management - Awareness Campaign - Provision of Outreach Services - Provision and Promotion of impregnated Bed nets - Health Education and Promotion |
| 2 | Young Mizo Association | 20,00,000/- |  |
| Total Funds Required |  | 37,00,000/- |  |

Necessary steps shall be undertaken as per financial allocation.

F.1.1.g :	Training /Capacity Building :

- Training, re-training and sensitization of staffs on the latest strategy and approach adopted by the Central and State needs to be done at regular interval to ensure correct implementations of guidelines.

- Proposed Training list for 2014-2015 under DBS includes :

- Malaria Inspectors

- Spray men and IRS related staffs

- Multipurpose workers

- Health Supervisors

Estimated Funds to be required for training/capacity building is as follows:

| Sl. No | Post | Number of trainees | No of training days | Average TA + DA | Proposed month for training | Training venues rent and resource Persons | Funds Required |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Malaria Inspectors | 8 | 4 | 4000 + 1600 | March | 4x(5000 + 2000) | 83,300/- |
| 2 | Spray men and IRS related staffs | 350 | 1 | 500 + 200 | February | 9x( 4000 + 2000) | 4,91,500/- |
| 3 | Health Supervisors | 152 | 1 | 4000 + 400 | November | 10000 + 2000 | 7,65,500/- |
| 4 | Multipurpose Workers | 584 | 1 | 500 + 400 | May | 9x(4000 + 2000) | 9,00,800/- |
| 5 | Training of trainers | 9x4 (9 districts x 4 representatives from each district) | 2 | 5000 + 700 | 10 days prior to district training | 2x(8000 + 2000) | 4,72,200/- |
| 6 | Contingencies |  |  |  |  |  | 4,00,000/- |
| Total Fund Required for 2014-2015 |  |  |  |  |  |  | 31,13,300/- |

- Cost of Lunch @ Rs 200/- per participants per day.

- Incidental expenditure, photocopying, stationeries, job aids, LCD etc @ Rs 250/- per participants per day

F.1.1.h :	Zonal Entomological Unit :-

Entomological Surveillance :

The State Entomologist, unfortunately, expired in the year 2008. Because of financial constraints, the State Entomologist post is still vacant and yet to be filled up even though candidates are available. The importance of Entomological Surveillance is very much recognized by the State for the Control of Vector Borne Diseases. For revival of the Entomological Surveillance Programme in the State, an entomologist is indispensable.

Setting up a State Entomological Surveillance Unit is proposed along with District Entomological Surveillance units to strengthen the ongoing control of vector borne diseases and will be a huge factor in achieving our goals and targets of the 12th Five Year Plan. As of present, the state does not have an Entomological Surveillance Unit.

The formulated plan for Entomological Surveillance in the State:

- Setting up an Entomological Surveillance Unit at State level headed by State Entomologist. The State Entomologist (new post) shall be attached to State Vector Borne Disease Control Programme, Mizoram, with a monthly salary of Rs 40,000/- per month.

- District Entomological Surveillance Units which will include one Insect Collector (new post) for each District (9 Districts) and an additional Insect Collector which is to be attached to the proposed UMS of Lunglei Town.

- One Entomological Technician, shall be posted in the State Entomological Surveillance Unit with monthly salary of Rs 25,000/-.

- Entomological Surveillance shall be conducted throughout the year and necessary research carried out.

Following are the estimated requirements for the State Entomological Surveillance :

| No of Entomological Units : 10 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1. | State Entomological Surveillance Unit : 1 |  |  |  |  |
|  | 2. | District Entomological Surveillance Unit : 9 |  |  |  |  |
|  | a. | Human Resources |  | Quantity | Unit Cost (Rs) Per Month | Fund Required for a year |
|  |  | i. | State Entomologist | 1 | 40,000/- | 4,20,000/- |
|  |  | ii. | Technician | 1 | 25,000/- | 3,00,000/- |
|  |  | iii. | Insect Collectors | 10 (including one for UMS) | 8,000/- | 9,60,000/- |
|  |  |  | Total |  |  | 16,80,000/- |
|  | b. | Operational cost |  |  |  |  |
|  |  | i. | Trainings for Insect Collectors |  |  | 5,00,000/- |
|  |  | ii. | Modification of Rooms |  |  | 6,00,000/- |
|  |  | iii. | Operational Research for vector prevalence in high focus(endemic) districts |  |  | 5,00,000/- |
|  |  | iv. | Hiring of Vehicles (Mobility) |  |  | 8,00,000/- |
|  |  | v. | Equipments eg Insect collecting kits, light trap, collecting jar, insect nets, light microscope, susceptibility test tubes, insecticide impregnated papers etc including office expenses |  |  | 10,00,000/- |
|  |  | vi. | Contingencies |  |  | 5,00,000/- |
|  |  | Total |  |  |  | 38,40,000/- |
|  | Grand Total (a+b) |  |  |  |  | 56,04,000/- |

Proposed timeline for setting up Entomological Surveillance Units are as follows :

- Modification of rooms and recruitment of Human Resources during the 1st quarter of 2014-2015. Rooms will have to be rented as there is no space available in the SVBDCP Centre.

- Necessary training within a month of recruitment, during the 1st quarter.

- 10 insect collectors, one for each district (9 Districts) with additional one insect collector to be attached with UMS (Lunglei Town)

- Procurement of equipments and other necessities during the 2nd quarter so that Entomological Surveillance can be carried out by end of 2nd quarter 2014-2015.

F.1.1.i :	Biological and Environment Management through VHSC :-

- As blanket coverage of the whole State under IRS, LLINs and impregnated bed nets is preferred, Biological and Environmental Management may not be considered as separate undertaking. Nonetheless, under Public Private Partnership with NGO particularly, YMA, involving and sensitizing the community on the importance of biological and environmental management is intended.

F.1.1.j : 	Larvivorous Fish Support :-

- Although habitats closer to the rivers and other water bodies shows higher API in the State, usage of additional Larvivorous Fish Support would be very helpful in reduction of Malaria Cases. But for the moment, utilization and implementation of Larvivorous Fish Support is not yet considered for inclusion in the Mizoram State Vector Borne Disease Control Strategy.

F.1.1.k :	Construction and Maintenance of hatcheries : -

- As mentioned above, construction and maintenance of hatcheries may be considered later and is not included in the current Malaria Control Programme Strategy adopted by the State.

F.1.1.l :	Any Others :-

- F.1.1.l.a : Urban Malaria Scheme :-

At present, Urban Malaria Scheme(UMS) has not yet been implemented in any of the cities/ towns of the State. Lunglei town fits the criteria for implementation of UMS i.e. population of > 40,000 and API of >2.

With a population of over 50,000 and API of 6.11 in 2013, Malaria is still a major health problem in Lunglei town. Lunglei is the most populated town in the State. Decreased acceptance of IRS inspite of IEC/BCC undertakings seems to be one of the reasons behind a consistently high API in the town. Further, numerous mosquito breeding pockets due to faulty drainage system in the town and the climatic conditions experienced in the region favours the prevalence of indigenous malaria in the town.

| Name of Town | Population (2011) | API (2013) | ABER (2013) | Total Malaria Case positive |
| --- | --- | --- | --- | --- |
| Lunglei | 49,871 | 6.11 | 12.95 | 305 |

Apart from Malaria, the abundance of other vectors (Culex and Aedes Mosquitoes) in the town and peripheral bordering areas poses a serious threat of harbouring other diseases viz Dengue, Chikungunia and Japanese Encephalitis. Hence the need of implementing the Urban Malaria Scheme for the town is a much needed strategy for achieving the goals and target set in the 12th Five Year Plan.

(i). Proposal for Initiation of Urban Malaria Scheme for 2014-2015:

Lunglei town is proposed for UMS initiation during the year 2014-2015.

Status of Lunglei Town as on January 2014:-

| UMS Town | Populat-ion* | Town Area (Sq Kms) | Quantity of unpolluted water (Linear metres) | Quantity of Polluted water (Linear Metres) | Person examined during 2013 | Total Malaria Cases 2013 | Total number of deaths |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lunglei | 49,871 | 55 sq Kms | 1150 metres | 6000 metres | 6462 | 305 | 1 |

*Population taken from 2011 census.

(ii). Requirements for 2014-2015

- Larvicides and Pyrethrum requirements ;

| UMS town | Total Population (2011) | Larvicides Required |  |  |  | For Space Spray |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | For Polluted waters (Bacillus thuringiensis israelensis (Bti) – H-14 WP @Rs 950 per litre) |  | For Non- Polluted Waters (Temephos 50% EC @ Rs 600 per litre) |  | Pyrethrum Extract 2% @ Rs 1200/- per litre |  |
|  |  | Quantity Required (Litres) | Fund Required (Rs) | Quantity required (Litres) | Fund Required (Rs) | Quantity Required (Litres) | Fund Required (Rs) |
| Lunglei | 49,871 | 1500 | 14,25,000/- | 600 | 3,60,000/- | 300 | 3,60,000/- |
| Total fund required |  | 21,45,000/- |  |  |  |  |  |

- Estimated Fund Requirements under UMS for 2014-2015:

- For setting up UMS in Lunglei ,the proposed strategy and resources required are as follows:

- UMS will be attached to District Malaria Control Programme.

- Provision for recruiting a Biologist, shall be made with a monthly salary of Rs 30,000/-.

- An additional insect collector shall be attached to UMS from District Entomological Surveillance Units (which is proposed for 2014-2015).

- Water treatment with larvicides(Temephos 50% EC and Bti -14 WP) shall be undertaken after every 7 days (polluted) and 14 days (unpolluted) from last treatment for each water body/collection/drain. This shall be carried out for 6 months a year (during high rainfall months).

- Space spraying with Pyrethrum 2% shall be undertaken only in case of malaria outbreaks.

- Field workers shall be hired on daily wage basis for 20 days a month with a wage of Rs 300/- per day

- The Technician of State Entomological Surveillance Unit shall be attached.

Fund requirement for setting up UMS in Lunglei Town and operational expenses for the year 2014-2015 is as follows:

|  | Particulars |  | Quantity | Unit Cost (Rs) | Fund Required (per annum) |
| --- | --- | --- | --- | --- | --- |
| 1. | Human Resources |  |  |  |  |
|  | i. | Biologist | 1 | 30,000/- pm | 3,60,000/- |
|  | ii. | Field Workers | 6 | 300/- per day for 120 days | 2,16 ,000/- |
|  | iii. | Insect Collectors | 1 | - | Mentioned under Entomological Surveillance Unit |
|  | iv. | Technicians | 1 | - | Will be covered by the Technician of State Entomological Surveillance Unit |
|  | Total |  |  |  | 5,76,000/- |
| 2. | Anti-Larva Measures |  |  |  |  |
|  | i. | Temephos 50% EC | 600 Litres | 600/- | 3,60,000/- |
|  | ii. | Bti H-14WP | 1500 Litres | 950/- | 14,25,000/- |
|  | iii. | Pyrethrum Extract 2% | 100 Litres | 1400/- | 3,60,000/- |
|  | Total |  |  |  | 21,45,000/- |
| 3 | Others |  |  |  |  |
|  | i. | Training | 1 | 2,00,000/- | 2,00,000/- |
|  | ii. | Mobility and operational cost |  | 7,00,000/- | 7,00,000/- |
|  | ii. | Modification of Rooms and Store room | 1 | 6,00,000/- | 6,00,000/- |
|  | ii. | Equipments eg hand compression sprayer, protective gears etc |  | 3,00,000/- | 3,00,000/- |
|  | iii. | Contingencies |  | 5,00,000/- | 5,00,000/- |
|  | Total |  |  |  | 23,00,000/- |
| Total Estimated Fund Requirement for 2014-2015 |  |  |  |  | 50,21,000/- |

The proposed timeline for setting up UMS centre in Lunglei is as follows :

- UMS Centre is proposed to be established during the 1st quarter of 2014-2015. Room shall be rented due to non availability of room in District VBDCP centre in Lunglei.

- Biologist, Fieldworkers and Insect Collectors will be recruited during the 2nd quarter of 2014-2015.

- Training shall be conducted in the 2nd quarter, within a month of recruitment.

- Field workers shall be employed for 120 days a year, with a wage of Rs 300/- per working day.

- Insect collectors proposed under Entomological Surveillance Units shall be incorporated in UMS.

- Technical supervision shall be covered by State Entomological Surveillance Unit Technician.

- Larvicides, equipments and other necessaries shall be procured during the 2nd quarter to ensure UMS will be operational by 3rd quarter of 2014-2015.

- Dengue and Chikungunya

- Disease Situation : The disease situation in the State, District-wise for 2012 and 2013.

- 2012 (October - December)

| Sl. No. | Name of district/ Corporation | Dengue |  |  |  | Chikungunya |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Suspected cases | Blood samples tested | Positive cases | Deaths | Suspected cases | Blood samples tested | Positive cases |  |
| 1 | Aizawl East | 23 | 23 | 3 | Nil | Nil | Nil | Nil |  |
| 2 | Aizawl West | 40 | 40 | 2 | Nil | Nil | Nil | Nil |  |
| 3 | Champhai | 9 | 9 | 1 | Nil | Nil | Nil | Nil |  |
| 4 | Kolasib | 3 | 3 | 0 | Nil | Nil | Nil | Nil |  |
| 5 | Mamit | 8 | 8 | 0 | Nil | Nil | Nil | Nil |  |
| 6 | Lawngtlai | 0 | 0 | 0 | Nil | Nil | Nil | Nil |  |
| 7 | Lunglei | 4 | 4 | 0 | Nil | Nil | Nil | Nil |  |
| 8 | Saiha | 0 | 0 | 0 | Nil | Nil | Nil | Nil |  |
| 9 | Serchhip | 3 | 3 | 0 | Nil | Nil | Nil | Nil |  |
|  | Total | 90 | 90 | 6 | 0 | 0 | 0 | 0 |  |

- 2013

| Sl. No. | Name of district/ Corporation | Dengue |  |  |  | Chikungunya |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Suspected cases | Blood samples tested | Positive cases | Deaths | Suspected cases | Blood samples tested | Positive cases |  |
| 1 | Aizawl East | 30 | 30 | 1 | Nil | Nil | Nil | Nil |  |
| 2 | Aizawl West | 25 | 25 | 1 | Nil | Nil | Nil | Nil |  |
| 3 | Champhai | 28 | 28 | 5 | Nil | Nil | Nil | Nil |  |
| 4 | Kolasib | 3 | 3 | 0 | Nil | Nil | Nil | Nil |  |
| 5 | Mamit | 3 | 3 | 0 | Nil | Nil | Nil | Nil |  |
| 6 | Lawngtlai | 1 | 1 | 0 | Nil | Nil | Nil | Nil |  |
| 7 | Lunglei | 2 | 2 | 0 | Nil | Nil | Nil | Nil |  |
| 8 | Saiha | 1 | 1 | 0 | Nil | Nil | Nil | Nil |  |
| 9 | Serchhip | 3 | 3 | 0 | Nil | Nil | Nil | Nil |  |
|  | Total | 96 | 96 | 7 | 0 | 0 | 0 | 0 |  |

- Dengue Control Programme was implemented for the first time in the State during 2012-2013 (October 2012).  Prior to the programme implementation, the State was thought to be Dengue and  Chikungunya free and so had no provision for detection of Dengue and Chikungunya.

- There is a great potential for Dengue as the vector Aedes mosquitoes are abundant in the State. Sentinel Surveillance was started at in Civil Hospital, Aizawl in the latter half of 2012. Henceforth, random blood samples were taken from OPD patients presenting with suspected dengue fever in the Sentinel Surveillance Hospital.

- Specific constraints, newer strategy and innovation proposed for implementation of the programme :

- As mentioned earlier, before the initiation of Dengue Control Programme, the State did not have provisions for detection/diagnosis of Dengue and Chikungunya.

After implementation of the Dengue and Chikungunya Control Programme in the State, these are the constraints and innovation proposed :-

| Sl. No | Specific Constraints | Newer Strategy | Innovation proposed for Implementation of the Programme |
| --- | --- | --- | --- |
| 1 | IgM Mac Elisa Test Kit was received from NIV pune and till now the state received 96 Test Kits |  | Regular supply of IgM Mac Elisa Test Kits, if not possible monthly, at least quarterly supply of Test Kits |
| 2 | IgM Mac Elisa Test Kits received from NIV Pune is cumbersome and it requires 5-6 hrs for incubation |  | More advance and less time consuming IgM Elisa Kits may be supplied to the State |
| 3 | There is only one Sentinel Surveillance Hospital for Dengue in the State i.e. Civil Hospital, Aizawl. It takes a too long time to receive serum samples from periphery and far off places. | Additional Sentinel Surveillance Hospitals is required to cover the Southern Zone as the current SSH is located in Northern Mizoram | Civil Hospital, Lunglei is proposed as a new Sentinel Surveillance Hospital which will cover the Southern Part of the State. |
| 4 | Unavailability of Funds for procurement of NS1 antigen test Kits for Dengue | During the unavailability of IgM Mac Elisa Test Kits, NS1 antigen test kits will be used for diagnosing suspected Dengue Cases | More provisions of funds for procurement of NS1 antigen test Kits. |

- Time lag in receiving reports is a huge constraint. Although no fatality cases have been recorded as yet, it is imperative to have more Sentinel Surveillance Hospital in the State. For the 2014-2015, one additional SSH is proposed to cover the Southern part of the State. Civil Hospital, Lunglei is the proposed SSH.

- Fortunately, as Blood Donation programme is very well implemented in the State, Blood bank and blood component separation facilities related are available in most of the Districts of the State although Southern Districts viz Lawngtlai, Saiha and Lunglei may not at par with the other Districts.

- Strategy and Innovation proposed for Implementation of Mid-term Plan Strategy in Urban and Rural areas :

- Dengue and Chikungunya is relatively a new disease to majority of the population in the State. Much needs to be done via IEC/BCC for awareness, social mobilization and elimination of vector breeding grounds.

- Entomological Surveillance: As in the case of Anopheles Mosquitoes, Aedes Mosquitoes are abundant in the State. The State does not have a functional Entomological Unit and hence as proposed earlier under Malaria Control Programme, initiation of two Entomological Units during 2014-2015 for all Vector Borne Diseases must be given priority.

- Inter-sectoral convergence for elimination of vector breeding to minimised transmission and prevention of occurrence of out breaks is necessary. As mentioned earlier under Public Private Partnership, partnering with NGOs namely YMA (Young Mizo Association) is proposed and is seen as a practical and effective strategy in vector breeding elimination.

- With the possible setup of an additional SSH in Civil Hospital, Lunglei, clearer picture of the disease situation in the State is warranted and hence will pave way for better evaluation and formulation of improved strategy.

- Diagnostic Facilities : Number of Sentinel Surveillance functional against number identified for Dengue are as follows (all Nil for Chinkugunya) :

| Name of District | Name of SSH Identified | Name of functional SSH | Kits received from NIV, Pune/Utillized | Ns1 Kits Procured | Sample received/ Tested |  | Found Positive |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IgM | NS1 | IgM | NS1 |
| Aizawl West | Civil Hospital, Aizawl | Civil Hospital, Aizawl | 96 Test Kits | Nil | 32 | Nil | 6 | Nil |

- RDT procurement by state : Nil

- Number of New SSH Proposed for 2014 – 2015 :

- One additional SSH is proposed for 2014 -2015.

- Civil Hospital, Lunglei is the newly proposed SSH. This will cater patients from Southern part of the State.

- Details of Kit requirements for 2014 – 2015 :

| District | Sentinel Surveillance Hospital | IgM Mac Elisa |  | NS1 antigen Kits | ELISA Reader and Washer |
| --- | --- | --- | --- | --- | --- |
|  |  | Dengue | Chikungunya |  |  |
| Aizawl West | Civil Hospital, Aizawl | 10 kits (960 Test) | 6 Kits (576 Test) | 10 Kits (960 Test) | NIL |
| Lunglei | Civil Hospital, Lunglei | 8 Kits (768 Test) | 6 Kits (576 Test) | 8 Kits (768 Test) | 1 |

note : Civil Hospital, Lunglei does not have ELISA reader and Washer

- Vector Control Team selected and population target :

| Name of Focus District | Population | Dengue Cases reported in 2013 | Death due to Dengue | Death due to Chikungunya | No of Volunteer required for breeding source reduction and social mobilization | Funds required (20 days x 5 Months @ Rs 100 for workers) |
| --- | --- | --- | --- | --- | --- | --- |
| Aizawl West | 1,54,951 | 1 | Nil | Nil | 6 | 60,000/- |
| Aizawl East | 2,33,735 | 1 | Nil | Nil | 6 | 60,000/- |
| Champhai | 1,25,370 | 5 | Nil | Nil | 6 | 60,000/- |
| Lunglei | 1,47,191 | 0 | Nil | Nil | 6 | 60,000/- |
| Total | 5,35,877 | 7 | Nil | Nil | 24 | 2,40,000/- |

- Requirement for commodity as per technical norms and considering of stores, consumptions capacity and justification :

- Insecticides and Larvicides requirements are included under Urban Malaria Scheme.

- Financial Requirement for Dengue and Chikungunya :

The financial Requirements for Dengue and Chikungunya are mentioned below :-

F.1.2 Dengue and Chikungunya

F.1.2.a : Strengthening Surveillance :

- F.1.2.a. i : Apex Referral Labs Recurrent : Nil

- F.1.2.a. ii : Sentinel Surveillance Hospital Recurrent :

- The State will have two Sentinel Surveillance if the proposed additional SSH is approved. The Fund requirements are as follows :-

| Sl no | Sentinel Surveillance Hospital | Cost of Sentinel Surveillance per annum | Funds required |
| --- | --- | --- | --- |
| 1 | Civil Hospital, Aizawl | 1,00,000/- | 1,00,000/- |
| 2 | Civil Hospital, Lunglei | 1,00,000/- | 1,00,000/- |
| Total Fund requirement for 2014-2015 |  |  | 2,00,000/- |

Note - SSH, Lunglei shall be functional as soon as ELISA facility is procured which is recommended to be accomplished by 1stquarter of 2014-2015.

- F.1.2.a. iii : ELISA Facility to Sentinel Surveillance Labs :

- Civil Hospital, Lunglei does not have ELISA Reader and Washer.

- The funds required for ELISA facility is as follow :

| Sl No | SSH | Availability of ELISA | Required | Cost | Funds Required |
| --- | --- | --- | --- | --- | --- |
| 1 | Civil Hospital, Aizawl | Yes | Nil | Nil | Nil |
| 2 | Civil Hospital, Lunglei | No | 1 | 5,00,000/- | 5,00,000/- |
|  | Total Fund required for ELISA facility for 2014-2015 |  |  |  | 5,00,000/- |

Procurement of ELISA facility for Civil Hospital, Lunglei is proposed to be completed by 1st quarter so as SSH Civil Hospital, Lunglei shall be functional by 2nd quarter of 2014-2015.

F.1.2.b : Test Kit to be supplied by GoI :

- The test kits to be supplied by GoI is as follows :

|  | IgM Mac ELISA | NS1 antigen kits |
| --- | --- | --- |
| Dengue | 18 Kits ( 1728 tests) | 18 kits (1728 tests) |
| Chikungunya | 12 Kits (1152 tests) | Nil |
| Total | 30 Kits (2880 test) | 18 Kits (1728 tests) |

F.1.2.c : Monitoring/ Supervision and Rapid Response :-

- The fund requirements and activities proposed are as follows :

| Sl No | Activity | No of Activities | Cost (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Monitoring by M&E Consultant | 5 times a year | 20,000 per tour | 1,00,000/- |
| 2 | Supervision by SPH Consultant | 5 times a year | 20,000 per tour | 1,00,000/- |
| 3 | State Review meeting | 4 (Quarterly) | 2,00,000/- per Meeting | 8,00,000/- |
| Total Fund required for 2014-2015 |  | 14 |  | 10,00,000/- |

F.1.2.d. : Epidemic Preparedness :-

- As per recommendation in the guideline, the State projects a tentative sum of Rs 3,00,000/-  for Epidemic Preparedness.

F.1.2.e : Case Management :-

- The State would require a tentative sum of Rs 2,00,000/- for Case Management.

F.1.2.f : Vector Control, Environmental Management and fogging machine

- During high transmission seasons of Dengue, 24 workers will be hired daily for 20 days, 5 months @ Rs 100/day per worker, as per NVBDCP guidelines.

- 6 Fogging machines will be needed by the state.

- Insecticides requirements are mentioned under UMS.

| Sl. No | Items | Amount | Rate (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Workers | 24 | Rs 100 x 20 days x 5 months | 2,40,000/- |
| 2 | Fogging Machines | 6 | 70,000/- per machine | 4,20,000/- |
| Total Fund Required for 2014-2015 |  |  |  | 6,60,000/- |

F.1.2.g : IEC/BCC for Social Mobilization :

- Since Dengue and Chickungunya are relatively unknown to majority of the population, much work is to be done on awareness and sensitizing the community on elimination of the Vector breeding grounds.

- Proposed IEC/BCC components includes :

| Sl no | Activities | Amount | Rate | Funds Required |
| --- | --- | --- | --- | --- |
| 1 | Anti –Dengue Month | 1,00,000/- |  | 1,00,000/- |
| 2 | Dengue Booklets | 2000 | 35/- | 70,000/- |
| 3 | Radio Talk / Discussions | 5 | 5000 | 25,000/- |
| 4 | Production of TV spot Ads | 2 | 20,000/- | 40,000/- |
| 5 | Spot Ads TV | 6 | 20,000/- per month | 1,20,000/- |
| 6 | Awareness Campaign | 40 | 2500/- | 1,00,000/- |
| 7 | Display Ads | 40 | 3000/- | 1,20,000/- |
| 8 | Banner Ads | 30 | 2500 | 75,000/- |
| 9 | Scroll Ads TV | 5 | 15,500/- per month | 77,500/- |
| 10 | Pamphlets | 2000 | 35 | 70,000/- |
| 11 | Hoardings | 3 | 25,000/- | 75,000/- |
| Total Fund required for 2014-2015 |  |  |  | 9,12,500/- |

F.1.2.h : Inter-sectoral Convergence :-

- Dengue and Chikungunya Control Programme goes hand in hand with Malaria Control Programme. As mentioned under Malaria Control Programme, Public Private Partnership with NGOs and CBOs is essential in eradication of Vector Breeding grounds. The Church Based Organizations and NGOs esp, the Young Mizo Association will be the main partners for the year 2014 – 2015.

Funds Required for Dengue and Chikungunya as separate programme is estimated as below :

| Sl No | Public Private Partnership | Activities to be performed | Estimated fund required |
| --- | --- | --- | --- |
| 1 | Church Based Organization, - Northern Zone - Southern Zone | - Sanitation Drive and Environment Management - Awareness Campaign - Provision of Outreach Services - Health Education and Promotion | 1,00,000/- 1,00,000/- |
| 2 | Young Mizo Association |  | 2,00,000/- |
| Total Funds Required for 2014-2015 |  |  | 3,00,000/- |

F.1.2.i : Training & Printing of guidelines, formats including operational research

- Training and re-sensitization of Clinicians and allied is extremely necessary. With respect to this, the funds required are as below :

| Sl. No | Items | Activity | No of Activities | Cost | Funds required |
| --- | --- | --- | --- | --- | --- |
| 1 | CMOs, MOs, Clinicians, DVBPO | Training/workshop | Once a year for each District | 2 Lakhs for each Districts | 18,00,000/- |
| 2 | Printing of guidelines etc | - | - | 2 Lakhs | 2,00,000/- |
| Total Funds Required for 2014-2015 |  |  |  |  | 20,00,000/- |

Workshop on Dengue and Chikungunya is proposed to be conducted once a year in each District. Tentatively, Rs 2 lakhs per District is proposed for conduction of workshop.

- Acute Encephalitis Syndrome including Japanese Encephalitis :

- Disease Situation :

- The State has long been a known endemic region of Malaria. The disease prevalence of AES/JE is not known as the Programme has not been implemented in the State.

- Factors favouring a high chance of AES/JE prevalence are as follows :

- Culex Mosquitoes are abundant in the State

- 27 Deaths due to suspected ‘Viral Encephalitis’ was recorded among age group of 7-20 during the year 2008-2012 with symptoms and clinical findings including high fever, intense headache, vomiting, semi-coma, unconscious etc.

- Pigs, the amplifiers of the virus are the most common live stock animal in the State. In sub-urban and rural areas, most of the families rear at least one pig.

- In the Medical History of Mizoram, it was reported that two persons had succumbed to Japanese Encephalitis and it was known only after their blood Sample was sent outside the State for Confirmation.

- Due to improvement of transport, intermixing of populations and long international boundaries with Bangladesh and Myanmar including neighbouring states like Assam, Manipur and Tripura, where cases of Japanese Encephalitis are not uncommon, there is every possible chances of JE prevalence in the State as well.

- Since the State does not have any means to diagnose a case of JE, the disease prevalence is still in the dark.

With respect to the possibilities of AES/JE prevalence in the State, proposal for supply of test reagents and test kits for AES/JE by GoI during 2014-2015 is made. Civil Hospital, Aizawl which is equipped with ELISA facility is proposed for the testing centre in the State.  This will enable the State to know the disease situation in the State and pave way for measures and strategies to adopt thereafter.

- Epidemiological Situation of AES/JE 2012-2013 :

| Sl No | Name of District | Block wise no of AES/JE cases | No. of Deaths | No. of Sera/CSF Sample Tested | No. of Confirmed for JE | No. of Vaccinated children confirmed with JE infection |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | Control Programme not yet implemented and no survey has been undertaken, the incidence of AES/JE is not known in the State |  |  |  |  |
| 2 | Aizawl West |  |  |  |  |  |
| 3 | Champhai |  |  |  |  |  |
| 4 | Kolasib |  |  |  |  |  |
| 5 | Mamit |  |  |  |  |  |
| 6 | Lawngtlai |  |  |  |  |  |
| 7 | Lunglei |  |  |  |  |  |
| 8 | Saiha |  |  |  |  |  |
| 9 | Serchhip |  |  |  |  |  |

- Specific Constraints, newer Strategies and Innovations proposed for implementation of the programme :

  - Until now, there are no specific constraints or strategies to mention for AES/JE as the programme is not yet implemented in the State. However, the State would like to know the disease situation of the State during 2014-2015 through supply of test reagents and test kits by GoI and if the survey dictates, the programme will be initiated by 2015-2016.

  - The followings are proposed for the initiation and implementation of the Programme for the financial year 2015-2016 :

- Sentinel Surveillance Hospital: For initiation of the Programme, one Sentinel Surveillance Hospital is proposed for the State, Civil Hospital, Aizawl. Only after establishing SSH for AES/JE, the disease situation will be clear.

- Japanese Encephalitis Test Kits : As Civil Hospital, Aizawl will be the sole JE testing centre in the State, for a starter, two test Kits (192 Tests ) will be required.

- Training : Trainings on diagnostic procedures and case management of J.E to Chief Medical Officers, Medical Specialist, Medical Officers and District Vector Borne Disease Project Officers (DVBPO) shall be given.

- Awareness Programme : As JE is relatively uncommon in the state, re-sensitizing the Medical Practitioners in the State is necessary. Further,  for awareness and social mobilization, IEC/BCC components like leaflets, pamphlets and audio-visual short plays will be taken up.

- Malathion : Small quantity, 200 litres of Malathion will be needed for the initial implementation of the Programme. In case of possible emergency conditions like outbreaks, the required insecticides will be met from other sources.

- Emergency preparedness : for emergency preparedness and early response to JE outbreaks, the State would require at least 2 fogging machines.

- Monitoring and functioning of Sentinel Surveillance Hospital/ Site :

- As mentioned earlier, the programme has not yet been implemented in the State. However, a proposal to implement the programme by 2015-2016 has been laid down with Civil Hospital, Aizawl as the lone Sentinel Surveillance Hospital in the State.

F.1.3 : Acute Encephalitis Syndrome including Japanese Encephalitis

F.1.3.a : Strengthening of Sentinel Sites which will include Diagnostics and Case Management, Supply of Kits by GoI :

- As disease situation is unknown in the State, it is proposed that reagents for diagnosis and test kits be supplied by GoI during the 1st quarter of 2014-2015.

| Sl No | Particulars | Quantity |
| --- | --- | --- |
| 1. | Test Kits | 500 |

- The State does not have Sentinel Surveillance Hospital/ Site as yet. However, having one SSH from the year 2015-2016 is proposed and with it, the requirements are as follows :

| Sl No | Particulars | Quantity | Funds Required (Rs) |
| --- | --- | --- | --- |
| 1 | Modifications of rooms for initiation of SSH | 1 room | 2,50,000/- |
| 2 | Computers and Peripherals |  | 70,000/- |
| 3 | Reagents for Diagnostic Facilities |  | 1,00,000/- |
| 4 | Case Managements |  | 2,00,000/- |
| 5 | Diagnostic Test Kits | 2 kits (192 Tests) | To be supplied by GoI |
| 6 | Data Entry Operator | 1 @ Rs 15,000/- Pm | 1,80,000/- |
| 7 | Training for Diagnostic Facilities |  | 1,00,000/- |
| 8 | Operational Cost | 20,000/- pm | 2,40,000/- |
| 9 | Contingencies |  | 2,00,000/- |
| Total Fund Required for Functional SSH by 2015-2016 |  |  | 13,40,000/- |

F.1.3.b : IEC/BCC :

- After Programme Implementation and Disease Situations in the State become clear, necessary actions and measures on IEC/BCC shall be undertaken.

F.1.3.c : Capacity Building :

- Workshops shall be conducted after programme initiation.

F.1.3.d : Monitoring and Supervision :

- State Consultants, will perform Monitoring and Supervision of Districts with AES/JE cases after programme implementation.

| Sl No | Activity | No of Activities | Cost (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Monitoring by M&E Consultant | 4 | 20,000 per tour | 80,000/- |
| 2 | Supervision by SPH Consultant | 4 | 20,000 per tour | 80,000/- |
| Total fund required |  |  |  | 1,60,000/- |

F.1.3.e : Procurement of Insecticides :

- For emergency preparedness, 200 litres of Malathion will be required .

Funds required for 200 litres of Malathion @ 150 per litre is Rs 30,000/-

F.1.3.f : Fogging Machines :

- For emergency preparedness, fogging machines shall be required by the State. Tentatively, two fogging machines @ Rs 70,000/- per machine should be sufficient. Hence the total fund required for procurement of fogging machines is Rs 1,40,000/-.

F.1.3.g : Operational Cost for Malathion Fogging :

- In case of emergency, 2 person for each fogging machine shall be hired @ Rs 200 per day for 20 days.

The funds requirement in Operational Cost is

| Sl. No | Activity | Amount | Cost | Funds Required |
| --- | --- | --- | --- | --- |
| 1 | Fogging operation | 4 person | @ Rs 200 per day for 20 days | 16,000/- |
| 2 | Fogging Supervisor | 2 | @ 500 per day for 20 days | 20,000/- |
| 3 | Travel etc expenses |  |  | 1,00,000/- |
| Total funds Required for Operational Cost |  |  |  | 1,36,000/- |

F.1.3.h : Operational Research :

- No provision for operational research is made by the State as for now

F.1.3.i : Rehabilitation Setup for selected endemic district :

- No provision for Rehabilitation Setup is made by the State as the programme has not yet been initiated in the State.

F.1.3.j : ICU Establishment in Endemic Districts :

- No provision for ICU Establishment is made by the State.

F.1.3.k : ASHA Insentivization for sensitizing the community :

- Sensitizing the community before Disease Situation survey reports are availiable is not recommended by the State. This shall be undertaken only after detailed Disease Situation of the State is known.

F.1.3.l : Other charges for training/workshop Meeting and Payment to NIV towards JE kits at Head Quarters :

- As no case of Japanese Encephalitis has clearly been diagnosed in the State, after Programme implementation, Trainings and Re-sensitization on Preventive, Diagnostic and Case Management needs to be given to :

- All Chief Medical Officers

- All Medical Officers

- Medical Specialists

- DVBPO

- DVB Technical Supervisors

- One workshop shall be conducted at State Level. Further District wise workshop may be conducted according to Survey reports of Sentinel Surveillance Hospital .

Tentative Fund requirement for training and workshops are as follows :

| Sl.No | Activities | Amount | Rate | Funds Required |
| --- | --- | --- | --- | --- |
| 1 | Training /Worshop at State level | 1 | 4,00,000/- | 4,00,000/- |
| 2 | Training/ Workshop at District level | 9 | 1,50,000/- | 13,50,000/- |
| Total |  | 10 |  | 17,50,000/- |

- As per guidelines, tentative proposal for contingencies of Rs 1,50,000/- per District is made by the State.

| Items | Number of Districts | Tentative Cost per District | Funds required |
| --- | --- | --- | --- |
| Contingencies | 1 | 1,50,000/- | 1,50,000/- |

F.1.3.m : Establishing District Counselling Centre :

- No provision for setting up District Counselling Centre is proposed for the year 2014 -2015.

- Lymphatic Filariasis

- Goal :

Elimination of lymphatic filariasis by 2015.  To achieve elimination, the micro-filaria rate in all the endemic districts should be less than 1% to interrupt the transmission.

- Lymphatic Filariasis is not a major problem in the State and is almost unknown to the people in majority. However Elephantiasis and hydrocele are infrequently found in the Districts of Lawngtlai, Lunglei, Mamit and Kolasib especially among immigrants and labourers. It is not an indigenous disease of the State and the burden of the filariasis is insignificant in the State.

- Cases of Lymphatic Filariasis is very rare in Mizoram. Incidence could not be shown as the Programme is not implemented in the State.

| Sl no | Name of District | Population at Risk | Coverage of eligible population under MDA | Microfilaria rate | No. Of line listed total lymphoedema case | No. Of line listed total hydrocele case | No of hydrocele operations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | Programme not yet implemented and Survey not yet carried out in the State |  |  |  |  |  |
| 2 | Aizawl West |  |  |  |  |  |  |
| 3 | Champhai |  |  |  |  |  |  |
| 4 | Kolasib |  |  |  |  |  |  |
| 5 | Mamit |  |  |  |  |  |  |
| 6 | Lawngtlai |  |  |  |  |  |  |
| 7 | Lunglei |  |  |  |  |  |  |
| 8 | Saiha |  |  |  |  |  |  |
| 9 | Serchhip |  |  |  |  |  |  |

F.1.4 : Lymphatic Filariasis :

- The Programme for elimination of Lymphatic Filariasis has not been implemented in the State. As the disease burden is insignificant in the State, the programme is not recommended for implementation in the State

- Hence no funding is required by the State under Lymphatic Filariasis Elimination Programme

Kala-Azar

- Goal :

Kala-azar is targeted for elimination by 2015.  The elimination is to bring down the number of kala-azar cases less than 1 per 10,000 population at block level.

- Disease Situation :

- Kala-Azar is endemic only in Bihar, West Bengal, Jharkhand and parts of U.P.

- Kala-Azar is not found in the State nor a health problem in the State. Hence the Programme is neither implemented nor recommended for implementation.

| Monitoring of Diagnosis and Treatment Compliance of Kala Azar Patients |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| % age of people treated after diagnosis % age of people received complete treatment |  |  |  |  |  |
| District | Cases | Deaths | Cases treated | Cases fully treated (Treatment Compliance) | % Treatment Compliance |
| Aizawl East | Programme not implemented in the State |  |  |  |  |
| Aizawl West |  |  |  |  |  |
| Champhai |  |  |  |  |  |
| Kolasib |  |  |  |  |  |
| Mamit |  |  |  |  |  |
| Lawngtlai |  |  |  |  |  |
| Lunglei |  |  |  |  |  |
| Saiha |  |  |  |  |  |
| Serchhip |  |  |  |  |  |

F.1.5 : Kala-Azar :

- The Programme for Elimination of Kala Azar is not implemented in the State nor is recommended for implementation in the State due to virtually non existence of Case.

- Hence, no funding is required by the State under Kala Azar elimination Programme.

F.2 : Externally aided components :

F.2.a : World Bank support for Malaria (Identified State) :

- The State is not identified for World Bank support for Malaria

F.3 GFATM support for Malaria (NEStates)

- F.3.a : Project Management Unit including human resources of N.E.States :

- The funds in human resources need to be revised and enhanced accordingly due to the following reasons :

- Rise in price of daily commodities.

- Great discrepancies of pay scale of same grade/ qualification as compared to other State Departments.

- Great discrepancies of Pay scale of same grade/qualification as compared to other National/ State Programmes.

- To ensure better work productivity and sound environment in the work places, salaries needs to be adjusted in accordance with  other sectors.

- To retain and avoid frequent attrition of staffs.

These are the new proposed hike in salary of Contractual Post under NVBDCP which is being funded via GFATM for the year 2014-2015.

| Sl.No | Post | No of Post available | New Proposed (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | State Public Health Consultant (VBD) | 1 | 80,000/-pm | 9,60,000/- |
| 2 | Monitoring & Evaluation (Medical Graduate with PH degree ) | 1 | 80,000/-pm | 9,60,000/- |
| 3 | Finance & accounts Consultant | 1 | 60,000/-pm | 7,20,000/- |
| 4 | PSCM Consultant | 1 | 60,000/-pm | 7,20,000/- |
| 5 | IEC/BCC Consultant | 1 | 60,000/-pm | 7,20,000/- |
| 6 | MO Sentinel Surveillance Hospital | 2 | 70,000/-pm | 16,80,000/- |
| 7 | DVBDPO | 9 | 60,000/-pm | 64,80,000/- |
| 8 | MTS | 16 | 20,000/-pm | 38,40,000/- |
| 9 | State Statistical Assistant | 1 | 30,000/-pm | 3,60,000/- |
| 10 | Secretarial Asst cum DEO | 11 | 15,000/-pm | 19,80,000/- |
| 11 | Laboratory Technician | 10 | 15,000/-pm | 18,00,000 |
| Total fund required for 2014-2015 |  |  |  | 202,20,000/- |

F.3.b : Training Capacity :

- Training, re-training and sensitization of staffs on the latest strategy and approach adopted by the Central and State needs to be done at regular interval to ensure correct implementations of the Programme as per guidelines.

- Proposed Training list for 2014-2015 under GFATM includes :

- Medical Officers

- ASHAs

- Malaria Technical Supervisors

- Lab Tech/ Microscopist

Fund requirement for conducting training during 2014-2015 is as follows :

| Sl. No | Post | Number of trainees | No of training days | Average TA + DA | Proposed month for training | Cost for Training Venues and resource Persons | Funds Required |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Medical Officers | 70 | 2 | 6000 + 2000 | December | 2*(10000 + 3000) | 6,26,150/- |
| 2 | ASHAs | 987 | 1 | 1000 + 400 | February | 9 *( 4000 + 2000) | 19,80,300/- |
| 3 | Malaria Technical Supervisors | 16 | 1 | 4500 + 400 | January | 10000 + 2000 | 90,400/- |
| 4 | Lab Tech/ Microscopist | 72 | 1 | 4500 + 400 | November | 4000 + 2000 | 3,99,500/- |
| 5 | Training of trainers | 9*4 | 1 | 5000 + 700 | 10 days prior to district training | 1*(8000 + 2000) | 2,36,100/- |
| 6 | Contingencies |  |  |  |  |  | 4,00,000/- |
| Total Funds Required for 2014-2015 |  |  |  |  |  |  | 37,32,450/- |

Note – Rs 200/- per participants for lunch and snacks & Rs 250/- per participants for incidental expenditure e.g. stationeries, photocopies, projectors etc are included.

F.3.c : Planning and Administration :

- An estimated Rs 3,00,000/- per month is proposed with the total funds requirement at Rs 40,00,000/- for 2014-2015.

F.3.d : Monitoring,Supervision & Review Meetings :

- Monitoring, Evaluation and Supervision :

As per travelling expenditure guideline under IMCP-II Round 9 Phase-II GFATM, the fund requirements for 2014-2015 is as follows :

| Sl No | Particulars | Expenditure per month | Fund Required |
| --- | --- | --- | --- |
| 1 | State Level Consultants (5 Consultants) | 65,000/- | 7,80,000/- |
| 2 | District VBD Consultants (9 Districts) | 20,000/- per district | 21,60,000/- |
| Total Fund required during 2014-2015 under M&S |  |  | 29,40,000/- |

However, since Mizoram State is a hilly area with a very hard terrain, the roads apart from National highway and State highway are mostly un-metalled and dirt roads. The government approved rate per km is Rs 19/- and Rs 25/- for metalled roads and un-metalled roads respectively in the State. However, the cost for vehicle rental differs in each District. The cost is very high in Lawngtlai and Saiha District, moderately high for some areas in Lunglei, Mamit and Champhai Districts eg the cost of one vehicle rental (two way) from Lawngtlai town to Vaseitlang of Lawngtlai District which is about 138 kms is around Rs 25,000/- . The same distance would be around Rs 12000/- in Lunglei District and Rs 6500/- in Aizawl West District. This is due to the very difficult terrain and lack of proper roads in the Districts.

According to the guidelines, travelling expenditure for District Consultants @ Rs 20,000/- per district per month for M&E is hugely inadequate for 4 of the Districts with high API. The API(2013) of Lawngtlai was 35.96 ,Saiha -  8.47, Lunglei –  26.01 and Mamit – 22.28. The Monitoring, Evaluation and Supervision fund allocation for these 4 districts needs to be reassessed. The progress of SVBDCP largely depends on laying more emphasis on monitoring of these highly endemic districts. With regards to the number of villages to be covered and the cost of vehicle hiring, the proposed fund allocation for Monitoring, Evaluation and Surveillance is as follows:

| Sl No | Particulars | Expenditure per month | Fund Required |
| --- | --- | --- | --- |
| 1 | State Level Consultants (5 Consultants) | 65,000/- | 7,80,000/- |
| 2 | District VBD Consultants (5 Districts with API < 8) | 20,000/- per district | 12,00,000/- |
| 3 | Lawngtlai District (API = 35.96 and 181 villages) | 65,000/- | 7,80,000/- |
| 4 | Saiha District (API = 8.47 and 81 villages) | 45,000/- | 5,40,000/- |
| 5 | Lunglei District (API = 26.0 and 185 villages) | 50,000/- | 6,00,000/- |
| 6 | Mamit District (API = 22.28 and 74 villages) | 45,000/- | 5,40,000/- |
| Total Fund required during 2014-2015 under M&S |  |  | 44,40,000/- |

- Review Meetings :

- Quarterly review meeting : Quarterly review meeting is held in the State Capital.

The requirements of funds for conducting 2 day review meeting is as follows :-

| Sl. No | Particulars | No | Rate/ TA&DA (average for 2 days) | Fund Required |
| --- | --- | --- | --- | --- |
| 1 | Meeting Centre/ Hall Rent | 1 | 20000/- | 20,000/- |
| 2 | SPO | 1 | 2000/- | 2000/- |
| 3 | Dy Director (Malaria) | 1 | 2000/- | 2000/- |
| 4 | Chief Guest | 1 | 1000/- | 1000/- |
| 5 | CMOs/DMOs | 9 | 8000/- | 72,000/- |
| 6 | Assistant Malaria Officers | 3 | 7000/- | 21,000/- |
| 7 | State Consultants | 5 | 1400/- | 7000/- |
| 8 | DVBPOs/DPOs | 9 | 7000/- | 63,000/- |
| 9 | MTSs | 16 | 5700/- | 91,200/- |
| 10 | Lab Tech/ Microscopist | 9 | 5700/- | 51,300/- |
| 11 | Malaria Inspectors | 8 | 5700/- | 45,600/- |
| 12 | State VBD Staffs | 8 | 1000/- | 8000/- |
| 13 | Total Participants | 70 |  |  |
| 14 | Lunch, Tea & Snacks | 70 | 200/- per participants per day | 28,000/- |
| 15 | Incidental expenses including Stationeries, photocopy, etc | 70 | 250/- per participants (only for day 1) | 17,500/- |
|  | Contingencies |  |  | 10,000/- |
| Total Fund required per Review Meeting |  |  |  | 4,39,600/- |
| Total Fund required for 2014-2015 |  |  |  | 17,58,400/- |

- District Review Meeting :

Tentative sum of Rs 1 lakhs is proposed for each Quarterly District Review Meeting. Total Fund required for 9 districts is Rs 36,00,000/-.

- Annual Pre-Spray Micro-Action Plan Meeting : Annual Pre-Spray Meeting is conducted at District Level prior to 1st round of IRS. All Medical Officers, Health Supervisors and Health Workers in the district are included in the pre-spray meeting. Tentative sum of Rs 1 lakhs is proposed for each District.
Total fund required for 9 districts is Rs 9,00,000/-.

- Post Spray Review Meeting : After 2nd round of IRS, Post Spray Review Meeting for one day is held every year in the State capital.

The requirement of funds for conducting Post Spray Review Meeting is as follows :

| Sl.No | Particulars | No | Rate/TA&DA (Average) | Funds Required |
| --- | --- | --- | --- | --- |
| 1 | Meeting Centre/Hall | 1 | 10,000/- | 10,000/- |
| 2 | SPO | 1 | 1000/- | 1000/- |
| 3 | Dy Director (Malaria) | 1 | 1000/- | 1000/- |
| 4 | Resource Persons | 2 | 1000/- | 2000/- |
| 4 | CMOs/DMOs | 9 | 6000/- | 54000/- |
| 5 | DVBPOs/DPOs | 9 | 5500/- | 49500/- |
| 6 | State Consultants | 5 | 700/- | 3500/- |
| 7 | MTSs | 16 | 5300/- | 84,800/- |
| 8 | Malaria Inspectors | 8 | 5300/- | 42,400/- |
| 9 | State VBD Staffs | 8 | 500/- | 4000/- |
| 10 | Total Participants | 59 |  |  |
| 11 | Lunch /Tea Snacks | 59 | 200/- per participants | 11800/- |
| 12 | Incidental expenditure including Stationeries, demonstration kits etc | 59 | 250/- per participants | 14750/- |
| 13 | Contingencies |  |  | 10000/- |
| Total Fund required for yearly Post Spray Review Meeting |  |  |  | 2,87,750/- |

The total fund required under Monitoring, Supervision and Review meetings is :

| Sl. No | Particulars | Fund Required (Rs) |
| --- | --- | --- |
| 1 | Monitoring, Supervision and Evaluation | 44,40,000/- |
| 2 | Quarterly Review Meetings | 17,58,400/- |
| 3 | Quarterly District Meetings | 36,00,000/- |
| 4 | Pre-spray Meetings | 9,00,000/- |
| 5 | Post –Spray Review Meeting | 2,87,750/- |
| Total fund required for 2014-2015 |  | 109,86,150/- |

F.3.e : IEC/BCC :

As evident from the last few years, IEC/BCC progress is largely reflected in the State’s Malaria Control Programme. The IEC/BCC activities undertaken have huge impact in the State especially in the urban and sub-urban areas. However, much greater effort needs to be put into the sub-urban and rural areas where API continues to be very high. Remembering that IEC/BCC is a continual process, giving more efforts in the region with high API and at the same time, continuing the activities in the improved areas is the strategy the State plans to adopt.

The activities proposed for 2014-2015 as per financial norms for IEC/BCC activities are:

| Sl No | Communication Material | No of Activities | Rate (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Miking | 1842 | 600 | 11,05,200/- |
| 2 | School Activity | 150 | 800 | 1,20,000/- |
| 3 | BCC Mass media | 360 | 3300 | 11,88,000/- |
| 4 | Infotainment | 1842 | 600 | 11,05,200/- |
| Total Fund required for IEC/BCC under GFATM for 2014-2015 |  |  |  | 35,18,400/- |

F.3.f : Operational cost for treatment of bed nets and Infrastructure and other equipments :

- The State requirement for LLINs District-Wise is as shown :

| Sl.No | Name of District | LLINs Requirements |  |  | Fund Under GFATM |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Families living in areas with API>2 | For Jhum Cultivators | Total | ASHAs / HWs Incentives (Rs) | Total Fund Required for Distribution (Rs) |
| 1 | Aizawl East | Nil | 11323 | 11323 | 10/- | 113230/- |
| 2 | Aizawl West |  |  |  |  |  |
| 3 | Champhai |  | 9545 | 9545 | 10/- | 95,450/- |
| 4 | Kolasib | 8180 | 6298 | 14478 | 10/- | 1,44,780/- |
| 5 | Mamit | 6520 | 6457 | 12977 | 10/- | 1,29,770/- |
| 6 | Lawngtlai | 12172 | 13888 | 26060 | 10/- | 2,60,600/- |
| 7 | Lunglei | 14720 | 13156 | 27977 | 10/- | 2,79,770/- |
| 8 | Saiha | 5760 | 3216 | 8976 | 10/- | 89,760/- |
| 9 | Serchhip | Nil | 4550 | 4550 | 10/- | 45,500/- |
|  | Total | 47352 | 68433 | 115785 |  | 11,57,850/- |

For distribution of LLINs, the total fund required during 2014-2015 is Rs 11,57,850/-.

Hence, the total fund required for distribution of LLINs is estimated at:

| Sl.No | Activity | Quantity | Cost (Rs) | Fund Required (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Distribution of LLINs | 115785 | Rs 10/- per net | 11,57,850/- |
| Total fund required for 2014-2015 |  |  |  | 11,57,850/- |

- The State requirement for Maintenance of Equipments (Computers, laptops, printers, motor cycles for MTS)

| Sl. No. | Name of items | No. of Items |  |  | Maintenance cost per item month in Rs | Fund required per year in Rs |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | State | District | Total |  |  |
| 1. | Laptops | 6 | 9 | 15 | 300 | 90,000 |
| 2. | Desktops | 7 | 9 | 16 | 300 | 96,000 |
| 3. | Internet connection | 6 | 18 | 24 | 1300 | 3,74,400 |
| 3. | Printers | 4 | 9 | 13 | 5000 | 7,80,000 |
| 4. | Fax machine | 1 | 9 | 10 | 2000 | 2,40,000 |
| 5. | Xerox machine | 2 | 9 | 11 | 4000 | 5,28,000 |
| 6. | Bikes (MTS) |  | 16 | 16 | 1500 | 2,88,000 |
| 7. | *New Motorcycles (MTS) |  | 5 | 5 |  | 4,00,000/- |
| Total |  |  |  |  |  | 27,96,400/- |

*Purchase of 5 additional bikes for MTS is required. The guideline on cost of MTS motorcycles needs to be revised for the State. Previously, 110 cc motorcycles were purchased according to the guidelines for MTS. Since Mizoram is a hilly area, and the roads apart from the national highway and state highways are extremely difficult. For the purpose of Monitoring, a 110cc motorcycles is not practical except for few districts in the State. At worst, a 150cc motorcycles will be needed to navigate the rural area roads of  Lawngtlai, Saiha, Lunglei and Mamit. And these are High Priority Districts.  150cc – 180cc motorcycles with complete registration and insurance is estimated @  Rs 80,000/- per bike.

NRHM FLEXI POOL : NVBDCP

The State requirement for RDK and ACT-AL is calculated as per guideline with an expected increase of 15% consumption from the actual consumption during 2013 with 25% as buffer stock.

| - REQUIREMENT OF RDK (Bi-valent) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SL.NO. | Name of District |  |  | Unit of measurement |  | JAN - DEC 2013 consumption |  |  |  | 40% increased (15% increased consumption and 25% buffer stock) |  |  | TOTAL REQUIREMENT FOR 2014-2015 |  |  |  |  |
| i | ii |  |  | iii |  | iv |  |  |  | v |  |  | vi (iv+v) |  |  |  |  |
| 1 | Aizawl East |  |  | Test |  | 17317 |  |  |  | 6927 |  |  | 24244 |  |  |  |  |
| 2 | Aizawl West |  |  | Test |  | 13017 |  |  |  | 5207 |  |  | 18224 |  |  |  |  |
| 3 | Kolasib |  |  | Test |  | 9497 |  |  |  | 3799 |  |  | 13296 |  |  |  |  |
| 4 | Mamit |  |  | Test |  | 10010 |  |  |  | 4004 |  |  | 14014 |  |  |  |  |
| 5 | Champhai |  |  | Test |  | 9357 |  |  |  | 3743 |  |  | 13100 |  |  |  |  |
| 6 | Serchhip |  |  | Test |  | 5661 |  |  |  | 2265 |  |  | 7926 |  |  |  |  |
| 7 | Lunglei |  |  | Test |  | 22544 |  |  |  | 9018 |  |  | 31562 |  |  |  |  |
| 8 | Lawngtlai |  |  | Test |  | 19039 |  |  |  | 7616 |  |  | 26655 |  |  |  |  |
| 9 | Saiha |  |  | Test |  | 6173 |  |  |  | 2470 |  |  | 8642 |  |  |  |  |
| Total |  |  |  |  |  | 112615 |  |  |  | 45049 |  |  | 157664 |  |  |  |  |
|  | State Hqr. |  |  | Test |  | 5% for State Hqr |  |  |  |  |  |  | 7884 |  |  |  |  |
| TOTAL REQUIREMENT OF RDK (Bi-valent) |  |  |  |  |  |  |  |  |  |  |  |  | 165548 |  |  |  |  |
| - REQUIREMENT OF ACT-AL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SL.NO. | Name of District | 2013 CONSUMPTION | 40% increase (15% increased consumption and 25% as buffer stock) |  | TOTAL QUANTITY (ADULT + CHILDREN) REQUIRED FOR 2014-2015 |  | REQUIREMENT OF ACT - AL (ADULT) FOR THE YEAR 2014-2015 |  | REQUIREMENT OF ACT (CHILDREN) FOR THE YEAR 2014-2015 |  | AGE WISE REQUIREMENT OF ACT-AL FOR THE YEAR 2014-2015 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | (5 mths-3 Yrs) (30% of g) | 3 yrs. - 8 yrs. (32% of g) |  |  | 9-14 yrs. (38% of g) |  |
| a | b | c | d |  | e |  | f |  | g |  | h | i |  |  | J |  |
| 1 | Aizawl East | 177 | 70.8 |  | 247.8 |  | 148.68 |  | 99.12 |  | 29.736 | 31.7184 |  |  | 37.6656 |  |
| 2 | Aizawl West | 231 | 92.4 |  | 323.4 |  | 194.04 |  | 129.36 |  | 38.808 | 41.3952 |  |  | 49.1568 |  |
| 3 | Kolasib | 276 | 110.4 |  | 386.4 |  | 231.84 |  | 154.56 |  | 46.368 | 49.4592 |  |  | 58.7328 |  |
| 4 | Mamit | 1574 | 629.6 |  | 2203.6 |  | 1322.16 |  | 881.44 |  | 264.432 | 282.0608 |  |  | 334.9472 |  |
| 5 | Champhai | 70 | 28 |  | 98 |  | 58.8 |  | 39.2 |  | 11.76 | 12.544 |  |  | 14.896 |  |
| 6 | Serchhip | 55 | 22 |  | 77 |  | 46.2 |  | 30.8 |  | 9.24 | 9.856 |  |  | 11.704 |  |
| 7 | Lunglei | 3508 | 1403.2 |  | 4911.2 |  | 2946.72 |  | 1964.48 |  | 589.344 | 628.6336 |  |  | 746.5024 |  |
| 8 | Lawngtlai | 4081 | 1632.4 |  | 5713.4 |  | 3428.04 |  | 2285.36 |  | 685.608 | 731.3152 |  |  | 868.4368 |  |
| 9 | Saiha | 368 | 147.2 |  | 515.2 |  | 309.12 |  | 206.08 |  | 61.824 | 65.9456 |  |  | 78.3104 |  |
|  |  | 10340 | 4136 |  | 14476 |  | 8686 |  | 5790 |  | 1737 | 1853 |  |  | 2201 |  |
| 10 | State Hqr. | 5% of the total requirement is to be kept at the State Hqr. as buffer stock |  |  | 724 |  | 435 |  | 290 |  | 87 | 93 |  |  | 111 |  |
| TOTAL REQUIREMENT OF ACT-AL |  |  |  |  | 15201 |  | 9121 |  | 6080 |  | 1824 | 1946 |  |  | 2312 |  |

- Fund requirement under NRHM Flexi Pool :

- RDK (Bi-Valent)

| Sl.No. | Particulars | Unit of measurement | Quantity | Rate (In Rupees) | Amount (In Lakhs) |
| --- | --- | --- | --- | --- | --- |
| 1 | RDK (Bivalent) | Test | 165548 | 60.00 | 99.33 |

b.   ACT-AL

| Sl.No. | Particulars | Unit of Measurement | Quantity | Rate (in Rupees) | Amount Required (In Lakhs) |
| --- | --- | --- | --- | --- | --- |
| 1 | Adult | Per Kit | 9121 | 180.00 | 16.42 |
| 2 | 5 mths - 3 yrs. | Per Kit | 1824 | 50.00 | .92 |
| 3 | 3 - 8 yrs. | Per Kit | 1946 | 115.00 | 2.24 |
| 4 | 9-14 yrs | Per Kit | 2312 | 140.00 | 3.24 |
| TOTAL |  |  |  |  | 22.82 |

- Total funds required from NRHM flexi pool is : Rs 122,15,000/-

| SL.NO | PARTICULARS | FUND REQUIRED (in lakhs) |
| --- | --- | --- |
| 1 | RDK (Bi-Valent) | 99.33 |
| 2 | ACT-AL | 22.82 |
| 3 | Total | 122.15 |