PROGRAMME IMPLEMENTATION PLAN 2014-15 FOR NATIONAL PROGRAMME FOR

PREVENTION AND CONTROL OF DEAFNESS (NPPCD), MIZORAM

NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF DEAFNESS

Hearing loss is the most common sensory deficit in humans today. As per WHO estimates in India, there are approximately 63 million people, who are suffering from significant auditory impairment; this places the estimated prevalence at 6.3% in Indian population. As per NSSO survey, currently there are 291 persons per one lakh population who are suffering from severe to profound hearing loss (NSSO, 2001). Of these, a large percentage is children between the ages of 0 to 14 years. With such a large number of hearing impaired young Indians, it amounts to a severe loss of productivity, both physical and economic. An even larger percentage of our population suffers from milder degrees of hearing loss and unilateral (one sided) hearing loss.

OBJECTIVES OF THE PROGRAMME

- To prevent avoidable hearing loss on account of disease or injury.

- Early identification, diagnosis and treatment of ear problems responsible for hearing loss and deafness.

- To medically rehabilitate persons of all age groups, suffering with deafness.

- To strengthen the existing inter-sectoral linkages for continuity of the rehabilitation programme, for persons with deafness.

- To develop institutional capacity for ear care services by providing support for

equipment, material and training personnel.

Long term objective: To prevent and control major causes of hearing impairment and deafness, so as to reduce the total disease burden by 25% of the existing burden by the end of 12th Five Year Plan.

COMPONENTS OF THE PROGRAMME

- Manpower training and development – For prevention, early identification and management of hearing impaired and deafness cases, training would be provided from medical college level specialists (ENT and Audiology) to grass root level workers.

- Capacity building – for the district hospital, community health centers and primary health center in respect of ENT/ Audiology infrastructure.

- Service provision–Early detection and management of hearing and speech impaired cases and rehabilitation, at different levels of health care delivery system.

- Awareness generation through IEC/BCC activities – for early identification of hearing impaired, especially children so that timely management of such cases is possible and to remove the stigma attached to deafness.

STRATEGIES

- To strengthen the service delivery for ear care.

- To develop human resource for ear care services.

- To promote public awareness through appropriate and effective IEC strategies with special emphasis on prevention of deafness.

- To develop institutional capacity of the district hospitals, community health centers and primary health centers selected under the Programme.

State level:

State Cell-

To strengthen Monitoring of the programme at State level. The Cell will be manned by following Manpower on contractual basis.

- Consultant 1 (Monthly salary of Rs. 50000/-)*

- Programme Assistant: 1 (Monthly salary of Rs. 15000/- )*

- Data Entry Operator 1 (Monthly salary of Rs. 15000/- )*

State Health Society and Programme Committee (under NRHM)-

Already constituted state mission under NRHM will look into the activities at state level. Under the programme, funds will be transferred to State Health Society, for carrying out various activities through District Health Society.

Functions

- Preparation of District plans for implementation of National Programme for prevention and control of Deafness.

- Monitor and supervise Implementation of National Programme for Prevention and Control of Deafness in the state in reference to the programme activities related to training of Medical and non-medical professionals, IEC and Social mobilization and Manpower development.

- Release and monitor flow of funds to District Health Societies.

- Review and take appropriate measures in the expenditure of funds by District Health Society.

State Nodal Officer-

State Nodal Officer preferably an ENT surgeon at the directorate/ Secretariat level will provide technical guidance and expertise to the State Health Society for the purpose of implementation of the programme in the various districts of the state.

District level

District Health Society and Programme Committee (under NRHM)-

Functions

- Planning : Preparation of District Micro-plan based on magnitude and distribution of deaf/hearing impaired persons and resources available for ear care.

- Implementation of the programme through utilization of government facilities, involvement of NGOs and community participation.

- Monitoring of programme: activities and quality control.

- Financial and Material Management ;

- Social mobilization and public awareness

- Orientation of various functionaries of health and other related sectors.

- Procurement of equipments and other materials.

- Arrangements for screening camps- through identified NGOs, having adequate infrastructure for carrying out activities under the programme.

- Monitoring and Financial Assistance for organizing camps.

District Hospital:

It is proposed to strengthen the ear care services at district level by providing manpower support such as one ENT Surgeon, one Audiologist, one Audiometric Assistant and one Instructor for hearing impaired at each district on contractual basis.

- ENT Surgeon: An ENT Surgeon with Post Graduate Qualification wherever ENT specialists are not present in the district hospital. The job responsibility of the Contractual ENT surgeon will be as under:

- To provide ENT Clinical Services at the District Hospital,

- Conducting Training Programmes

Proposed salary: Rs 60,000 per month with a yearly increment of 10%.

- Audiologist (Audiologist & Speech language Pathologist): A technical person with 4 years graduation in Audiology & Speech language Pathology. The job responsibility of the Audiologist will be as under:

- Provision of audiological services & prescribing hearing aids

- Assist in training programmes

- Monitoring and Evaluation of the Programme

- Maintenance of Database

Proposed Salary: Rs. 30,000 per month with a yearly increment of 10%.

- Audiometric Assistant: A technical person with 1 year diploma in Audiology. The audiometric assistant will provide support to CHC in screening of HI persons. The job responsibility of the Audiologist will be as under:

- Assist in providing audiological services

- Visit CHC by visiting on fixed day for screening of HI persons

- Assist in training programmes

- Monitoring and Evaluation of the Programme

- Maintenance of Database

Proposed Salary: Rs. 15,000 per month with a yearly increment of 10%.

- Instructor for the Young Hearing Impaired Children: It is proposed that a Instructor may be inducted on contractual basis, to look after the therapy and training of the young hearing impaired children at the district level. The job responsibility of the Instructor will be to provide training, therapy and early education for the young hearing impaired children.

Proposed salary: Rs. 15000 per month with a yearly increment of 10%.

SERVICE DELIVERY AND REFERRAL SYSTEM

- Primary level- CHCs/PHCs/SCs/Primary School teachers/Health Workers/Panchayat

Functions:

- Early identification of cases of hearing impairment and their management in collaboration with NRHM (RBSK- Rashtriya Bal Swasthya Karyakram).

- Primary ear care.

- Promoting public awareness in respect of prevention of deafness.

- Sensitization training of health workers.

- Support to School Ear care programme.

- Secondary level- District Hospital

Functions:

- Management of cases referred from PHCs/CHCs.

- Organization of Ear care screening camps in collaboration with NRHM and Ministry of Social Justice & Empowernment (M/o SJ&E) .

- Organization of School Ear Care Programme.

- Training of manpower- PHC doctors, nurses, Audiometric assistants, health workers, school teachers.

PROGRAMME COMPONENTS

1. 	MANPOWER TRAINING & DEVELOPMENT

Objectives:

- To orient all the Health Care personnel from the district to grassroot level about prevention, promotion, early identification and rehabilitation of all types of ear diseases leading to deafness.

- To make these personnel aware of the existing facilities available for deafness in order to facilitate appropriate referral.

- To sensitize the health care personnel regarding their specific roles in the programme.

- To enable the health providers to provide a leadership role in creating awareness about hearing impairment.

- To facilitate development of suitable manpower, in order to be able to implement this programme in the entire nation, in a phased manner.

Training would be imparted to the following functionaries at all levels:

- Sensitization of the State medical college experts

- District level ENT officers

- Sensitization of Audiologists

- Medical Officers under CHC/PHC

- Obstetricians and Pediatricians at the district and CHC level

- Medical Officer under School Health Scheme

- Medical Officers involved in industrial health available in the district

- Multi Purpose Workers- male and female

- Primary School teachers at village level

- Functionaries at grass root level such as :

- Anganwadi workers

- Accredited Social Health Activist (ASHA)

- Trained Birth Attendants

A budgetary provision of Rs.10.00 lakhs per district has been made for above seven level training programmes.

SERVICE PROVISION INCLUDING REHABILITATION in collaboration with NRHM &

M/o SJ&E

Service components will include:

- Early detection

- Ear Screening camps

- Treatment: medical and surgical

- Appropriate referral

- Rehabilitation of hearing and speech disorders and hearing aid provision.

- Awareness creation in the community.

- Early Detection

- The detection would be by sensitized personnel at grass root level including family members/parents, selected school teachers, MPWs at sub centre level, Public Health Nurses & medical officers in PHCs and CHCs and district level personnel. Personnel at all levels would be assigned a specific task in order to ensure that the right guidance is provided at the appropriate time to the affected persons.

- House to house surveys will be conducted by the AWWs & ASHAs, under the supervision of the male and female MPWs for detection of cases of hearing impairment and deafness. The deafness cases will be noted in the disability column of ANM’s village register.

- The MPWs will maintain records of each family based on a Family performa provided to them.

- The District level Pediatricians and Gynecologists will be responsible for referring any child born of a high risk pregnancy or delivery, as well as other children who are exposed to a high risk factor in infancy and who show features suggestive of hearing impairment. These children will be screened by the district level ENT doctor / Audiologist with OAE and then subjected to diagnostic tests.

- School teachers will undertake to screen the children in the school with the help of pre-prepared proformas. These will help to identify children with any ear or hearing problem. They will then be referred to the School Health doctor for evaluation, diagnosis and guidance regarding treatment.

- Ear Screening Camps

Functions

- Screening camps will be organized in collaboration with NRHM (RBSK)/ M/o SJ&E at the PHC/CHC and District level for screening the general population in respect of ear problems, hearing impairment and deafness.

- Detection and treatment of common ear problems.

- Spreading awareness regarding ear problems, early detection of deafness, available treatment and health care facilities for referral of such cases.

- Education of community, especially the parents of young children regarding importance of right feeding practices, various common ear problems, early of deafness in young children and available treatment for hearing impairment/deafness.

- Education of Panchayat members, members of Mahila Mandals and Youth leaders.

Conduct of Screening Camps

- Ear screening camps will be conducted by the PHC/CHC doctors and district level ENT specialists, trained under the programme.

- The screening camps will be facilitated in collaboration with NRHM (RBSK) or by the NGOs, identified by the M/o SJ&E/ District Health Society. These NGOs will require adequate infrastructure to carry out screening camps and experience of work at the community level.

- One screening camp will be organized per month at any PHC or CHC or District hospital by rotation.

Budget: No budgetary provision has been made for screening camps under NPPCD.

3. 	Treatment

Treatment of all affected persons would be undertaken at the following levels:

- Public Health Nurses and MPWs: would provide treatment of common ear ailments such as Wax, Acute Suppurative Otitis Media etc. under the guidance of the PHC doctor. The Public Health Nurses &MPWs will have the capacity to distribute relevant ear drops and medicines under the guidance of the PHC doctor.

- Trained PHC/CHC doctors will provide early diagnosis of ear diseases and treatment of all common ear ailments. All persons requiring special diagnostic facilities, complicated cases and those needing surgical intervention will be referred to the District hospital.

- District hospital: The District level ENT doctors and Audiologists will provide comprehensive preventive, promotive and curative and medical rehabilitative services. Wherever feasible, suitable linkages would be developed with the Comprehensive Rehabilitation Centres (CRC) and DDRC in coordination with the Ministry of Social Justice & Empowerment, for provision of rehabilitative services.

- The District level Paediatricians will also be responsible for treating ear diseases such as Acute Otitis media, so that progress to Deafness can be prevented.

4. 	Referral services:

Effective linkages would be developed from peripheral level to district level with the help of functionaries and personnel from grass root level (AWW, ASHA and sensitized parents and PRIs), subcentre level (Male and female MPWs), PHC level medical officers, Public health nurses, School teachers and School health doctors, ENT private practitioners and District level officers.

5. 	Rehabilitation and Hearing Aid provision:

- All patients who are identified as having an ear problem that either requires surgery, hearing aid fitting or rehabilitative therapy will be referred to the ENT doctor and Audiologist at the district level.

- Those who need surgery will be given the appropriate treatment at the district hospital.

- Complicated cases that cannot be adequately handled at the District hospital will be further referred to the State Medical College for expert treatment.

- Patients who suffer with Sensorineural hearing loss that is not amenable to medical or surgical correction and which requires hearing aid, will be fitted with the same at the district level which will be provided by Ministry of Social Justice &Empowerment. This will include children who are suffering with Bilateral sensorineural hearing loss.

- The hearing aids will be issued as per existing rules. It is proposed that collaboration with the Ministry of Social Justice & Empowerment will be established for this purpose.

- The requirement for Speech therapy and Hearing therapy will be met with by the Audiologist at the District level.

Budget- Under NPPCD, no budgetary allocation has been kept separately for provision of hearing aids.

6. 	Awareness Creation among Parents/ community:

- Community level health workers and doctors will undertake this activity on a continuous basis. This will also form a part of the IEC activities at\various levels.

- Sensitization will be done regarding various aspects relating to early detection of hearing loss. They will be educated about the various ill effects of hearing loss on the speech, mental and social development of the child.

- Information regarding various treatment modalities as well as techniques of rehabilitation.

- Sensitization to ill effects of hearing loss in the elderly so that they may refer the aged hearing impaired persons for suitable management/rehabilitation.

Budget: Provision of Rs 20.00 lakhs at State level and in addition Rs 2.00 lakhs at each district level has been kept for IEC activities under NPPCD.

CAPACITY BUILDING

- At the PHC and CHC level: for screening of ear morbidity and detection of hearing loss, the equipment required would be:

PHC Kit which will consist :

- Head Lights

- Ear Speculas

- Ear Syringes

- Otoscope

- Jobson Horne Probes

- Tuning forks of 256, 512, 1024 Hz

- Noise Maker

- Pure tone audiometer (only for CHC)

.

Logistics/Medicines :

Medicine kit i.e. Borospirit ear drops, wax dissolving drops and Antibiotic ear drops, including cotton swabs and normal saline solution, for use by the Health care workers.

Budget : Provision of Rs. 20,000/- per kit for PHC and Rs 50,000 per kit for CHC has been kept.

- District hospital:

The District hospital is to be an important center for the management of ear problems and deafness cases, which are referred from the health care facilities at various levels.

Provision of following equipments has been made-

Equipment required

- Microscope

- 2 sets of Microdrills with 2 handpeices and burrheads

- 2 sets of micro-ear surgery instruments.

- Pure Tone Audiometer

- Impedance Audiomter

- OAE machine

- Sound treated room

Budget : Provision of Rs. 20.00 lakh per district hospital has been kept.

.

Programme Proposal in Mizoram

The National Programme for Prevention and Control of Deafness (NPPCD) have not been implemented in the State of Mizoram. It is proposed to implement the NPPCD programme in 3 districts of Mizoram – Aizawl East District, Aizawl West District and Lunglei District.

Aizawl East District will cover –

- District Hospital 			-	1

- Community Health Centre	-	3

- Primary Health Centre		-	5

Aizawl West District will cover –

- District Hospital			-	1

- Community Health Centre	-	1

- Primary Health Centre		-	6

Lunglei District will cover –

- District Hospital			-	1

- Community Health Centre	-	1

- Primary Health Centre		-	9

CAPACITY BUILDING

PHC & CHC : 	For screening of ear morbidity and detection of hearing loss, the equipment required would be :

Total number of CHC & PHC = 25

| Sl.No | Name of equipments | No. reg. | Rate (Rs) | Total in lakh |
| --- | --- | --- | --- | --- |
|  | Bull’s Eye Camp | 24 | 2,000 | 0.48 |
|  | Head mirror | 24 | 500 | 0.12 |
|  | Head light | 24 | 50,000 | 12.00 |
|  | Aural Specula set | 24 | 500 | 0.12 |
|  | Otoscope | 24 | 7,000 | 1.68 |
|  | Noise Maker | 24 | 500 | 0.12 |
|  | Josson Horne Probe | 24 | 150 | 0.036 |
|  | Tunning Fork | 24 | 1,000 | 0.24 |
|  | Ear Syringe | 24 | 700 | 0.168 |
|  | Total |  | Total | Rs 14.964 |

District Hospital : 	The District Hospital is to be an important centre for the management of ear problem and deafness cases, which are referred from the health facilities at various levels.

The two district hospitals, namely Civil Hospital, Aizawl and Civil Hospital, Lunglei will be included in the programme. The requirement for the district hospital are :

| Sl.No | Name of equipments | No. reg. | Rate (Rs) | Total in lakh |
| --- | --- | --- | --- | --- |
|  | Operating Microscope | 2 | 15,00,000 | 30.00 |
|  | Sets of Microdrills with hand pliers and burr heads | 4 | 5,000 | 2.00 |
|  | Microsurgery instruments | 4 | 2,00,000 | 8.00 |
|  | Audiometer (Diagnostic) | 2 | 5,50,000 | 11.00 |
|  | Audiometer (Screening) | 2 | 60,000 | 1.20 |
|  | OAL machine | 2 | 5,00,000 | 10.00 |
|  | Sound treated Room | 2 | 1,00,000 | 2.00 |
|  |  |  | Total | Rs 64.2 |

Format for submission of PIP 2014-15 under National Programme for Prevention & Control of Deafness

- Programme Execution & expansion-

Presently National Programme for Prevention and Control of Deafness is being implemented in Nil Districts of the State. It is proposed to include another 3  District in year 2013-14 under the programme.

The districts selected for the implementation of the Programme are-

| Sl.No | Existing district under NPPCD | Proposed districts under NPPCD (2014-15) |
| --- | --- | --- |
| 1 | Nil | Aizawl East District |
| 2 | Nil | Aizawl West District |
| 3 | Nil | Lunglei District |

- Presents status of implementation of the programme in the existing districts of the state.

| Sl.No | Districts name | Equipments procured | Manpower recruited | Training conducted | No.of Screening camps conducted | No.of hearing aids distributed |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Nil | Nil | Nil | Nil | Nil | Nil |
| 2 | Nil | Nil | Nil | Nil | Nil | Nil |
| 3 | Nil | Nil | Nil | Nil | Nil | Nil |

- Time line of activities

| Sl. No | Activities | 1st Quarter | 2nd Quarter | 3rd Quarter | 4th Quarter |
| --- | --- | --- | --- | --- | --- |
| 1 | Training : 1-7 level (to be mentioned here separately) |  |  | - District Level ENT Officers, sensitization of Audiologists - Medical Officers under CHC/PHC - Obstetricians and Pediatricians at the district and CHC level - Medical Officer under School Health Scheme | - Multi Purpose Workers-male and female - Primary School teachers at village level - Functionaries at grass root level such as - Anganwadi workers - Accredited Social Health Activist (ASHA) - Trained Birth Attendants |
| 2 | Procurement of Equipments - PHC Kits - CHC Kits - District Hospital - Sound treated room |  |  | - PHC Kits - CHC Kits - District Hospital - Sound treated room |  |
| 3 | Recruitment of - ENT Surgeon (where not available - Audiologist - Audiometric Assistant - Instructor for Hearing Impaired |  |  | - ENT Surgeon (where not available - Audiologist - Audiometric Assistant - Instructor for Hearing Impaired |  |
| 4 | Organizing Screening camps in collaboration with NRHM/Ministry of SJ &E |  |  | Organizing Screening camps in collaboration with NRHM/Ministry of SJ &E | Organizing Screening camps in collaboration with NRHM/Ministry of SJ &E |
| 5 | IEC activities |  |  | IEC activities | IEC activities |
| 6 | Public Private Partnership |  |  | Public Private Partnership | Public Private Partnership |
| 7 | Monitoring cell at State level |  |  | Monitoring cell at State level | Monitoring cell at State level |

National Programme for Prevention and Control of Deafness (NPPCD)

PIP 2014-15

| FMR Code | Components of NPPCD | Physical Target | Funds Required in lakhs | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Recurring grant |  |  |  |
| L.1.3 | Man power at district level | 3 |  |  |
| L.1.3.a | -ENT Surgeon @ Rs.60,000/-pm* | 3 | 21.6 |  |
| L.1.3.b | -Audiologist @ Rs.30,000/-pm* | 3 | 10.8 |  |
| L.1.3.c | -Audiometric Assistant @ Rs.15,000/- pm* | 3 | 5.40 |  |
| L.1.3.d | -Instructor for Hearing Impaired Children @ Rs.15,000/-pm* | 3 | 5.40 |  |
| L.1.4 | IEC/BCC acivities |  |  |  |
| L.1.4.a L.1.4.b | State Level @ Rs.20,00,000/-annually – District Level @ Rs.2,00,000/-annually | 1 3 | 20.00 6.00 |  |
| L.1.1 | NPPCD Monitoring Cell at state Level |  |  |  |
| L.1.1.a | -Consultant @ Rs.50,000/-pm*(1 no) | 1 | 6.00 |  |
| L.1.1.b | - Programme Assistant @ Rs.15,000/-pm* (1 No) | 1 | 1.80 |  |
| L.1.1.c | - DEO @ Rs.15,000/-pm* (1 No) | 1 | 1.80 |  |
| L.1.2 | Public Private Partnership - @ 41322 per district for 2014-15 for early identification |  |  |  |
| L.2 | Non-recurring grant-in-aid |  |  |  |
| L.2.1 | Training (Provision of TA/DA, including accommodation as per existing NRHM norms) |  |  |  |
|  | Level – I Level – II Level – III Level – IV Level – V Level – VI Level – VII |  |  |  |
|  | A budgetary provision of RS 10.00 lakh per district for above seven levels for training | 3 | 30.00 |  |
| L.2.1.a | Procurement of equipment |  |  |  |
| L.2.1.b | District Hospital @ 20.00 lakh/district | 3 | 60.00 |  |
| L.2.1.c | Sub-Divisional Hospital @ Rs 50,000/- per kit / CHC @ Rs 50,000/- kit | 5 | 2.50 |  |
| L.2.1.d | PHC @ Rs 15,000/- kit | 20 | 3.00 |  |
|  | TOTAL |  | 174.30 |  |

PROGRAMME IMPLEMENTATION PLAN FOR NATIONAL PROGRAMM FOR PREVENTION AND CONTROL OF DEAFNESS (NPPCD) 2015-16

In the year 2015-16 the programme is intended for expansion in 1 more district namely Saiha district which consist of :

- District hospital – 1

- CHC – 0

- PHC – 4

The following contractual staff will be recruited for Saiha district :

- ENT Surgeon – 1

- Audiologist – 1

- Audiometric Assistant – 1

- Instructor for hearing impaired children – 1

The above contractual staff will be posted at District Hospital, Saiha.

National Programme for Prevention and Control of Deafness (NPPCD)

PIP 2015-16

| FMR Code | Components of NPPCD | Physical Target | Funds Required in lakhs | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Recurring grant |  |  |  |
| L.1.3 | Man power at district level |  |  |  |
| L.1.3.a | -ENT Surgeon @ Rs.60,000/-pm* | 4 | 28.80 | 1 new district proposed |
| L.1.3.b | -Audiologist @ Rs.30,000/-pm* | 4 | 14.40 | 1 new district proposed |
| L.1.3.c | -Audiometric Assistant @ Rs.15,000/- pm* | 4 | 7.20 | 1 new district proposed |
| L.1.3.d | -Instructor for Hearing Impaired Children @ Rs.15,000/-pm* | 4 | 7.20 | 1 new district proposed |
| L.1.4 | IEC/BCC acivities |  |  |  |
| L.1.4.a L.1.4.b | State Level @ Rs.20,00,000/-annually – District Level @ Rs.2,00,000/-annually | 1 4 | 20.00 8.00 | 1 new district proposed |
| L.1.1 | NPPCD Monitoring Cell at state Level |  |  |  |
| L.1.1.a | -Consultant @ Rs.50,000/-pm*(1 no) | 1 | 6.00 | 1 new district proposed |
| L.1.1.b | - Programme Assistant @ Rs.15,000/-pm* (1 No) | 1 | 1.80 | 1 new district proposed |
| L.1.1.c | - DEO @ Rs.15,000/-pm* (1 No) | 1 | 1.80 | 1 new district proposed |
| L.1.2 | Public Private Partnership - @ 41322 per district for 2014-15 for early identification |  |  |  |
| L.2 | Non-recurring grant-in-aid |  |  |  |
| L.2.1 | Training (Provision of TA/DA, including accommodation as per existing NRHM norms) |  |  |  |
|  | Level – I Level – II Level – III Level – IV Level – V Level – VI Level – VII |  |  |  |
|  | A budgetary provision of RS 10.00 lakh per district for above seven levels for training | 1 | 10.00 | 1 new district proposed |
| L.2.1.a | Procurement of equipment |  |  |  |
| L.2.1.b | District Hospital @ 20.00 lakh/district | 1 | 20.00 | 1 new district proposed |
| L.2.1.c | Sub-Divisional Hospital @ Rs 50,000/- per kit / CHC @ Rs 50,000/- kit |  |  |  |
| L.2.1.d | PHC @ Rs 15,000/- kit | 4 | 0.60 | 1 new district proposed |
|  | TOTAL |  | 125.80 |  |

PROGRAMME IMPLEMENTATION PLAN FOR NATIONAL PROGRAMME FOR PREVENTION AND CONTROL  OF DEAFNESS (NPPCD) 2016-17

In the year 2016-17 the programme is intended for expansion in 1 more district namely Champhai district which consist of :

- District hospital – 1

- CHC – 3

- PHC – 11

The following contractual staff will be recruited for Champhai district :

- ENT Surgeon – 1

- Audiologist – 1

- Audiometric Assistant – 1

- Instructor for hearing impaired children – 1

The above contractual staff will be posted at District Hospital, Champhai.

National Programme for Prevention and Control of Deafness (NPPCD)

PIP 2016-17

| FMR Code | Components of NPPCD | Physical Target | Funds Required in lakhs | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Recurring grant |  |  |  |
| L.1.3 | Man power at district level |  |  |  |
| L.1.3.a | -ENT Surgeon @ Rs.60,000/-pm* | 5 | 38.16 | 1 new district + 10% increment for staff employed in 2014-15 |
| L.1.3.b | -Audiologist @ Rs.30,000/-pm* | 5 | 19.08 |  |
| L.1.3.c | -Audiometric Assistant @ Rs.15,000/- pm* | 5 | 9.60 |  |
| L.1.3.d | -Instructor for Hearing Impaired Children @ Rs.15,000/-pm* | 5 | 9.60 |  |
| L.1.4 | IEC/BCC acivities |  |  |  |
| L.1.4.a L.1.4.b | State Level @ Rs.20,00,000/-annually District Level @ Rs.2,00,000/-annually | 1 5 | 20.00 10.00 | 1 new district proposed |
| L.1.1 | NPPCD Monitoring Cell at state Level |  |  |  |
| L.1.1.a | Consultant @ Rs.55,000/-pm*(1 no) | 1 | 6.60 | 10% increment |
| L.1.1.b | Programme Assistant @ Rs.16,500/-pm* (1 No) | 1 | 2.00 | 10% increment |
| L.1.1.c | DEO @ Rs.16,500/-pm* (1 No) | 1 | 2.00 | 10% increment |
| L.1.2 | Public Private Partnership - @ 41322 per district for 2014-15 for early identification |  |  |  |
| L.2 | Non-recurring grant-in-aid |  |  |  |
| L.2.1 | Training (Provision of TA/DA, including accommodation as per existing NRHM norms) |  |  |  |
|  | Level – I Level – II Level – III Level – IV Level – V Level – VI Level – VII |  |  |  |
|  | A budgetary provision of RS 10.00 lakh per district for above seven levels for training | 1 | 10.00 | 1 new district proposed |
| L.2.1.a | Procurement of equipment |  |  |  |
| L.2.1.b | District Hospital @ 20.00 lakh/district | 1 | 20.00 | 1 new district proposed |
| L.2.1.c | Sub-Divisional Hospital @ Rs 50,000/- per kit / CHC @ Rs 50,000/- kit | 3 | 1.50 | 1 new district proposed |
| L.2.1.d | PHC @ Rs 15,000/- kit | 11 | 1.65 | 1 new district proposed |
|  | TOTAL |  | 150.19 |  |

Format for submission of information by States/UTs under National Programme for Prevention and Control of Deafness (NPPCD)

- Total Number of districts-  3

- Prevalence of Hearing Impairment –  14000 approx. in Aizawl Dist. 8000 approx. in Lunglei Dist.

- Number and Name of districts where ENT surgeon (s) is posted in the District Hospital –  2 Districts – Aizawl Dist. & Lunglei Dist.

- Number and Name of districts where Audiologist/Audiological Assistant is posted in the District Hospital – 1 – Civil Hosp. Aizawl.

- Number of CHCs and PHCs districts – wise – 	Aizawl East :  CHC – 3		PHC – 5

Aizawl West: CHC – 1		PHC – 5

Lunglei Dist : CHC – 1		PHC – 9

- Manpower availability –

| Sl.No | District Name | Number available |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ENT Doctors | Audiologist | Obstetricians | Paediatricians | Medical Officers | PHNs | MPW Supervisors | CDPQs | Anganwadi Supervisors | ASHAs | TBAs | Primary School Teacher |
| 1 | Aizawl East. | 6 at Civil Hospital, Aizawl. | 1 at Civil Hospital, Aizawl | 8 at Civil Hospital, Aizawl | 6 at Civil Hospital, Aizawl | 10 | 277 | 198 | 4 | 238 | 124 | 36 | 866 |
| 2 | Aizawl West |  |  |  |  | 10 | 76 | 171 | 3 | 254 | 119 | 48 | 570 |
| 3 | Lunglei dist. | 1 | Nil | 1 | 1 | 11 | 100 | 167 | 4 | 383 | 183 | 55 | 855 |

- Equipment availability –

| Sl. No | District Name | Equipments available at District Hospital |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ENT Operating Microscope | Microdrills with burrheads | Micro-ear surgery instruments | OAE Machine | Pure tone Audiometer | Impedance Audiometer | Sound Treated Room |
| 1 | Aizawl East | Civil Hospital, Aizawl | Civil Hospital, Aizawl | Civil Hospital, Aizawl | Nil | Civil Hospital, Aizawl | Civil Hospital, Aizawl | Nil |
| 2 | Aizawl West | Nil | Nil | Nil | Nil | Nil | Nil | Nil |
| 3 | Lunglei | Nil | Nil | Nil | Nil | Nil | Nil | Nil |