Operationalizing MDR Software Training plan in the State of Mizoram

Though the GOI Guideline suggest to  identify only 3-5 districts for rolling out of MDR software at the initial stage, but it has been proposed to cover all 9 districts in the State wherever MD reporting is possible by using the software. Accordingly MDR Software training and its implementation plan has been formulated for all 9 districts covering 8 DHs, 2 SDHs, 9 CHCs, 57 PHCs, 8 UPHCs and 13 Private Hospitals.

As per the guiding note training will be conducted in 2 phases – 1st training – for creating a pool of Master Trainers for State and Districts. Trainers for this pool will be drawn from AVNI. 2 phase training – Block level training – State and districts Master trainers will conduct this training for Block/Facilities persons.

Budget requirement for the above trainings is worked out as tabulated below:

SUMMARY BUDGET:

| Sl.No | Budget Heads | Amount (Rs) |
| --- | --- | --- |
| 1 | Phase I ( Master Training) | 1,74,800/- |
| 2 | Phase II ( Block/Facility Level Training) | 5,10,000/- |
| 3 | Miscellaneous Expenses | 34,400/- |
|  | Expenditure to be incurred for Resource person from AVNI for phase I & II | 1,39,500 |
| Total |  | 8,58,700/- |

Rupee Eight lakhs Fifty Eight Thousand Seven Hundred only

DETAILED BUDGET:

PHASE I:

DAY 1:

State Level Master Training ( To be trained by AVNI)

1. Target Load			= 20

2. No of Batches		= 1

3. Participants per batch	= 20

4. Duration of Training	= 1 day

| Components | Rate/day (Rs) | No of days | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 1 | 20 | 14,000 |
| Training Materials | 250 | - | 20 | 5000 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 1000 | 1 |  | 1000 |
| TA | - | - | - | - |
| Total |  |  |  | Rs. 26,000/- |

# Budget for 1batches = 1X Rs. 26,000 /- = Rs. 26,000 /-

# Day 2:

District Level Master Training ( To be trained by AVNI)

1. Target Load			= 40

2. No of Batches		= 2

3. Participants per batch	= 20

4. Duration of Training		= 1 day

| Components | Rate/day (Rs) | No of days ( DA to trainees will be disbursed including transit day and hence budget is calculated for 3 days) | No of Participants/ batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 3 | 20 | 42,000/- |
| Training Materials | 250 | - | 20 | 5,000/- |
| Working Lunch, Tea & Snacks | 200 | 1 | 25 | 5,000/- |
| Venue Hiring | 1000 | 1 |  | 1,000/- |
| TA | 1070 | - | 20 | 21,400/- |
| Total |  |  |  | Rs. 74,400/- |

# Budget for 2 batches = 2X Rs. 74,400 /- = Rs. 1,48,800 /-

# Sub Total for Phase I = Rs.1,74,800/-

# As recommended by the Dr. Dhawal AVNI, expenditure to be incurred for Resource person from AVNI for Phase I & II.

# Phase I budget requirement estimation for resource Persons.

| # S.No | # Component | # Rate | # No of Person | # No of Days | # Amount # (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| # 1 | # Resource Person Travel | # 15000 | # 2 | # 2 days # (To and Fro) | # 60,000 |
| # 2 | # Resource Person Local Travel | # 500 | # 2 | # 3 | # 3,000 |
| # 3 | # Resource person stay | # 3500 | # 2 | # 3 | # 21,000 |
| # 4 | # Resource person honrarium | # 1000 | # 2 | # 3 | # 6,000 |
| # 5 | # Per Diem | # 500 | # 2 | # 3 | # 3,000 |
| # TOTAL |  |  |  |  | # 93,000 |

# Sub Total Rs. 93,000/-

# Phase II budget requirement estimation for resource Persons.

| # S.No | # Component | # Rate | # No of Person | # No of Days | # Amount # (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| # 1 | # Resource Person Travel | # 15000 | # 1 | # 2 days # (To and Fro) | # 30,000 |
| # 2 | # Resource Person Local Travel | # 500 | # 1 | # 3 | # 1,500 |
| # 3 | # Resource person stay | # 3500 | # 1 | # 3 | # 10,500 |
| # 4 | # Resource person honrarium | # 1000 | # 1 | # 3 | # 3,000 |
| # 5 | # Per Diem | # 500 | # 1 | # 3 | # 1,500 |
| # TOTAL |  |  |  |  | # 46,500 |

# Sub Total Rs. 46,500/-

# Total budget requirement for resource Persons for Phase I & II is Rs. 1,39,500/- as recommended by AVNI.

# PHASE II:

Training for Block/Facility including Private Facilities in all Districts (To be trained by State/District Master Trainers)

1. Target Load			= 200

2. No of Batches		= 10

3. Participants per batch	= 20

4. Duration of Training		= 1 day

| Components | Rate/day (Rs) | No of days ( DA to trainees will be disbursed including transit day and hence budget is calculated for 3 days) | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 3 | 20 | 24,000/- |
| Honorarium of Resources Person | 1000 | 1 | 3 | 3,000/- |
| Training Materials | 250 | - | 20 | 5,000/- |
| Working Lunch, Tea & Snacks | 200 | 1 | 20 | 4,000/- |
| Venue Hiring | 1000 | 1 |  | 1,000/- |
| TA of Trainees | 700 | - | 20 | 14,000/- |
| Total |  |  |  | Rs. 51,000/- |

# Budget for 10 batches = 10 x Rs. 51,000 /- = Rs.5,10,000/-

Sub Total for Phase II = Rs.5,10,000/-

Other Miscellaneous expenses:

- Hiring of Vehicle for Master Trainers @ Rs.18 Per k.m (Approximate estimated distance to be covered for each training is 300 k.m ( i.e 150 km each for to & fro)) @ Rs.18 per k.m = 18 x 300 + 2000 for night halt charge  = Rs. 7,400/-

- DA for Master trainers on transit days @ Rs.500/- per day for 3 persons = 500 x 18 days x 3 = Rs.27,000/-

Sub Total for Miscellaneous expenses = Rs.34,400/-

Training Calender

| Sr.No | Training Proposed | No of Batches | Tentative plan |
| --- | --- | --- | --- |
| A |
| 1 | State Official | 1 | September,2014 |
| 2 | District Hqtrs Official | 2 | September,2014 |
| B |
| 1 | Aizawl East District | 1 | October,2014 |
| 2 | Aizawl West District | 2 | October,2014 |
| 3 | Champhai District | 1 | Noveber,2014 |
| 4 | Kolasib District | 1 | October,2014 |
| 5 | Lawngtlai District | 1 | December,2014 |
| 6 | Lunglei District | 1 | December,2014 |
| 7 | Mamit District | 1 | Noveber,2014 |
| 8 | Saiha District | 1 | December,2014 |
| 9 | Serchhip District | 1 | Noveber,2014 |
|  | Total B | 10 Batches |  |