STATE VECTOR BORNE DISEASE CONTROL PROGRAMME, Mizoram

Supplementary PIP for inclusion in NRHM for the year 2014-2015

INTRODUCTION:

The SVBDCP, Mizoram is very grateful to the Central Government for assisting the State financially and materially in the control of vector borne diseases especially Malaria. Much has been accomplished through the aid and guidance provided. Although the indigenous malaria disease incidence and death rate are declining, there still remain much to be done. Malaria still remain a major public health problem in the state. Beside indigenous Malaria, Dengue and Japanese Encephalitis posses a potential threat to the State. Dengue Control Programme was initiated during 2012-2013 and cases have been detected in the approved Sentinel Surveillance Hospital : Civil Hospital Aizawl, although, no fatality case have been reported. As Culex Mosquitoes are prevalent in the state, there is also every possibility of Acute Encephalitis Syndrome / Japanese Encephalitis (JE) occurrence in the State. Lack of diagnostic kit in the State seems to be curtaining the disease prevalence as there is a recorded case of two patients succumbing to J.E in the state, which was recognised after referral to outside of the State. It is, therefore, felt the need to make and strengthen the strategies in combating the dreadful diseases and reduce the burden on health and economic development of the thousands affected by these vector borne diseases.

The Salient points on Malaria and Dengue in Mizoram are as follows:

| YEAR | MALARIA |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | ABER | SPR | Pf% | API | Death |
| 2010 | 33.74 | 4.70 | 92.42 | 15.85 | 31 |
| 2011 | 17.41 | 4.93 | 94.49 | 8.58 | 30 |
| 2012 | 14.29 | 5.87 | 95.49 | 8.38 | 25 |
| 2013 | 20.88 | 5.11 | 88.02 | 10.67 | 21 |

| YEAR | DENGUE |  |  |
| --- | --- | --- | --- |
|  | Suspected Case | Positive | Death |
| 2011 | NIL | NIL | NIL |
| 2012 | 90 | 6 | NIL |
| 2013 | 96 | 7 | NIL |

STRATEGIC PLAN FOR MALARIA CONTROL IN INDIA (2012-2017)

MISSION :

To reduce the morbidity and mortality due to malaria and improving the quality of life, thereby contributing to health and alleviation of poverty in the country.

GOALS :

- Screening all fever cases suspected for malaria (60% through quality microscopy and 40% by Rapid Diagnostic Test).

- Treating all P. falciparum cases with full course of effective ACT and primaquine and all P. vivax cases with 3 days chloroquine and 14 days primaquine.

- Equipping all Health Institutions ( PHC level and above), especially in high-risk areas, with microscopy facility and RDT for emergency use and injectable artemisinin derivatives.

- Strengthening all District and Sub-District Hospitals in malaria endemic areas as per IPHS with facilities for management of severe malaria cases.

OBJECTIVE :

To achieve by the end of 2017, an API of < 1 per 1000 Population at National Level.

OUTCOME INDICATORS :

- At least 80% of those suffering from malaria get correct, affordable, appropriate and complete treatment within 24 hours of reporting to the health system by the year 2017.

- At least 80% of those at high risk of malaria get protected by effective preventive measures such as ITN/LLIN or IRS by 2017.

- At least 10% of the population in high-risk areas is surveyed annually (Annual Blood Examination Rate >10%).

IMPACT INDICATORS :

- To bring down annual incidence of malaria to less than 1 per 1000 population at National level by 2017.

- At least 50% reduction in mortality due to malaria by the year 2017, taking 2010 level as baseline.

ACHIEVEMENTS OF MIZORAM STATE ON MALARIA CONTROL PROGRAMME

| YEAR | MALARIA |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2009 | 17.52 | 9.59 | 119 |
| 2010 | 33.74 | 15.85 | 31 |
| 2011 | 17.41 | 8.58 | 30 |
| 2012 | 14.29 | 8.38 | 25 |
| 2013 | 20.88 | 10.67 | 21 |

MIZORAM STATE GOALS AND TARGETS FOR THE 12TH FIVE YEAR PLAN :

| Year | STATE GOALS FOR THE 12TH FIVE YEAR PLAN |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012-2013 | >16.5% | < 5 | < 22 |
| 2013-2014 | >18% | < 4 | < 16 |
| 2014-2015 | >19.5% | < 3 | < 11 |
| 2015-2016 | >21% | < 2 | < 8 |
| 2016-2017 | >22.5% | < 1 | < 5 |

Considering the high incidence of Malaria in Mizoram, especially with Malaria Pf rate of over 95.09 %, the SVBDCP, Mizoram, is of the opinion that blanket coverage of DDT spray, distribution of LLINs and impregnation of bed nets in the whole state is pertinent. Example can be cited for the same on how 4 years back DDT spray was not undertaken in few areas where API was less than 2.  Consequently, it was found out that Malaria incidence increased to a great extent in the following years in those unsprayed areas.

Apart from DDT spray, it is felt that much of the Malaria cases and the few fatalities which was witnessed during 2013 could have been prevented with the distribution of LLINs and impregnation of local bed nets as majority of the inhabitants of areas with high API do not own bed nets or have impregnated bed nets. Due to non supply of K-Othrine (Deltamethrin 2.5%) for impregnation of bed nets and distribution of LLINs, it was witnessed that the API still remains very high in spite of improved IRS coverage in many endemic regions. Hence LLINs distribution and provision for impregnation of bed nets are crucial to the State and is regarded to be one of the major factors in preventing deaths due to Malaria. Provision for impregnation of bed nets is essential as majority of the population prefers to use their own bed nets which have their tailoring of choice over distributed LLINs.

After careful analysis of the State situation and performance, the yearly API target set during the 12th Five year plan was found not feasible and far fetched. All the while keeping the State Goals in mind, yearly revised targets set are as below:

| Year | ABER | API | MORTALITY |
| --- | --- | --- | --- |
| 2014-2015 | > 23% | < 9.5 | <18 |
| 2015-2016 | >23.5% | < 9 | < 15 |
| 2016-2017 | > 24% | < 8 | <10 |

OBJECTIVES AND TARGETS OF DENGUE CONTROL PROGRAMME:

OBJECTIVES : Following are the specific objectives of the Mid Term Plan

- To reduce the incidence of Dengue and Chikungunya and to bring down the disease burden.

- To reduce the case fatality rate due to Dengue.

TARGETS :

- Dengue cases fatality rate to below 1%.

- Functional Sentinel Surveillance Hospital in all endemic districts/towns/cities.

- Functional Rapid Diagnostic Response team in all endemic districts/towns/cities.

By the latter part of 2012, Dengue and Chikungunya Control Programme was implemented in the State. Civil Hospital, Aizawl was identified as Sentinel Surveillance Hospital for Dengue. Random Sampling was done from the OPD patients and 6 cases were found to be positive for Dengue infection in the year 2012 and & cases in the year 2013.

Due to delayed release of funds in 2012 (as well as unreleased of funds) for Dengue and Malaria in the second instalment, the State faced problems in procurement of Dengue NS1 antigen test kit. The IgM MAC ELISA test kit (96 test) received from NIV Pune was used up within a short period of time and the State could not proceed further in diagnosing Dengue Disease during 2012-2013.

It is also felt necessary to increase the number of Sentinel Surveillance sites to have better coverage of the population at risk. Keeping in mind the high percentage of patient attendance in Private Hospitals of the State, setting up additional Sentinel Surveillance sites at three other hospitals, namely, Presbyterian Hospital, Durtlang in northern Mizoram, Civil Hospital, Lunglei and Christian Hospital, Serkawn in the southern part of Mizoram is proposed.

STATUS OF MIZORAM FOR DENGUE IS AS FOLLOWS:

| Year | Suspected Cases | Positive Cases | Deaths |
| --- | --- | --- | --- |
| 2012 | 90 | 6 | Nil |
| 2013 | 96 | 7 | Nil |

Note – 5 cases were detected in the year 2010 from Private Hospital before programme was implemented in the State.

EXECUTIVE SUMMARY

The disease situation in Mizoram State is as follows:

| Year | Malaria Cases | Malaria Deaths | Dengue Cases | Dengue Deaths | Chikungunya Cases | AES/ JE Cases | AES/ JE Deaths | Kala-azar Cases | Kala-azar Deaths | Micro-filaria Rate % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 | 9883 | 25 | 6 | Nil | Nil | Nil | Nil | Nil | Nil | Nil |
| 2013 | 11408 | 21 | 7 | Nil | Nil | Nil | Nil | Nil | Nil | Nil |

In the State, Malaria is still a major public health problem till date. 15 cases of Dengue were identified during 2012-2013. Two cases of registered death due to AES/JE were also seen in the state but due to lack of diagnostic facilities, the actual prevalence of the disease cannot be estimated as yet.

Malaria is endemic (API>2) in 5 districts (out of 9) namely :

- Mamit District

- Kolasib District

- Lunglei District

- Lawngtlai District and

- Saiha District

The requirement for programme implementation has been indicated in detail and summary is indicated below:

| Disease | Unspent Balance as on -----January, 2014 in lakhs | Committed expenditure for 2013-14 in lakhs | Cash assistance required from NVBDCP for 2014-15 in lakhs | State resources |
| --- | --- | --- | --- | --- |
| Malaria : |  |  |  |  |
| - Domestic Budget Support | 44.19 | 184 | 642.23 |  |
| - World bank fund for project states | Nil | Nil | Nil |  |
| - GFATM for Project states | 278.83 | 382 | 413.48 |  |
| Dengue (from Domestic Budget) | 1.35 | 20 | 60.73 |  |
| Chikungunya (from Domestic Budget) | Nil | Nil |  |  |
| AES including JE (from Domestic Budget) | Nil | Nil |  |  |
| Filaria (from Domestic Budget) | Nil | Nil | Nil |  |
| Kala-azar (from Domestic Budget) | Nil | Nil | Nil |  |
| Kala-azar (World Bank Project assistance) | Nil | Nil | Nil |  |
| Total | 324.37 | 586 | 1055.71 |  |

ANNUAL ACTION PLAN/PIP 2014 – 2015

- Demographic Profile of Mizoram :

Population of the State :

| Infrastructure | Number |
| --- | --- |
| District | 9 |
| CHCs | 12 |
| PHCs | 57 |
| UHCs | 5 |
| HSCs | 370 |
| Health Clinics | 130 |
| ASHAs | 987 |
| Villages | 925 |

- Inaccessible/ Hard to reach villages :

Mizoram is a highly terrain State with many hard to reach villages and villages inaccessible by road, especially during monsoon. The following are the list of inaccessible/hard to reach villages, District-wise:-

| Sl.No | Name of District | No of hard to reach Villages |
| --- | --- | --- |
| 1 | Aizawl East | 18 |
| 2 | Aizawl West | 0 |
| 3 | Champhai | 6 |
| 4 | Kolasib | 4 |
| 5 | Lawngtlai | 35 |
| 6 | Lunglei | 34 |
| 7 | Mamit | 12 |
| 8 | Saiha | 0 |
| 9 | Serchhip | 0 |
|  | Total | 109 |

- District-wise status of Manpower (Sanctioned and Vacant):

- Regular Post :

| Sl.No | Regular Post | Required | Sanctioned | In position | Vacant |
| --- | --- | --- | --- | --- | --- |
| 1 | District Malaria Officer/ District VBD Control Officer | 9 | 0 | 9 | 0 |
| 2 | District Filaria Officer | 0 | 0 | 0 | 0 |
| 3 | Asst Malaria Officer/ VBD Officer | 6 | 3 | 3 | 0 |
| 4 | Medical Officer | 0 | 0 | 0 | 0 |
| 5 | Senior Malaria Inspector | 0 | 0 | 0 | 0 |
| 6 | Malaria Inspector | 61 | 8 | 8 | 0 |
| 7 | Multi Purpose Health Supervisor | 19 | 171 | 152 | 19 |
|  | Regular Post | Required | Sanctioned | In position | Vacant |
| 8 | Multi Purpose Health Asst or Multipurpose Worker | 186 | 770 | 584 | 186 |
| 9 | Lab Tech. | 5 | 67 | 62 | 5 |

- Contractual Post:-

| Sl.no | Post | In Position | Proposed | Remarks |
| --- | --- | --- | --- | --- |
| 1 | MPW regular | Nil | Nil | Financed by State or NRHM |
| 2 | MPW (Male) Contract under NVBDCP | 75 | 109 | There are 109 inaccessible villages and the State is having 75 MPWs. So 34 additional MPWs are required to be financed by NVBDCP |
| 3 | Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor(MTS) | 16 | 11 | There are 27 Blocks in the State. Additional 11 MTS are required which are to be financed by NVBDCP |

- Special emphasis needs to be paid to Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor. The State requires an additional 11 MTS as there are 11 Malaria Units/blocks in the State which is not covered by MTS. These areas show higher API. Thus the proposed 11 additional posts for MTS is very crucial to boost the Malaria Programme Control in the State.

- MALARIA :

Target :  During the 12th Plan period, the proposed target is as below :

ABER > 10%, API<1 per thousand population (during 12th plan, the objective is to bring down annual incidence of malaria cases to less than 1 per 1000 population at national level by 2017 and its monitoring at district level).

The target and goals set by the State is as follows:

| Year | STATE GOALS FOR THE 12TH FIVE YEAR PLAN |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012-2013 | >16.5% | < 5 | < 22 |
| 2013-2014 | >18% | < 4 | < 16 |
| 2014-2015 | >19.5% | < 3 | < 11 |
| 2015-2016 | >21% | < 2 | < 8 |
| 2016-2017 | >22.5% | < 1 | < 5 |

After careful analysis of the State situation and performance, the yearly API target set during the 12th Five year plan was found not feasible and far fetched. All the while keeping the State Goals in mind, yearly target is set for the year 2014-2015 as below :

| Year | ABER | API | MORTALITY |
| --- | --- | --- | --- |
| 2014-2015 | > 23% | < 9.5 | <18 |

Achievement during the year 2012&2013 :

| YEAR | MALARIA |  |  |
| --- | --- | --- | --- |
|  | ABER | API | MORTALITY |
| 2012 | 14.29 | 8.38 | 25 |
| 2013 | 20.88 | 10.67 | 21 |

- Epidemiological Data  :

- District-wise for 2012 :-

| District | Person Examined |  | Positive | Pf | No of Deaths | ABER | API | Pf% | SPR | SFR | Total BE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |  |
| Aizawl East | 19353 | 9387 | 137 | 122 | 0 | 8.27 | 0.59 | 89.05 | 0.71 | 0.63 | 19325 |
| Aizawl West | 20637 | 9008 | 219 | 196 | 9 | 13.32 | 1.41 | 89.50 | 1.06 | 0.95 | 20637 |
| Champhai | 17301 | 7331 | 96 | 82 | 1 | 6.75 | 0.37 | 85.42 | 0.55 | 0.47 | 17301 |
| Kolasib | 18547 | 8865 | 329 | 306 | 1 | 22.68 | 4.02 | 93.01 | 1.77 | 1.65 | 18547 |
| Lawngtlai | 29272 | 17865 | 5034 | 4911 | 7 | 24.05 | 41.36 | 97.56 | 17.2 | 16.78 | 29272 |
| Lunglei | 31368 | 12276 | 3042 | 2833 | 3 | 21.31 | 20.67 | 93.13 | 9.70 | 9.03 | 31368 |
| Mamit | 16584 | 5927 | 774 | 759 | 1 | 25.46 | 11.88 | 98.06 | 4.67 | 4.58 | 16584 |
| Saiha | 7966 | 3394 | 182 | 163 | 1 | 13.83 | 3.16 | 89.56 | 2.28 | 2.05 | 7966 |
| Serchhip | 7421 | 4285 | 70 | 65 | 2 | 12.28 | 1.16 | 92.86 | 0.94 | 0.88 | 7421 |
| Total / Average | 168421 | 78338 | 9883 | 9437 | 25 | 14.29 | 8.38 | 95.49 | 5.87 | 5.60 | 168421 |

- District wise  for 2013 :

| District | Person Examined |  | Positive | Pf | No of Deaths | ABER | API | Pf% | SPR | SFR | Total BE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |  |
| Aizawl East | 39387 | 17317 | 232 | 177 | 0 | 16.73 | 0.94 | 76.29 | 0.56 | 0.43 | 56704 |
| Aizawl West | 31504 | 13017 | 312 | 231 | 2 | 22.49 | 1.94 | 74.04 | 0.86 | 0.64 | 44521 |
| Champhai | 14331 | 9357 | 92 | 70 | 1 | 10.65 | 0.68 | 76.09 | 0.64 | 0.49 | 23688 |
| Kolasib | 18182 | 9497 | 312 | 276 | 3 | 21.96 | 3.81 | 88.46 | 1.74 | 1.54 | 27679 |
| Lawngtlai | 24580 | 19039 | 4619 | 4081 | 1 | 21.51 | 35.96 | 88.35 | 16.72 | 14.77 | 43619 |
| Lunglei | 47130 | 22544 | 3972 | 3508 | 1 | 32.66 | 26.01 | 88.32 | 7.96 | 7.03 | 69674 |
| Mamit | 19904 | 10010 | 1649 | 1574 | 8 | 28.41 | 22.28 | 95.45 | 7.84 | 7.48 | 29914 |
| Saiha | 6488 | 6173 | 488 | 368 | 2 | 20.26 | 8.47 | 75.41 | 4.18 | 3.15 | 12661 |
| Serchhip | 9721 | 5661 | 71 | 55 | 3 | 15.43 | 1.12 | 77.46 | 0.73 | 0.56 | 15382 |
| Total / Average | 211227 | 112615 | 11747 | 10340 | 21 | 20.88 | 10.67 | 88.02 | 5.11 | 4.50 | 323842 |

- District in the State categorized based on their API (2013) :

| Sl. No | Name Of District | API (Descending Order) |
| --- | --- | --- |
| 1 | Lawngtlai | 35.96 |
| 2 | Lunglei | 26.01 |
| 3 | Mamit | 22.28 |
| 4 | Saiha | 8.47 |
| 5 | Kolasib | 3.81 |
| 6 | Aizawl West | 1.94 |
| 7 | Serchhip | 1.12 |
| 8 | Aizawl East | 0.94 |
| 9 | Champhai | 0.64 |

Mizoram State falls into Category 3 :- State with more than 1 API with either all the districts with more than 1 API or few districts with less than 1 API and few with more than 1 API.

F.1.1 Malaria

F.1.1.a :	Contractual Payments :

- F.1.1.a.i : Multipurpose Worker (Male) Contractual :-

- There were 75 contractual Multipurpose Workers (Male) in the State provided by NVBDCP, GoI with remuneration of Rs. 6000/- per month. All these posts have been terminated in the month of September, 2014.

- In the ROP 2014-2015, only Rs. 4.5 lakhs was released for salary of 75 MPWs while Rs. 27 lakhs was needed. So, additional Rs. 22.5 lakhs is required.

F.1.1.c :	Operational Cost :

- F.1.1.c.ii : Operational cost for IRS :-

- New Hand Compression Pumps with pressure gauze:

After detailed study on low IRS acceptance, the major factor for low acceptance of IRS in Urban and Semi-urban areas was primarily related to the spray quality. Families who are economically more privileged have their walls painted. Those homes do not accept IRS due to the fact that DDT spraying leaves much streaking on the painted walls and thus spoils their interior decoration. Lack of proper application of spraying technique by the spray team is an added factor to the streaking of walls apart from the shortcomings of our current HC pumps. The reasons are as follows :

- The current HC Pumps used for DDT spraying do not have an inbuilt pressure gauze. Although spray teams are taught to frequently measure the discharge rate from nozzle, it is impractical to constantly measure the pressure from discharge rate as much homes needs to be covered. Thus the prescribed pressure is often neglected. This results in DDT sprayed to be in excess of how much the wall could adsorb which then leads to trickling of DDT suspensions and thus streaking the walls. Thus the pressure needs to be constantly monitored so that the right amount of DDT suspension is released per second to prevent excess or inadequate discharge rate. As frequent manual measurement of pressure is burdensome, not accurate enough and not very practical in the actual field, HC pumps with inbuilt pressure gauge is needed to improve the spray quality.

- When the correct distance for spraying is not maintained in addition to the correct amount of time used for one swipe, which is usually due to lack of sufficient training days for spray men so that by experience and practise, they master the correct distance and duration to be maintained, overlapping of DDT spray occurs which results in DDT suspension to trickle and thus streaking the walls.

With regards to these factors, a HC pumps with inbuilt pressure gauge is needed so as to minimise the streaking of walls. There is no other realistic alternative but to improve the spray quality by minimising streaking of DDT spray if we want to improve the IRS acceptance in the urban and semi-urban areas. Improving IEC/BCC for these areas will not improve the IRS acceptance if emphasis on spray quality is not made. This issue is prominent in the urban and sub-urban areas. Earlier strategies were focussed on spray coverage while spray quality was not given much priority. Since the importance of spray quality has been recognized, focus needs to be shifted to improving spray quality which will eventually improve the IRS acceptance. So, the Backpack Sprayer with pressure gauge will initially be used for urban and semi-urban areas. IEC/BCC undertakings can still improve IRS in the rural areas.

Hence, the requirement for procurement of Backpack Sprayers with pressure gauge (HC pumps) is as follows :

| Sl.No | Particulars | Quantity | Rate (Rs) | Total fund required |
| --- | --- | --- | --- | --- |
| 1 | New Backpack Sprayers with Pressure Gauge (HC Pumps) | 120 | 11,000/- | 13,20,000/- |

- Spray parts and repair cost :

As mentioned earlier on the importance of spray quality, sufficient spare parts needs to available to the spray team so as not to compromise on the spray quality and thus reducing the IRS acceptance. This is very crucial as one poor spray quality due to insufficiency of spare parts e.g. faulty nozzles, can lead to non acceptance of IRS by many in the sensitive urban and semi-urban areas. This leads to non-acceptance of IRS in the subsequent years. Thus, each spray team should have sufficient spare parts as they have to travel to remote villages.

Moreover, repairing of HC pumps is constantly required and must be done as soon as possible each time to minimise the delay in IRS coverage as per plan.  This delay should be kept at minimum because the number of HC pump is limited and a halt in their work would be a big problem in each field of planning involving IRS operation. Some repairs cannot be done by the spray team and requires the help of repair mechanics. Hence the repair mechanic must be well equipped with sufficient spare parts and transportation mode as most of the pumps needs repair during ongoing spraying in remote and hard to reach villages. The fund required for procurement of spare parts and  TA/DA for Repairs of HC pumps are as follows :

| Sl No | Particulars | Approximate fund required (Rs) |
| --- | --- | --- |
| 1 | Purchase of Spare parts | 5,00,000/- |
| 2 | TA/DA for HC Pump repairs | 4,00,000/- |
| Total Fund required |  | 9,00,000/- |

- Distribution of DDT within the state :

Each District requirement of fund for vehicle hiring for DDT dropping differs according to the terrain, road conditions and distance to be covered. The requirements for DDT dropping are as follows:

| Sl.No | District | No of Villages | No of Sub Centres/Clinics | Fund required for DDT dropping (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 116 | 55 | 1,70,000/- |
| 2 | Aizawl West | 93 | 40 | 1,70,000/- |
| 3 | Champhai | 102 | 59 | 2,00,000/- |
| 4 | Lunglei | 185 | 71 | 2,50,000/- |
| 5 | Lawngtlai | 181 | 37 | 2,00,000/- |
| 6 | Kolasib | 48 | 28 | 1,00,000/- |
| 7 | Mamit | 74 | 30 | 1,80,000/- |
| 8 | Saiha | 81 | 24 | 1,80,000/- |
| 9 | Serchhip | 41 | 26 | 1,00,000/- |
| 10 | State to District HQ | 9 District HQ |  | 5,00,000/- |
| Total fund required for DDT dropping for 2014-2015 |  |  |  | 20,50,000/- |

- Transportation of spray teams :

Transportation of Spray teams to their spraying destination is necessary and must be aided from the SVBDCP. As the spray wages are less, the spray team cannot be expected to hire their own vehicle. The State government cannot provide vehicles for the transportation of Spray Men hence fund allocations need to be made as some of the villages are very far from towns and with no daily vehicle services. In some areas, boats have to be hired to reach the villages. Transportation problems faced by the spray men are the biggest reason why attrition rate is very high, almost above 95%. This necessitate the recruitment of previously inexperienced persons as spray men each year, and thus progress cannot be made regarding improvement in spray quality which eventually lowers the IRS acceptance inspite of much progress in IEC/BCC components.

Hence, to retain a dedicated and experienced spray men, apart from increase in their daily wages, their transportation needs to be provided to minimise their expenditure. The morale of spray men would definitively be boosted resulting in attrition rate to fall, which will eventually leads to improved IRS acceptance via improved spray quality.

The transportation cost for spray team differs with Districts in relation to number of villages, conditions of roads and distance needed to be covered. The fund required for transportation of spray teams are :

| Sl.No | District | No of Villages | No of Sub Centres/Clinics | Fund required for DDT dropping (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 116 | 55 | 2,00,000/- |
| 2 | Aizawl West | 93 | 40 | 1,80,000/- |
| 3 | Champhai | 102 | 59 | 2,00,000/- |
| 4 | Lunglei | 185 | 71 | 2,70,000/- |
| 5 | Lawngtlai | 181 | 37 | 3,25,000/- |
| 6 | Kolasib | 48 | 28 | 1,50,000/- |
| 7 | Mamit | 74 | 30 | 2,00,000/- |
| 8 | Saiha | 81 | 24 | 2,40,000/- |
| 9 | Serchhip | 41 | 26 | 1,20,000/- |
| Total fund required for transportation of Spray Teams for 2014-2015 |  |  |  | 18,85,000/- |

- Equipments for IRS :

The equipments required by the spray teams are :

| Sl no | Item | Quantity | Cost (Rs) | Fund required (Rs) |
| --- | --- | --- | --- | --- |
| 1. | Buckets with measurements | 1000 | 250/- | 2,50,000/- |
| 2. | Mugs with measurements | 1000 | 75/- | 75,000/- |
| 3. | Long sleeve Rubber gloves | 700 | 250/- | 1,75,000/- |
| 4. | Face Masks | 1000 | 100/- | 1,00,000/- |
| 5. | Towels | 1000 | 150/- | 15,00,000/- |
| 6. | Soaps | 20000 | 10/- | 2,00,000/- |
| 7. | Filtering cloth | 3000 | 50/- | 1,50,000 |
| 8 | Goggles | 400 | 350/- | 1,40,000/- |
| 9 | Pens | 1000 | 10/- | 10,000/- |
| 10 | Printed Spray reporting book | 1500 | 35/- | 52,500/- |
| 11 | Plastic DDT carrying bags | 800 | 30/- | 24,000/- |
| 12 | Miscellaneous |  |  | 2,00,000/- |
| Total Fund required for IRS equipments for 2014-2015 |  |  |  | 15,26,500/- |

Total operational cost for IRS :

| Sl No | Particulars | Fund required (Rs) |
| --- | --- | --- |
| 1 | Backpack sprayer (HC Pumps) with pressure gauge | 13,20,000/- |
| 2 | Spray Parts and repair cost | 9,00,000/- |
| 3 | DDT dropping | 20,50,000/- |
| 4 | Transportation of Spray Teams | 18,85,000/- |
| 5 | Equipments for IRS | 15,21,500/- |
| 6 | Miscellaneous | 4,00,000/- |
| Total fund required for Operational IRS for 2014-2015 |  | 80,81,500/- |

F.1.1.h :	Zonal Entomological Unit :-

Entomological Surveillance :

The State Entomologist, unfortunately, expired in the year 2008. Because of financial constraints, the State Entomologist post is still vacant and yet to be filled up even though candidates are available. The importance of Entomological Surveillance is very much recognized by the State for the Control of Vector Borne Diseases. For revival of the Entomological Surveillance Programme in the State, an entomologist is indispensable.

Setting up a State Entomological Surveillance Unit is proposed along with District Entomological Surveillance units to strengthen the ongoing control of vector borne diseases and will be a huge factor in achieving our goals and targets of the 12th Five Year Plan. As of present, the state does not have an Entomological Surveillance Unit.

The formulated plan for Entomological Surveillance in the State:

- Setting up an Entomological Surveillance Unit at State level headed by State Entomologist. The State Entomologist (new post) shall be attached to State Vector Borne Disease Control Programme, Mizoram, with a monthly salary of Rs 40,000/- per month.

- District Entomological Surveillance Units which will include one Insect Collector (new post) for each District (9 Districts) and an additional Insect Collector which is to be attached to the proposed UMS of Lunglei Town.

- One Entomological Technician, shall be posted in the State Entomological Surveillance Unit with monthly salary of Rs 25,000/-.

- Entomological Surveillance shall be conducted throughout the year and necessary research carried out.

Following are the estimated requirements for the State Entomological Surveillance :

| No of Entomological Units : 10 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1. | State Entomological Surveillance Unit : 1 |  |  |  |  |
|  | 2. | District Entomological Surveillance Unit : 9 |  |  |  |  |
|  | a. | Human Resources |  | Quantity | Unit Cost (Rs) Per Month | Fund Required for a year |
|  |  | i. | State Entomologist | 1 | 40,000/- | 4,20,000/- |
|  |  | ii. | Technician | 1 | 25,000/- | 3,00,000/- |
|  |  | iii. | Insect Collectors | 10 (one for UMS) | 8,000/- | 9,60,000/- |
|  |  |  | Total |  |  | 16,80,000/- |
|  | b. | Operational cost |  |  |  |  |
|  |  | i. | Trainings for Insect Collectors |  |  | 5,00,000/- |
|  |  | ii. | Modification of Rooms |  |  | 6,00,000/- |
|  |  | iii. | Operational Research for vector prevalence in high focus(endemic) districts |  |  | 5,00,000/- |
|  |  | iv. | Hiring of Vehicles (Mobility) |  |  | 8,00,000/- |
|  |  | v. | Equipments eg Insect collecting kits, light trap, collecting jar, insect nets, light microscope, susceptibility test tubes, insecticide impregnated papers etc including office expenses |  |  | 10,00,000/- |
|  |  | vi. | Contingencies |  |  | 5,00,000/- |
|  |  | Total |  |  |  | 38,40,000/- |
|  | Grand Total |  |  |  |  | 56,04,000/- |

Proposed timeline for setting up Entomological Surveillance Units are as follows :

- Modification of rooms and recruitment of Human Resources during the 4th quarter of 2014-2015. Rooms will have to be rented as there is no space available in the SVBDCP Centre.

- Necessary training within a month of recruitment, during the 4th quarter.

- 10 insect collectors, one for each district (9 Districts) with additional one insect collector to be posted at the State Headquarter.

- Procurement of equipments and necessaries during the 3rd quarter so that Entomological Surveillance can be carried out by end of 3rd quarter 2014-2015.

F.3 GFATM support for Malaria (NEStates)

- F.3.a : Project Management Unit including human resources of N.E.States :

- F.3.a.viii : Additional MTS:-

| Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor(MTS) | 11 nos. of additional MTS @Rs. 20,000/month | Rs. 26.40 lakhs | There are 27 Malaria Units in the State. Additional 11 MTS are required besides the existing 16 MTS which are to be financed by NVBDCP |
| --- | --- | --- | --- |

- Special emphasis needs to be paid to Malaria Technical Supervisor/ Vector Borne Disease Technical Supervisor. The State requires an additional 11 MTS as there are 11 Malaria Units/blocks in the State which is not covered by MTS. These areas show higher API. Thus the proposed 11 additional posts for MTS is very crucial to boost the Malaria Programme Control in the State.

F.6.m Any others (Please Specify)

- The following items are necessary for smooth functioning of the Programme as there are no funds allotted for procuring these items.

| Sl.No | Particulars | Quantity | Rate | Amount |
| --- | --- | --- | --- | --- |
| 1 | Lab Reagent |  |  | 500000 |
| 2 | Coton Wool 200 g | 1000 Rolls | 97 | 97000 |
| 3 | Blood Slide | 4000 boxes | 70 | 280000 |
| 4 | Blood lancet | 1000 boxes | 180 | 180000 |
| 5 | Tab. Paracetamol 500mg | 500000 tabs | 1.50 | 750000 |
| 6 | Syr. Paracetamol | 20000 | 25 | 500000 |
| Total funds required for miscellaneous items |  |  |  | Rs. 23,07,000 |