EXECUTIVE SUMMARY

The State of Mizoram highly appreciates the initiatives and activities taken up under the National Rural Health Mission through which the people have access to better Health Care facilities in terms of Infrastructure and better equipped and skilled manpower right at their own villages. During 2011-12, Mizoram was recognized as the ‘Most improved State in Health care among the Small States’ by Times of India Group.

The overall objectives/goals to be achieved in 2012-13 are as follows:

| Main Goals | Current Status | Proposed Goal for 2012-13 |
| --- | --- | --- |
| MMR | 72 (State HMIS 2010-11) | 65 |
| IMR | 37 (SRS 2010) | 35 |
| TFR | 2.9 (NFHS-3) | 2.8 |

The plan for the year 2012-13 is formulated keeping in mind the new guidelines and instructions made by the Government of India. The District plans which were submitted to the State on the 12th December 2011 went a long way in helping to form the current PIP.

The State Program Implementation plan recognizes the need of three most difficult districts in the state, namely Saiha, Lawngtlai and Mamit Districts, which are the districts that contribute most to the IMR, MMR and TFR of the state. New initiatives to address the needs of these districts are reflected in the PIP.

There will be decentralization of power to the Districts, especially in terms of rational deployment of Human resources with minimal interference from the Government who has already expressed their willingness in such a venture.

The main emphasis will be on monitoring and analysis of the implementation of the State Program. For this the State and District Monitoring committee will be made to act as per the guidelines. The State Program Unit will be responsible for the overall monitoring and strict implementation of guidelines received from the Government of India.

The State has 71 delivery points as per norms. The plan is to have at least 1 SBA trained staff and NSSK trained staff at these points and the setting up of Newborn Care Corners up to the PHC level and at least an indigenous Baby Warmer (to be made from RKS funds etc) and neonatal resuscitation kit up to the sub Centre level within 2012-13.

Incentives to the mother for each delivery worth Rs 300 in kind like Baby cloth etc. is proposed to be continued to be given to Mothers who deliver in both Government and Private facilities in certain difficult areas to reduce the labour load at District Hospitals so that 48 hours post delivery stay can be ensured.

JSSK for which the Government order was issued on 15th December 2011 has been stalled in implementation due to non availability of funds. It will be implemented in full swing immediately when fund is received.

More robust monitoring of the Infant and Maternal Death audits to ascertain their accountability and to cover all Infant and Maternal deaths within the prescribed time limits without fail, so that the State plans can be modified according to the needs of each District.

The State aims to reduce the disease burden under all Disease Control Programs. The State is very grateful for the improvement in Human resources and Infrastructure seen since the implementation of NRHM.

BUDGET SUMMARY

| SN | Main Heads | Components | Budget Amount (Rs in Lakh) |
| --- | --- | --- | --- |
| 1 | Human Resources | Contractual Remuneration for ANMs, Nurses, SNs, LHVs | 972.21 |
|  |  | Contractual Remuneration for LTs,MPWs | 61.63 |
|  |  | Contractual Remuneration of Specialists (Anesthetists, | 50.00 |
|  |  | Pediatricians, Ob/Gyn, Surgeons, Physicians, Dental |  |
|  |  | Surgeons, Radiologist, Sonologist, Pathologist, Specialist for CHCs.) |  |
|  |  | Medical Officers at CHCs / PHCs | 229.35 |
|  |  | Contractual Remuneration of PHNs at CHC, PHC level |  |
|  |  | Additional Allowances/ Incentives to M.O.s of PHCs and CHCs |  |
|  |  | Payment to Others - Computer Assistants/ BCC Co-ordinator/ Dental Surgeon/Pharmacist/X-Ray Technicians/BEE/ FP Counsellor etc | 234.22 |
|  |  | Incentive/ Awards etc. to SN, ANMs etc. |  |
|  |  | Human Resources Development (Other than above) |  |
|  |  | Other Incentives Schemes (Please Specify) |  |
|  |  | Strengthening of SHS /SPMU (Including HR, Management Cost, Mobility Support, Field Visits) | 114.25 |
|  |  | Strengthening of DHS/DPMU (Including HR, Management Cost, Mobility Support, Field Visits ) | 111.55 |
|  |  | Strengthening of Block PMU (Including HR, Management Cost, Mobility Support, Field Visits ) | 103.70 |
|  |  | Strengthening (Others) | 8.00 |
|  |  | Other Programme Management Costs (Audit Fees,Concurrent Audit etc.) | 18.00 |
|  |  | Mobility Support, Field Visits to BMO/MO/Others |  |
|  |  | Payment to AYUSH M.O.s |  |
|  |  | Payment to AYUSH Other Staffs |  |

| 2 | Training | Training under Maternal Health | 39.39 |
| --- | --- | --- | --- |
|  |  | Training under Child Health | 32.66 |
|  |  | Training under Family Planning Services | 4.62 |
|  |  | Strengthening Training Institutions |  |
|  |  | Development of training packages & Monitoring | 25.00 |
|  |  | IMEP Trainings | 4.86 |
|  |  | ARSH Training including School Health Training | 39.74 |
|  |  | Programme Management Training | 6.63 |
|  |  | Training (Nursing) |  |
|  |  | Training (Other Health Personnel) |  |
|  |  | Training for Cold Chain Handlers/refrigerator mechanics |  |
|  |  | Training of M.O.s /Other Staffs on R.I. |  |
| 3 | Infrastructure | Upgradation of CHCs, PHCs, Dist. Hospitals to IPHS | 1409.06 |
|  |  | Strengthening of District, Sub-divisional Hospitals, CHCs, |  |
|  |  | PHCs |  |
|  |  | New Constructions/ Renovation and Setting up CHCs, PHCs, |  |
|  |  | HSCs, |  |
|  |  | Construction (Others) |  |
|  |  | Minor civil works for operationalisation of FRUs |  |
|  |  | Minor civil works for operationalisation of 24 hour services |  |
|  |  | at PHCs |  |
|  |  | Civil Work under RNTCP |  |
|  |  | Other Civil Works |  |
| 4 | Procurement | Procurement of Drugs & Supplies | 300.00 |
|  |  | Procurement of Equipment | 501.15 |
|  |  | Procurement of Others (School Health) | 47.44 |
| 5 | IEC/BCC | Development of State BCC/IEC strategy | 227.26 |
|  |  | Implementation of BCC/IEC strategy |  |
|  |  | Health Mela |  |
|  |  | Creating awareness on declining sex ratio issue |  |
|  |  | Other activities |  |

| 6 | Untied funds | Untied funds for,VHSC, SC CHC,PHC | 137.50 |
| --- | --- | --- | --- |
|  |  | Annual Maintenance Grants for CHCs, PHCs | 74.50 |
|  |  | Panchayati Raj Initiatives | 37.50 |
| 7 | ASHA | ASHA Payments under NRHM Additionalities | 98.74 |
|  |  | Selection & Training of ASHA |  |
|  |  | Procurement of ASHA Drug Kit |  |
|  |  | Incentive to ASHAs under JSY | 62.21 |
|  |  | Incentive under Family Planning Services |  |
|  |  | Incentive under Child Health | 28.75 |
|  |  | Incentive to ASHA's for motivating families for Sanitary |  |
|  |  | Toilets/Other Incentives |  |
|  |  | Awards to ASHA's/Link workers |  |
|  |  | ASHA Incentive under Immunisation |  |
|  |  | ASHA Incentive under NLEP |  |
|  |  | ASHA Incentive under NVBDCP |  |
|  |  | ASHA Incentive under NBCP |  |
|  |  | ASHA Incentive under RNTCP |  |
| 8 | RKS | Corpus grants to RKS | 106.00 |
| 9 | JSY | Home Deliveries | 12.88 |
|  |  | Institutional Deliveries | 89.93 |
|  |  | Administrative Expenses | 8.25 |
| 210 | Sterlisation | Compensation for Male sterlisation | 0.15 |
|  |  | Compensation for Female sterlisation | 34.00 |
|  |  | NSV Camps |  |
|  |  | Female Sterlisation Camps | 2.25 |
|  |  | IUD Camps |  |
|  |  | Social Marketing of contraceptives |  |
|  |  | Repairs of Laparoscopes |  |
|  |  | Other Expenses | 38.84 |
| 11 | Referral Transport | Referral Transport (EMRI) | 395.32 |
| 12 | JSSK under MH | Total requirement of JSSK | 316.90 |
|  | Other Maternal Health activities | RCH Camps, Monitoring, RTI/STI etc | 23.88 |

|  | JSSK under Child Health | Total requirement of JSSK | 3.60 |
| --- | --- | --- | --- |
|  | Other Child Health activities | Operationalization of SNCU,NBSU, NBCC Monitoring etc | 28.35 |
|  | Other Components (please list) |  |  |
| 13 | Other RCH Activities | ARSH | 78.60 |
|  |  | Urban RCH | 31.38 |
|  |  | PNDT | 4.00 |
| 14 | Vulnerable Group | Tribal RCH |  |
|  |  | Vulnerable Groups |  |
| 15 | Other Mission activities | Research Studies, |  |
|  |  | New Initiatives | 60.40 |
|  |  | Support to other programmes | 163.50 |
|  |  | District Health Action Plan | 50 |
|  |  | Mainstreaming of AYUSH | 178.03 |
|  |  | MMUs | 171.46 |
|  |  | SHSRC |  |
|  |  | School Health Programme | - |
|  |  | Health Insurance | 128.89 |
|  |  | External evaluation of infrastructure and programme |  |
|  |  | Planning , Implementation, Monitoring |  |
| 16 | PPP/NGO | NGO activities, PPP under NRHM Additionalities | 127.98 |
|  |  | Other NDCPs (RNTCP, NPCB etc) |  |
| 17 | Operational Cost (NDCPs) | Mobility, Review Meeting ,field visits, formats & reports, Communication etc for NDCPs | IDSP – 136.00 NLEP – 112.84 RNTCP – 421.27 NVBDCP – 1445.42 NPCB – 474.60 NIDDCP – 46.00 |
|  |  | Lab consumables, AMC etc for NDCPs |  |
| 18 | Financial aid/grant to Institutions (NDCPs) | Financial Support to Medical colleges |  |
|  |  | Financial Support to Referral Institutes |  |
|  |  | Financial Support to Sentinel sites |  |
| 19 | Other Components (please list) | HMIS | 186.08 |
| 20 |  | National Programme for prevention and control of Floursis | 40.00 |
| 21 |  | Immunisation | 159.47 |
|  |  | Mental Health | 374.00 |
|  |  | Direction & Admn. (Treasury Route) | 2616.24 |
|  | TOTAL |  | 13049.41 |

Programee/Scheme wise summary

| Sl.No | Scheme/Programme | Proposed Amount (in crore) |
| --- | --- | --- |
| 1 | RCH Flexible Pool | 28.20 |
| 2 | NRHM Mission Flexible Pool | 44.04 |
| 3 | Immunisation and PPI Operation Cost | 1.59 |
| 4 | NIDDCP | 0.46 |
| 5 | IDSP | 1.36 |
| 6 | NVBDCP | 14.45 |
| 7 | NLEP | 1.13 |
| 8 | NPCB | 4.75 |
| 9 | RNTCP | 4.21 |
| 10 | National Programme for prevention and control of Floursis | 0.40 |
| 11 | Direction & Admn. (Treasury Route) | 26.16 |
| 13 | Mental Health | 3.74 |
|  | TOTAL | 130.49 |

CHAPTER-1: STATE SPECIPIC TARGETS FOR NEXT FIVE YEARS

A.  Outcome Indicators

| Indicators | Current status as on latest available data | Cumulative Target for next five year | 2012- 13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Maternal Mortality Ratio (MMR) | 68.82 ( HMIS 2011-12) | 35 | 65 | 60 | 55 | 45 | 35 |
| Infant Mortality Rate (IMR) | 37 (SRS 2010) | 18 | 35 | 32 | 25 | 20 | 18 |
| Total Fertility Rate (TFR) | 2.9 (NFHS-3) | 2.1 | 2.8 | 2.7 | 2.4 | 2.2 | 2.1 |
| Malaria Mortality Reduction Rate | 30 deaths (75%) | 5 | 22 | 16 | 11 | 8 | 5 |
| Kala Azar Mortality Reduction Rate | - | - | - | - | - | - | - |
| Dengue Mortality Reduction Rate | - | - | - | - | - | - | - |
| Cataract operations | 1200 | Yearly/Annual target was set by GOI, MOH&FW |  |  |  |  |  |
| Leprosy Prevalence Rate | 0.02 | 0.00 | 0.02 | 0.01 | 0.01 | 0.00 | 0.00 |
| Tuberculosis Cure Rate | 85% | 85% | 85% | 85% | 85% | 85% | 85% |

B.  Output Indicators

|  | Activity / Measurable indicator | Current status as on latest availablee data | Cumulative Targets for the 2nd Phase of NRHM (2012-17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012- 13 | 2013-14 | 2014-15 | 2015- 16 | 2016-17 |
| A | Maternal Health |  |  |  |  |  |  |
| 1 | Institutional Deliveries (%) | 83 | 85 | 87 | 90 | 92 | 95 |
| 2 | 24x7 Facilities (Sub-District/ 24*7 PHC) | 41 | 41 | 42 | 43 | 44 | 45 |
| 3 | Functional First Referral Units | 4 | 4 | 5 | 6 | 7 | 8 |
| B | Child health |  |  |  |  |  |  |
| 4 | Sick New Born Care Units | 1 | 1 | 1 | 1 | 2 | 2 |
| 5 | New Born Care Corners | 23 | 17 | 10 | 10 | 10 | - |
| 6 | Stabilization Units in FRUs | 2 | 5 | 3 | 3 | 3 | 3 |
| 7 | Full Immunization (%) | 60 | 90 | 91 | 92 | 93 | 95 |
| C | Population Stabilization |  |  |  |  |  |  |
| 8 | Male Sterilization | 0 | 10 | 12 | 13 | 14 | 15 |
| 9 | Female Sterilization | 1445 | 3400 | 3420 | 3450 | 3460 | 3500 |
| 10 | No. of IUD Insertions | 2090 | 5000 | 5100 | 5200 | 5300 | 5400 |
| D | Disease Control |  |  |  |  |  |  |
| 11 | Annualized New Smear Positive Detection Rate of TB (%) | 70 | 70 | 75 | 80 | 85 | 90 |
| 12 | Success Rate of New Smear Positive Treatment initiated on DOTS (%) | 85 | 86 | 87 | 88 | 89 | 90 |
| 13 | ABER for malaria (%) | 16.61 | 18.00 | 19.50 | 21.00 | 22.50 | 25.50 |
| 14 | API for malaria (per 1000 population) | 8.19 | 5.00 | 4.00 | 3.00 | 2.00 | 1.00 |

|  | Activity / Measurable indicator | Current status as on latest available data | Cumulative Targets for the 2nd Phase of NRHM (2012- 17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 15 | Annual New Case Detection Rate for Leprosy (per 1,00,000 population) |  |  |  |  |  |  |
| 16 | Cataract Surgeries performed | 1500 (35.5%) | 50% | 60% | 65% | 70% | 80% |
| E | Training |  |  |  |  |  |  |
| 19 | Doctors trained on EmOC | 10 | 1 | 1 | 2 | 2 | 2 |
| 20 | Doctors trained on LSAS | 10 | 1 | 1 | 2 | 2 | 2 |
| 21 | Doctors trained in NSV/ Conventional vasectomy |  | 1 | 1 | 1 | 1 | 1 |
| 22 | Doctors trained in Abdominal Tubectomy (Minilap) | 81 | 10 | 10 | 10 | 10 | 10 |
| 23 | Doctors trained in laparoscopic Tubectomy | 4 teams | 1 | 1 | 1 | 1 | 1 |
| 24 | Personnel trained in IMNCI | MO-127 ANM-775 | 120 | 120 | 120 | 120 | 120 |
| F | Community Processes |  |  |  |  |  |  |
| 25 | Functional VHSCs | 815 | 815 | 815 | 815 | 815 | 815 |
| 26 | ASHAs with Drug kits | 987 | 987 | 987 | 987 | 987 | 987 |
| 27 | ASHAs trained in 6th and 7th modules | 987 | 987 | 987 | 987 | 987 | 987 |
| G | Improved Management |  |  |  |  |  |  |
| 28 | Evaluation and Assessment of NRHM Activities | 9 | 9 | 9 | 9 | 9 | 9 |
| 29 | Cold Chain Management (number of functional ILR points) |  |  |  |  |  |  |  |  |  |  |
| H | Infrastructure |  |  |  |  |  |  |
| 30 | Construction of sub-centre buildings | 370 |  |  |  |  |  |
| 31 | Construction of PHC buildings | 57 |  |  |  |  |  |
| 32 | Construction of CHC buildings | 12 | 0 | 0 | 0 | 0 | 0 |
| 33 | Construction of District Hospital buildings | 8 | 0 | 0 | 0 | 0 | 0 |
| 34 | Construction of Other Hospital buildings | 0 | 0 | 0 | 0 | 0 | 0 |
| I | MMU and Referral Transport |  |  |  |  |  |  |
| 35 | No. Of Functional Mobile Medical Units | 9 | 9 | 9 | 9 | 9 | 9 |
| 36 | No. Of Emergency and Referral Transport vehicles | 0 | 12 | 12 | 12 | 12 | 12 |
| J | Operationalisation of MCTS |  |  |  |  |  |  |
| 37 | % of registration of pregnant women in MCTS | 76.6 | 80 | 82 | 85 | 90 | 95 |
| 38 | % of registration of children in MCTS | 56.4 | 70 | 78 | 85 | 90 | 95 |
| 39 | % of facilities (SC, PHC, CHC, DH & others) uploading data | NA | NA | NA | NA | NA | NA |
| 40 | % of facilities having internet connectivity | 5 | 10 | 15 | NA | NA | NA |
| 41 | % of data validated at State level | 5 | 10 | 15 | NA | NA | NA |
| K | Operationalisation of HMIS |  |  |  |  |  |  |
| 42 | % of facilities (SC, PHC, CHC, DH & others) uploading data | 5 | 10 | 15 | NA | NA | NA |
| 43 | % of districts uploading committing HMIS data within a week of reporting month/quarter | 5 | 10 | 15 | NA | NA | NA |

|  | Activity / Measurable indicator | Current status as on latest available data | Cumulative Targets for the 2nd Phase of NRHM (2012- 17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Other Indicators |  |  |  |  |  |  |
| 44 | Collocation of AYUSH at health facilities | 8 DH | 9 CHC | 20 PHC | 15 PHC | 12 PHC | 10 PHC |

| L | Human Resources |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| L. 1 | Category | Number of Sanctioned post |  |  | Number of vacant post against sanctioned |  |  | Target for Filling up of vacant posts |  |  |  |  |  |
|  |  | R | C | Total |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | R | C | Total | 2012-13 |  |  | 2013-14 |  |  |
|  |  |  |  |  |  |  |  | R | C | Total | R | C | Total |
| 45 | Gynecologists | 7 | 2 | 9 | 0 | 2 | 2 |  |  |  |  |  |  |
| 46 | Pediatricians | 6 | 2 | 8 | 0 | 1 | 1 |  |  |  |  |  |  |
| 47 | Anesthetists | 3 | 2 | 5 | 0 | 1 | 1 |  |  |  |  |  |  |
| 48 | Other Specialists | 29 | 2 | 31 | 0 | 0 | 0 |  |  |  |  |  |  |
| 48 | Doctors | 152 | 55 | 207 | 0 | 15 | 15 |  |  |  |  |  |  |
| 49 | Staff Nurses | 402 | 231 | 633 | 6 | 0 | 6 |  |  |  |  |  |  |
| 50 | LHV | 85 | NA | 85 | 12 | NA | 12 |  |  |  |  |  |  |
| 51 | ANM | 241 | 295 | 536 | 64 | 9 | 73 |  |  |  |  |  |  |
| 45 | MPW | 263 | NA | 124 | 387 | 107 | - |  |  |  |  |  |  |
| 46 | Laboratory Technicians (D ) | 67 | 36 | 103 | 25 | 4 | 29 |  |  |  |  |  |  |
|  | Laboratory Technicians ( C ) | NA | 18 | 18 | NA | 8 | 8 |  |  |  |  |  |  |
| 47 | Pharmacists | 93 | 18 | 111 | 9 | 8 | 17 |  |  |  |  |  |  |
| 48 | Others:- Dental Surgeons | 28 | 40 | 68 | 0 | 18 | 18 |  |  |  |  |  |  |
|  | X-ray Tech | 44 | 18 | 62 | 7 | 3 | 10 |  |  |  |  |  |  |
|  | FP Counsellor | NA | 2 | 2 | NA | 0 | 0 |  |  |  |  |  |  |
|  | BEE | 14 | 9 | 23 | 0 | 0 | 0 |  |  |  |  |  |  |

| L. 2 | Category | New post Creation (as per IPHS) |  |  |  |  |  | Filling up of vacant posts |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012-13 |  |  | 2013-14 |  |  | 2012-13 |  |  | 2013-14 |  |  | 2014-15 |  |  |
|  |  | R | C | Total | R | C | Total | R | C | Total | R | C | Total | R | C | Total |
| 49 | Gynecologists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 50 | Pediatricians |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 51 | Anesthetists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 52 | Other Specialists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 53 | Doctors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 54 | Staff Nurses | 38 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 55 | LHV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 56 | ANM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 | MPW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 58 | Laboratory Technicians |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 59 | Pharmacists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 60 | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Information on Programme Management Units |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Level | No. of Regular Staff |  | No. of contractual Staff in important positions like Programme managers and Consultants who have been employed for their technical expertise |  |  |  |  | No. of contractual support staff such as programme assistants/ DEOs/ typists/ peons |  |  | Total Number of Staff in SPMU |  |  |
| SPMU | 8 |  | 5 |  |  |  |  | 18 |  |  | 31 |  |  |
| DPMU | 2 |  | 9 |  |  |  |  | 46 |  |  | 57 |  |  |
| BPMU |  |  |  |  |  |  |  | 66 |  |  | 66 |  |  |
| Total | 10 |  | 14 |  |  |  |  | 130 |  |  | 154 |  |  |
| CHAPTER 2: OUTCOME ANALYSIS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY* |  |  | Financial |  |  |  |  | Physical |  |  |  |  |  |
|  |  |  | 2010-11 |  |  | 2011-12 |  | 2010-11 |  |  |  |  |  |
|  |  |  | Amount Approved |  | Exp | Amount Approved | Exp | Expected Output |  | Achievements | Expected Output |  | Achievements |
| RCH Flexipool |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maternal Health |  |  | 21.48 |  | 13.27 | 28.48 | 6.55 |  |  |  |  |  |  |
| Child Health |  |  | 6.80 |  | 6.03 | 17.93 |  |  |  |  |  |  |  |
| Family Planning |  |  | 5.50 |  | 4.54 | 14.55 | 4.50 |  |  |  |  |  |  |
| ARSH |  |  | 12.60 |  | 6.58 | 63.28 |  |  |  |  |  |  |  |
| Urban RCH |  |  | 31.00 |  | 17.84 | 31.32 | 12.28 |  |  |  |  |  |  |
| Tribal RCH |  |  | - |  | - | - | - |  |  |  |  |  |  |
| PNDT & Sex Ratio |  |  | 1.40 |  | 1.40 | 2.40 | 1.20 |  |  |  |  |  |  |
| Infrastructure & HR |  |  | 419.50 |  | 373.96 | 1298.41 | 657.59 |  |  |  |  |  |  |
| Training |  |  | 180.66 |  | 120.44 | 184.95 | 28.20 |  |  |  |  |  |  |
| Program Management |  |  | 182.50 |  | 105.40 | 186.55 | 129.49 |  |  |  |  |  |  |
| Vulnerable Groups |  |  |  |  |  |  |  |  |  |  |  |  |  |
| JSY |  |  | 165.60 |  | 139.54 | 178.21 | 71.60 |  |  |  |  |  |  |
| Sterilisation & IUD compensation and NSV camps |  |  | 39.63 |  | 23.15 | 38.36 | 15.35 |  |  |  |  |  |  |
| Other Activities approved under RCH during 2010-11 such as PPP/NGO, Institutional Strengthening, IEC/BCC, Procurement |  |  | 537.21 |  | 435.62 |  |  |  |  |  |  |  |  |
| Mission Flexible Pool |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ASHA Programme |  |  | 94.3 |  | 36.77 | 53.73 | 31.35 |  |  |  |  |  |  |
| Untied Fund |  |  | 138.25 |  | 139.53 | 138.75 | 137.55 |  |  |  |  |  |  |
| AMG |  |  | 71.5 |  | 40.17 | 77.50 | 65.30 |  |  |  |  |  |  |
| Hospital Strengthening |  |  | - |  | 1140 | - | - |  |  |  |  |  |  |
| New Construction/ Renovation and setting up |  |  | 592 |  | 968 | 123 | 151.64 |  |  |  |  |  |  |
| Corpus grants to HMS/RKS |  |  | 107.003.67 |  | 79.95 | 109.00 | 109.00 |  |  |  |  |  |  |
| DHAP |  |  | 32.00 |  | 20.03 | 50.00 | 28.96 |  |  |  |  |  |  |
| Panchayati Raj Initiative |  |  | 16.6 |  | - | - | - |  |  |  |  |  |  |
| Mainstreaming of AYUSH |  |  | - |  | - | 42.00 | 23.40 |  |  |  |  |  |  |
| IEC-BCC NRHM |  |  | 169.19 |  | 67.90 | 89.00 | 24.60 |  |  |  |  |  |  |
| Mobile Medical Units |  |  | 169.23 |  | 75.10 | 169.65 | 131.26 |  |  |  |  |  |  |
| Referral Transport |  |  | - |  | - | 69.60 | - |  |  |  |  |  |  |
| PPP/NGO |  |  | - |  | - | 6523 | 50.93 |  |  |  |  |  |  |
| Planning, Implementation and Monitoring |  |  | 57.74 |  | 3.67 | 99.65 | 37.79 |  |  |  |  |  |  |
| Procurement |  |  | 50.85 |  | 55.83 | 584.10 | 443.01 |  |  |  |  |  |  |
| Regional Drugs warehouses |  |  | - |  | - | 9.49 | - |  |  |  |  |  |  |
| New Initiatives/ Strategic Interventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Insurance Scheme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research, Studies, Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |
| State level health resources center (SHSRC) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support services |  |  | - |  | - | 29.39 | 29.77 |  |  |  |  |  |  |
| Other expenditures |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobility support for Supervision and Monitoring at districts and State level. |  |  | 5.50 |  | 5.50 | 5.50 | 4.28 |  |  |  |  |  |  |
| Cold chain maintenance |  |  | 1.23 |  | 1.23 | 1.53 | 0.82 |  |  |  |  |  |  |
| Alternate Vaccine Delivery to Session sites |  |  | 10.32 |  | 7.18 | 10.32 | 8.02 |  |  |  |  |  |  |
| Focus on urban slum & underserved areas |  |  | 14.61 |  | 3.07 | 14.61 | 0.39 |  |  |  |  |  |  |
| Social Mobilization by ASHA /Link workers |  |  | 15.48 |  | - | 15.48 | 7.50 |  |  |  |  |  |  |
| Computer Assistants support at State/district level |  |  | 11.22 |  | 7.56 | 11.22 | 8.02 |  |  |  |  |  |  |
| Printing and dissemination of immunization cards, tally sheets, charts, registers, receipt book, monitoring formats etc. |  |  | 1.53 |  | 1.22 | 1.53 | - |  |  |  |  |  |  |
| Quarterly review meeting at State/District/Block level |  |  | 2.15 |  | 0.75 | 2.15 | 2.31 |  |  |  |  |  |  |
| District level Orientation for 2 days ANMs, MPHW,LHV |  |  | 2.65 |  | - | 0.79 | 0.79 |  |  |  |  |  |  |
| Trainings |  |  | 4.26 |  | 6.46 | 4.26 | 4.70 |  |  |  |  |  |  |
| To develop micro plan at sub-centre level and block level |  |  | 0.8 |  | 0.8 | 0.8 | 0.8 |  |  |  |  |  |  |
| For consolidation of micro plan at PHC/CHC level |  |  | - |  | - | - | - |  |  |  |  |  |  |
| POL for vaccine delivery from State to District and PHC/CHCs |  |  | 9.0 |  | 9.0 | 9.0 | 6.54 |  |  |  |  |  |  |
| Consumables for computer including provision for internet access |  |  | 0.43 |  | 0.47 | 0.43 | 0.33 |  |  |  |  |  |  |
| Red/Black/Zipper bags |  |  | 0.80 |  | - | 0.80 | 0.80 |  |  |  |  |  |  |
| Bleach/Hypochlorite solution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Twin Bucket |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disease Control Program |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NVBDCP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Malaria |  |  | 419.5 |  | 344.27 | 413.00 | 200.64 |  |  |  |  |  |  |
| Filaria |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Dengue/Chikungunya |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash assistance for decentralized commodities |  |  | 17.35 |  | 17.30 | 15.00 | 7.30 |  |  |  |  |  |  |
| Commodity support by GoI |  |  | 280.28 |  | - | 373.72 | - |  |  |  |  |  |  |
| IDSP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surveillance preparedness, training & staff salary |  |  | 84.90 |  | 38.14 | 92.92 | 44.47 |  |  |  |  |  |  |
| Outbreak investigation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis & use of data |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NPCB |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grant in aid (for Cataract Operations) |  |  | 22.50 |  | 26.00 | 22.50 | 22.50 |  |  |  |  |  |  |
| Vision Centre (50X50,000) |  |  | 2.50 |  | 2.50 | 2.50 | 2.48 |  |  |  |  |  |  |
| Medical Colleges (3X40) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strengthening of District Hospital / Sub District Hospital |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Eye Donation Centre (Non Recurring 3X1) |  |  | 1.00 |  | 1.00 | 1.00 | 1.00 |  |  |  |  |  |  |
| Remuneration (SBCS) & Staff Salary/ Other Activities/Post Requirement |  |  | 30.64 |  | 27.03 | 42.80 | 26.85 |  |  |  |  |  |  |
| IEC Activities (50X20 Thousand + SBCS 1 Lacs) |  |  | 7.83 |  | 9.56 | 10.00 | 5.09 |  |  |  |  |  |  |
| Proposal for Sutures /(Per Pieces 10.0) /Ophth. Equipments |  |  | 5.00 |  | 45.29 | 25.00 | 33.55 |  |  |  |  |  |  |
| NIDDCP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishment of IDD Control Cell |  |  | 36.00 |  | 5.30 | 26.99 | 2.50 |  |  |  |  |  |  |
| Establishment of IDD |  |  |  |  | 4.2 |  | 1.10 |  |  |  |  |  |  |
| Monitoring Lab |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a)Health Education and Publicity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) Salt Testing Kits supplies by GOI (3,84,000 No) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IDD surveys |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NLEP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractual Services |  |  | 11.00 |  | 13.35 | 19.80 | 11.29 |  |  |  |  |  |  |
| Services through ASHA/USHA |  |  | 1.50 |  | 3.80 | 10.00 | 4.80 |  |  |  |  |  |  |
| Office expenses & Consumables |  |  | 1.50 |  | 4.69 | 2.05 | 2.18 |  |  |  |  |  |  |
| Capacity building |  |  | 5.00 |  | 1.88 | 2.80 | 0.58 |  |  |  |  |  |  |
| Behavioural Change Communication |  |  | 10.00 |  | 6.31 | 15.00 | 4.25 |  |  |  |  |  |  |
| POL/Vehicle operation & hiring |  |  | 5.00 |  | 6.22 | 4.10 | 4.16 |  |  |  |  |  |  |
| DPMR |  |  | 1.50 |  | 0.00 | 1.94 | 1.75 |  |  |  |  |  |  |
| Material & Supplies |  |  | 1.00 |  | 0.00 | 0.90 | 0.00 |  |  |  |  |  |  |
| Urban Leprosy Control |  |  | 0.50 |  | 0.00 | 0.20 | 0.00 |  |  |  |  |  |  |
| Supervision, Monitoring & Review |  |  | 3.00 |  | 0.03 | 2.62 | 0.00 |  |  |  |  |  |  |
| Cash assistance |  |  | 2.00 |  | 0.00 | 0.00 | 0.00 |  |  |  |  |  |  |
| NIPPCD |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building PHCs/CHCs & District Hospitals |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Manpower at district level |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Screening Camps |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hearing Aids 200 HI per district per year |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Central Cell at State level |  |  |  |  |  |  |  |  |  |  |  |  |  |

CHAPTER 3: POLICY AND SYSTEMIC REFORMS IN STRATEGIC AREAS

| S. NO. | Strategic Areas | Target for Policy and Systemic reforms | New Policies should try to address the following issues |
| --- | --- | --- | --- |
| 1. | HR policies for Doctors, Nurses paramedical staff and programme management staff |  | As mentioned in the PIP guidelines, Contractual staff under NRHM regularization under the State Government was put up in the Mizoram State Health Mission, absorption of 25% of the contractual staff under NRHM has been resolved in meeting. |
| 2. | Accountability and Performance appraisal |  | Facility based monitoring; Incentive for both the HSP and the facility based on functioning. Performance appraisal against benchmarks, renewal of contracts based on performance. Incentives for performance above benchmark, special Incentives for difficult areas. |
| 3. | Policies on drugs, procurement system and Logistics management |  | Procurement will be done as per GOI guidelines, and implementation of ProMIS has been under process |
| 4. | Equipments |  | Availability of essential functional equipments in all Facilities, regular needs assessment. Timely indenting and procurement and identification of unused/faulty equipment, regular maintenance and MIS. |
| 5. | Ambulance Services and Referral Transport |  | This has been addressed under JSSK and Emergency referral scheme and from |

| 6 | Maintenance of Buildings. Sanitation, Water, Electricity, laundry, kitchen |  | 24 x 7 maintenance and round the clock plumbing, electrical, carpentry services, power backup, cleanliness and sanitation in PH facilities, upkeep of toilets, Electricity, clean linen, diet for pregnant women. |
| --- | --- | --- | --- |
| 7 | Diagnostics |  | It should be addressed under JSSK Scheme |
| 8 | Patients feedback and grievance redressal |  | Complaint box / Feedback box should be put up in each and every primary health care level |
| 9 | Private Public Partnership (PPP) |  | To supplement Govt effort in underserved area, partnership with mission hospital in Marpara PHC. Another newly established institution under border area (i.e Borapansury) by state Govt was decided by the state Health Mission to hand over to Autonomous District council for specific period as the state govt faced difficulty in posting manpower due to financial constraint presently. The area needs upliftment due to increase influx of population from other states. |
| 10 | Intersect oral convergence |  | There is a good effective coordination in supplying of clean water to Health institute with PHE Dept., school health programme, Adolescent health and IEC with Education Dept. Good relationship with AWW and other social welfare Dept etc. at present more effort in Maternal and child health activities with social welfare dept. like IMGSY, SABLA and MCTS etc. |
| 11 | Community mobilization |  | Active Community participation is acquired by sensitizing the public leader and religious leader with NGOs. Well organized strong VHSC meet regularly and social audit done regularly. PHC Doctors are mobilized to supervise VHS&NC. |
| 12 | IEC |  | More effort on IEC through public leaders and political leaders at various level i.e member of autonomous District council, village panchayat and NGOs especially targeting three backward District i.e Mamit, Saiha and Lawngtlai District. More effort to motivate District administrative personnel by giving more responsibilities within their District so as to increase public awareness on health care service and activities. |
| 13. | Civil Registration Sys tem (CRS) |  | 100% registration of births and deaths, capturing of births in private institutions, reliability to health data on institutional deliveries, sex ratio etc. |
| 14. | Supportive Supervision |  | For supervision of field activities more financial support for mobility is given to District authorities and also at block/PHC level. |
| 15. | Monitoring and Review |  | At present HMIS data cannot be operated in the state due to lack of IT facilities and problems in allocating various village under ministry web portal. Effort is under process with Central Government to overcome such difficulties. At present, PHC/Block level are informed to submit as before so as to have regular analysis of state performance in order to have regular and effective monitoring and supervision. State and District level committee are doing monitoring and evaluation at the District level. |
| 16 | Meetings of State Health Mission/Society/Dist rict Health Society |  | The State Health Mission has been organized regularly and the meetings for the District Health Society have been observed periodically. Review meeting, future road map and agenda have been followed up. |
| 17 | Medical Colleges (New Colleges and Upgradation of existing ones) |  | State Government after seeing health situation, in order to improve our present status, effort for establishing Medical College is under process. Besides this, up gradation of our existing Health institutions are under progress in order to strengthen NRHM activities. |
| 18 | Nursing Schools |  | Beside the existing one Government Nursing College and one Government GNM School and three private Nursing School with one regional institute under MOHFW named RIPANS – where Para medical courses are being conducted . GOI allowed the State to open 4 GNM school in different district. Construction of infrastructure being started from November 2011. When all these institutions are made functional it is expected that about 350 Nurses approx. will be provided by the State. The State will be able to export skilled manpower to other State and even to foreign countries. |
| 19 | Paramedical education |  | In order to improve quality of services and enhance activities regular training of Para medical staff like SBA, NSSK, IUCD, IMNCI, IMEP, RTI/STI etc. are regularly done. Besides these, in-service training in medical care, administration and nursing care are done by State Government. |
| 20 | Capacity building |  | As already stated above, in-service training are conducted for all Doctors and Para Medicals in Skill trainings and a centralized log is formulate under RCH as well as by different specific Health Programmes. |

- RCH Flexi Pool

RCH Monitorable indicators:

Quarterly targets both for High Focus districts and other districts and State total for RCH monitorable indicators should also be provided in the format below:

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A | Maternal Health |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.1 | % Pregnant women registered for ANC in the quarter | 72.8 | 76.9 | 21 | 22.5 | 21 | 22.5 | 21 | 22.5 | 21 | 22.5 | 85 | 90 |
| A.1.2 | % PW registered for ANC in the first trimester, in the quarter | 1849 (46%) | 10155(56.6%) | 48 | 60 | 50 | 62 | 53 | 65 | 55 | 70 | 55 | 70 |

| A.1.3 | Institutional deliveries (%) in the quarter | 1774 (59.6%) | 12183 (83%) | 62 | 85 | 63 | 86 | 65 | 88 | 75 | 90 | 75 | 90 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.1 | % unreported deliveries in the quarter | 22% 9 | 17% | 30 | 20 | 25 | 15 | 20 | 10 | 15 | 10 | 15 | 10 |

| SN. | INDICATOR |  | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  |  | Annual Target |  |
|  |  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |  | HF Distts. | State total |
| A.2.2 | % high risk pregnancies identified (a) % women having hypertension | 24 (0.59% against total ANC) |  | 248 (1.38% against total ANC) | 1 | 2 | 2 | 3 | 2.5 | 4 | 3 |  | 5 | 3 | 5 |
|  | (b) % women Having low Hb level | 5 (0.12%) |  | 56 (0.31%) | No Target |  |  |  |  |  |  |  |  |  |  |
| A.2.3 | % of Home Delivery by SBA (i.e. assisted by doctor/ nurse/ ANM) | 461 (35 %) |  | 1102 (44.6%) | 36 | 45 | 37 | 48 | 40 | 50 | 50 |  | 60 | 50 | 60 |
| A.2.4 | C-sections performed (%) (a) in Public facilities | 38 (2.14%) |  | 809 (7.9%) | 2.5 | 7.9 | 3 | 7.9 | 3 | 7.9 | 4 |  | 8 | 4 | 8 |
|  | (b) in private | 21 (13.8%) |  | 412 (21%) | 12 | 18 | 11 | 16 | 11 | 16 | 10 |  | 15 | 10 | 15 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
|  | accredited facilities |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5 | % of deliveries discharged after at least 48 hours of delivery (out of public inst deliveries) | 618 (34.8%) | 2949 (28.8%) | 37 | 37 | 38 | 38 | 39 | 39 | 40 | 40 | 40 | 40 |
| A.2.6 | % of still births | 30 (0.9%) | 123 (0.8%) | 0.8 | 0.7 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 |
| A.2.7 | %age of maternal deaths audited | 2 (100%) | 10 (100%) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| A.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.1 | % of 24x7 PHCs operationalised as per the GoI guidelines | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |
| A.3.2 | % of FRUs operationalised as per the GoI guidelines (Current status and target indicated in absolute no.) | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 |
| A.3.3 | % of SCs doing More than 3 deliveries per month. ( status & target indicated in absolute no) | 0 | 37 | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 5 | 9 | 18 |
| A.3.4 | % of PHCs/non FRU CHCs doing 10 deliveries per month | NA | NA | 0 | 0 | 1 | 5 | 1 | 4 | 1 | 2 | 3 | 10 |
| A.3.5 | % of FRUs (except DH) conducting 20 deliveries per month. | - | - | - | - | - | - | - | - | - | - | - | - |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A.3.6 | % ANMs/ LHVs/ SNs trained as SBA | 46.4 | 32.94 | 0 | 23 | 0 | 27 | 0 | 27 | 0 | 23 | 0 | 100 |
| A.3.5 | % doctors trained as EmOC . ( status & target indicated in absolute no) | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 (for lawngtlai Dist) |
| A.3.6 | % doctors trained as LSAS . ( status & target indicated in absolute no) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |
| A.4 | HR productivity |  |  |  |  |  |  |  |  |  |  |  |  |
| A.4.1 | % of LSAS trained doctors giving spinal anaesthesia | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70 |
| A.4.2 | Average no. of c-sections assisted by LSAS trained doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| A.4.3 | % of EmOC trained doctors conducting c-sections. | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70 |
| A.4.4 | Average no. of c-sections performed by EmOC trained doctor | 0 | 13 | 0 | 3 | 0 | 6 | 0 | 11 | 0 | 15 | 0 | 15 |
| A.4.5 | Average no. of deliveries performed by SBA trained SN/LHV/ANM | NA | 0 | State HMIS does not capture this data. It is expected to be in place in the coming year |  |  |  |  | 0 | 0 | 0 | 0 | 0 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A.4.6 | % of SBA trained ANMs/SNs conducting deliveries | 75 | 90.6 | 75 | 100 | 75 | 100 | 80 | 100 | 80 | 100 | 80 | 100 |
| A.5 | Facility utilization |  |  |  |  |  |  |  |  |  |  |  |  |
| A.5.1 | % of FRUs conducting C- section | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| A.5.2 | Average no. of c- sections per FRU | 5 | 193 | 0 | 50 | 0 | 50 | 0 | 50 | 0 | 50 | 0 | 200 |
| A.5.3 | Average no. of MTPs performed in FRUs | 4 | 39 |  | 10 |  | 10 |  | 10 |  | 10 |  | 40 |
| A.5.4 | Average no. of deliveries per 24x7 PHCs per month |  | 11 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |
| A.5.5 | Average no. of MTPs performed per 24x7 PHC |  | 0.3 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.4 |
| A.5.6 | % of SC conducting at least 5 deliveries per month | 0 | 0 |  | - | - | - | - | - | - | - | - | - |
| B | Child Health |  |  |  |  |  |  |  |  |  |  |  |  |
| B.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| B.1.1 | Children 9-11 months age fully immunised (%)(Against estimated below 1 year) | 48 % (2688) | 60 % (13996) | 50 | 65 | 60 | 70 | 70 | 80 | 83 | 90 | 83 | 90 |
| B.1.2 | % children Breast fed within 1 hour of birth | 2592 (81%) | 12439 (85.6%) | 84 | 86 | 86 | 89 | 88 | 92 | 90 | 95 | 90 | 95 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| B.1.3 | % of low birth weight babies | 64 (2.42%) | 677 (5%) | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 |
| B.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| B.2.1 | %age of women receiving PP check up to 48 hrs to 14 days | 1082 (33.47% against Total delivery) | 9708 (66.26% against Total delivery) | 35 | 67 | 38 | 68 | 40 | 69 | 55 | 70 | 55 | 70 |
| B.2.3 | % drop out from BCG to measles | 260 (8%) | 1253 (8%) | 6 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 |
| B.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| B.3.1 | % of SNCUs Operationalised (Indicated in absolute no) |  | 0 |  |  |  |  |  |  |  | 1 |  | 1 |
| B.3.2 | % of stabilisation units operationalised | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 40 | 0 | 0 | 3 | 5 |
| B.3.3 | % of new born baby care corners operationalised | 0 | 0 | 9.5 | 28.5 | 9.5 | 28.5 | 9.5 | 28.5 | 4.7 | 14.5 | 0 | 21 |
| B.3.4 | % of personnel trained in IMNCI | 0 | 40.83 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 100% (120 Nos) |
| B.3.5 | % of personnel trained in F-IMNCI | 0 | 22.62 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 100% (144 Nos) |
| B.3.6 | % of personnel trained in NSSK | 0 | 11.86 | 0 | 26 | 0 | 26 | 0 | 22 | 0 | 26 | 0 | 100% (360 Nos) |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| B.4 | Facility utilization |  |  |  |  |  |  |  |  |  |  |  |  |
| B.4.1 | Average no. of children treated in SNCUs | 0 | 933 | 0 | 300 | 0 | 300 | 0 | 300 | 0 | 300 | 0 | 1200 |
| B.4.2 | Average no. of children treated in NBSUs | 0 | 120 | 0 | 45 | 0 | 45 | 0 | 45 | 0 | 45 | 0 | 180 |
| C | Family Planning |  |  |  |  |  |  |  |  |  |  |  |  |
| C.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| C.1.1 | % of total sterilisation against ELA | 311 (78%) | 1445 (41%) | 79 | 79 | 79 | 79 | 79 | 79 | 80 | 80 | 80 | 80 |
| C.1.2 | % post partum sterilisation | 87 (44%) | 578 (38%) | 47 | 40 | 50 | 60 | 60 | 70 | 75 | 80 | 75 | 80 |
| C.1.3 | % male sterilizations | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 4 |
| C.1.4 | % of IUD insertions against planned | 265 (44%) | 2090 (42%) | 47 | 50 | 50 | 60 | 60 | 70 | 70 | 80 | 70 | 80 |
| C.1.5 | % IUD retained for 6 months | NA | NA | 65 | 75 | 70 | 80 | 75 | 85 | 80 | 90 | 80 | 90 |
| C.1.6 | % Sterilization acceptors with 2 children | NA | NA | 50 | 60 | 50 | 60 | 50 | 60 | 50 | 60 | 50 | 60 |
| C.1.7 | % Sterilisation acceptors with 3 or more children | NA | NA | 63 | 75 | 65 | 76 | 68 | 77 | 70 | 80 | 70 | 80 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| C.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| C.2.1 | % of complications following sterilisation | 6 (2% out of female sterilization) | 30 (2% out of female Sterilization) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| C.3.1 | % doctors trained as minilap | - | 50 |  | 20 |  | 40 |  | 20 |  | 20 |  | 10 |
| C.3.2 | % doctors trained as NSV | - | - |  |  |  |  |  |  |  | 100% |  | 100% (1 No) |
| C.3.3 | % doctors trained as laparoscopic sterilisation | - | - |  |  |  |  |  | 100% |  |  | - | 100% (1 Team) |
| C.3.4 | % ANM/LHV/SN/MO trained in IUD insertion |  | 136% |  |  |  | 60 |  | 40 |  |  | - | 100% (50 Nos) |
| C.4 | HR productivity |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.1 | Average no. ofNSVs con ducted by trained doctors | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.4.2 | Average no. of minilap sterilisations conducted by minilap trained doctors | 4 | 11 | 40 | 240 | 40 | 240 | 40 | 240 | 40 | 240 | 160 | 960 |
| C.4.3 | Average no. of laparoscopic |  |  |  |  |  |  |  |  |  |  |  |  |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
|  | sterilisations conducted by lap sterilisation trained doctors |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.4 | Average no. of IUDs inserted by MO trained in IUD insertion |  | 3 | 10 | 62 | 10 | 62 | 10 | 63 | 10 | 63 | 40 | 250 |
| C.4.5 | Average no. of IUDs inserted by MO trained in IUD insertion |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.6 | Average no. of IUDs inserted by SN/ LHV/ ANM trained in IUD insertion | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.5 | Facility utilisation |  |  |  |  |  |  |  |  |  |  |  |  |
| C.5.1 | Average no. of sterilizations performed in FRUs | 24 | 129 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 |
| C.5.2 | Average no. of sterilizations performed in 24x7 PHCs | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |

RCH FLEXIPOOL BUDGET SUMMARY:

| Sl.No | Components | FMR Code | Amount Proposed 2012-13 ( in lakhs) |
| --- | --- | --- | --- |
| 1 | Maternal Health including JSY | A.1 | 514.05 |
| 2 | Child Health | A.2 | 60.70 |
| 3 | Family Planning including Compensation | A.3 | 75.24 |
| 284 | Adolescent Reproductive and Sexual Health | A.4 | 78.60 |
| 5 | Urban RCH | A.5 | 31.38 |
| 6 | Tribal RCH | A.6 |  |
| 7 | PNDT & Sex Ratio | A.7 | 4.00 |
| 8 | Infrustructure and Human Resources | A.8 | 1547.39 |
| 9 | Training | A.9 | 152.90 |
| 10 | Programme Management | A.10 | 355.50 |
| 11 | Vulnerable Groups | A.11 |  |
| Total |  |  | 2819.76 |

I.MATERNAL HEALTH

GOAL: To reduce MMR from 68.82 (State HMIS) to 65 in 2012-13 and to 35 by 2016-17

| Year | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 |
| --- | --- | --- | --- | --- | --- |
| MMR (State HMIS) | 58 | 20 | 50 | 72 | 68.82 |

In order to achieve the target set for for the next 5 years various activities such as relocation of staff, up gradation of health facilities, training of health providers, IEC/BCC activities, outreach services, monitoring will be emphasized. The Maternal Death review findings will be prioritized and actions will be taken based on their findings. Priority will be given to low performing districts/High focus districts namely Saiha, Lawngtlai and Mamit districts.

Maternal Health Key Strategies

- Increasing the accessibility of essential and emergency obstetrics and new born care services.

- Improving the quality of care through skill trainings and better equipments

- Improving the coverage and quality of antenatal, intranatal and postnatal care,  with emphasis on detection of anaemia

- Improving referral Services

- Ensure availability of blood at all blood storage facilities

- Improving the accessibility of safe abortion services by training of  untrained MOs in MTP and Abortion Care.

Maternal Health Major Interventions

- Operationalization of 4 FRUs at Kolasib DH, Champhai DH, Kulikawn SDH and Vairengte CHC

- Implementation of JSSK throughout the State

- Improving ANC & PNC services by giving incentives to ASHA

- Providing facility for Hb testing at all Sub Centres

- Institutional and Community level Maternal Death Review

- Capacity building of various Health Personnel

- Improving quality of Services by Quality Assurance Committee at all levels

MH FORMAT FOR PIP

Progress on key MH indicators :

| MMR | RGI (2004-06) | RGI (2007-09) | AHS (2010-11) |
| --- | --- | --- | --- |
|  | NA | NA | NA |

| Indicators (in %) | DLHS III | CES (2009) | HMIS (2010-11) | HMIS (2011-12) upto Nov, 2011 |
| --- | --- | --- | --- | --- |
| Any ANC | 89.5 | 91.9 | 100 | 76.9 |
| 3+ ANC | 75.6 | 79 | 77 | 78.3 |
| Registration within 12 weeks | 44 | - | 46 | 56.6 |
| Full ANC | 32.9 | 21.7 | 77 | 78.3 |
| Ins. Delivery | 55.9 | 83 | 81 | 83 |
| Safe Delivery | 63.5 | 85.1 | 90 | 93 |
| Home Delivery | 42.7 | 17 | 19 | 17 |
| % of C-Sections out of total reported institutional deliveries | - | 9.2 | 9.6 | 10 |
| At Public | - | - | 8.6 | 7.9 |
| At Private | - | - | 25 | 21 |
| % of Anaemic women out of total registered pregnancies | - | - | 7 | 10 |
| % of severely anaemic women out of total anaemic pregnant women | - | - | 2 | 3 |

Achievements

| Activity | 2010-11 (cumulative) | 2011-12 (till Nov) (cumulative) |
| --- | --- | --- |
| No. of fully functional FRUs | 4 | 4 |
| No of fully functional 24x7 PHCs | NA | 20 |
| No. of Blood Banks licensed and functional | NA | 7 |
| No. of Blood banks non- functional due to any reason | NA | 1 |
| No. of Blood Storage Units licensed and functional | NA | 2 |
| No. of Blood Storage Units non- functional due to any reason | NA | 7 |
| No. of VHNDs held | 4360 | 2470 |
| No. trained in LSAS | 12 | 12 |
| No. trained in EmOC | 4 | 5 |
| No. trained in SBA | SN-118 ANM-69 | SN-134 ANM-117 |
| No. trained in MTP | 79 | 81 |
| No. trained in RTI/STI | MO-46 HW-770 | MO-46 HW-770 |
| No. of Maternal deaths reported | 16 | 10 |
| No. of Maternal deaths reviewed | 16 | 8 |

Total functional delivery points in Public Health Facilities of Mizoram	Annexure A-I

State/UT-	Date as on -----

| S.No |  |  |  | Indicator |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Number |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  | Total No. of SCs |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 370 |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of SCs conducting >2 deliveries/month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36 |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  | Total No. of 24X7 PHCs |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 41 |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of 24X7 PHCs conducting > 6 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  | Total No. of any other PHCs |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16 |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of any other PHCs conducting > 6 deliveries/ month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  | Total No. of CHCs ( Non- FRU)/SDH |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 11 |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of CHCs ( Non- FRU) conducting > 6 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8 |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  | Total No. of CHCs ( FRU) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of CHCs (FRU) conducting > 20 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of CHCs (FRU) conducting C-sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  | Total No. of any other FRUs (excluding CHC-FRUs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of any other FRUs (excluding CHC-FRUs) conducting > 20 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of any other FRUs (excluding CHC-FRUs) conducting C- sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  | Total No. of DH |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8 |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of DH conducting > 30 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8 |  |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of DH conducting C-section |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7 |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  | Total No. of District Women And Children hospital (if separate from DH) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of District Women And Children hospital (if separate from DH) conducting > 50 deliveries /month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of District Women And Children hospital (if separate from DH) conducting C-section |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  | Total No. of Medical colleges |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of Medical colleges conducting > 50 deliveries per month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of Medical colleges conducting C-section |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| 10 |  |  |  | Total No. of Accredited PHF |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NA |  |  |  |  |  |  |  |  |
| a |  |  |  | No. of Accredited PHF conducting > 10 deliveries per month |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NA |  |  |  |  |  |  |  |  |
| b |  |  |  | No. of Accredited PHF conducting C-sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NA |  |  |  |  |  |  |  |  |
| Report on Delivery points on KPI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| District |  | Sl no |  | Name and Type of Facility |  |  | Total deliveries in the institution (including CS)(1st & 2nd Qtr figures only. Figures for S/C are available for October, 2011 only) |  | No. of CS (where applicable) |  | Total no of PW detected with Hb level 7gm and below |  | No of maternal deaths in the facility |  | Functional LR with NBCC |  | Functional OT |  | Functional BSU/BB |  |  | Availability of essential drugs |  | BMW |  | MO & Specialists posted |  | No of SN/ANM posted at facility |  |  |  |
| Aizawl East |  | 1 |  | Saitual CHC FRU |  |  | 20 |  | na |  | na |  | na |  | Y |  | y |  | y |  |  | Y |  | y |  | MO-2 |  | Sn-21 |  |  |  |
|  |  | 2 |  | Sakawrdai CHC |  |  | 10 |  | na |  | na |  | na |  | Y |  | y |  | y |  |  | Y |  | y |  | MO-1 |  | SN-6 |  |  |  |
|  |  | 3 |  | Thingsulthliah 24*7 PHC |  |  | 25 |  | na |  | na |  | na |  | Y |  | n |  | n |  |  | Y |  | y |  | MO-1 |  | SN-6 |  |  |  |
|  |  | 4 |  | Darlawn 24*7 PHC |  |  | 5 |  | na |  | na |  | na |  | Y |  | n |  | n |  |  | Y |  | y |  | MO-1 |  | SN-6 |  |  |  |
|  |  | 5 |  | Khawruhlian 24*7 |  |  | 12 |  | na |  | na |  | na |  | Y |  | n |  | n |  |  | Y |  | y |  | MO-1 |  | SN-4 |  |  |  |
|  |  | 6 |  | Phuaibuang 24*7 PHC |  |  | 4 |  | na |  | na |  | na |  | Y |  | y |  | y |  |  | Y |  | y |  | MO-1 |  | SN-4 |  |  |  |
| Aizawl West |  | 7 |  | Civil hospital, Aizawl FRU |  |  | 409 |  | 85 |  | na |  | 2 |  | Y |  | y |  | y |  |  | Y |  | y |  | MO-28,PG-68,Specialist-22 |  | S/N-203 |  |  |  |
|  |  | 8 | Kulikawn Hospital |  |  | 35 |  | na |  | Na |  | na |  | Y |  | y |  | y |  |  | Y |  | y |  | MO-2,Specialist-1 |  | SN -8 |  |  |  |
|  |  | 9 | Lengpui CHC |  |  | 7 |  | na |  | na |  | na |  | Y |  | n |  |  |  |  | Y |  | y |  | MO-2 |  | SN-5 |  |  |  |
|  |  | 10 | Sairang 24*7 PHC |  |  | 35 |  | na |  | na |  | na |  | Y |  | n |  | n |  |  | y |  | y |  | MO-1 |  | SN-6 |  |  |  |
|  |  | 11 | Hmunpui SC |  |  | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  |  | Y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |  |  |

| Champhai | 12 | Champhai DH |  | 65 |  | na |  | na |  |  |  | Y |  | y |  | y |  | Y |  | y |  | MO-7 |  | SN-24 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 13 | Ngopa CHC |  | 7 |  | na |  | na |  | na |  | Y |  | y |  | n |  | y |  | y |  | MO-1 |  | SN-6 |  |
|  | 14 | Kawlkulh 24*7 PHC |  | 8 |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-4 |  |
|  | 15 | Khawzawl 24*7 PHC |  | 8 |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-4 |  |
|  | 16 | Hnahlan 24*7 PHC |  | 8 |  | na |  | na |  | na |  | y(no NBCC) |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-2 |  |
|  | 17 | Farkawn 24*7 PHC |  | 25 |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-3 |  |
|  | 18 | Khawbung 24*7 PHC |  | 15 |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-4 |  |
|  | 19 | MimbungPHC |  | 9 |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | na |  | SN-3 |  |
|  | 20 | N E Khawdungsei PHC |  | 35 |  | na |  | na |  | na |  | n |  | n |  | n |  | y |  | y |  | MO-1 |  | SN-3 |  |
|  | 21 | Tlangsam SC |  | 3 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 22 | N. Khawbung SC |  | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | HW-1 |  |
|  | 23 | Ruantlang SC |  | 2 |  | na |  | na |  | na |  | N |  | n |  | n |  | n |  | y |  | na |  | H/W(F) – 2 |  |
|  | 24 | Hmunhmeltha SC | 0 |  | na |  | na |  | Na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-2 |  |
|  | 25 | Melbuk SC | 5 |  | na |  | na |  | na |  | n |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1 |  |
|  | 26 | Ngur SC | 3 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 27 | Sesih SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 28 | Khuangleng SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 29 | Dungtlang SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 30 | Samthang SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F) - 2 |  |
|  | 31 | Khuangthing SC | 4 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 32 | Dulte SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 33 | Hliappui SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 34 | Chhawrtui SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 35 | Tualte SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |
|  | 36 | Ngaizawl SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 37 | Vanzau SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
|  | 38 | Sazep SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1 |  |
|  | 39 | Khankawn SC | 1 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1,H/W(F)-1 |  |
|  | 40 | Vaphai SC | 5 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W(M)-1, H/W(F)-1 |  |
| Kolasib | 41 | Kolasib District Hospital | 61 |  | na |  | na |  |  |  | Y |  | y |  | y |  | y |  | y |  | MO-2 |  | SN-28 |  |
|  | 42 | Vairengte CHC | 30 |  | na |  | na |  | na |  | Y |  | y |  | y |  | y |  | y |  | MO-2 |  | SN-5 |  |
|  | 43 | Kawnpui 24*7 PHC |  |  | na |  | na |  | na |  | Y |  | n |  | n |  | y |  | y |  | MO-1 |  | S/N-5 |  |
|  | 44 | Saipum SC | 5 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W (F) - 1 H/W (M) – 1 |  |
|  | 45 | Saiphai SC | 0 |  | na |  | na |  | na |  | N |  | y |  | n |  | y |  | y |  | na |  | H/W (F) - 1 H/W (M) – 1 |  |
|  | 46 | Thingdawl SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W (F) - 1 H/W (M) – 1 |  |
|  | 47 | Bualpui SC | 0 |  | na |  | na |  | na |  | N |  | n |  | n |  | y |  | y |  | na |  | H/W (F) - 1 H/W (M) – 1 |  |
|  | 48 | N. Hlimen SC | 0 |  | na |  | na |  | na |  | N |  |  |  | n |  | y |  | y |  | na |  |  |  |
|  | 49 | Zanlawn SC | 2 |  | na |  | na |  | na |  | N |  | n |  | y |  | y |  | y |  | na |  | H/W (F) - 1 H/W (M) – 1 |  |
|  | 50 | Phaisen SC | 0 |  | na |  | na |  | na |  | N |  |  |  | n |  | y |  | y |  | na |  | H/W(F)-1 |  |

| Lawngtlai | 51 | Lawngtlai District Hospital | 35 | na | na |  | Y | y | y | y | y | MO-3, Specialist-1 | SN-10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 52 | Chawngte CHC | 5 | na | na | na | Y | N | y | y | y | MO-2 | S/N-7 |
|  | 53 | Bungtlang S 24*7 PHC | 33 | na | na | na | n | n | n | y | y | MO-1 | SN-3 |
| Lunglei | 54 | Lunglei District Hospital | 100 | 30 | na |  | Y | y | y | y | y | MO-6, Specialist-2 | S/N-46 |
|  | 55 | Tlabung SDH | 13 | na | na | na | y | y | n | y | y | MO-2 | SN-6 |
|  | 56 | Hnahthial CHC | 12 | na | na | na | y | n | n | y | y | MO-2 | SN-9 |
| Mamit | 57 | Mamit District Hospital | 22 | 2 | na | 1 | y | y | y | y | y | MO-2,Specialist-1 | S/N- 11 |
|  | 58 | Kawrthah CHC | 10 | na | na | na | y | y | y | y | y | MO-2 | SN-6 |
|  | 59 | Marpara 24*7 PHC | 4 | na | na | na |  | n | n | y | y | MO-1 | S/N-4 |
|  | 60 | West Phaileng 24*7 PHC | 7 | na | na | na | y | n | n | y | y | MO-1 | SN-3 |
|  | 61 | Kawrtethawveng PHC | 9 | na | na | na | y | n | n | y | y | MO-1 | SN-2 |
|  | 62 | Rawpuichhip PHC | 36 | Na | Na | Na | n | n | n | y | y | MO-1 | SN-3 |
| Saiha | 63 | Saiha District Hospital |  | 15 | na | na | y | y | y | y | y | MO- 5 Specialist-3 | SN-20 |
|  | 64 | Tuipang 24*7 PHC | 29 | Na | Na | Na | N | N | N | y | y | MO-1 | SN-3 |
| Serchhip | 65 | Serchhip District Hospital | 45 | 5 | na | na | Y | y | y | y | n | MO-3, Specialist-2 | S/N-23 |
|  | 66 | Thenzawl CHC | 20 | na | na | na | Y | y | y | y | y | MO-2 | SN-8 |
|  | 67 | North Vanlaiphai 24*7 PHC | 8 | na | na | na | Y | n | n | y | y | MO-1 | SN-3 |
|  | 68 | Chhiahtlang SC | 0 | na | na | na | N | n | n | n | y | na | H/W(F)-2 H/W(M)-2 |
|  | 69 | Keitum SC | 2 | na | na | na | n | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 70 | Bungtlang SC | 1 | na | na | na | N | n |  | n | y | na | H/W (F) - 1 |
|  | 71 | Mualcheng SC | 6 | na | na | na | N | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 72 | Thentlang SC | 0 | na | na | na | N | y | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 73 | Hmuntha SC | 0 | na | na | na | N | n | n | y | y | na | H/W F) - 2 |
|  | 74 | Hualtu SC | 2 | na | na | na | N | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 75 | Lungchhuan SC | 2 | na | na | na | N | n | n | n | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 76 | S. Chawngtui SC | 0 | na | na | na | N | N | n | N | y | na | H/W (F) - 1 H/W (M) - 1 |

Lessons Learnt and State Strategies

1. Burden of Normal Deliveries on District Hospitals

It has emerged from the State HMIS the major burden of all institutional deliveries fall at the Hands of the District Hospitals and the greatest burden falls on Civil Hospital, Aizawl which alone handles more deliveries than all the other District Hospitals combined. This burden of Normal in the Deliveries is putting an undue burden on the District Hospitals in providing care to the patients due to the sheer number of cases which results in an adverse level of care for patients who actually need the tertiary services provided and an adverse effect on the quality of  PNC, with 48 hours stay after delivery becoming virtually impossible. It also results in compromised manpower and other levels of care.

Response of the State :

- Functional operation of CHC FRUs, UHCs and CHC needs to be taken up on a priority basis. Delivery points will be prioritized.

- Prioritize the manpower training, acquisition of equipments and  supplies and supportive supervision at all levels below the District Hospitals

- Focus will be given to BEmOC training of Medical Officers to be able to handle both normal and assisted deliveries more efficiently.

- Monitoring of services at all MCH levels by both the District and the State Quality Assurance Team

- IEC/BCC activities to decrease the number of Home Deliveries and to make the public aware of the high quality of care available in those facilities below District Hospitals

- All ANMs and SNs posted in Delivery points who are yet to be trained in SBA will be trained batch-wise.

- Standard Treatment Protocols is planned to be displayed at all Delivery Points

2. Availability of Emergency Obstetrics Care

In Mizoram, only Civil hospital, Aizawl (rate 20%) and Serchhip District Hospital (rate 21%) have a high rate of LSCS. This can be attributed to the fact that most cases which require elective LSCS are sent to these two centers.

Response:

The disparity in the availability of Emergency Obstetrics Care is one of the challenges for the State and various steps are being undertaken to make these services more widely to the general public.

- Since there is a lack of specialists in the State, EmOC and LSAS trainings are given priority. The facilities where these trained MOs are to be posted is being made into fully functional CHC FRUs., however, the pace is slow due to problems in acquiring equipments. Re deployment of manpower will also be taken up.

- Monitoring of the CHC FRUs to ensure that Emergency Services are carried out in a proper manner and skill trainings are utilised

- The Blood Storage Facilities in all the CHCs will be strengthened with priority given to CHC FRUs.

3.  Quality of ANC/PNC Care and Anaemia during Pregnancy

| ANC (State HMIS April – November, 2011) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Total no. of pregnant women Registered for ANC | 3935 | 3,059 | 2307 | 1,555 | 1,689 | 2,080 | 1,266 | 1,088 | 974 | 17953 |
| No. registered within first trimester | 2,589 | 1,524 | 1646 | 1,082 | 642 | 894 | 653 | 554 | 571 | 10155 |

| INC (State HMIS) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Deliveries conducted at Public Institutions | 738 | 3797 | 1426 | 794 | 591 | 1049 | 558 | 625 | 652 | 10230 |
| No. of Deliveries at acctd Pvt Institutions | 1,293 | 137 | 0 | 0 | 152 | 371 | 0 | 0 | 0 | 1953 |
| Total no of institutional Deliveries | 2031 | 3934 | 1426 | 794 | 743 | 1420 | 558 | 625 | 652 | 12183 |

| Post Natal Care (April to November, 2011) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Total no of deliveries | 2200 | 4010 | 1660 | 989 | 1332 | 1822 | 931 | 970 | 738 | 14652 |
| Women receiving post partum check-up within 48 hours after delivery | 1157 | 3831 | 1013 | 877 | 748 | 1499 | 624 | 810 | 748 | 10952 |
| Women getting a post partum check up between 48 hours and 14 days | 2897 | 1931 | 1206 | 837 | 446 | 1358 | 391 | 245 | 393 | 9708 |
| PNC maternal complications attended | 11 | 0 | 3 | 0 | 6 | 0 | 15 | 0 | 5 | 40 |

| Post Natal Care (April to November, 2011) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Total no of deliveries | 2200 | 4010 | 1660 | 989 | 1332 | 1822 | 931 | 970 | 738 | 14652 |
| Women receiving post partum check-up within 48 hours after delivery | 1157 | 3831 | 1013 | 877 | 748 | 1499 | 624 | 810 | 748 | 10952 |
| Women getting a post partum check up between 48 hours and 14 days | 2897 | 1931 | 1206 | 837 | 446 | 1358 | 391 | 245 | 393 | 9708 |
| PNC maternal complications attended | 11 | 0 | 3 | 0 | 6 | 0 | 15 | 0 | 5 | 40 |

Annexure A-III

| Institutional Deliveries in both Public and Private Institution |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Facility | Total number of estimated deliveries in the State in current FY (2011-12) | Total No. of deliveries Conducted in current month (Nov, 2011) | Cumulative No. of deliveries Conducted in Fy. Year (April, 2011- to current month) | No of C-sections Conducted in the current month (Nov, 2011) | Cumulative No. of C- sections Conducted in Fy. Year (April – Nov , 2011) | No. of Maternal Deaths Reported in Fy. Year (April, 2011- to current month) |
| Public Health Facilities | 16100 | 1,342 | 10,230 | 104 | 809 | 6 |
| Private Accredited Health Facilities | 3430 | 226 | 1,953 | 53 | 412 | 2 |
| Other Private Health Facilities | NA | NA | NA | NA | NA | 2 |
| TOTAL | 19530 | 1,568 | 12,031 | 157 | 1,221 | 10 |

Annexure A-IV

| Key Performance Indicators (KPIs) for Maternal Health( District Compiled Sheet) |  |  |
| --- | --- | --- |
|  | Estimated No. of Pregnancies in the year 2011-12 | 23,500 |
|  | Estimated No. of Deliveries in the year 2011-12 | 23,000 |
| S. N. | Key Performance Indicators for Maternal Health | Cumulative achievement for the current Fin. Yr.( April-November 2011 ) |
| 1 | Total No. of Registered pregnancies | 17,953 |
|  | Pregnancies registered within 12 weeks | 10,155 |
| 2 | Deliveries conducted at Institution | 12,183 |
|  | Public | 10,230 |
|  | Private | 1,953 |
| 3 | Total No of C-section | 1,221 |
|  | Public | 809 |
|  | Private | 412 |
| 4 | Tracking of severe Anaemia |  |
|  | Total No. of PW detected with Hb level below 7 gm | 56 |
| 5 | Total No. of Maternal Deaths | 10 |
|  | Public | 6 |
|  | Private | 2 |
|  | Home | 2 |

In Mizoram the number of any ANC as per State HMIS is 79.4% (April – Dec 2011), of these only 56.7% are registered in the First Trimester. Due to this, a large number of problems remain unidentified or identified late, leading to complications and other undesirable outcomes at a later state. The no of Anaemic Pregnant women is low. Whether this is due to the fact that many women are not checked for Hb estimation due to unavailability of Hb meter set remains to be seen.

In some Hospitals in the State, most notably Civil Hospital, Aizawl, there is an acute shortage of beds. At a delivery rate of 350-450 per month and there are 21 beds. Due to this, most mothers are unable to stay for 48 hours after delivery. A new building for Obs & Gynae is being constructed, which is expected to be complete soon and will alleviate the situation.

In the meantime,to reduce delivery load of Civil Hospital Aizawl so that proper INC and PNC can be done, other Health facilities in Aizawl city will be promoted. The delivery load at the other Hospitals on the outskirts of the city namely, Kulikawn SDH, Falkawn Hospital, Ramhlun UHC, ITI UHC, Chawlhhmun UHC and Hlimen UHC is very low compared to Civil Hospital Aizawl.

Response:

- Hemoglobinometer with N/10 set is proposed to be acquired for all SCs, and all Health Workers will be trained at the nearest PHC in the use of it.

- MCPC has been given to all District CMOs and Sensitization of District Officials was done. They will in turn sensitize the ANMs and monitor the effective implementation and use of MCPC

- Supportive Supervision by both State and District officials will be initiated.

- Counseling of newly married couples by ANMs & ASHAs for early registration

- Pregnancy test kit has been provided to ANMs & ASHAs for early diagnosis of pregnancy.

- Observing Village Health and Nutrition day as per GOI guidelines in all the Anganwadi Centres. Regular monitoring of VHND by Medical Officer I/C. VHNDs will be given support supervision

- Incentives are given to ASHA for ANC, institutional delivery and PNC under JSY

- Tracking of pregnant mothers as per guidelines by ANMs & ASHAs up to 48 hrs after delivery. Monitoring of such activities is to be done regularly and budget kept under Monitoring.

- Incentive is proposed to be given to ASHAs for tracking of Mothers who avail private facilities @ Rs 50/- per case. Incentives will be given after 42 days of delivery

- Emphasis on 48 Hours Post delivery Stay: In some Hospitals in the State, most notably Civil Hospital, Aizawl, there is an acute shortage of beds. At a delivery rate of 350-450 per month and there are 21 beds. Due to this, most mothers are unable to stay for 48 hours after delivery. A new building for Obs & Gynae is being constructed, which is expected to be complete soon and will alleviate the situation. In order to reduce delivery load of Civil Hospital Aizawl other Health facilities in Aizawl city will be promoted. The delivery load at the other Hospitals on the outskirts of the city namely, Kulikawn SDH, Falkawn Hospital, Ramhlun UHC, ITI UHC, Chawlhhmun UHC and Hlimen UHC is very low compared to Civil hospital Aizawl. IEC activities to increase the delivery loads could alleviate Civil Hospital Aizawl and the performance of post delivery 48 hours stay may increase substantially. Moreover, Post natal kits is not given at Civil Hospital, Aizawl and only those mothers who stay for 48 hours after delivery are given post natal IEC activities to increase the delivery loads could alleviate Civil Hospital Aizawl and the performance of post delivery 48 hours stay may increase substantially. Moreover, Post natal kits is not given at Civil Hospital, Aizawl and only those mothers who stay for 48 hours after delivery are given post natal kits. Post natal kits to be given to mothers for institutional deliveries has been implemented since August 2010. It has been found to be effective and is proposed to be continued during 2012-13. The post natal kit worth is Rs 300/- per kit and will be distributed to the mothers in kind such as baby blanket/mosquito net/diaper etc. if they deliver in the health institutions. This will be in addition to other benefits like JSY, JSSK etc.

- The number of Institutional Deliveries is still less in the High Focus Districts. More emphasis on IEC activities is planned in these areas to bring the Pregnant Women into the institutional fold

Availability of HR and Capacity Building

| Availability of District-Wise Human Resource in the State – Annexure A-V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of District | Availability(in position) of Specialist/PGMO, MO, and other Staff ( Give total Numbers available in the distric) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Paediatrics | Anaesthetics |  | Gynaecology |  |  | No. of MO s |  | No of SNs |  | No of ANM s |  | MOs trained in LS AS | Mos trained in EmOC | No. of SBA Trained SNs/ ANMs | No. of LTs |  |
|  |  | Regul ar | Contra ctual | Regul ar |  | Con tract ual | Regul ar |  | Con tract ual |  |  |  |  |  |  |  |  |  |
| 1 | Aizawl East | - | - | - |  | - | - |  | - |  | 11 |  | 50 | 113 | 1 | 2 | SN -19 HW-13 | 7 |
| 2 | Aizawl West | 5 | 1 | 9 |  | 1 | 9 |  | 1 |  | 24 |  | 340 | 155 | 1 | 1 | SN-24 HW-21 | 23 |
| 3 | Champhai | - | - | 1 |  | - | - |  | - |  | 19 |  | 67 | 87 | -- | 1 (under training) | SN-10 HW-18 | 19 |
| 4 | Kolasib | - | - | 1 |  | - | 1 |  | - |  | 5 |  | 47 | 40 | 2 | 1(under training) | SN-13 HW-5 | 14 |
| 5 | Lawngtlai | 1 | - | - |  | - | - |  | - |  | 4 |  | 22 | 22 | 1 | 1 | SN-6 HW-11 | 8 |
| 6 | Lunglei | 1 | - | 1 |  | - | 1 |  | - |  | 23 |  | 170 | 105 | 3 | 1 | SN-28 HW-19 | 19 |
| 7 | Mamit | - | - | - |  | - | 1 |  | - |  | 13 |  | 35 | 25 | 1 | 1 | SN-8 HW-7 | 12 |
| 8 | Saiha | 1 | - | - |  | 1 | - |  | - |  | 8 |  | 20 | 32 | - | 1 | SN-7 HW-18 | 8 |
| 9 | Serchhip | 1 | - | - |  | 1 | 1 |  | - |  | 10 |  | 51 | 61 | 1 | 1 | SN-8 HW-7 | 1 |

4. Strengthening of Pre Service Trainings

Response:

- Pre Service SBA training has been included in the curriculum of ANMTCs and Nursing Schools in the State

- Revised and updated SBA training modules, MCP Card, Safe Mothehood booklets, referral slips, Discharge Cards, Partographs and all Maternal Health related material are to be provided to ANMTC for inclusion in pre service training

- Provision kept in the PIP for strengthening the ANMTCs and Nursing Schools with advanced teaching equipments.

JSSK

JSSK physical and financial target have been worked out as per comments made by Maternal Health Division as follows

Expected No of Delivery- 18000 (total); Expected C-section 10 %(1800));

(based on HMIS(2010-11)+ 20% add on for 2012-13)

| Activity | Rate | Amount (in lakhs) |
| --- | --- | --- |
| Drugs for ANC, PNC and Normal Deliveries | @ Rs 350*16200 | 56.70 |
| Drugs for C.S. Other complications, MTP/safe abortion cases | @ Rs 1600*1800 | 28.80 |
| Diet for N.D for 3 days | @ Rs 100*16200*3 days | 48.60 |
| Diet for C.S | @ 100*1800*7 days | 12.60 |
| Lab investigations @200/ | @Rs 200*18000 | 36.00 |
| Blood @ Rs 300 for 1800 cases | @Rs 300*1800 | 5.40 |
| Treatment cost for sick new born @ 10% of Inst. Deliveries (1800) | @ Rs 200 *1800 | 3.60( drugs for sick- new borns are budgeted @ Rs 200 (budget under CH) |
| Referral |  |  |
| Call Centre at all District Hospital, SDH, CHC, PHC, UHC | Lumpsum budget | 10.00 |
| Referral for PW & Sick new born ( 10% of inst.delivery i.e 1800) from home to facility@ Rs 15 per km(avg distance-20km) | @ Rs 15*20*19800 | 59.40 |
| Referral for PW & Sick new born ( 10% of inst.delivery i.e 1800) for Drop Back@ Rs 15 per km(avg distance-20km) | @ Rs 15*20*19800 | 59.40 |
| Referral for PW between the health facilities |  | State’s own ambulances |
| Total |  | 320.50 |

Delivery Points

As per the relaxed norms for identifying delivery points in the State, i.e.

- DH>30 deliveries/month

- FRU>20 deliveries/month

- PHC>6deliveries/month

- SC>2 deliveries/month

| Functional Delivery Points List |  |  |
| --- | --- | --- |
| S no | District | Facility |
|  | Aizawl East |  |
| 1 |  | Saitual CHC |
| 2 |  | Sakawrdai CHC |
| 3 |  | Thingsulthliah 24*7 PHC |
| 4 |  | Darlawn 24*7 PHC |
| 5 |  | Khawruhlian 24*7 PHC |
| 6 |  | Phuaibuang 24*7 PHC |
|  | Aizawl West |  |
| 7 |  | Civil Hospital, Aizawl |
| 8 |  | Kulikawn Hospital |
| 9 |  | Sairang 24*7 PHC |
| 10 |  | Lengpui PHC |
| 11 |  | Hmunpui SC |
|  | Champhai |  |
| 12 |  | Champhai DH |
| 13 |  | Ngopa CHC |
| 14 |  | Kawlkulh 24*7 PHC |
| 15 |  | Khawzawl 24*7 PHC |
| 16 |  | Hnahlan 24*7 PHC |
| 17 |  | Khawbung 24*7 PHC |
| 18 |  | Farkawn 24*7 PHC |
| 19 |  | Mimbung PHC |
| 20 |  | N.E. Khawdungsei PHC |
| 21 |  | Khawhai PHC |
| 22 |  | Tlangsam SC |
| 23 |  | N. Khawbung SC |
| 24 |  | Ruantlang SC |
| 25 |  | Hmunhmeltha SC |
| 26 |  | Melbuk SC |
| 27 |  | Ngur SC |
| 28 |  | Sesih SC |
| 29 |  | Khuangleng SC |
| 30 |  | Dungtlang SC |
| 31 |  | Samthang SC |
| 32 |  | Khuangthing SC |
| 33 |  | Dulte SC |
| 34 |  | Hliappui SC |
| 35 |  | Chhawrtui SC |
| 36 |  | Tualte SC |
| 37 |  | Ngaizawl SC |
| 38 |  | Vanzau SC |
| 39 |  | Sazep SC |
| 40 |  | Khankawn SC |
| 41 |  | Vaphai SC |
|  | Kolasib |  |
| 42 |  | Kolasib District Hospital |
| 43 |  | Vairengte CHC |
| 44 |  | Kawnpui 24*7 PHC |
| 45 |  | Saipum SC |
| 46 |  | Saiphai SC |
| 47 |  | Thingdawl SC |
| 48 |  | Bualpui SC |
| 49 |  | N. Hlimen SC |
| 50 |  | Zanlawn SC |
| 51 |  | Phaisen SC |
|  | Lawngtlai |  |
| 52 |  | Lawngtlai District Hospital |
| 53 |  | Chawngte CHC |
| 54 |  | Bungtlang S 24*7 PHC |
|  | Lunglei |  |
| 55 |  | Lunglei District Hospital |
| 56 |  | Tlabung SDH |
| 57 |  | Hnahthial CHC |
|  | Mamit |  |
| 58 |  | Mamit District Hospital |
| 59 |  | Kawrthah CHC |
| 60 |  | Marpara 24*7 PHC |
| 61 |  | West Phaileng 24*7 PHC |
| 62 |  | Kawrtethawveng PHC |
| 63 |  | Rawpuichhip PHC |
|  | Saiha |  |
| 64 |  | Saiha District Hospital |
| 65 |  | Tuipang 24*7 PHC |
|  | Serchhip |  |
| 66 |  | Serchhip District Hospital |
| 67 |  | Thenzawl CHC |
| 68 |  | North Vanlaiphai 24*7 PHC |
| 69 |  | Chhiahtlang SC |
| 70 |  | Keitum SC |
| 71 |  | Bungtlang SC |
| 72 |  | Mualpheng SC |
| 73 |  | Thentlang SC |
| 74 |  | Hmuntha SC |
| 75 |  | Hualtu SC |
| 76 |  | Lungchhuan SC |

As per the revised Guidelines, the Delivery Points have been mapped and selected for strengthening of Delivery Services. The State will now focus exclusively on  the strengthening of these delivery points for MCH services.

| Sl No | Type of Health Institution | Total No. |
| --- | --- | --- |
| 1 | District Hospital | 8 |
| 2 | Sub District Hospital | 2 |
| 3 | CHC | 8 |
| 4 | 24*7 PHC | 16 |
| 5 | PHC | 6 |
| 6 | SC | 36 |
|  | Total | 76 |

Service Strengthening at all Delivery points will be done in a stepwise and comprehensive manner to provide essential care for mothers and newborns, Family Planning, ARSH, CAC etc. The budget for equipments, capacity buildings, supplies, infrastructure strengthening is built around these delivery points only.

Priority of Strengthening will be in the three high focus districts i.e Saiha, Mamit & Lawngtlai Districts.

Display of MCH Protocols and Signs at Functional Delivery Points

Standard Treatment Protocols for Institutions below FRU level is required. Systematic supply of such protocols have not been done yet. The protocols will be made in the local language for the SCs, while the others will be provided in English.

Justification:

All functional delivery points will have Standard Treatment Protocols by the end of this year. This will include posters which can be displayed as well as flip charts and in book form.

Janani Suraksha Yojana plan 2012-13

Institutional Deliveries % Year Wise

JSY was launched in 2005 in Mizoram. After which the percentage of Deliveries shows an upward climb. The State is very encouraged to continue JSY as it can be clearly seen that it improves the Institutional Deliveries.

Response:

Under Janani Suraksha Yojana mothers are given incentives for institutional deliveries at all Public Health Institutions and in 10 Private institutions accredited to dispense JSY benefits. The following Private Institutions are accredited to dispense JSY benefits :

- Med–aim Adventist Hospital, Champhai

- Lairam Christian Medical Centre, Lawngtlai

- Christian Hospital, Serkawn, Lunglei

- Nazareth Hospital, Kolasib

- Aizawl hospital, Mission veng

- Seventh Day Adventist Hospital, Seventh Day Tlang

- Grace Nursing Home, Zarkawt

- Bethesda Hospital, Chaltlang

- New Life Hospital, Chanmari

- Presbyterian Hospital, Durtlang

. The Percentage of JSY beneficiaries out of the total institutional and home deliveries is as below.

| JSY Beneficiaries | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 (April to Nov) |
| --- | --- | --- | --- | --- | --- |
| % of JSY beneficiaries out of Institutional Deliveries | 62% | 93% | 79% | 72% | 60% |
| % of JSY beneficiaries out of home deliveries | 28% | 26% | 11% | 9.6% | 5.2% |

The percentage (%) of JSY beneficiaries out of home deliveries is less since most home deliveries are not eligible for JSY benefits.

JSY is being implemented in the state as per GOI guidelines. ASHAs who attend pregnant women for ANC, institutional delivery and PNC will be given incentives as per the guidelines. Estimate for JSY beneficiaries is calculated as below:

Estimated total no of live birth for 2012-13						: 23,000

Estimated no of JSY beneficiaries (70% of live birth)					:16,100

Estimated Institutional Beneficiaries (84% of JSY beneficiaries)		 		:13,524

Estimated Home Deliveries for BPL mothers including NMBS beneficiaries

(16% of Live birth)									: 2,576

Institutional deliveries out of beneficiaries

Rural (estimated 65%)									: 8790

Urban (estimated 35%)									: 4734

Budget Proposed for JYS 2012-13

| Activity | Physical Target | Unit cost ((Rs) | Amount ( Rs.in lakh) |
| --- | --- | --- | --- |
| Home Delivery | 2576 | 500 | 12.88 |
| Institutional Delivery - Rural | 8790 | 700 | 61.53 |
| Institutional Delivery - Urban | 4734 | 600 | 28.40 |
| C-Section |  |  |  |
| ASHA incentives – Rural | 8790 | 600 | 52.74 |
| ASHA incentives - Urban | 4734 | 200 | 9.47 |
| Administrative cost 5% |  |  | 8.25 |
| Total |  |  | 173.27 |

District Wise Estimated number of JSY beneficiaries

| District | Number of expected JSY beneficiaries |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aizawl West | Aizawl East | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Institution | 4200 | 2300 | 1600 | 812 | 763 | 2018 | 651 | 503 | 677 | 13524 |
| Home | 202 | 189 | 294 | 266 | 390 | 320 | 350 | 300 | 265 | 2576 |
| Total | 4402 | 2489 | 1894 | 1078 | 1153 | 2338 | 1001 | 803 | 942 | 16100 |

| I | II | III | IV | Total |
| --- | --- | --- | --- | --- |
| 300 | 300 | 300 | 300 | 1200 |

NMBS

In compliance with the Hon’ble Supreme Court order dated 20th November, 2007 in the W.P. (C) No. 196 of 2001 (PUCL vs Union of India & others) National maternity Benefit Scheme (NMBS) will also be implemented for BPL pregnant women @ Rs 500/- per birth. They will receive NMBS money from the 3rd order of birth and the expenditure will be borne from JSY funds. The above calculation of home deliveries includes NMBS beneficiaries.

As per Comment on JSY plan, the State has commited –

- To make payment to beneficiaries and full amount of financial assistance to the beneficiary before being discharged from the health facility after delivery

- To strengthen grievance redressal mechanism as stipulated under JSY quidelines

Maternal Death review

- Audit of maternal death as per GOI guidelines which will be reviewed at State and District level.

- Incentive to ASHAs for death report @ Rs. 50/-, Incentive to 3 ANM/Staff Nurses etc for Field verification of maternal death @ Rs. 100/-, Incentive to 2 deceased family @ Rs. 200/- (Total incentive = Rs. 750/- per case) which is already approved.

- During 2011-12 till November maternal death report is only 10 numbers. It is therefore estimated that maternal death for the coming year will not be more than 20. Also audit of child death will be reviewed at State and District level along with maternal deaths.  Incentives to ASHA, audit team and deceased family will be given as per MH guidelines. Estimated of infant death is 650 nos and budgeted under Maternal Health.

- The same incentive has also been proposed for Child Deaths.

Annexure A-IX

REPORTING FORMAT TO ASCERTAIN THE STATUS OF IMPLEMENTATION

Name of State: Mizoram

| SN. | Activity |  | Status / Remarks |
| --- | --- | --- | --- |
| 1 | Name, contact no. and e-mail address of State Nodal Officer for MDR | Dr. R. Lalthanga State Program Officer, RCH 0389 2328045 nrhmmizoram@yahoo.com |  |
| 2 | Number of medical/paramedical personnel trained or oriented on MDR | Medical College faculty | - |
|  |  | State officials (Directorate. SPMU, etc.) | All State program Officers |
|  |  | District Officials (CMO, DRCHO, DPMU, others) | 18 |
|  |  | Others including I/Cs of private hospitals | 2 |
|  |  | Block Officials (BMOs, BPMU, etc.) | - |
|  |  | MO I/Cs of public health facilities | 66 |
|  |  | ASHAs/ AWWs/ ANMs/ SHGs/ others | - |
| 3 | Constitution of Maternal Death Review Committee / Task Force as per GOI guidelines { Give no. at each level} | State Task Force (Yes/No) | Yes |
|  |  | Number of districts in the State | 9 |
|  |  | Number of districts where MDR Committee has been constituted) | 9 |
|  |  | Total number of health facilities (FRUs, DHs, private accredited hospitals) identified for FBMDR | 10 |
|  |  | Number of health facilities where FBMDR Committees has been constituted | Govt. order has been issued and is under process |
| 5 | Total number of MDs reported at the State level (April to the reporting month,2011-12) | Through CBMDR (Community Based MDR) | 10 |
|  |  | Through FBMDR (Facility Based MDR) | 0 |
| 6 | Total number of MDs reviewed by District MDR committees (CMO) (April to the reporting month, 2011-12) |  | 8 |
| 7. | Number of MDs reviewed by State Task Force out of total reported in column 4 |  | 8 |
| 8 | Causes of maternal deaths reported in column 4 (in numbers) |  |  |
| 8.1 | Haemorrhage |  | 2 |
| 8.2 | Sepsis |  | 3 |
| 8.3 | Abortion |  | - |
| 8.4 | Obstructed labour |  | - |
| 8.5 | Hypertensive disorders in pregnancy (includes eclampsia) |  | 2 |
| 8.6 | “Others” (include anaemia) |  | Uterine rupture-1 Retained placenta-1 others-1 |
| 9 | Analysis of MDR findings done by the State e.g. major causes of MDs (medical/systemic/others), geographical distribution- concentration in specific districts/blocks, whether conforming to the AHS High Mortality districts etc. | NA |  |
| 10 | Compliance with submission of State Monthly MDR Reports for April to the reporting month (2011-12); reasons for non- compliance. | - |  |

Maternal Health Trainings

Annexure A VI

| Posting and performance of EmOC trained doctor |  |  |  | Posting and performance of LSAS trained doctor |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| District | Name | Facility where posted | Performance | Name | Facility where posted | Performance |
| Aizawl West | Dr.Jeremy Vanramenga Pachuau | Civil Hospital, Aizawl FRU | Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly | Dr. Fabiola Kharkongar | Kulikawn SDH, Sub District Hospital | Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly |
| Aizawl East | Dr. J. Zolawmzuala | Saitual CHC, Community Health Centre |  | Dr. Lucy Lalsangpuii | Saitual CHC, Community Health Centre |  |
|  | Dr. Lalmalsawmi Khawlhring | Ramhlun UHC, Urban Health Centre |  |  |  |  |
| Champhai | Dr. Lalramengi (currently in training) | Champhai DH District Hospital |  |  |  |  |
| Kolasib | Dr. C. Laldinpuii | Vairengte CHC, Community Health Centre |  | Dr. C. Lalrinchhana | Vairengte CHC Community Health Centre |  |
|  |  |  |  | Dr. Ramdinthari | Kawnpui PHC, Primary Health Centre |  |
| Lawngtlai | Dr. Vanlallawma Khiangte | Chawngte CHC, Community Health Centre |  | Dr. Lalrinfela | Lawngtlai DH, District Hospital |  |
| Lunglei | Dr. James Lalzuitluanga | Tlabung SDH, Sub District Hospital |  | Dr. Lalrengpuii Ralte | Hnahthial CHC, Community Health Centre |  |
|  |  |  |  | Dr. Isaac Lallawmsanga | Buarpui PHC, Primary Health Centre |  |
|  |  |  |  | Dr. Benjamin Malsawmtluanga | Bunghmun PHC, Primary Health Centre |  |
| Mamit | Dr. Freddie Lalrintluanga Chhangte | Kawrthah CHC, Community Health Centre |  | Dr. Saitluanga Sailo | Kawrthah CHC, Community Health Centre |  |
| Serhhip | Dr. Remlalnghaki | Thenzawl CHC, Community Health Centre |  | Dr. Christopher L Hmar | Thenzawl CHC, Community Health Centre |  |
| Saiha | Dr. Vabeilysa | Saiha District Hospital, FRU | CS done at an average of 15 per month |  |  |  |
|  | Dr. Sangzuala | Went for further studies |  | Dr. Lalmuankimi | Went for further studies |  |
|  |  |  |  | Dr. Robert Lalfakzuala |  |  |

- LSAS and EmOC Trainings:

- Draft PIP for this training was not approved. The trained MOs will be posted at FRUs and those centres where EmOC, LSAS and F-IMNCI trained MOs  are already posted together will be upgraded into FRUs

- Log book will be maintained by all LSAS and EmOC trained MOs in the state for reference.

- BEmOC Training

- BEmOC training is conducted at Civil Hospital, Aizawl. The State has 3 Trainers and the batch size is 2, with a training duration of 10 days. The training is given to doctors posted in PHCs with preference given to those posted in the High focus Districts and Functional Delivery Points.

- MOs from the High Focus Districts will be trained first. However, during the rainy season, due to the increased case load of malaria in Mizoram, some MOs may be unable to leave their post for training due to lack of manpower. In such cases, MOS from other Districts will also be considered.

- Training is conducted as per GOI guidelines. A total of 20 MOs are planned to be trained this year.

- SBA Training

The State has 4 SBA Training Centres at

| Sl no | Training Centre | Batch Size |
| --- | --- | --- |
| 1 | Civil Hospital, Aizawl | 5 |
| 2 | Lunglei District Hospital | 2 |
| 3 | Kolasib District Hospital | 1 |
| 4 | Christian Hospital, Serkawn | 1 |

- Training is conducted for ANMs and SNs with training duration of 21 days. The batch sizes are kept in accordance to the no. of deliveries conducted by the Training institution per month.

- Re-accreditation of training centers is planned during the first two weeks of April, 2012, The Training centers will be checked every quarter to ensure functionality as per accreditation.

- Any remaining untrained ANM and SN in the Functional Delivery Points will be prioritized for this training.

Note : The state could not achieve as per the Training plan for 2011-12 as there were unavoidable gaps where the Trainers took leave for various reasons and due to lack of funds.

D. Blood Storage Centre & Training

Taken up by Mizoram SACS in the State

e. MTP Training

- The State has one II TIER training centre at Civil Hospital, Aizawl. There are 2 trainers and duration of 12 working days. The Training Centre will be visited and checked prior to every training to ensure functioning as per accreditation.

- 6 MOs will be trained in 3 batches.

- MVAs had been supplied to all the health facilities in the previous years.

- MMA Drugs will be procured and supplied to all Health facilities where MTP is taking place and budget for MH drugs will be used for this purpose.

CAG guidelines will be made available at all Public Health Institutions dispensing this service.

f. RTI/STI Training

- The State has 8 Training Centres at all the District Hospitals. Refresher Training for District Trainers is planned this year who in turn will train all untrained Medical Officers and Staff Nurses in all the districts.

- All Health Workers will be trained in Whole finger prick test at the nearest PHC

- HIV kits and RPR kits and post exposure prophylactic drugs are supplied by MSACS

| Progress of MH Trainings Annexure A VII |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| pe of Training | No. of Medical Colleges conducting training | No. of District Hospitals conducting training | Any other Facilities conducting training | No. of Master Trainers Trained | Target for NR HM period (up to 2012 ) | Achievement cumulative till March 2011 | Target for 2011- 12 | Achievement or Nos. trained in 2011- 12 (April 11-till December, 2011) * | Target for 2012- 13 | No. of trained MOs posted at facilities where their skills are being utilised - e.g. FRUs for LSAS & EmOC/ MTP; 24X7 PHCs for BeMOC/M TP; Facilities conducting delivery for SBA in the relevant column | Performance (Specify No. of deliveries, No. of C- section and No. of Spinal Anaesthesia, No. of MTPs, No. of any other complications attended in the relevant column) Cumulative since 2005 till date |
| LSAS | - | 1 (II TIER) | - | - | 11 | 12 | 2 | - | - | - | NA |
| EmOC | - | 1 (II TIER) | - | 2 | 10 | 4 | 6 | 5 | 2 | 1 | NA |
| BEmOC | - | 1 | - | 3 | 16 | - | 16 | 2 | 20 | 2 | NA |
| SBA | - | 3 | 1 | 20 (17 state trained) | SN-315 ANM-333 | SN-118 ANM-69 | SN-60 ANM-110 | SN-16 ANM-48 | SN-68 ANM-32 | NA | NA |
| MTP | - | 1 | - | 2 | MTP-90 | 79 | 4 | 2 | 6 | NA | NA |
| RTI/STI | - | 8 | - | 16 | MO-90 | MO-46 HW-770 | ANM-60 | - | MO-30 SN-90 | NA | NA |

Supervision, Monitoring and Quality Assurance.

Monitoring from State Level:

State level monitoring team was already constituted in 2010-11 under the chairmanship of Mission Director. The team consists of Program Officers of various vertical programs under NRHM, MIS Manager/ Consultant, Finance consultant Accounts Manager, Data Manager.

The Team will meet once in a quarter (date to be fixed), and ensure the dissemination of guidelines and manuals etc. Protocols for treatments will be adapted and disseminated to all Health facilities. The team will review and make suggestions on all maternal and Infant Death reports in the State, and monitor Accredited Private Health facilities to ensure implementation of national standards. The team will carry prescribed checklist for monitoring and submit the detail report to the State Mission Director. A copy of the monitoring report will be sent to each district with feedback and suggestion of improvement. Quarterly review meeting will be held at the State and District level. A proper record of all the findings and the actions taken will be kept. Timings, frequency of visits etc will be decided for the next quarter at every meeting.

Monitoring from District Level:

A District Level Joint Monitoring Team was already formed in 2010-11 to monitor various programs under NRHM in their respective district will be strengthened.

The team is headed by Chief Medical Officer of the respective districts and other team members consist of District Immunization Officer, District Program Manager, District Accounts Manager, District Data Manager etc. The team will carry prescribed checklist for monitoring and submit the detail report to the District Health Society meeting with a copy to the Mission Director. A copy of the monitoring report will be send to each CHC/PHC with feedback and suggestion for improvement. The feedback will be discussed at the CHC/PHC level during monthly meeting and corrective measures will be taken.

It will also review all cases of Maternal and Infant Deaths in the District, and submit the reports to the State. It will review all PHFs and ensure their functioning as per national standards. It will be involved in the review of all trainings and their implementation and other community and facility based interventions etc. QAC visits to facilities and report and discussion of these findings at all the monthly meetings. The District team will report to the State Monitoring and QAC team and pursue the State authorities for follow up. Frequency and timing of visits will be decided in the monthly meetings.

A proper record of the findings and actions taken will be kept.

Integrated Outreach Camps

4 camps each has been proposed for 3 HF district. These camps will be held in the remote areas where RCH facilities are not available.

Detailed Budget for conducting one outreach camp

Details of Last year held RCH camp - Reuben

| Particulars | Amount in Rupees |
| --- | --- |
| Manpower: Gynaecologist Paediatrician Medical Officer Other Staff | 1,000/- 1,000/- 8,00/- 1,200/- Total : 4,000/- |
| Publicity Banner Sound System Local IEC requirements | 2,500/- |
| Camp arrangement Layout of services Generators Tents/ hiring Chairs | 4,000/- |
| Transport POL for specialists, Medical Officers, District Officers etc | 2,000 |
| Drugs & other Consumables | 5,000 |
| Contingency | 2,500 |
| TOTAL | 20,000 |

VHNDs

Village Health and Nutrition day is to be held at each Anganwadi Centers in each month. There are 1682 Anganwadi centres in the state. However, in some places, there are more than 5 Anganwadi Centres under the care of a single Health worker and cannot attend each and every VHND. Supportive monitoring will be done by the MO i/c at regular intervals.

Format for Performance on Comprehensive Abortion Care at State Level (April-September 2011)

Name of State/U.T:  Mizoram	          Number of districts in the State:  9

| SN | Indicator |  | Numbers |
| --- | --- | --- | --- |
| 1 | Number of districts where District Level Committee (DLC)* has not been constituted |  | 0 |
| 2 | Number of applications pending in the districts with the DLCs | For one year | - |
|  |  | More than one year | - |
| 3 | Is MVA equipment being procured and supplied to the districts? (Y/N) |  | None in the current year Supplied in 2009-10 |
| 4 | Are the drugs for MMA included in the essential drug list? (Y/N) |  | None in the current year |

1)	Indicators:

* As per MTP Act, Rules and Regulations 2002-2003

2)  Service Availability and Utilisation:

| Availability: Number of institutions providing services |  |  |  |  | Utilisation: Number of MTPs performed-any method |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Health Facility | Up to 12 weeks services | Up to 20 weeks services |  |  | Up to 12 weeks | 12 -20 weeks |
| Government (Total) | 61 | 8 |  |  | 239 | 20 |
| Private certified (Total) | - | - |  |  | - | - |
| “Delivery Points” providing services. |  |  |  |  |  |  |
| PHCs/non FRU CHCs | 24 | - |  |  | Data not available |  |
| FRUs (CHCs, SDH etc.) | 4 | - |  |  |  |  |
| DHs /DWH etc. | 8 | 8 |  |  |  |  |
| Medical Colleges | - | - |  |  |  |  |
| Private certified | - | - |  |  |  |  |

3)  Does the State have an IEC/BCC plan for MTP Services(Y/N) No

If yes, please indicate frequency/ periodicity of IEC/BCC activities

| SN | IEC/BCC Activity | Frequency/ periodicity |
| --- | --- | --- |
| 1 | Print | - |
| 2 | Audio | - |
| 3 | Video | - |
| 4 | Any Other (specify) | - |

Proposed Budget 2012-13:

| Area | Budget Head & Activity code | Unit Cost | Budget proposed in PIP 2012-13 |
| --- | --- | --- | --- |
| MMA Drugs | - | - | - |
| MVA/ EVA Equipments | Already supplied in previous years |  |  |
| MTP-Training MOs | - | 46,000/- | 2,30,000/- |
| MTP training of other field functionaries (counselling and post abortion care) | - | - | - |
| MTP-IEC/BCC Activities | Budgeted under IEC |  |  |
| MTP: Monitoring and Supevision | Budgeted under Monitoring and supervision |  |  |

RTI/STI Services

STATUS OF STI/RTI SERVICES DELIVERY IN THE STATE

1.   Allocation of fund for STI/RTI services in the PIP:

Fund Allocated for the STI/RTI services in 2011-12:

| Activities | Fund allocated in the PIP (in Lacs) | Expenditure till date (inLacs) |
| --- | --- | --- |
| Training of ANMs (Training cost, printing of module, stationary, venue etc) | 1.19 | - |
| Monitoring and supervision of the facilities | To be monitored comprehensively with other programs |  |
| Upgrading of infrastructure of the facilities (audio-visual privacy, examination facilities, speculum, gloves etc) | - | - |
| RPR test Kits | Taken up by MSACS |  |
| Colour coded STI/RTI drug kits | Budget for MH Drugs to be utilised |  |
| Total Budget in PIP | 1.19 | - |

- Coordination Meetings:

No coordination meeting has been organised yet in the current year regarding RTI/STI.

- Training:

a.   Training of the District Level trainer including District RCH Officer:

Training for District level trainer and training for 2 batches of Medical officer have been conducted at State level as well as 1 batch for MO at Lunglei district in the previous year. Orientation Training for Health workers have also been conducted in all the districts in collaboration with MSACS. 90% of the Laboratory Technicians have been trained in the State.

b.   Training of the Sub-district level Health Facilities staffs:

30 Medical Officers (remaining untrained) and 90 Staff Nurses covering all the sub-district level health facilities  are planned to be trained in the coming year.

Training Status of Sub-District Level Staffs:

| Cadre | Targe tfor 2011- 2012) | Cumulative Achievement (Since inception -till date) | Proposed numbers to be trained in 2012-13 | Timeline 2012-2013 (specify the number of providers to be trained in each quarter) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| MO | - | 46 | 30 | 30 |  |  |  |
| SN | - | - | 90 |  | 30 | 30 | 30 |
| ANM | - |  |  |  |  |  |  |

- Supply of STI/RTI colour Coded Drug Kits:

Colour coded drug kits have not been procured or distributed by the state. However, drugs (not colour coded) for RTI/STI have been procured and distributed along with the other essential drugs and supplied to each district.

- Implementation of STI/RTI Service Delivery:

Has the service delivery started at the sub district health facilities?

| Name of the District | Service Delivery Started (Yes/NO) | If No, Reasons why the Services have not started | Time Line when the Service will start |
| --- | --- | --- | --- |
| Aizawl East | Yes | - | - |
| Aizawl West | Yes | - | - |
| Champhai | Yes | - | - |
| Kolasib | Yes | - | - |
| Lawngtlai | Yes | - | - |
| Lunglei | Yes | - | - |
| Mamit | Yes | - | - |
| Saiha | Yes | - | - |
| Serchhip | Yes | - | - |

Reporting Status on STI/RTI:

| Name of the district | Is this district reporting in HMIS/SIMS on STI/RTI (M-8, a,b column) | If not what is the reason and when the reporting will start |
| --- | --- | --- |
| Aizawl East | Yes | - |
| Aizawl West | Yes | - |
| Champhai | Yes | - |
| Kolasib | Yes | - |
| Lawngtlai | Yes | - |
| Lunglei | Yes | - |
| Mamit | Yes | - |
| Saiha | Yes | - |
| Serchhip | Yes | - |

RTI/STI program is taken up by the Chief Medical Officer in each District

| State /District Team | Number of Visit made to the District for program Implementation | Number of District Visited | Number of Sub-district health Facilities Visited |
| --- | --- | --- | --- |
| State RCH Officer/MH Officer | 4 trips | 9 | 25 PHC/CHC 70 SC |
| SPMU | 4 trips | 9 | 25 PHC/CHC 70 SC |
| District RCH Officer/ADMO in- charge of RCH Programme | 5 trips |  | 9 CHC, 57 PHC 360 SC |
| DPMU | 5 trips |  | 9 CHC, 57 PHC 360 SC |

Incentives under Maternal Health

| Target | Reason for giving incentive | Amount/case (in rupees) |
| --- | --- | --- |
| ASHA | Community based Maternal Death Review | 50 |
|  | Janani Suraksha Yojana for complete ANC and institutional dleivery | Urban – 200 Rural - 600 |
| ANM/ SN | Community based Maternal Death Review | 100 |
| Deceased family | Community based Maternal Death Review | 200 |

II.CHILD HEALTH

GOAL: To reduce IMR from 37 (SRS 2010) to 18 by 2016-17

In order to achieve the target set for for the next 5 years various activities such as relocation of staff, up gradation of health facilities, training of health providers, IEC/BCC activities, outreach services, Child Death Review and monitoring will be emphasized. Priority will be given to low performing districts namely Saiha, Lawngtlai and Mamit districts.

.    Estimated Child Population (of the State/UT)

23000

Estimated live births per year

Estimated number of children under 5 years

1,42,665

2.    Situation Analysis (STATE/UT)

| Child Mortality | SRS 2007 | SRS 2008 | SRS 2009 | SRS 2010 | Trend Analysis |
| --- | --- | --- | --- | --- | --- |
| Neo Natal Mortality Rate (State HMIS) | - | - | 3 | 6 | Increasing trend |
| Infant Mortality Rate | 23 | 37 | 36 | 37 | Slight Increasing trend |
| Under Five Mortality (State HMIS) | 6 | 6 | 6 | 6 | Constant |

| Nutrition | NFHS 3 | CES* 2009 |
| --- | --- | --- |
| % of children age 6-35 months who are anaemia | 51.7 | NA |
| % of children (under 3 years) who are underweight | 21.6 | NA |
| % of children (under 3 years) who are severely wasted /SAM (< -3SD) | 9.2 | NA |

*Coverage Evaluation Survey

| Infant & Young Child Feeding | NFHS 3 | DLHS 3 | CES 2009 |
| --- | --- | --- | --- |
| Children age 6 months and above exclusively breastfed | 15.40 | 29.1 | 36.6 |
| Diarrhoea & ARI | NFHS 3 | DLHS 3 | CES 2009 |
| Children with Diarrhoea in the last 2 weeks who received ORS | 51.2 | 55.5 | 60.8 |
| Children with ARI or fever in the last 2 weeks who were given treatment at facilities. | 50.1 | 56 | 87.6 |
| itamin A Supplementation | NFHS 3 | DLHS 3 | CES 2009 |
| Percentage of children (age 9 months and above) received at least one dose of Vitamin A supplement | 42.2 | 75.5 | 65.4 |

|  | Newborn Care |  | Source : |
| --- | --- | --- | --- |
|  | Percentage of institutional deliveries | 83 | CES |
|  | Percentage of newborns with low birth weight | 4.6 | HMIS |
|  | Percentage of mothers staying for 48 hours at the facility | NA | CES |

3.1 Essential New born Care

At present, there are 71 Delivery Points (34 DH/SDH/CHC/PHC and 37 sub centres) in Mizoram, out of which 13 Delivery Points have Newborn Care Corners, and 23 Delivery Points have at least 1 health provider trained in NSSK. 21 Newborn Care Corners are proposed to be established and Training of 240 staff nurses and 120 ANMs in NSSK is proposed for 2012-13.

|  | S.No. |  |  |  | Name of the district |  |  | No. of existing delivery points |  |  |  | No. of NBCCs operational |  | NO. of NBCCs at Delivery points |  |  | No. of NBCCs proposed (2012-2013) |  | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | High Focus districts |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Lawngtlai |  |  | 2 |  |  |  | 3 |  |  | 1 |  | 1 |  |  |  |
|  |  |  |  |  | Mamit |  |  | 5 |  |  |  | 3 |  |  | - |  | 5 |  |  |  |
|  |  |  |  |  | Saiha |  |  | 1 |  |  |  | 1 |  |  | - |  | 1 |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Other districts |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Aizawl East |  |  |  | 6 |  |  | 4 |  |  | 4 |  | 2 |  | Proposal for NBCCs is for all Functional Delivery points where NBCC is not yet set up |  |
|  |  |  |  |  | Aizawl West |  |  |  | 3 |  |  | 1 |  |  | 1 |  | 2 |  |  |  |
|  |  |  |  |  | Champhai |  |  |  | 8 |  |  | 4 |  |  | 3 |  | 5 |  |  |  |
|  |  |  |  |  | Kolasib |  |  |  | 3 |  |  | 2 |  |  | 2 |  | 1 |  |  |  |
|  |  |  |  |  | Lunglei |  |  |  | 3 |  |  | 2 |  |  | 1 |  | 2 |  |  |  |
|  |  |  |  |  | Serchhip |  |  |  | 3 |  |  | 3 |  |  | 1 |  | 2 |  |  |  |
|  | Total |  |  |  |  |  |  |  | 42 |  |  | 23 |  |  | 13 |  | 21 |  |  |  |

|  | Name of the district |  | Total Units (NBCCs) proposed in 2012-2013 |  | 2012-13 |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 7 |  | 2 |  | 2 |  | 2 |  | 1 |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 14 |  | 4 |  | 4 |  | 3 |  | 3 |  |  |
|  | Total |  | 21 |  | 6 |  | 6 |  | 5 |  | 4 |  |  |

3.2 Care of sick newborn

At present, there is only one SNCU in Mizoram at Aizawl Civil Hospital. This is the only Hospital in Mizoram which qualifies according to the GOI guidelines i.e at least 3000 deliveries per year. It may be mentioned that the guidelines applicable for the big states can in no way be applied to the small states like Mizoram. One SNCU has therefore been proposed to be set up at Lunglei District Hospital during 2012-13 which will provide services to South Mizoram, and the existing SNCU at Civil Hospital, Aizawl will serve thenorthern part of Mizoram.

The state has 2 functioning NBSUs at present at Lunglei District Hospital and Kolasib District Hospital. NBSUs are proposed to be set up at the remaining 5 District Hospitals since manpower is readily available in these institutions.

Re-assessment of SNCU and NBSUs will be done on a 6 monthly basis as per the checklist provided in FBNC operational guidelines by the State and District Officials.

|  | S.No . |  | Name of the district |  | Existing SNCU (Yes/No) |  | If yes, date of operational ization |  | SNCU Proposed for 2012-2013 (Yes/No) |  | Timeline |  |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 |  | Aizawl West |  | Yes |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 |  | Lunglei |  | No |  | - |  | Yes ( 1 No) |  |  |  |  |  |  |  | 1 |  |  |  |
|  | Total |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*Only those units where patients are being admitted should be considered as functional units.

|  | S.No. |  | Name of the district |  | No. of existing NBSUs |  | No. of NBSUs proposed for 2012-13 2013 |  | Timeline |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Lawngtlai |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  |  |  | Mamit |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  |  |  | Saiha |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  | Champhai |  | - |  | 1 |  |  |  |  |  | 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Serchhip |  | - |  | 1 |  |  |  |  |  | 1 |  |  |  |  |
|  |  |  | Kolasib |  | 1 |  | - |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Lunglei |  | 1 |  | - |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  | 2 |  | 5 |  |  |  | 3 |  | 2 |  |  |  |  |

10. JSSK As per guidelines the cost of free drugs, diagnostics, treatment has been worked out and budgeted under Child Health. All other cost like transport has been budgeted under Maternal Health component. Please refer Maternal Health Section

3.3 Home Based New Born Care

As per the Home Based Newborn Care Operational Guidelines, ASHAs will visit homes to provide essential newborn care. All ASHAs in Mizoram have undergone training in Round 1 of module 6 & 7, Home based Newborn Care and will be practiced in full swing in the coming year.

It is proposed to give Incentives to ASHA for home visit . Budget is worked out below:

ASHA Incentive will be given on completion of home visits as per norms

3.4 Promoting IYCF practices

The Dept. of Social Welfare under ICDS is taking up IYCF in the State,. As regards to RCH, Two (2) Lactation Counselors have been appointed at Civil Hospital Aizawl on a pilot basis. They counsel all parents with newborns in the OPD in a separate Lactation Counseling Room, they also provide counseling to Pregnant Women in ANC and to all mothers in the Pre and post natal wards. This practice may be considered to be extended in the High Focus Districts.

IEC – refer to IEC Chapter Part B. of PIP

3.5, 3.6 Micronutrient supplementation and management of Children with malnutrition

Micronutrient Supplementation (Vitamin A and IFA Supplementation) to children 6-60 months and management of children with malnutrition have been taken up by the State Social Welfare Department under ICDS. Hence, No activities have not been planned by the Health Department to avoid duplication.

3.7 Integrated Management of Child hood and Neonatal Illnesses

IMNCI trainings for HWs, have been conducted covering 78% of all the Districts. 127 MOs and 775 Health Workers have been trained till date. . All the remaining untrained HWs will be trained in the coming year. Medical Officers and Staff Nurses are now given F-IMNCI training in lieu of IMNCI training. Trainings for LHVs is not conducted as the state does not have LHVs. All ASHAs in the State have been trained in module 6 & 7 1st round.

Pre service IMNCI has also been included in the syllabus at ANM and Nursing training Schools, namely:

- Health Worker Training School, Aizawl

- Mizoram College of Nursing, Aizawl

- Regional Institute Paramedical and Nursing Sciences, Aizawl

- Nursing School, Lunglei

3.8 Diarrhoea Management and ARI

As per guidelines Diarrhoea Management and ARI is on going activities. Procurement of ORS and Zinc tablets will be done and budgeted under part B. Reorientation  of health providers will be done during child health/ maternal health training and meetings. IEC- BCC activities focusing on hygiene, hand washing, preparation and use of ORS, feeding during a episode of diarrhoea and healthcare seeking behavior will also be taken up. ORS corners may be established in facilities but no separate budget is required.

4. 	Trainings:

Details of Child Health training plan may be seen in the training chapter.  As for supervision of post training, State and District level Monitoring team will take up during field visits. Training status is tabulated below as per prescribed format.

| Achievement in Child Health Training 2011- 2012 | IMNCI |  | F-IMNCI |  | NSSK |  | Total Numb er of ASHA s in the State | ASHA - Modul e 6 & 7 Round One | ASHA - Modul e 6 & 7 Round Two | ASHA - Modul e 6 & 7 Round Three | ASHA - Modul e 6 & 7 Round Three |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Prop osed | Achi eved | Prop osed | Ach ieve d | Pro pose d | Ach ieve d | 987 | Achieved |  |  |  |
| Number of Districts covered | 2 | 1 | 9 |  | 9 |  |  |  |  |  |  |
| AWW | - | - |  |  |  |  |  |  |  |  |  |
| ASHA | - | - |  |  |  |  |  |  |  |  |  |
| ANM | 48 | 49 |  |  |  |  |  |  |  |  |  |
| MPW (M) | - | - |  |  |  |  |  |  |  |  |  |
| LHV | - | - |  |  |  |  |  |  |  |  |  |

| Supervisor (M) | - | - |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | - | - | 36 | - | 480 | 76 |  |  |  |  |  |
| MO | - | - | 48 | 19 | - | - |  |  |  |  |  |
| Others | - | - |  |  |  |  |  |  |  |  |  |
| Total | 48 | 49 | 84 | 19 | 480 | 76 |  |  |  |  |  |

Budgeting for Child Health Trainings should be done under appropriate budget line.

4.1 IMNCI:

The State has at present, 2 active training sites at Saiha District Hospital and Aizawl Civil Hospital. There are 6 Master Trainers in Mizoram.

IMNCI trainings for health Personnel have been conducted covering 78% of all the Districts.

Status of IMNCI trainings

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of batches to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 150 |  | 127 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ANM |  | 1030 |  | 775 |  | 120 (4 batches) |  | 1 |  | 1 |  | 1 |  | 1 |  |  |
|  | LHV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | AWW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4.2 F-IMNCI

At present, training of F-IMNCI is done only at Civil Hospital, Aizawl and the state has 4 Master Trainers (2 state trained).

Medical Officers who have been trained in IMNCI will be trained in F-IMNCI for 5 days. Priority will be given to existing NBSU staff and for those planned for setting up of NBSU

Status of F IMNCI Training

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of providers to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 96 |  | 67 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SN |  | 36 |  | - |  | 144 (12 batch) |  | 3 |  | 3 |  | 3 |  | 3 |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

C. NSSK

The State has one Training Centre at Present at Aizawl Civil Hospital. 4 more District Centres where Paediatricians are in place are planned to be opened in the coming year.

All Health personnel in the Functional Delivery points will be  trained in NSSK with priority given to those already trained in SBA. Steps will be taken to ensure that both SBA and NSSK trained personnel are posted at delivery points.

Status of NSSK training

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of batches to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 120 |  | 87 |  | - |  |  |  |  |  |  |  |  |  |  |
|  | SN |  | 360 |  | 108 |  | 240 |  | 4 |  | 4 |  | 2 |  |  |  |  |
|  | ANM |  | 120 |  | - |  | 120 |  |  |  |  |  | 1 |  | 4 |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

D. ASHA training in module 6 & 7

All ASHAs in the State have been trained in Module 6 & 7 1st round.

Training Plan for ASHA Module 6 and 7

|  | Module 6 and 7 |  | Total training load, 2012- 2013 |  | To be achieved in |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | Round 1 |  |  |  |  |  |  |  |  |  |  |  | Details training plan under Mission Flexi pool |
|  | Round 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Round 3 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Round 4 |  |  |  |  |  |  |  |  |  |  |  |  |

E. Orientation on MCP card:

The MCP Card was translated into the local language and printed. No orientation or training has been conducted yet. MCP card will be used after sensitization workshop under the guidance of DPM and District RCH Officers.

F. Facility Based Management of children with SAM

All nutrition related works are taken up by the Social Welfare Department under ICDS.

G. SNCU training

1.   Training of health service providers posted at SNCU should be undertaken. A 4 days training programme (batch size 24), along with 12 days of Observer ship (batch size 4) at an identified facility is recommended.

2.   National Collaborative Centre at Kalawati Saran Children‟s Hospital (Delhi) and Regional

Collaborative Centre at ICH (Chennai), PGIMER Chandigarh, AMC (Dibrugarh), KEM Mumbai, Maulana Azad Medical College (Delhi) and IPGMER (Kolkata) should be contacted for assistance in training and any support required for newborn care units.

3.   State/UT needs to identify one Medical College in consultation with National/ State Collaborative Centre to coordinate with identified Regional Resource Centre and utilize their services for the purpose of capacity building, mentoring, operational research etc.

|  | SNCU training plan 4 days with batch size 24 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cadre |  | Total training |  | To be achieved in |  | Remarks |

|  |  |  | load 2012- 2013 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MOs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNCU Observer ship 12 days National/ Regional/ State Collaborative Centre batch size 4 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Cadre |  | Total training load 2012- 2013 |  | To be achieved in |  |  |  |  |  |  |  | Remarks |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MOs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |

4. Miscellaneous:

- Dissemination of guidelines. -

FBNC guidelines are to be kept at all Newborn Stabilization Units and Sick Newborn Care Units. Charts given in FBNC guidelines may be adopted as protocol and made into chart books to be kept at all Newborn Stabilization Units and Sick Newborn Care Units etc.

Budget for dissemination of various guidelines refer to…

- Reporting Formats for Newborn Care Units: Orientation and sensitization regard;

- ing the various data collection will take place at the Quarterly review meetings.

- Budget for Quarterly Child Health Review Meeting refer to…

- Separate Strategy Proposal for High Focus Districts –

Saiha : Re-orientation training in IMNCI for ANMs in Saiha District is planned. The district has 55 ANMs who will be re trained in 2 batches at Civil Hospital, Aizawl.

5. Child Health Activities under NRHM

IEC, BCC –Child Health:

- Leaflets, wall writings, TV and Radio spots, endorsement by locally famous persons, short plays etc. Special emphasis to be given regarding sensitization of the community about the danger signs of ARI and Diarrhoea in children.

- Funding given under BCC/IEC

Infrastructure

Equipment

- Radiant Warmers -

- Dummies for F-IMNCI Training – 2

- Dummies for NSSK Training - 30

| 6. Human resources |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The detail of new contractual staff for child health (e.g SNCUs: MOS 4, 10 SNs, 4 support workers, 1 counsellor, 1 data entry operator and 1 part time lab technician), proposed in the PIP, should be specified. Cost should be budgeted under appropriate heads in NRHM |  |  |  |  |  |  |
| S.No. | Name of the district | Personnel to be hired (eg; Specialists, Medical officers, Staff nurses, Data operators, Dieticians, Cooks etc.) | No. of personnel to be hired | Unit cost (Monthly remuneration x no. of months) | FMR code | Remarks (eg. Facility where these personnel will be posted, if the staff is being hired fro NRCs or New born care units) |
|  | Budget for Child Health |  |  |  |  |  |
|  | Intervention | Unit cost | Physical targets proposed for 2012-13 | Proposed budget | FMR code | Remarks |
| 1 | Essential Newborn care |  |  |  |  |  |
|  | Cost for New NBCC | 85,000 | 21 | 1785000 |  | Budget under Part B |
|  | Operational cost (existing +new) | 20,000 | 44 | 880000 | A.2.2.1 |  |
| 2 | Sick Newborn Care |  |  | 0 |  |  |
|  | One time cost for new SNCUs | 41,00,000 | 1 | 4100000 |  | Budget under Part B |
|  | Operational cost for SNCUs (existing + new) | 10,00,000 | 1 | 1000000 | A.2.2.1 |  |
|  | One time cost for new NBSUs | 5,75,000 | 5 | 2875000 |  | Budget under Part B |
|  | Operational cost for NBSUs (existing + new) | 1,75,000 |  |  |  | To operationalise from state budget |
|  | Janani Shishu Suraksha Karyrakram (JSSK) | 200 | 1800 | 360000 | A.2.5.3 | Cost of free diagnostics, drugs, treatment ( Physical & Financial target have been put as per comment on JSSK) |
|  | Intervention | Unit cost | PhysicalTargets proposed for 2012-2013 | Proposed budget | FMR code | Remarks |
| 3 | Home Based newborn Care |  | births |  |  |  |
|  | ASHA incentives | 250 | 11500 (50% of live birth) | 2875000 |  |  |
|  | Equipments, medications & Consumables for ASHA kit |  |  |  |  |  |
| 4 | Promotion of IYCF |  |  |  |  |  |
|  | Orientation programmes/Trainings |  | SWD |  |  |  |
|  | Other activities |  |  |  |  |  |
| 5 | Micronutrient Supplementation programme |  | SWD |  |  |  |
|  | Vitamin A |  |  |  |  |  |
|  | IFA |  |  |  |  |  |
| 6 | Management of children with SAM |  |  |  |  |  |
|  | One time cost for establishing new NRC | 2,00,000 (Indicative) | SWD |  |  |  |
|  | Operational cost for existing + new NRCs | 7,80,000/ unit/ year (Indicative) | SWD |  |  |  |
| 7 | IMNCI programme |  |  |  |  |  |
|  | Supplies, Logistics, Supportive supervision |  |  |  |  |  |
| 8 | Management of Diarrhoea and ARI |  |  |  |  |  |
| 9 | Trainings (Cost / Batch) |  |  |  |  |  |
|  | IMNCI (TOT) |  |  |  |  |  |
|  | IMNCI (HW/ANM) | 218300 / batch | 4 batches | 873200 | A.9.5.1.3 | Plse ref training chapter of PIP |
|  | F-IMNCI (TOT) |  |  |  |  |  |
|  | F-IMNCI (Staff Nurses) | 123200 / batch | 12 batches | 1478400 | A.9.5.2.3 | Plse ref training chapter of PIP |
|  | NSSK (Staff Nurses) | 61000/batch | 10 batches | 610000 | 9.5.5.1.3 | Plse ref training chapter of PIP |
|  | NSSK (ANM/HW) | 61000 | 5 | 305000 | 9.5.5.1.4 | Plse ref training chapter of PIP |
|  | Orientation on MCP card |  |  |  |  | Can be budgeted under MH/CH /Trainings |
|  | Facility Based Management of children with SAM |  |  |  |  |  |
|  | SNCU training |  |  |  |  |  |
|  | SNCU Observership |  |  |  |  |  |
| 10 | Miscellaneous |  |  |  |  |  |
|  | Rapid Assessment of SNCUs |  |  |  |  |  |
|  | Dissemination of guidelines |  |  |  |  |  |
|  | Quarterly reviews |  |  |  |  |  |
|  | Intervention | Unit cost | Physical Targets proposed for2012-2013 | Proposed budget | FMR code | Remarks |
| 11 | Infant Death Review |  | 650 |  | A.1.5 | Write up and Budget under Maternal Health ( Buget for 650 infant deaths & 20 maternal Deaths = 670 deaths) |
|  | Orientation of programme managers on reporting formats for newborn care units and NRCs |  |  |  |  |  |
|  | Operational Research |  |  |  |  |  |
| 12 | Other costs |  |  |  |  | These costs are only to be listed here ; budget to be included under appropriate budget heads |
|  | IEC-BCC :Child Health |  |  |  |  | Plse ref relevant section |
|  | Hiring of new contractual staff for CH |  |  |  |  |  |
|  | Child Health Equipments |  |  |  |  |  |
|  | Procurement of drugs &supplies for CH |  |  |  |  | Plse ref relevant section |

III. FAMILY PLANNING

GOAL: To reduce TFR  from 2.9 (NFHS-3) to 2.1 by 2016-17

Family planning performance has not been convincing but it is to be mentioned that there are high resistance from the apex body of the church and NGOs against advocacy of family planning in any form. But when there is stiff resistance there are also increasing percentage of unmet needs as per NFHS but a declining figure in DLHS-2 to DLHS-3. There is a correlation of female sterilization with unmet needs. As female sterilization goes down there is growing percentage of unmet needs as indicated in NFHS (1-3).  This could be the failure of service delivery. However DLHS shows the percentage of female sterilization is growing as such the % of total unmet need is declining. Emphasis will be made in the financial year to cover more unmet needs and promote more of Pills and Condom distribution which is easy and IUD insertion through health workers. The contribution of ASHA in family planning is also worth mentioning, they act as community distributors of contraceptives. Birth rate and TFR shows a growing trend. Much efforts need to be undertaken to reduce TFR and delay of marriage and meeting of unmet need are challenge the state has to undertake so that population growth can be controlled.

|  | 1998-99 |  | 2005-06 |  | 2002-04 |  | 2007-08 |  | 2009-10 |  | 2010-11 | 2011-12 (upto Nov) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | NFHS-2 |  | NFHS-3 |  | DLHS-2 |  | DLHS-3 |  | STATE HMIS |  | STATE HMIS | STATE HMIS |
| FAMILY PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |
| Any Method (%) | 57.7 |  | 59.9 |  | 53.8 |  | 53.9 |  | 49.04 |  | 47 | 29.4 |
| Any Modern method (%) | 57.1 |  | 59.6 |  | 52.6 |  | 53.1 |  | 49.04 |  | 47 | 29.4 |
| Male Sterilization (%) | 0.1 |  | 0.0 |  | 0.1 |  | 0.2 |  | 0.04 |  | 0.04 | 0 |
| Female Sterilization (%) | 45.4 |  | 42.9 |  | 39.2 |  | 35.9 |  | 24 |  | 24 | 13.4 |
| Pill (%) | 5.4 |  | 10.6 |  | 5.9 |  | 11.6 |  | 5 |  | 6 | 3.8 |
| IUD (%) | 5.4 |  | 4.7 |  | 4.9 |  | 4.3 |  | 15 |  | 13 | 10.7 |
| Condom (%) | 0.9 |  | 1.4 |  | 2.3 |  | 1.2 |  | 3 |  | 4 | 1.5 |
| Total Unmet need (%) | 15.5 |  | 17.3 |  | 25.0 |  | 16.7 |  | NA |  | NA | NA |

CONTRACEPTIVE USE

PROPOSED ACTIVITIES FOR 2012-13

State: Mizoram

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD/Target | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 1 | FAMILY PLANNING MANAGEMENT |  |  |  |  |  |  |  |
| 1.1 | Review meetings on Family Planning performance and initiatives at the State and district level (periodic; including QAC meetings)) | NR | Quarterly | Quarterly | Q I,II, III & IV | Quarterly at State & Dists | 4.00 | State level & 9 districts @ Rs.10000/-each per qtr |
| 1.2 | Monitoring and supervisory visits to districts/ facilities | NR | 100 facilities | 81 facilities | Q I,II, III & IV | 100 facilities | 9.00 |  |
| 1.3 | Orientation workshops on technical manuals of FP viz. standards, QA, FDS approach, SOP for camps, Insurance etc. | NR | 3 batches | - | Q II | 2 batches | 1.00 | - |
| 2 | SPACING METHOD (Providing of IUD services by districts) |  |  |  |  |  |  |  |
| 2.1 | Plan for providing FDS (Fixed Day Static) IUD services at health facilities in districts (at least 2 days in a week at SHC and PHC level) – number of facilities to be provided | - | - | - | Q I,II, III & IV | 9 CHCs, 2 SHD & 40 PHC atleast 2 days in a week | - |  |
| 2.2 | No. of IUD camps in districts | NR | - | - | - | - | - | - |
| 2.3 | Compensation for IUD | NR | 5000 | 2090 | Q I,II, III & IV | 5000 | 1.00 | Budget as per GOI norms |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 2.4 | Plan for strengthening PPIUCD services | NR | - | - | Q I,II, III & IV | 3000 | 4.50 | Incentive to ASHAs for retention of IUD for 3 visits Rs.50 at each visit ( 3moths, 6months & 1 year) |
| 3 | TERMINAL/LIMITING METHODS ( Providing sterilisation services in districts) |  |  |  |  |  |  |  |
| 3.1 | Plan for facilities providing FEMALE sterilisation services on fixed days at health facilities in districts (number of facilities) | NA | 9 CHC & 41 PHC once in a month | 8 CHC & 24 PHC | Monthly | 9 CHC & 41 PHC once in a month | - | Separate budget not requred |
| 3.2 | Plan for facilities providing NSV services on fixed days at health facilities in districts (number of facilities) | - | - | - | - | - | - | IEC activities will be emphasised |
| 3.3 | Number of FEMALE Sterilisation camps in districts. | NR | 25 | 11 | Q I,II, III & IV | 15 camps | 2.25 |  |
| 3.4 | Number of NSV camps in districts. | NR | - | - | - | - | - | - |
| 3.5 | Compensation for sterilisation (female) | NR | 3520 | 1445 | Q I,II, III & IV | 3400 | 34.00 |  |
| 3.6 | Compensation for sterilisation NSV (male) | NR | 10 | 0 | Q I,II, III & IV | 10 | 0.15 | - |
| 3.7 | Additional mobility support to surgeon’s team (if required) | NR | 10 teams | 2 teams | Q I,II, III & IV | 10 teams | 2.00 | Please see write up below |
| 3.8 | Accreditation of private centres/ NGOs for sterilization services (number accredited) | 3 | 1 | 1 | Q II | 1 | 0.50 | - |

|  | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) |  | PLAN NED |  | ACHI EVE D |  | WORK PLAN |  |  | SCHEDU LED/ Trg. LOAD |  | BUDGET (In lakhs) |  | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2011-12 |  |  |  | 2012-13 |  |  |  |  |  |  |  |
| 3.9 | Plan for post partum sterilisation | NR |  | 1520 |  | 578 |  | Q I,II, III & IV |  |  | 1600 |  | - |  | To be done on fixed day at health facilities |
| 4 | SOCIAL MARKETING OF CONTRACEPTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Delivery of contraceptives by ASHA at door step | NR |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 4.2 | Any other social marketing activity for family planning | NR |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 5 | FAMILY PLANNING TRAINING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | IUD Insertion training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.1 | TOT for IUD insertion | 25 |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 5.1.2 | Training of Medical officers in IUD insertion | 83 |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 5.1.3 | Training of staff nurses in IUD insertion | 37 |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 5.1.4 | Training of ANMs / LHVs in IUD insertion | 603 |  | 30 |  | 41 |  | - |  |  | 50 |  | 1.88 |  | - |
| 5.1.5 | Refresher training in IUD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | PPIUCD training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.1 | TOT for PPIUD insertion | - |  | - |  | - |  | - |  |  | - |  | - |  | - |
| 5.2.2 | Training of Medical officers in PPIUD insertion | - |  | - |  | - |  | - |  |  | - |  | - |  | - |
| SN. | STRATEGY / ACTIVITY |  | Cumulati ve achievem ent (as on 31st March 2011) |  | PLAN NED |  | ACHI EVE D |  | WORK PLAN | SCHEDU LED/ Trg. LOAD |  | BUDGET (In lakhs) |  | REMA RKS |  |  |
|  |  |  |  |  | 2011-12 |  |  |  | 2012-13 |  |  |  |  |  |  |  |
| 5.2.3 | Training of staff nurses in PPIUD insertion |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |
| 5.3 | Laparoscopic Sterilisation Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3.1 | TOT on laparoscopic sterilisation |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |
| 5.3.2 | Laparoscopic sterilisation training for service providers (gynaecologists /surgeons) |  | 4 teams |  | 1 team |  | - |  | - | 1 team |  | 0.44 |  | Planned for 2011-12 is commited activity |  |  |
| 5.3.3 | Refresher training (if required) |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |
| 5.4 | Minilap Training for MOs/ MBBS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4.1 | TOT on Minilap |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |
| 5.4.2 | Minilap training for service providers (medical officers) |  | 81 |  | 4 |  | 2 |  | - | 10 |  | 2.30 |  | - |  |  |
| 5.4.3 | Refresher training (if required) |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |
| 5.5 | Non-Scalpel Vasectomy (NSV) Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5.1 | TOT on NSV |  | - |  | - |  | - |  | - | - |  | - |  | Cases are very few and hence not proposed training in NSV |  |  |
| 5.5.2 | NSV training for medical officers |  | - |  | - |  | - |  | - | - |  | - |  |  |  |  |
| 5.5.3 | Refresher training (if required) |  | - |  | - |  | - |  | - | - |  | - |  |  |  |  |
| 5.5 | No. of Contraceptive Update trainings for health providers in the districts |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 5.7 | Other family planning trainings (please specify) |  |  |  |  |  |  |  |
| 6 | „World Population Day‟ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities. | NR |  | 9 dist Hqrs | - | State, Dist & CHC/PHC | 9.00 |  |
| 7 | BCC/ IEC activities - Campaigns/ melas / print/ audio/ video materials for family planning | NR |  |  |  |  |  | Budget under part B of IEC |
| 8 | PROCUREMENT of DRUGS/MATERIALS |  |  |  |  |  |  |  |
| 8.1 | NSV Kits | - | - | - | - | - | - |  |
| 8.2 | IUD insertion Kits | - | - | - | Q II | 450 | 4.50 | Budget under procurement |
| 8.3 | Minilap Set | - | 65 | - | Q III | 41 | 4.10 |  |
| 8.4 | Procurement/ repair of laparoscopes | - | - | - | Q III | 8 nos | 40.00 |  |
| 8.5 | Provision for buffer stock for (subject to maximum of 25% of last year‟s utilisation): |  |  |  |  |  |  | To be procured by state |
|  | IUDs |  |  |  |  |  |  |  |
|  | Tubal Rings |  |  |  |  |  |  |  |
|  | Condom |  |  |  |  |  |  |  |
|  | OCPs |  |  |  |  |  |  |  |
|  | ECPs |  |  |  |  |  |  |  |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 9 | Other innovatory schemes for promoting FP at State or district level – Family planning counsellor | NR | 2 | 2 |  | 2 | 3.00 | Plse see write up below |
| 10 | Performance based rewards to institutions and providers for FP performance at State and district level | NR | For HF dists |  | - | Plan for service providers, institutions, Districts | 7.84 |  |

COMPENSATION TO ASHAs FOR RETENTION OF IUD:

As per the findings of NFHS-3, Infant mortality rate of previous birth interval 2-3 years is only 21 whereas <2 years is 64. As per appraisal of FP Comment,  Incentive to ASHAs has been proposed for retention of IUD ( instead of incentive to clients) and which is considered to be effective to promote birth spacing as well as reduction of IMR. ASHAs will conduct 3 visits in a year to ensure that mother actually retain IUD . Moreover since all the government institutions keep proper records for monitoring and implementation will not be a problem. ASHA will be given money incentive @ Rs.50/- at each visit upto one year i.e 3 months, 6 months and one year. In order to motivate ASHAs and to promote this new initiative It is suggested that  incentive be given for visiting mothers who avail IUD services during March, 2011

Additional Mobility Support to Surgeon Teams/POL for Family Planning:

POL for Family planning has been proposed as mobility support in the camp budget is not adequate in some places. The case load in Sterilization camps varies from one place to another and camps are used to conducted in hard to reach areas where unmet need are high. Moreover identical mobility cost per camp is not applicable in hilly terrain like Mizoram. Mobility / POL for family planning is required not only for Surgeon teams but for targeted beneficiaries also. Expenditure for picking up of mothers to the camp place from surrounding villages and dropping back after sterilization is very high in some places. From the past experience, It is learnt that out of the proposed 15 Sterilization camps, additional mobility support/ POL will be required atleast at 10 camps @Rs.20,000/-. As such additional mobility has been budgeted for consideration.

Performance Based Reward:

# As proposed performance based reward was approved for 2011-12 for 3 high focus district namely Lawngtlai, Saiha and  MamitIt is learnt that this has been motivating the 3 districts and in turn it will result improvement in services delivery. For the year 2012-13 it is proposed to extend performance reward to services providers, institutions wise and district wise covering not only HF districts but  for all other districts. Performance criteria : District wise, Institution wise targets will be made which will be finalized shortly. Targets will be set in all Family planning services such as Sterilization, Contraceptive use, Utilization of trained providers etc. Achievable targets from the current status will be made for each district and institution.

# Reward will be disbursed in kinds as follows:

- Reward to Services providers to be disbursed at District Level:

# 1st Prize		= Rs.8,000/-

# 2nd Prize		= Rs.6,000/-

# 3rd Prize		= Rs.4,000/-

# Total		=Rs.18,000/-

# Total for 9 districts = Rs.18,000/- X 9 = Rs.1,62,000/-

- Reward to Institutions i.e SDH/CHC/PHC to be disbursed at District Level:

# 1st Prize		= Rs.10,000/-

# 2nd Prize		= Rs.8,000/-

# 3rd Prize		= Rs.6,000/-

# Total		=Rs.24,000/-

# Total for 9 districts = Rs.24,000/- X 9 = Rs.2,16,000/-

- Reward to S/C level to be disbursed at District Level:

# 1st Prize		= Rs.10,000/-

# 2nd Prize		= Rs.8,000/-

# 3rd Prize		= Rs.6,000/-

# Total		=Rs.24,000/-

# Total for 9 districts = Rs.24,000/- X 9 = Rs.2,16,000/-

- Reward to District Level:

# 1st Prize		= Rs.80,000/-

# 2nd Prize		= Rs.60,000/-

# 3rd Prize		= Rs.50,000/-

# Total		=Rs.1,90,000/-

Family Planning Counselor: 2 existing Family Planning Counselors in 2 biggest Hospitals i.e Aizawl and Lunglei Civil Hospital will be reengaged.  The proposed monthly salary has been reduced from Rs.15750 to Rs.12500 which has been  considered to be appropriate keeping price escalation, higher cost of living etc.

Budget for this under Human resources.

IV. ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH

MIZORAM REVISED ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH PIP FOR 2012-13

ARSH:Background information

Mizoram has a population of a 1 million in the 2011 census with a sex ratio 937 . Adolescents comprise of approximately 22% of the total population. Intervention activities among adolescent group has been one of the major challenges in the overall health response. The youth dynamic represent high risk activities and ventures which are uncommon in other   The stage of rapid physical growth, psycho-social development and sexual transformation. They are critical to the success of any reproductive and sexual health. Healthy and unhealthy practices adopted at this stage can last a lifetime. In Mizoram unhealthy habits such as alcoholism and drug addiction among out going adolescents are peculiar problems. The adolescent age group needs focus attention on their specific problems. The contribution made by the State AIDS control Society towards Adolescent Health is worth mentioning. Though detailed data for measuring Adolescents health are not available, yet it may be estimated that the health status of Adolescent has been improving since the initiative taken by various department such as NRHM, MSAC, Social welfare , Sport and Youth services,  IEC/BCC activities towards knowledge of RTI/STI, HIV/AIDS and harmfulness of marriage during teenage is highly required . Adolescent friendly services also need to be improved in order to motivate them to access health services.

Convergence with Mizoram SACs:  Convergence process with SACs to address overall Adolescent Health was slow during the 1st five years of NRHM. With the initiatives taken by representative of UNICEF, NRHM/NACP convergence Nodal Officer has been appointed and which promotes integrated services delivery approach. At present, there are 9 Mobile ICTCs and  27 ICTCs in 8 DHs, 9 CHCs, 8 24*7 PHCs, 2 in Private Hospitals. In all ICTCs qualified counselor have been appointed and th ese counselors have undergone training in ARSH, Maternal Health etc. The existing AFHC in 5 Districts Hospitals namely Aizawl, Lunglei, Champhai, Lawngtlai, Kolasib have been operationalized by integrating with ICTC. During 2012-13, it has been plan to established 34 AFCH in 3 DHs,2SHD, 9CHC and 20 20*7 PHC. Integration of AFHC would be done where ICTC were already existed. In addition to these, quarterly Coordination meeting to review progress, Joint monitoring, Outreach services will held ( Expenditure will be met from M&E, Monitoring budget heads of NRHM/RCH).

Current status of Adolescents population:

| Population | Male | Female | Total |
| --- | --- | --- | --- |
| Total Population of Mizoram (2011 Census) | 552339 | 538675 | 1091014 |
| Approx Adolescent Population (22% of Population) | 1.22 | 1.18 | 2.4 |

ARSH SUMMARY BUDGET

| FMR CODE | PROPOSED ACTIVITIES | BUDGET ( Rs.In Lakh) | BUDGET HEAD In the PIP |
| --- | --- | --- | --- |
| A.4.1.1 | Disseminate ARSH Guidelines ( Printing of training Modules) | 3.00 | Adolescent Reproductive and Sexual Health |
| A.4.1.2 | Establishment of New clinics at DH/SDH level | 5.00 |  |
| A.4.1.3 | Establishment of New clinics at CHC/PHC level | 29.00 |  |
| A.4.1.3.1 | Operating expenses of existing Clinics | 0.20 |  |
| A.4.1.4 | Outreach Activities | 27.00 |  |
|  | SUB TOTAL | 64.20 |  |
| A.9.7.4 | Training | 13.69 | Training under RCH |
| B.10.2.4 | IEC/BCC | 17.95 | IEC/BCC under Mission Flexi Pool |
|  | TOTAL FOR ARSH | 95.84 |  |

Major Strategies & Activities Proposed for 2012-13:

- Strengthening of Convergence with SACS, SW Deptt (Co-ordination Meeting, Joint Monitoring etc). Under the NACP-NRHM Convergence Committee Chaired by the Health Secretary monitoring of ARSH will be scaled up through administrative review of performances and quarterly reports. DD (RCH) will feed the committee on the progress, challenges and issues related to ARSH and convergence.This committee will sit quarterly and report to both NRHM (MoHFW) and NACO (Deptt of AIDS)

- Enhanced capacity of Adolescents friendly Health Clinic to provide comprehensive services in terms of life skills, nutrition and hygiene, STI/HIV, substance abuse to increase service uptake and quality coverage of target group through training and enhanced capacity building system.

- Training of Service providers & Development of training Modules

- Strategic IEC/BCC activities targeting on adolescent health

- Strengthen the services of ICTC counselors, STI Counselors in District Hospital and Staff Nurses

- Weekly Iron Folic Acid and Supplementation (WIFS) through School teachers (IFA to be procured from Procurement budget for Maternal Health under Mission Flexi Pool, Hence no separate budget is required)

- Provision of RTI/STI drugs from District Hospital to 24x7 PHCs

- Outreach activities – Youth Festival & Mela in convergence with SACS Sport & Youth Services, SWD, Education Department etc

- Organize VHND in 150 AWW centre every month ( Budget under Maternal Health @ Rs.200/- per VHND)

Status, Achievements and Detailed Activities & Budget:

( Status, Achievement, Plan for 2012-13 have been indicated as far as possible)

As for information and data required by the Ministry, It may be noted that information cannot be furnished as per prescribed format as most activities have not been taken up properly as per PIP guidelines in the previous years.  Most of the activities indicated in the following table are new initiatives to be undertaken in Mizoram. It is therefore proposed to take up activities as per guidelines from 2012-13 as far as possible. It will be emphasized better integration with SACs, SW Deptt etc for the coming years.

| Activity | Status as on 01.04.2012 | Planned for 2011- 12 | Achievement against Plan till 31.12.11 | Plan for 2012-13 |
| --- | --- | --- | --- | --- |
| State Level Training of Trainers (3 days) | - | - | 4 | - |
| Translation of Training Modules | - | - | Already translated | - |
| Printing of Training Modules for MO and ANM/LHV | - | - | Printing done | 1500 C |
| Helpline for ARSH | - | - | - | Yes |
| Peer Educators Trained | - | - | - | - |
| Any other Activity (Please Specify) | - | - | - | - |

Printing of Training Modules: Printing of training modules 1500 copies has been proposed for training of 300 Staff Nurses ,43 ICTC counsellors  one day orientation for 987 ASHAs (1287) . 170 extra copies has been included in the budget to meet urgent requirement.

ARSH Training:

As indicated in the table below, 99 MOs and 637 ANMs have undergone training on ARSH which is considered to be appropriate for the time being. Also all the counselors working in the ICTC  have been trained. Therefore, training of Staff Nurses has been proposed to give clinical care and counseling ( to support counselors) in AFHC and other health facilities where there is no ARSH clinics. As proposed by Mizoram SACs, 3 days training in counseling technique  may also be given to 43 ICTC counselors so that they can handle the problems being faced by Adolescents comprehensively

There are 987 ASHAs in the entire State. It may also be noted that ASHAs are participating in most of all activities of RCH ( MH, CH, FP, ARSH etc). They are the first contact persons of Adolescents. They should have general knowledge on ARSH to make the target groups aware about the availability of services, harmfulness of early pregnancy, menstrual hygiene etc. It is therefore proposed to orient them on ARSH during 3rd & 4th round of Modules 6 & 7 training is given.( Separate budget for ASHA is not required, expenditure to be met from ASHA budget under Mission Flexi Pool)

| District | Training Status as on 01.04.11 |  |  | Training Planned for 2011-12 |  |  | Achievement Against Plan Till 31.12.2011 |  |  | Planning for 2012- 13 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M O | ANM/ LHV | Counsel lor | MO | ANM/ LHV | Couns ellor | MO | ANM/ LHV | Couns ellor | M O | ANM/ LHV | Coun sellor |
|  | MO-99, ANM-637 |  |  | ANM-60 |  |  |  |  |  | 300 SN, 43 Counselors ( and Orientation for 987 ASHAs |  |  |

Budget calculation for Training of Staff Nurses ( 12 batches)

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 5 | 25 | 50,000 |
| Honorarium of Resources Person | 600 | 5 | 3 | 9,000 |
| Incidental expenditure | 250 | - | 25 | 6,250 |
| Working Lunch, Tea & Snacks | 200 | 5 | 30 | 30,000 |
| Venue Hiring | 500 | 5 | - | 2,500 |
| TA (Actual Maxi Cab / Bus Fare, Taking average ) | 500 | - | 25 | 6,250 |
| Total |  |  |  | Rs. 1,04,000/- |

Budget for 12 batches = 12,48,000/-

Budget calculation for Training of Counselors

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 3 | 43 | 51,600/- |
| Honorarium of Resources Person | 600 | 3 | 3 | 5,400/- |
| Incidental expenditure | 250 | - | 43 | 10,750/- |
| Working Lunch, Tea & Snacks | 200 | 3 | 50 | 30,000/- |
| Venue Hiring | 500 | 3 | - | 1,500/- |
| TA (Actual Maxi Cab / Bus Fare, Taking average ) | 500 | - | 43 | 21,500/- |
| Total |  |  |  | Rs. 1,20,750/- |

Adolescent Friendly Health Clinic (AFHC)

To provide easy, accessible, affordable and friendly health services for adolescents, AFHC facilities will be increased during 2012-13.  As already mentioned 5 AFHCs have been functioning in District Hospital by integrating with ICTC namely Aizawl DH, Lunglei DH, Champhai DH, Lawngtlai DH and Kolasib DH. Comprehensive ARSH services have been provided through these AFHC. 34 new AFHC are planned to be established during 2012-13 as indicated in the following tables

AFHC in DH & SDH

| Total Districts | Total DH | Total DH with Functional AFHC | Planned in 2011-12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in DH in 2012-13 | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 9 | 8 | 5 | - |  | 3 DH, 2 SDH | 3 DH & 1 SDH by integrating with ICTC and SDH to be stand alone i.e Tlabung SDH in Lunglei District |

Budget Break up for establishment of AFHCs in DH and SDH:

| Activities | Rate / Clinic | Physical Target | Amount (Rs) | Remarks |
| --- | --- | --- | --- | --- |
| Projector/ DVD | 30000 | 5 | 1,50,000/- | For 3 DH & 2 SDH |
| Television | 12000 | 5 | 60,000/- | For 3 DH & 2 SDH |
| Examination Table | 20000 | 5 | 1,00,000/- | For 3 DH & 2 SDH |
| Chair | 2000 | 5 | 10,000/- | For 3 DH & 2 SDH |
| Renovation of Rooms | 90000 | 2 | 1,80,000/- | For 2 SDH |
| Total for DH & SDH |  |  | 5,00,000/- |  |

Operating Expenses for Existing 5 AFHC: It has also been proposed operating expenses for 5 existing AFHC @ Rs.4000/- each per year, Total requirement comes to Rs.20,000/-

AFHC in CHC and PHC

| Total Districts | Total CHC | Total CHC with Functional AFHC | Planned in 2011- 12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in CHC in 2012- 13 | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 9 | 9 | - | - | - | 9 |  |
| Total Districts | Total PHC | Total PHC with Functional AFHC | Planned in 2011- 12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in PHC in 2012- 13 |  |
| 9 | 57 |  |  | - | 9 CHC & 20 PHC | 9 CHC & 8 24*7 PHC by integrating with ICTC and 12 24*7PHC to be stand alone ( In proposed new 12 PHC, Same OPD will be utilized in the afternoon twice a week) |

Budget Break up for establishment of AFHCs in CHC and PHC

| Activities | Rate / Clinic | Physical Target | Amount (Rs) | Remarks |
| --- | --- | --- | --- | --- |
| Projector/ DVD | 30000 | 29 | 8,70,000/- | For 29 AFHC |
| Television | 12000 | 29 | 3,48,000/- | For 29 AFHC |
| Examination Table | 20000 | 29 | 5,80,000/- | For 29 AFHC |
| Chair | 2000 | 29 | 58,000/- | For 29 AFHC |
| Renovation of Rooms | 87000 | 12 | 10,44,000/- | For 12 AFHC |
| Total |  |  | 29,00,000/- |  |

OUTREACH ACTIVITIES

| Total Number of Outreach Sessions | In-School 2011-12 |  | Out-of-School 2011-12 |  | Planned with In-School 2012-13 |  | Planned with Out- of-School 2012-13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female | Male | Female | Male | Female |
| Direct in schools |  |  |  |  |  |  |  |  |
| Direct in colleges |  |  |  |  |  |  |  |  |
| VHNDs |  |  |  |  | In 150 AWW Centre every Month |  |  |  |
| School Health Team |  |  |  |  |  |  |  |  |
| Mobile Medical Unit |  |  |  |  | MMU already in placed in all districts to address Adolescent |  |  |  |
| Teen Clubs |  |  |  |  |  |  |  |  |
| Youth clubs/Gymnasium |  |  |  |  |  |  |  |  |
| SHGs |  |  |  |  |  |  |  |  |
| Vocational Training Centres |  |  |  |  |  |  |  |  |
| Youth Festivals |  |  |  |  | Will be organized in 8 district Hqrs and 1 SHD in Aizawl District (Saitual SDH) ( It may please noted that there are 8 administrative Districts in Mizoram, where as there are 9 districts under State Health Department as Aizawl district is divided into 2 under H&FW Deptt ( i.e Aizawl E & Aizawl W) |  |  |  |
| Health Mela |  |  |  |  |  |  |  |  |
| Others |  |  |  |  |  |  |  |  |

Note: One day Youth festival and Health mela will be clubbed and organized in 8 district Head quarters  in convergence with SABLA ( where Sabla is being implemented) and SACs . In the festival different activities such as Games & Sport, Musical Drama related to adolescent health, Solo & Beat contest etc will be conducted. Posters and audio visual will be displayed to address adolescent health. Clinics will also be opened during festival/mela.

Budget Break up for organizing Youth Festival

| Activities | Rate per Festival (Rs) | Phycical Target ( No of Festivals) | Amount (Rs) |
| --- | --- | --- | --- |
| Festival Arrangement – Decoration of Place, Electricity, Hiring of Sound System etc | 50,000/- | 9 | 4,50,000/- |
| Prize / Incentive to participants for solo Beat Contest, Musical Drama | 20,000/- | 9 | 1,80,000/- |
| Preparation / Purchase of Sport materials, Sport Dresses ( Sport like Football, Criket, Running events etc) | 1,20,000/- | 9 | 10,80,000/- |
| Prize / Incentive to sport persons | 30,000/- | 9 | 2,70,000/- |
| Poster and Audio visual materials etc | 20,000/- | 9 | 1,80,000/- |
| Preparation of Clinic / Stall during Festival ( Medicine, Hiring of Specialist/Paramedical Staff etc) | 15,000/- | 9 | 1,35,000/- |
| Refreshment for participants | 45,000/- | 9 | 4,05,000/- |
| Total | 3,00,000/- |  | 27,00,000/- |

| Peer Educators | Identified in 2011-12 |  | Trained in 2011-12 |  | To be Identified in 2012-13 |  | To be Trained in 2012- 13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female | Male | Female | Male | Female |

Activities planned with peer educators

| Activities planned with peer educators | Timeline | Remarks |
| --- | --- | --- |

Note: There is no separate plan for peer educator as ASHA can play the same role

IEC/BCC for ARSH:

| ADOLESCENT REPRODUCTIVE & SEXSUAL HEALTH (ARSH) | Physical Target | Unit cost (Rs) | Amount (Rs. in lakhs) |
| --- | --- | --- | --- |
| 1) Radio/TV Spots for MH ( AIR Azawl, AIR Lunglei, DDK, 5 local cables) | 150 times (60 seconds each) | 2500 | 375000 |
| 2) Wall writing | 100 nos | 4200 | 420000 |
| 3) Awareness campaign at schools and Question box activities at 200 schools. Students may ask any question about their mental & Physical problems without mentioning their name. While conducting awareness campaign at school, all the questions asked through the boxes will be discussed and explained. | 200 Schools | 4000 | 800000 |
| 4) Leaflets on frequently asked question on adolescent Health | 20000 | 10 | 200000 |
| Total for ARSH |  |  | 1795000 |

SCHEME  FOR  PROMOTION  OF  MENSTRUAL  HYGIENE  AMONG  ADOLESCENT GIRLS (10-19 YRS) IN RURAL AREAS

In formation regarding selected districts for implementation of Menstrual Hygien Scheme has not been received. As such separate  plan has not been formulated for 2012-13

2012 – 2013  NRHM - PIP FOR  SCHOOL HEALTH PROGRAMME (SHP)

FOR THE STATE OF MIZORAM

INTRODUCTION : The School Health programme (SHP)  of Mizoram has not been incorporated under the programme implementation plan (PIP) of NRHM and funded  through State Plan and Non-Plan fund and   the beneficiaries are only from the Government run Primary schools student of classes 1-IV till 2010-2011. Hence, the proposal was chalked out to cover from class I – XII  as per the guidelines of the NRHM for the State in phase manner to be completed within 3 years starting from 2011 – 2012. The current proposal is for the 2nd phase of the planned activity for School Health Programme in Mizoram.

Summary Budget for School Health

| Sl.No | Proposed Activity | Budget Proposed for 2012-13 ( Rs.in laks) | FMR Code |
| --- | --- | --- | --- |
| 1 | Contractual Staff at state level | 10.92 | A.10.1.1 |
| 2 | Mobility of state level contractual staff | 2.28 | A.4.2.4 |
| 3 | Hardware/equipment | 26.64 | B.16.1 |
| 4 | Medical Supply | 20.80 | B.16.2 |
| 5 | Printing of Modules/card | 5.00 | A.4.2.1 |
| 6 | Training | 26.05 | A.9.7 |
| 7 | Mobility support to ANM, doctors | 4.90 | A.4.2.3 |
| 8 | Referral support | 2.22 | A.4.3 |
|  | Total | 98.81 |  |

- Brief on the Programme:

School Health programme is a program for school health service under National Rural  Health Mission, which has been necessitated and launched in fulfilling the vision of NRHM to provide effective health care to population throughout the country. It also focuses on effective integration of health concerns through decentralized management at district with determinant of health like sanitation, hygiene, nutrition, safe drinking water, gender and social concern.

| Approved budget 2011-12 | Expenditure till February, 2012 |
| --- | --- |
| Rs.63.28 lakhs | Rs.21.56 lakhs |

ACHIEVEMENT REPORT UNDER SCHOOL HEALTH  PROGRAMME  (April to  Dec. 2011)

| Sl.No | Name of Items | DHS | AIZAWL ‘W’ | AIZAWL ‘E’ | LUNGLEI | KOLASIB | SERCHHIP | CHAMPHAI | MAMIT | SAIHA | LAWNGTLAI | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | No. of Schools visited | 31 | 722 | 322 | 558 | 96 | 172 | 103 | 32 | 130 | 30 | 2196 |
| 2. | No. of Students examined | 1371 | 37238 | 17241 | 31949 | 4504 | 7912 | 8228 | 2245 | 4989 | 713 | 116390 |
| 3. | Dental casesdetected | 578 | 600 | 342 | 948 | 89 | 108 | 428 | 115 | 281 | 40 | 3529 |
| 4. | Eye problems detected | 158 | 412 | 141 | 564 | 126 | 95 | 103 | 10 | 229 | 19 | 1857 |
| 5. | Total No. of referred cases | 292 | 141 | 104 | 560 | 4 | 33 | Nil | 10 | 132 | 78 | 1354 |
| 6. | Anaemia prevention |  |  |  |  |  |  |  |  |  |  |  |
| (a) | Iron folic Acid (No. of students covered) | 890 | 5912 | 3695 | 14288 | 327 | 872 | 26 | 167 | 513 | 570 | 27260 |
| (b) | Albendazole (No. of students covered) | 1371 | 88 | 793 | 2429 | 20 | 103 | 133 | 355 | 485 | 43 | 5820 |
| 7. | Health Education (No. of session organized) | Nil | 179 | 42 | 606 | 3 | 22 | 5 | Nil | 113 | 24 | 994 |
| 8. | Ear problems detected | 38 | 117 | 82 | 22 | 20 | 12 | 244 | Nil | 86 | 14 | 635 |
| 9. | Skin problems detected | 21 | 99 | 133 | 133 | 16 | 70 | 173 | Nil | 38 | 3 | 681 |
| 10. | Nutritional status (Moderate) | 481 | 529 | 341 | 1328 | 100 | 60 | 226 | Nil | Nil | 10 | 3076 |
| 11. | No. of Schools without sanitary latrine. | Nil | 17 | Nil | 212 | Nil | Nil | Nil | Nil | 40 | Nil | 269 |

2.	Rationale for School Health Programme:

The School Health programme is the only public sector programme specifically focused on school age children. Its main focus is to address the health needs of children, both physical and mental, and in addition, it provides for nutrition interventions, yoga facilities and counseling. It responds to an increased need, increases the efficacy of other investments in child development, ensures good current and future health, better educational outcomes and improves social equity and all the services are provided for in a cost effective manner.

- Components of School Health Program:

Health service provision:

•Screening, health care and referral:

⁰Screening of general health, assessment of Anaemia / Nutritional status, visual 	acuity, 	hearing problems, dental check up, common skin conditions, Heart defects, 	physical disabilities, learning disorders, behavior problems, etc.

⁰Basic medicine kit will be provided to take care of common ailments prevalent 	among young school going children.

⁰Referral Cards for priority services at District / Sub- District hospitals.

•Immunisation:

⁰As per national schedule

⁰Fixed day activity

⁰Coupled with education about the issue

•Micronutrient ( Vitamin A & IFA ) management:

⁰Weekly supervised distribution of Iron – Folate tablets coupled with education about the issue.

⁰Administration of Vitamin A in needy cases.

•De- Worming

⁰As per national guidelines

⁰Biannually supervised schedule

⁰Prior IEC

⁰Siblings of students also to be covered

Health promoting Schools

⁰Counseling services

⁰Regular practice of Yoga, Physical education, health education

⁰Peer leaders as health educators.

⁰Adolescent health education- existing in few places

⁰Linkages with the out of school children

⁰Health clubs, Health cabinets

⁰First Aid room / corners or clinics.

•Capacity building

•Monitoring& Evaluation

•Mid Day Meal

- The strategy suggested for the programme:

For the state of Mizoram the strategy of Option - 1 has been selected from amongst the various options from the guideline of the School Health Programme to be implemented in the state. A framework for continuing  the programme has been chalked out wherein the ANM is to be spared once a week for school Health only as there will be MPW (male) or second ANM to support her at the health sub centre. The Multi Purpose worker male would be entrusted for exclusive boys senior basic school.Wherever possible the he indicative costing of the programme has been formulated so as to continue the  programme in the year 2012-13.

Based on a cascading training strategy involving Health and Education Departments TOTs will take place at State and District levels and teachers will be oriented on the programme so that they internalize the core values and strategies of the programme. Apart from the teachers screening the children, area ANMs/MPWs will visit one school every week on an average for detailed screening and treatment of minor ailment and required referral. In addition, a Medical Officer will also visit one school per week for additional screening, treatment and referral.

Inferring from the indicative costing, it has been proposed that the programme may be taken up in a phased manner covering 20% schools in the first year and 40% schools each in second and third year. The proposed cost of implementation so phased can then be met out of RCH – II Flexible Pool/ Mission Flexible Pool.

5.   Management structure for effective management

Management structure has been provided for in the guidelines at state, and District levels.

The NRHM convergence mechanism will apply to this programme as well. The involvement of State Health Mission and District Health Mission has been ensured by placing the School Health Programme  management committees under the overall Supervision/ Guidance of these overarching structures.

In addition, emphasis has been placed at making these management committees multi–departmental involving the functionaries of various related departments/ organizations such as Education, Rural Development, Public Health Engineering (PHED)

Various School Health Promotion Committees recommended at the State, District, Block and School levels will formed.

School Health Coordinator on Contract basis at the State and District levels has been provided to support the programme in the areas of Coordination monitoring and evaluation.

- Plan for Monitoring :

These management committees have been proposed in a manner that they bring in convergence between related departments/ organizations. The main convergence required in the programme is between the Ministry of Health & Family Welfare (MOHFW) Ministry of Rural Development (MRD) MHRD will be partner in capacity building. IEC, monitoring and evaluation. MRD needs to take case of water, safety Education, Sanitation Education and garbage disposal waste management. The MOHFW will take care of screening, Health care Services, Immunization, Referral micronutrient, management, Health Education, capacity Building, monitoring and evaluation etc.

INDICATIVE COSTING FOR MAJOR ACTIVITIES UNDER SCHOOL HEALTH PROGRAMME

- Human Resources and Mobility Support under School Health Programme:

It has been proposed to reengage the following contractual staff to conduct school Health  visit in Aizawl City. During School visit activities such as Health Check up, Dewarming, IFA supplementation, necessary counseling, Health education session , Treatment, referral etc will be organized / conducted. They will also give training to ANM and sSchool teacher as required. School visits of District/ PHC and others will be conducted by MOs and ANMs as already mentioned  above in  the ‘Chapter of the Strategies Suggested for the Programme ‘,

| SN | Category of Staff | No of Staff | Monthly per Remuneration | Annual per state | FMR Code |
| --- | --- | --- | --- | --- | --- |
| 1. | Renumeration to school Health Programme coordinator (1 post ) MBA/ Master of social work ( with experience in training and outreach society work | 1 | Rs.25,000 | Rs.3,00,000/- | A.10.1.1 |
| 2 | Remuneration to School Health Programme(SHP)Medical Officer (MO) MBBS | 1 | Rs.25,000 | Rs.3,00,000/ |  |
| 3 | Remunaration to SHP Dental Surgeon(BDSc)1 post | 1 | Rs.25,000 | Rs.3,00,000/ |  |
| 4 | Remuneration to SHP Staff Nurse(BSc Nursing/GNM 1 post | 1 | Rs.10,000 | Rs.1,20,000 |  |
| 5 | Remuneration to SHP Ophthalmic Assistant (OA) | 1 | Rs.8000 | Rs. 72,000 |  |
|  | Total human Resources |  |  | Rs.10,92,000/- |  |
|  | Mobility Support to Contractual Staff | No of Staff | Monthly per Unit | Annual per state | FMR Code |
| 1 | Mobility Support to School Health Coordinator |  | Rs.5,000 | Rs.60,000 | A.4.2.4 |
| 2 | Mobility support to the MO |  | Rs.5,000 | Rs.60,000 |  |
| 3 | Mobility support to the Dental Surgeon |  | Rs.5,000 | Rs.60,000 |  |
| 4 | Mobility support to the Staff Nurse |  | Rs.2,000 | Rs.24,000 |  |
| 5 | Mobility support to the SHP –OA |  | Rs.2,000 | Rs.24,000 |  |
|  | Total Mobility Support |  |  | Rs.2,28,000 |  |

- Hardware and Medical supply

| Sl.No | Item to be procured | No of School (1st & 2nd Yr)/ Physical Target | Rate (in Rs) | Amount | FMR cord |
| --- | --- | --- | --- | --- | --- |
| 1 | Weighting scale | 1480 (for 2nd yr only) | 1200 | 1776000 | B-16.1 |
| 2 | High Measurement Equipment | 1480 | 600 | 888000 |  |
|  | Sub Total |  |  | 1776000 |  |
| 1 | Medical Kit | 2220 | 140 | 310800 | B-16.2 |
| 2 | IFA Tablet | 2220 | 547 | 1214340 |  |
| 3 | Albendazole | 2220 | 250 | 555000 |  |
|  | Sub Total |  |  | 2080140 |  |

- Printing of Training of Manuals and referral card

| Sl.No | Item to be procured | No of School (1st & 2nd Yr) | Rate (in Rs) | Amount | FMR cord |
| --- | --- | --- | --- | --- | --- |
| 1 | Training Manual | 2000 | 150 | 300000 | A.4.2.1 |
| 2 | referral cum cumulative health card | 20000 | 10 | 200000 |  |
|  | Total |  |  | 500000 |  |

I.E.C

No separate budget has been proposed for IEC under School Health Programme. Budget proposed for ARSH may be utilized for the same.

TRAINING:

Training of Masters, Training of District/ Block Trainer, School Teacher would be conducted as work out below:- (budgeted under FMR Code A.9.7)

1. Training of Master Trainers

1. Target Load			= 10

2. No of Batches		=1

3. Duration of Training	= 2 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 500 | 2 | 18 | 18000 |
| Honorarium of Resources Person | 1000 | 2 | 2 | 4000 |
| Incidental expenditure/training materials | 250 | - | 18 | 4500 |
| Working Lunch, Tea & Snacks | 200 | 2 | 25 | 10000 |
| Venue Hiring | 500 | 2 |  | 1000 |
| TA (POL) | 1000 | - | 18 | 18000 |
| Total |  |  |  | 55500 |

2. Training of School Teacher

1. Target Load			= 1480

2. No of Batches		= 15 (100 nos per batch)

3. Duration of Training	= 1 day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 100 | 40000 |
| Honorarium of Resources Person | 600 | 1 | 2 | 1200 |
| Incidental expenditure/Training materials | 200 | - | 100 | 20000 |
| Working Lunch, Tea & Snacks | 150 | 1 | 105 | 15750 |
| Venue Hiring | 500 | 1 |  | 500 |
| TA (POL) | 500 | - | 100 | 50000 |
| Total |  |  |  | 127450 |

Budget  for 15 batches = 1911750.00

Training of ANM (Health Worker)

1. Target Load			=  500

2. No of Batches		=  5 (100 nos per batch)

3. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 100 | 40000 |
| Honorarium of Resources Person | 600 | 1 | 2 | 1200 |
| Incidental expenditure/Training materials | 200 | - | 100 | 20000 |
| Working Lunch, Tea & Snacks | 150 | 1 | 105 | 15750 |
| Venue Hiring | 500 | 1 |  | 500 |
| TA (POL) | 500 | - | 100 | 50000 |
| Total |  |  |  | 127450 |

Budget for 5 batches = 637250.00

MOBILITY SUPPORT TO ANM TO VISIT SCHOOLS (FMR Code A.4.2.3)

|  |  |  | # Phasing |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Per day | # For 14 working days | # 1st Year # 20% | # 2nd year # 40% | # 3rd Year # 40% |
| # For 1 ANM each day | # Rs. 100 | # Rs. 1400 |  |  |  |
| # For 6 ANM in block | # Rs. 600 | # Rs. 8400 |  |  |  |
| # For 90 ANM in district | # Rs. 9000 | # Rs. 126000 |  |  |  |
| # For 1440 ANM in the state | # Rs. 14400 | # Rs. 201600 |  |  |  |
| # Total | # Rs. 24100 | # Rs. 337400 | # Rs. 67480 | # Rs. 134960 | # Rs. 134960 |

# Total fund required for 2012-13 is Rs. 202440.00

MOBILITY SUPPORT TO DOCTORS TO VISIT SCHOOLS (FMR Code A.4.2.3)

|  | # Phasing |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | # Per visit | # Fo 32 visit | # For 30 block in Mizoram | # 20% # (1st year) | # 40% # (2nd year) | # 40% # (3rd year) |
| # Mobility support to doctors to visit schools | # Rs. 500 | # Rs. 16000 | # Rs. 480000 | # Rs. 96000 | # Rs. 192000 | # Rs. 192000 |
| # Total Budget | # Rs. 500 | # Rs. 16000 | # Rs. 480000 | # Rs. 96000 | # Rs. 192000 | # Rs. 192000 |

# Total fund requirement for 2-12-13 is Rs. 288000.00

# TRAVEL COST FOR REFERRAL (FMR code A.4.3)

| # No of school/ estimated no of referral | # Rate | # Amount |
| --- | --- | --- |
| # 2220 | # Rs. 100 | # Rs. 220000 |
| # Total | # Rs. 100 | # Rs. 220000 |

# V. URBAN RCH

# Goal & Objective: To improve the health status of urban poor community by provision of integrated primary health care services.

| S.No. | Name of cities identified for implementing UHPs. In the State PIPs. Under Urban RCH, so far | Major urban health strategies/activities carried out under Urban RCH so far, city-wise | Urban health strategies/activities as proposed now in the State PIP under Urban RCH, city- wise | Brief on activities being supported by external agencies |
| --- | --- | --- | --- | --- |
| 1 | Aizawl – 4 UHCs | Ref write up below |  |  |
| 2 | Lunglei- 1 UHC | Ref write up below |  |  |

As mentioned in previous year PIP, Aizawl and Lunglei Cities have been taken up under urban Health RCH programme since 2004. In addition to the existing health facilities, 4 UHCs in Aizawl and 1 UHC in Lunglei were established to address poor community.

The existing Health facilities in the two cities other than Urban Health Centres are:

| Health Facilities | No of Facilities |  |
| --- | --- | --- |
|  | Aizawl | Lunglei |
| Government Hospital | 4 (State Hospital, Kulikawn Hospital & Falkawn Hospital, TB Hospital) | 1 |
| Sub Centre | 53 | 14 |
| Mission Hospital | 2 | 1 |
| Other Private Hospital | 7 | - |

Health care services delivery has been provided to the urban poor community through 4 UHCs in Aizawl city and 1 UHC in Lunglei. All these UHCs are located in the outskirt of the cities to make easily accessible health care services for targeted group. As per provisional data 2011 (Census of India) urban population in Mizoram comprises of 51.51% of the total population and the population of Aizawl and lunglei  is 264645 and 58339 respectively.  It can be stated that urban population growth rate will increse every year due to  Socia economic and Educational factors. Provision of assured and credible primary health services in urban areas is a priority considering rapid mushrooming growth of urban population. A large number of families have been migrated to city every year due to the above reasons stated.

The existing UHCs in Aizawl and Lunglei are useful to ensure provision of assured and credible health services in urban areas especially to slum/ poor people dwelling in the outskirt of the cities.  All UHCs except ITI UHC ( Aizawl East) were established in rented buildings. UHCs are providing round the clock services and operationalised as PHC/CHC. It has been experienced that UHCs are very useful and beneficial especially for urban poor community who are not able to access other government / private health facilities as they are providing all RCH activities as delivered in PHCs. UHCs also greatly promote ANC registration, Immunization, institutional delivery, breast feeding and reducing unmet needs. In addition to these, OPD are opened in the UHCs for the general out Patients. Not only mothers but general patients have been admitted for treatment. Considering the experiences of the significant roles played by UHCs for promoting urban poor community, it is proposed to continue urban health programme during 2012-13

The Approximate population coverage of each UHCs are: 1) Chawlhhmun UHC (Aizawl ‘W’)- 31000 2) ITI UHC (Aizawl ‘E’)-32000 3) Hlimen UHC (Aizawl ‘S’)- 27000 4) Ramhlun UHC- 56700. 5) Hrangchalkawn UHC-22000.

The average monthly Performance of UHCs are tabulated below:

| Indicators | Chalhhmun UHC | ITI UHC | Hlimen UHC | Ramhlun UHC | Hrangchalkawn UHC |
| --- | --- | --- | --- | --- | --- |
| No of Deliveries conducted | 9 | 8 | 6 | 16 | 6 |
| No of Out patients attended | 310 | 140 | 2019 | 200 | 150 |
| No of Female sterilized | 5 | 3 | Nil | 7 | 3 |
| No of IUD insertion done | 4 | 2 | 11 | 4 | 3 |
| No of JSY beneficiaries | 7 | 5 | 5 | 10 | 4 |

Activities to be carried out by UHCs are mentioned below:

1.Ensure timely and full ANC & PNC

2. Promote Institutional Delivery

3. Provide all FP services mentioned in the relevant chapter

4. Provide all Child Health services mentioned in the relevant chapter

5. Implement JSY & JSSK as per guidelines

6. Outreach camps

7. All other functions as provided in PHCs

8. Evaluation of urban RCH services will be done ( No separate budget is required)

Other Activities which need budget under Urban Health are
1. Reengagement of Support Staff ( Other staff budgeted under HR)

2.Building Rent for 4 UHCs ( 4 out 5 UHCs are in rented building)

3.Maintenance of UHC such as, Eletricity bill, Water bill, Indane Gas, Telephone bill etc

# Staff already recruited and on the roll are mentioned below:

| Category of Staff | No of staff per centre | Total no of Staff for 5 UHCs |
| --- | --- | --- |
| Medical Officer | 1 | 5 |
| Staff nurses | 4 nos | 20 |
| ANM/HW | 3 nos | 15 |
| Laboratory Technician | 1 no | 5 |
| Helpers / Support staff | 4 nos | 25 |

Note :

# 1) The above contractual staff already in place will be reengaged. Salary of contractual staff except Support staff is budgeted under the budget head of Human resources.

2) No proposal for engagement of Link workers as ASHA already in place can play the roll of link worker.

Detailed Budget calculation for Urban Health:

| Detailed Budget calculation for Urban Health 2012-13 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FMR/Budget Code | Proposed Activity | Physical Target | Rate | Proposed Budget 2012-13 (In lakhs) | Remarks |
| 5.1.3 | Implementation of Urban Health |  |  |  |  |
|  | Building Rent for 4 UHCs ( only I UHC in Government building) | 4 UHCs | 85000 per qtr | 3.40 | At present Rs.66000 per qtr is required for rent. Rs.85000/- per qtr is considered approprite for 2012-13 as rent will be given as per new assessment rate from April, 2012 |
|  | Water Bill to be purchased from private water supply due to non availability of Government supply | 5 UHCs | 50000 per qtr | 2.00 | The budget proposed for these activities will be required considering existing amount of expenditure |
|  | Telephone Bill | 5 UHCs | 37500 per qtr | 1.50 |  |
|  | Indane Gas/Kerosene oil etc | 5 UHCs | 25000 per qtr | 1.00 |  |
|  | Eletricity Bill | 5 UHCs | 37500 per qtr | 1.50 |  |
|  | Other- Minor repairs, Maintenance of equipment, Miscellenous urgent requirement such as medicine, laboratory materials, stationery etc | 5 UHCs | 65000 per qtr | 2.60 |  |
| 5.1.4 | Monitor progress, quality and utilisation of services. |  |  |  |  |
|  | Monitoring from State & Distric | 5 UHCs | 10000 per qtr | 0.50 | Planned to visit all UHC every month from State/Districts |
| 5.1.5 | Other Urban RCH strategies/activities (please specify) - |  |  |  |  |
|  | Salary of Support Staff | 25 | 6325 p.m | 18.98 | Activities to be continued as approved in the previous PIP |
| Total for Urban Health |  |  |  | 31.48 |  |

# VI. Tribal Health

The entire State of Mizoram is Tribal dominated area. 2001 census reveals that Tribal population is 94.46% out of the total population. It may be stated in this connection that all the RCH II strategic interventions in Mizoram are for promoting the health status of Tribal population. So, specific activities need not be taken up for Tribal health as RCH normal/ routine activities cover scheduled tribe and other castes.

VII. PC & PNDT and Gender Mainstreming:

Goal & Objective: To maintain equality between male and female in the society.

Strategies & Activities: As mentioned in the previous PIPs, gender discrimination is not a big problem and social evil in Mizoram. PNDT Act has been implemented in the state since RCH I to maintain the good relationship and rights of male and female / gender discrimination in the Society. Regular checking of records of diagnostic laboratories with ultra sound machines and regular monitoring of sex ratio at birth from records of birth registration in the health institutions will be done. Reorientation of Proramme managers medical officers and paramedics on the PNDT Act will also be conducted as convenient at state as well as district level. Other activities such as IEC /BCC activities to address the gender issue, Audit of facilities by QAC. Budget has been allocated for operationalization of PNDT cell ( this include IEC/BCC activities) and monitoring of facilities.

Detailed Budget calculation for PNDT:

| Detailed Budget calculation for Urban Health 2012-13 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FMR/Budget Code | Proposed Activity | Physical Target | Rate | Proposed Budget 2012-13 (In lakhs) | Remarks |
| A.7.1.1 | Operationalized PNDT Cell |  |  |  |  |
|  | Quarterly Review meeting | State & District level (9 dists) | 15000 | 1.50 |  |
|  | Preparation /Renovation of Hoarding /Sing board near the diagnostic laboratories / Prominent Places | 50 | 4000 | 2.00 |  |
|  | Discussion/Advertisement on PNDT Act at Radio/DDK/Local Cable TVs |  |  |  | To meet from Maternal Health budget for IEC, hence no separate budget is required |
| A.7.1.2 | Orientation of programme managers and service providers on PC & PNDT Act | 50 in 2 batches | 25000 | 0.50 |  |
|  | Total for PNDT |  |  | 4.00 |  |

VIII. TRAINING:

Skill development of health professional to provide quality services to the clients is one of the main objectives of NRHM. It is a well know fact that considerable improvement is possible in the workforce of the department by improving skills of the existing staff. As regard human resources development, the training activity in the department need more strengthen so that its contribution in capacity building is much more focused. At present there is no medical Colleges and State Institute of Health and Family welfare in the state for which Medical Officers are sent to outside the state to undergo training in EmoC and LSAS. Civil Hospital Aizawl is the only  training centre for Medical Officers in the state, other district hospitals are identified only to train other staff with small batch sizes.   Since the launch of NRHM, various trainings related to Maternal health, Child health, Family planning and Adolescent health have been conducted at the state and district levels. The batch size of training such as RTI/STI and SBA varies from district to district depending upon the case load, number of facilities and staff. The qualities of services being provided have also been very much improved which is possible as some health personnel have undergone various training in IMNCI, SBA etc.  Staff those who have undergone various training are indicated in the table below. However, there are still a number of staff to be trained in different MH,CH,FP etc related trainings. In order to attain further improvement in service delivery, it has been planned that training of staff will be continued during 2012-13. Physical target has been worked out as tabulated below.

# Proposed Training during 2012-13

| Name of Training | Staff & No to be trained During 2012-13 | Current Status |  | Training Centre |  | No. of participants/ batch | No. of Batches | Duration (in Days) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SBA | Staff Nurse (68) |  | 134 |  | CH, Aizawl | 5 | 8 | 21 Days |
|  |  |  |  |  | CH, Lunglei | 2 | 10 | 21 Days |
|  |  |  |  |  | DH, Kolasib | 1 | 8 | 21 Days |
|  | HW / ANMs ( 32) |  | 117 |  | CH, Aizawl | 5 | 4 | 21 Days |
|  |  |  |  |  | DH, Kolasib | 1 | 2 | 21 Days |
|  |  |  |  |  | Christian Hosp, Serkawn | 1 | 10 | 21 Days |
| EmOC | Medical Officer 1) |  | 10 |  | GMC, Guwahati & Civil Hospital Aizawl | 1 | 1 | 112 Days |
| BEmOC | Medical Officer (20) |  | - |  | Civil Hospital Aizawl | 2 | 10 | 10 Days |
| LSAS | Medical Officer (1) |  | 10 |  | RIMS Imphal | 1 | 1 | 126 Days |
| RTI/STI | Medical Officer (30) |  | 46 |  | Civil Hospital Aizawl | 30 | 1 | 2 Days |
|  | SN (90) |  | - |  |  | 30 | 3 | 1 day |
| MTP | Medical Officer (10) |  | 81 |  | Civil Hospital Aizawl | 2 | 5 | 12 Days |
| IMNCI | ANM/HW (120) |  | 775 |  | Civil Hospital Aizawl, | 30 | 4 | 8 Days |
| F-IMNCI | SN (144) |  | 0 |  | Civil Hospital Aizawl | 12 | 12 | 5 days |
| NSSK | SN ( 240) |  | 108 |  | Civil Hospital Aizawl | 24 | 15 | 2 days |
|  | ANM/HW (120) |  | 0 |  | Civil Hospital Aizawl | 24 | 5 | 2 days |
| MiniLap Tubectomy | Medical Officer (10) |  | 81 |  | Civil Hospital Aizawl | 2 | 5 | 12 Days |
| Alternative Training Methodology in IUCD | Health Worker/ ANM (50) |  | 603 |  | Civil Hospital Aizawl | 10 | 5 | 3 Days |
| IMEP | SN (300) |  | 0 |  | State & District | 30 | 20 | 1 day |

# ESTIMATED BUDGET FOR TRAININGS

# Maternal health Training

# 1. (i)Skilled Birth Attendants Training for Staff Nurses (Aizawl)

1. Target Load			= 40

2. No of Batches		= 8

3. Participants per batch	=5

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 5 | 42,000 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 5 Lectures | 1 | 3,000 |
| Incidental expenditure | 250 | - | 5 | 1,250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 5 | 21,000 |
| Institutional Overhead (15% of above) |  |  |  | 13,850 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 5 | 3,000 |
| Total |  |  |  | Rs. 1,09,300/- |

# Budget for 8 batches = 8X Rs. 1,09,300/- = Rs.8,74,400/-

# Quarter Wise – No of Batches to be trained

| SBA(Aizawl) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 3 | 3 | 2 | - |

# 1. (ii)Skilled Birth Attendants Training for Health Workers(Aizawl)

1. Target Load			= 20

2. No of Batches		= 4

3. Participants per batch	=5

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 5 | 42,000 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 5 Lectures | 1 | 3,000 |
| Incidental expenditure | 250 | - | 5 | 1,250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 5 | 21,000 |
| Institutional Overhead (15% of above) |  |  |  | 13,850 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 5 | 3,000 |
| Total |  |  |  | Rs. 1,09,300/- |

# Budget for 4 batches = 4X Rs. 1,09,300/- = Rs.4,37,200/-

# Quarter Wise – No of Batches to be trained

| SBA(Aizawl) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | - |  | 1 | 3 |

# 1. (iii) Skilled Birth Attendants Training for Staff Nurses(Lunglei district)

1. Target Load			= 20

2. No of Batches		= 10

3. Participants per batch	= 2

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 21 | 2 | 8,400 |
| Institutional Overhead (15% of above) |  |  |  | 7,800 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 2 | 1,200 |
| Total |  |  |  | Rs. 62,300/- |

# Budget for 10 batches = 10X Rs. 62,300/- = Rs.6,23,000/-

# Quarter Wise – No of Batches to be trained

| SBA(Lunglei) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 2 | 3 | 3 | 2 |

# 1. (iv) Skilled Birth Attendants Training for Staff Nurses (Kolasib district)

1. Target Load			=8

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 8 batches = 8X Rs. 47,100/- = Rs.3,76,800/-

# Quarter Wise – No of Batches to be trained

| SBA(Kolasib) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 2 | 2 | 2 | 2 |

# 1. (v) Skilled Birth Attendants Training for  Health Workers (Kolasib district)

1. Target Load			=2

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 2 batches = 2X Rs. 47,100/- = Rs.94,200/-

# Quarter Wise – No of Batches to be trained

| SBA(Kolasib) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | - | 1 | 1 | - |

# 1. (vi) Skilled Birth Attendants Training for Health Workers (Christian Hospital, Serkawn)

1. Target Load			=10

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 10 batches = 10X Rs. 47,100/- = Rs.4,71,000/-

# Quarter Wise – No of Batches to be trained

| Christian Hospital, Serkawn | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | 2 | 3 | 3 | 2 |

# 2. Basic Emergency Obstetric Care (BEmOC)

1. Target Load			= 20

2. No of Batches		= 10

3. Participants per batch	= 2

4. Duration of Training	= 10days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 10 | 2 | 14,000 |
| Honorarium of Resources Person | 600 | 10 | 2 | 12,000 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 10 | 2 | 4,000 |
| Institutional Overhead (15% of above) |  |  |  | 4,575 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 39,075/- |

# Budget for 3 batches = 10 X Rs. 39,075/- = Rs.3,90,750/-

# Quarter Wise – No of Batches to be trained

| BEmOC | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I |  | III | IV |
|  | 2 | 3 | 3 | 2 |

4.(i) RTI/STI Training for Medical Officer

1. Target Load			= 30

2. No of Batches		=1

3. Participants per batch	= 30

4. Duration of Training	= 2 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 2 | 30 | 42,000 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4800 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 2 | 30 | 12000 |
| Venue Hiring | 500 | 2 |  | 1000 |
| Institutional Overhead (15% of above) |  |  |  | 11000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 2000 | - | 30 | 60,000 |
| Total |  |  |  | Rs. 1,38,300/- |

# Quarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | 1 | - | - | - |

4. (ii) RTI/STI Training for Staff Nurses

1. Target Load			= 90

2. No of Batches		=3

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 4 | 2400 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4200 |
| TA (Actual Maxi Cab / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 50,600/- |

# Budget for 3 batches = 3 X Rs.50,600/- = Rs.1,51,800/-

# uarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | - | 3 | - | - |

4. (iii) RTI/STI Training for Health Workers

1. Target Load			= 90

2. No of Batches		=3

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 4 | 2400 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4200 |
| TA (Actual Maxi Cab/ Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 50,600/- |

# Budget for 3 batches = 3 X Rs.50,600/- = Rs.1,51,800/-

# Quarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | - | 3 | - |

5. MTP Training for Medical Officer

1. Target Load			= 6

2. No of Batches		= 3

3. Participants per batch	= 2

4. Duration of Training	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 12 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 12 | 2 | 4,800 |
| Institutional Overhead (15% of above) |  |  |  | 5,500 |
| TA (POL) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 46,000/- |

# Budget for 3 batches = 3X Rs. 46000/- = Rs.1,38,000/-

# Quarter Wise – No of Batches to be trained

| MTP | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | 2 | 1 | - |

Child Health Training:

1. IMNCI Training for Health Workers

1. Target Load			= 120

2. No of Batches		= 4

3. Participants per batch	= 30

4. Duration of Training	= 8 Days

| Components | Rate/day (Rs) | No of days | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 8 | 30 | 96,000 |
| Honorarium of Resources Person | 600 | 8 | 4 | 19,200 |
| Incidental expenditure | 250 | - | 30 | 7,500 |
| Working Lunch, Tea & Snacks | 200 | 8 | 30 | 48,000 |
| Venue Hiring | 500 | 8 |  | 4,000 |
| Institutional Overhead (15% of above) |  |  |  | 25,600 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 2,18,300/- |

# Budget for 4 batches = 4 X Rs. 2,18,300/- = Rs. 8,73,200/-

# Quarter Wise – No of Batches to be trained

| IMNCI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | 1 | 1 | 1 | 1 |

# 2. F-IMNCI Training for Staff Nurses

1. Target Load			=144

2. No of Batches		= 12

3. Participants per batch	= 12

4. Duration of Training	= 11 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 11 | 12 | 52,800 |
| Honorarium of Resources Person | 600 | 11 | 2 | 13,200 |
| Incidental expenditure | 250 | - | 12 | 3,000 |
| Working Lunch, Tea & Snacks | 200 | 11 | 12 | 26,400 |
| Venue Hiring | 500 | 11 |  | 5,500 |
| Institutional Overhead (15% of above) |  |  |  | 15,100 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 12 | 7,200 |
| Total |  |  |  | Rs.1,23,200 /- |

# 12 Batches x Rs. 1,23,200/- = Rs.14,78,400/-

# Quarter Wise – No of Batches to be trained

| F-IMNCI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 3 | 3 | 3 | 3 |

# 3.(1)NSSK Training for Staff Nurses

1. Target Load			=240

2. No of Batches		=10

3. Participants per batch	= 24

4. Duration of Training	= 2 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 2 | 24 | 19,200 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4,800 |
| Incidental expenditure | 250 | - | 24 | 6,000 |
| Working Lunch, Tea & Snacks | 200 | 2 | 24 | 9,600 |
| Venue Hiring | 500 | 2 |  | 1,000 |
| Institutional Overhead (15% of above) |  |  |  | 6,000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 24 | 14,400 |
| Total |  |  |  | Rs.61,000 /- |

# 10 Batches x Rs. 61,000/- = Rs. 6,10,000/-

# Quarter Wise – No of Batches to be trained

| NSSK | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 4 | 4 | 2 | - |

# 3.(ii) NSSK Training for Health Workers

1. Target Load			=120

2. No of Batches		=5

3. Participants per batch	= 24

4. Duration of Training	= 2 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 2 | 24 | 19,200 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4,800 |
| Incidental expenditure | 250 | - | 24 | 6,000 |
| Working Lunch, Tea & Snacks | 200 | 2 | 24 | 9,600 |
| Venue Hiring | 500 | 2 |  | 1,000 |
| Institutional Overhead (15% of above) |  |  |  | 6,000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 24 | 14,400 |
| Total |  |  |  | Rs.61,000 /- |

# 5 Batches x Rs. 61,000/- = Rs. 3,05,000/-

# uarter Wise – No of Batches to be trained

| NSSK | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | - | 1 | 4 |

Family Planning:

1. MiniLap Tubectomy Training for Medical Officer

1. Target Load			= 6

2. No of Batches		= 3

3. Participants per batch	= 2

4. Duration of Taining	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 12 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 12 | 2 | 4,800 |
| Institutional Overhead (15% of above) |  |  |  | 5,500 |
| TA (POL) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 46,000/- |

# Budget for 3 batches = 3X Rs. 46000/- = Rs.1,38,000/-

# Quarter Wise – No of Batches to be trained

| Minilap Tubectomy | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | 2 | 1 | - |

2. Laparoscopic Sterilisation Training

1. Target Load			= 1 Team

2. No of Batches		= 1

3. Participants per batch	= 3

4. Duration of Training	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees(Gynaecologist) | 700 | 12 | 1 | 8,400 |
| DA for Other trainees | 400 | 12 | 2 | 9,600 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 3 | 750 |
| Working Lunch, Tea & Snacks | 200 | 12 | 3 | 7,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (POL ) | - | - | - | 3,200 |
| Total |  |  |  | Rs. 43,550/- |

# Budget for 1 batches = 1X Rs. 43,550/- = Rs.43,550/-

# Quarter Wise – No of Batches to be trained

| Lap Sterilisation | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
|  | I | II | III | IV |
|  |  | - | 1 | - |

3. Alternative Training Methodology in IUCD for Health Workers

1. Target Load			= 50

2. No of Batches		= 5

3. Participants per batch	= 10

4. Duration of Training	= 3 days

| Components | Rate/day (Rs) | No of days | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 3 | 10 | 12,000 |
| Honorarium of Resources Person | 600 | 3 | 3 | 5,400 |
| Incidental expenditure | 250 | - | 10 | 2,500 |
| Working Lunch, Tea & Snacks | 200 | 3 | 10 | 6,000 |
| Venue Hiring | 500 | 3 |  | 1,500 |
| Institutional Overhead (15% of above) |  |  |  | 4,100 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 10 | 6000 |
| Total |  |  |  | Rs. 37,500/- |

# Budget for5 batches = 5X Rs. 37,500/- = Rs.1,87,500/-

Quarter Wise – No of Batches to be trained

| Alternative Methodology in IUCD | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | 3 | 2 | - |

IMEP Training for Staff Nurses

1. Target Load			= 300

2. No of Batches		=10

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 1 | 600 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 48,600/- |

# Budget for 10 batches = 10 X Rs.48,600/- = Rs.4,86,000/-

# Quarter Wise – No of Batches to be trained

| IMEP | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 3 | 7 | - | - |

# Programme Management Training: Average budget per participant as per training norms has been worked out. Please refer Budget sheet

# PUBLIC PRIVATE PARTNERSHIP & MNGO

# Goal: To improve the health status of the population of underserved/ difficult area through PPP.

Notes: 2 MNGOs cover 4 districts namely Aizawl, Champhai, Lunglei and Lawngtlai. Only Marpara PHC in mamit district is operationalized as PPP mode.

Public Private Partnership (PPP) has been implemented in the state w.e.f 2005-06 under RCH II program. 2(two) Mission Hospital namely Christian Hospital Serkawn run by Baptist Church of Mizoram in Lunglei district and Presbyterian Hospital Durtlang run by Mizoram Synod in Aizawl district were identified for Mother NGOs to cover 2 districts each. Christian Hospital Serkawn is functioning as MNGO in Lunglei and Lawngtlai districts and Presbyterian Hospital Durtlang is looking after Aizawl and Champhai districts. It has been proposed that the existing two MNGOs will continue their services to promote RCH programme.

As mentioned in the previous RCH II PIP, Marpara PHC under Mamit district has been operationalised in collaboration with Presbyterian Hospital Durtlang (biggest Mission Hospital in the state) . Marpara is located in the west of Mizoram (Mamit dist) .It is one of the remote and hard to reach areas. Marpara PHC covers 2 S/C, 6 villages with a population of around 7600. Due to its remoteness and bad climatic condition many service providers used to refuse to work in this area. Thus, the inhabitants in this area are still lacking good health care delivery system due to its location and non availability of dedicated staff and health infrastructure. In such a situation. The Mission Hospital agreed to extend its services in this area keeping its Mission for the backward people in mind.

As approved by Government of India, MOU was signed during 2008-09 and the contract is 5 years commencing from 1st July, 2008. The State Health Society under RCH II Program provides all necessary funding for staff salaries, maintenance of health infrastructure, all equipment etc required for comprehensive health care delivery through the Mission Hospital. As implementation of  PPP has been found successful, It is planned to continue during 2012-2013. The Mission hospital is services provider, and responsible for recruitment of staff, operationalization of PHC and provide necessary services in accordance with existing norms and instruction issue by the State Health Society.

The District being covered under PPP & MNGO are 1) Aizawl 2) Champhai 3) Lunglei 4) Lawngtlai and Marpara PHC under Mamit District

Budget for MNGOs and PPP under Mission Flexipool

HUMAN RESOURCES:

As per instruction issued by the Government of India, difficult areas have been identified and accordingly the whole state of Mizoram was identified and categorized into three groups as follows – Category A soft area/normal area, category B difficult area, category C very difficult area. It is proposed to reengage all the existing contractual staff.

# Clarification of Categorization:

- Very difficult are: These areas do not have regular power supply, running water supply and good educational institutions. The places remain inaccessible at least about 6 months during monsoon season. Accommodation facilities could not be provided to all medical and paramedical workers in these areas.

- Difficult area	: These areas are connected by unmetalled roads only, but cab be accessed most of the time except during the peak monsoon season. They are having slightly better power supply although with regard to running water and accommodation facilities, it is still difficult to provide them.

- Normal/Soft area: They are all weather road and reachable by vehicle throughout the year.

Existing Human resources and proposed pay for 2012-13. Sl.No; Category of staff; No of Staff; Approved pay as per ROP 2011-12; % Increase; Total Salary per Month; Salary for 1 year. 1; Specialist. Normal Area; 6; 38500; 15%; 44275; 3187800. Difficult area; 2; 42350; 15%; 48703; 1168860. Very Difficult Area; 1; 46585; 15%; 53573; 642873. Sub Total; 9; 4999533. 2; Medical Officer. Normal Area; 20; 24200; 25%; 30250; 7260000. Difficult area; 20; 27500; 25%; 34375; 8250000. Very Difficult Area; 15; 33000; 25%; 41250; 7425000. Sub Total; 55; 22935000. 3; Dental Surgeon (BDS). Normal Area; 18; 22000; 37.50%; 30250; 6534000. Difficult area; 14; 26400; 30.21%; 34375; 5775000. Very Difficult Area; 8; 28600; 44.23%; 41250; 3960000. Sub Total; 40; 16269000. 4; Staff Nurse. Normal Area; 77; 10000; 25%; 12500; 11550000. Difficult area; 73; 11000; 36%; 15000; 13140000. Very Difficult Area; 87; 12000; 35%; 16250; 16965000. Sub Total; 237; 41655000. 5; Pharmacist. Normal Area; 18; 8000; 25%; 10000; 2160000. Difficult area; 3; 8500; 25%; 10625; 382500. Very Difficult Area; 7; 9000; 25%; 11250; 945000. Sub Total; 28; 3487500. 6; X-ray tech. Normal Area; 5; 8000; 25%; 10000; 600000. Difficult area; 7; 8500; 25%; 10625; 892500. Very Difficult Area; 6; 9000; 25%; 11250; 810000. Sub Total; 18; 2302500. 7; BEE. Normal Area; 1; 6000; 50%; 9000; 108000. Difficult area; 6; 6500; 50%; 9750; 702000. Very Difficult Area; 2; 7000; 50%; 10500; 252000. Sub Total; 9; 1062000. 8; ANM. Normal Area; 57; 9000; 5%; 9450; 6463800. Difficult area; 122; 9900; 5%; 10395; 15218280. Very Difficult Area; 249; 10800; 5%; 11340; 33883920. Sub Total; 428; 55566000. 10; Laboratory Technician (Diplonma). Normal Area; 13; 8000; 20%; 9600; 1497600. Difficult area; 13; 8500; 20%; 10200; 1591200. Very Difficult Area; 10; 9000; 20%; 10800; 1296000. Sub Total; 36; 4384800. 11; Laboratory Technician (Certificate). Normal Area; 5; 6000; 25%; 7500; 450000. Difficult area; 5; 6500; 25%; 8125; 487500. Very Difficult Area; 8; 7000; 25%; 8750; 840000. Sub Total; 18; 1777500. 12; FP Counsellor. Normal Area; 2; 15000; 5%; 15750; 378000. Sub Total; 2; 378000. G.Total; 154816833.

| PROGRAMME MANAGEMENT SUPPORT UNIT The State Health Society of Mizoram functions as follows, there are 3 committees at the State level and one committee each at all the Districts. At the State level there is State Health Mission which is chaired by the Hon’ble Chief Minister, Governing body which is chaired by Chief Secretary and Executive Committee which is chaired by the Principal Secretary, H&FW Department, Government of Mizoram The State Programme Managemnet Support uinit is headed by the Mission Director under the umbrella of NRHM in which all programme division converge. The SPMSU engages key personnel on a contractual basis for planning, monitoring and implementation of the programme. At the district level the state constitute District Health Society which is under the chairmanship of the Deputy Commissioner. The DHS is the main implementing functionaries of NRHM Programme In Mizoram the block level administrative system is inconvenient under Health Department. However the CHC/PHC is considered as administrative unit. The state engages accounts clerk to assist in the programme and Finanacial management at all the CHC/PHC level Job Description : Medical Officer: Facilitate/ assist in preparation (through technical assistance) of a planning and monitoring including budgeting manual for NRHM/RCH II. Update the manual at least on an annual basis to reflect experience in implementation and changes/ revised guidelines from GoI, etc. Disseminate manual to districts, municipalities and other “ spending “ centres. Facilitate necessary training for personnel in use of the Manual. At the start of the planning cycle, prepare necessary proposals for allocation of resources/ flexible funds to districts, municipalities, spending centres. Obtain necessary approvals and facilitate communication to districts/ spending centres. Follow up, provide necessary assistance to ensure that the plans from district / municipalities, etc are prepared on time and in accordance with the manual. Coordinate/ facilitate appraisal of plans, on the basis of appropriate criteria (in accordance with the Manual) and recommend approval after changes, if required. Prepare a consolidated state PIP and provide assistance in obtaining necessary approvals from State Health Society/ Mission as well as GoI. Provide necessary assistance in reaching an agreement with MoHFW, GoI on the Memorandum of Understanding (MoU). Follow up to ensure that districts/ municipalities/ spending centres submit monthly/ quarterly reports in accordance with the Manual. Review, analyse these reports, visit districts if necessary, participate in review meetings and recommend corrective action. Prepare consolidated monthly/quarterly progress reports highlighting achievements (physical/ financial) against the PIP, reasons for delay/ adverse variance, corrective action to be taken, etc. Follow up to ensure that agreed corrective action is implemented. Consultant (HMIS): - Preparation and maintenance of data base on NRHM performance, population, demographic indicator for RCH at district/State level. - Facilitate the process of operationalizing bottom up planning in the State - Assist in compilation of monthly and periodical reports in prescribed format under NRHM - Examining the monthly progress report and provide feedback to the districts authorities for any clarification - Preparation of district wise performance every month - Support in conduct of facility survey at the district level - Desseminate the finding emerging from the data generated and reports submitted by the agencies - Undertake field visit in pursuance of task assigned. - Coordinate with other personnel under NRHM and other agencies/Department etc. Finance Consultant: # The consultant key tasks would include but not be limited to the following: - Develop an operational manual for management of funds in state society, district society and facility level societies (e.g. Rogi Kalyan Samitis); obtain necessary approvals - Manage society funds by: - Overseeing disbursement of funds to implementing agencies - Ensuring that the accounting procedures laid down in the operational manual are followed - Preparation of statement of expenditure and collection of utilisation certificates - Ensuring conduct of financial accounting/ management audits and compliance with findings - Ensure conduct of training needs assessment of state and district accounting staff and conduct of training programmes for them (such as double entry book keeping, using accounting software, etc). - Budget analysis of the state, district and facility level societies and developing proposals for improving financial management systems at these levels. NGO Cordinator : - Assist RCH II Programme Officer in the implementation of NGO related scheme activities at the state level & District level. - To look after scheme such as MNGOs, PPP etc - Monitor of NGO activities through compilation, analysis of physical and financial progress and send feedback to NGOs/Districts - Conduct meeting with NGOs to review progress of activities being carried out - All other activities carried out with NGOs as assigned to him/her from time to time State MIS Manager The State MIS Manager’s key tasks would include the following: - Work closely with the team entrusted with preparation of the planning and monitoring manual to ensure that monitoring/reporting formats at state and district level are rationalized. - Design and implement/ continuously update a data base providing all necessary information relevant to NRHM including e.g. district/ CHC PHC wise demographic data, performance against health indicators, status of public/ private facilities, etc. - Compile monthly physical and financial progress reports and critically examine discrepancies and areas of improvement in reporting - Implement systems and procedures for efficient functioning of the NRHM Director’s office - Assist the SPM in use of GIS for mapping of facilities and other tasks Data Manager (1) # The State Data Manager key tasks would include the following: - Work closely with the HMIS consultant and HMIS team in collection of data from the districts and other implementing agencies. - Insure timely submission of report and uploading of report in the web protal - Analyse HMIS data and sent feedback to the districts - Assist the SPM in use of GIS for mapping of facilities and other tasks - Collect data and reports and supply necessary information to the Mizoram NRHM Website. State Administrative Officer (1) # The State Administrative Officer key tasks would include the following: - Provide necessary assistance through e.g. arrangements for training, Recruitment of Manpower, Transfer & Postings etc - to enable DPMSUs to bring about continuous process improvement in delivery of services e.g. ASHA programme, RCH camps, referral transport, etc. - Identify opportunities for improved utilization of manpower resources across various Health programmes, obtain necessary approvals and follow up to ensure implementation. - Secretariat support to State Health Mission and Society including arrangements for meetings, maintenance of records of contractual positioning, follow up to ensure implementation etc. - Ensure periodic meetings of DPMU staff including for monitoring purposes and sharing of experiences. - Human Resources Development process improvement proposals prepared and implemented - Number of meetings of DPMSU staff held. - Arrangements for meetings of State Health Mission/ Society made including preparation of agenda papers, recording of minutes, etc Accounts Clerk: - Maintenance of books of accounts of the society, and monthly and annual closure of books of accounts. - Disbursement of funds to implementing agencies. - All bank related activities. Statistical Assistant & Data Entry Operator: - Assist the HMIS Consultant in preparation of monthly progress report on the implementation of programme activities in the Districts. - Assist the M&E in development of annual work plan based on the District action plan. - Assist in routine monitoring of programme activities through compilation and analysis of various reporting/monitoring format. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PHYSICAL & FINANCIAL TARGETS FOR STATE PROGRAMME MANAGEMENT UNIT (contractual Staff) |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff | No of Staff | Approved pay as per ROP 2011-12 |  | Increase % |  | Total Salary per Month |  | Salary for 1 year |  |
| 1 | Medical officer ( i/c of Maternal Health, Child Health, Family Planning and ARSH) | 4 | 35000 |  | 25% |  | 43750 |  | 2100000 |  |
| 2 | Consultant HMIS | 1 | 20000 |  | 25% |  | 25000 |  | 300000 |  |
| 3 | State Finance Manager | 1 |  |  |  |  | 55000 |  | 660000 |  |
| 4 | Consultant Finance | 1 | 20000 |  | 25% |  | 25000 |  | 300000 |  |
| 5 | NGO Coordinator | 1 | 12000 |  | 25% |  | 15000 |  | 180000 |  |
| 6 | Manager MiS | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 7 | Data Manager | 1 |  |  |  |  | 20000 |  | 240000 |  |
| 8 | Admi. Officer | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 9 | Accounts manager | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 10 | Asst. Engineer | 2 | 22000 |  | 25% |  | 27500 |  | 660000 |  |
| 11 | Junior engineer | 9 | 9000 |  | 25% |  | 11250 |  | 1215000 |  |
| 12 | Accountant | 1 | 10000 |  | 25% |  | 12500 |  | 150000 |  |
| 13 | Statistical Assistant | 1 | 9500 |  | 25% |  | 11875 |  | 142500 |  |
| 14 | Accounts Clerk/ Financial Assistant | 3 | 9000 |  | 25% |  | 11250 |  | 405000 |  |
| 15 | DEO | 3 | 8000 |  | 25% |  | 10000 |  | 360000 |  |
| 16 | Driver | 1 | 5500 |  | 25% |  | 6875 |  | 82500 |  |
| 17 | Helper | 3 | 5500 |  | 15% |  | 6325 |  | 227700 |  |
|  | Grand Total | 34 |  |  |  |  |  |  | 7832700.00 |  |
| Notes: For Programme Management Staff under School Health Programme, Please refer School Health Chapter and budget sheet District Programme Management Support Unit (DPMSU) The cornerstone of implementation of NRHM in the districts depends on the management capacity of District Programme Management Support Unit under the District Health Society. The District Support Unit was set up in 2006-07 and needs to be empowered and integrated with the requirements of programme implementation at the cost and time line laid down in the District Action Plan. The District Programme Management Support Unit is headed by District Programme Manager. The District team will be supported by functional manpower which has been provided in the plan. The district level functions include planning, implementation, monitoring and management of all components under RCH II, Mission Flexible Pool, Immunization, National Disease Control Programmes, and convergent actions. DPSMU has a professional team comprising of the Programme Manager, Accounts Clerk, Executive Assistant and Data Entry Operator and needs to be provided with basic support for programme implementation and monitoring. Technical, operational and executive support to all programmes and projects in the Districts, planning, implementation and monitoring of all components and capacity building, MIS, analysis of variances in implementation of district plans, regular reporting and feedback are critical activities performed by the District Societies. The District Accounts Clerk is responsible for the finance and accounting functions and ensuring adherence to lay down accounting standards timely submission of expenditure reports and utilization certificates. PHYSICAL & FINANCIAL TARGETS DISTRICT PROGRAMME MANAGEMENT UNIT |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff |  |  | No of Staff |  | Approved pay as per ROP 2011-12 | Increase % | Salary per Month |  | Salary for 1 year |  |
| 1 | District DPM |  |  | 9 |  | 18500 | 25% | 23125 |  | 2497500 |  |
| 2 | DEO |  |  | 9 |  | 8500 | 15% | 10625 |  | 1147500 |  |
| 3 | Project Asst/NGO Coordinator |  |  | 1 |  | 12000 | 25% | 15000 |  | 180000 |  |
| 4 | Accounts Manager |  |  | 18 |  | 9500 | 25% | 11875 |  | 2565000 |  |
| 5 | Stat Asst |  |  | 1 |  | 9500 | 25% | 11875 |  | 142500 |  |
| 6 | Executive Asst |  |  | 9 |  | 8500 | 25% | 10625 |  | 1147500 |  |
| 7 | Junior Engineer |  |  | 4 |  | 9000 | 25% | 11250 |  | 540000 |  |
| 9 | Section Asst |  |  | 1 |  | 9000 | 25% | 11250 |  | 135000 |  |
|  | TOTAL |  |  | 52 |  |  |  |  |  | 8355000 |  |
| Accounts Clerk and DEO at PHC /CHC For Efficient Financial Management the State currently engaged accountant at all the PHC and CHC. The State also envisage supplying Computer with accessories to CHC and PHC now that by using with web portal Facility based analysis of Data will be easier. PHYSICAL & FINANCIAL TARGETS BLOCK MANAGEMENT SUPPORT UNIT |  |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff |  |  | No of Staff |  | Approved pay as per ROP 2011-12 | Increase in % | Salary per Month |  | Salary for 1 year |  |
|  | ACCOUNTS CLERK IN CHC/PHC |  |  |  |  |  |  |  |  |  |  |
| 1 | Normal Area |  |  | 9 |  | 9000 | 25% | 11250 |  | 1215000 |  |
| 2 | Difficult area |  |  | 26 |  | 9500 | 25% | 11875 |  | 3705000 |  |
| 3 | Very Difficult Area |  |  | 31 |  | 10000 | 25% | 12500 |  | 4650000 |  |
|  | Total |  |  | 66 |  |  |  |  |  | 9570000 |  |

| DETAIL BUDGET RCH II: 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (States to provide details for high focus districts and for the State total) |  |  |  |  |  |  |  |  |  |
| S. No. | Budget Head | BASELINE/ CURRENT STATUS (pls specify, whether as on November or December 2010) | Unit of Measure | PHYSICAL TARGET (where applicable) |  | Rate (Rs./Unit) | BUDGET (RS. LAKHS) |  | Remarks / Justification |
|  |  |  |  | Total Annual |  |  | Total Annual Budget (Rs. Lakhs) |  |  |
|  |  | High focus districts |  | High focus districts | State Total |  | High focus districts | State Total |  |
| 1 | MATERNAL HEALTH |  |  |  |  |  |  |  |  |
| 1.1 | Operationalise facilities (only dissemination, meetings and quality assurance) |  |  |  |  |  |  |  |  |
| 1.1.1 | Operationalise FRUs |  |  |  |  |  |  |  |  |
| 1.1.1.1 | Organise dissemination workshops for FRU guidelines |  |  |  |  |  |  |  |  |
| 1.1.1.2 | Prepare plan for operationalisation across districts (cost of plan meeting should be kept) |  |  |  |  |  |  |  |  |
| 1.1.1.3 | Monitor progress and quality of service delivery |  | No of visit | 10 trips | 30 trips | 10000 | 1.00 | 3.00 |  |
| 1.1.2 | Operationalise 24x7 PHCs |  |  |  |  |  |  |  |  |
| 1.1.2.1 | Prepare plan for operationalisation across districts (cost of plan meeting should be kept) |  |  |  |  |  |  |  |  |
| 1.1.2.2 | Monitor progress and quality of service delivery |  |  |  |  |  |  |  |  |
| 1.1.3 | Operationalise Safe abortion services (including MVA/ EVA and medical abortion)at health facilities |  |  |  |  |  |  |  |  |
| 1.1.3.1 | Prepare plan for operationalisation across districts (priortise facilities for safe abortion services; cost of plan meeting should be kept) |  |  |  |  |  |  |  |  |
| 1.1.3.2 | Monitor progress and quality of service delivery |  | No of visit | 15 trips | 50 trips | 5000 | 0.75 | 2.50 |  |
| 1.1.4 | Operationalise RTI/STI services at health facilities |  |  |  |  |  |  |  |  |
| 1.1.4.1 | Prepare plan for operationalisation across districts (priortise facilities for RTI/STI services; cost of plan meeting should be kept) |  |  |  |  |  |  |  |  |
| 1.1.4.2 | Monitor progress and quality of service delivery. |  |  |  |  |  |  |  |  |
| 1.1.5 | Operationalise sub-centres (monitoring) |  | No of visit | 25 trips | 100 trips | 1000 | 0.25 | 1.00 |  |
| 1.1.5.1 | Prepare plan for operationalising services at sub-centres (for a range of RCH services including antenatal care and post natal care; cost of plan meeting should be kept) |  |  |  |  |  |  |  |  |
| 1.1.5.2 | Monitor quality of service delivery and utilisation including through field visits |  |  |  |  |  |  |  |  |
| 1.2 | Referral Transport (home to facility, interfacility, dropback) |  |  |  |  |  |  |  |  |
| 1.3 | Integrated outreach RCH services |  |  |  |  |  |  |  |  |
| 1.3.1 | RCH Outreach Camps in un-served/ under-served areas (state should focus on facility based services and outreach camps to be restricted to areas without functional health facilities) |  |  | 12 | 12 | 20000 | 2.40 | 2.40 |  |
| 1.3.2. | Monthly Village Health and Nutrition Days( plan to conduct in 450 AWW centres per month) |  | No | 280 | 1800 | 200 | 0.56 | 3.60 |  |
| 1.3.2.1 | Monitor quality of services and utilisation |  |  |  |  |  |  |  |  |
| 1.4. | Janani Suraksha Yojana / JSY |  |  |  |  |  |  |  |  |
| 1.4.1 | Dissemination of JSY guidelines to districts and sub-districts |  |  |  |  |  |  |  |  |
| 1.4.2 | Implementation of JSY by districts. |  |  |  |  |  |  |  |  |
| 1.4.2.1 | Home deliveries |  | No | 1040 | 2576 | 500 | 5.20 | 12.88 |  |
| 1.4.2.2 | Institutional deliveries |  |  |  |  |  |  |  |  |
| 1.4.2.2.1 | Rural |  | No | 1917 | 8790 | 700 | 13.42 | 61.53 |  |
| 1.4.2.2.2 | Urban |  | No |  | 4734 | 600 |  | 28.40 |  |
| 1.4.2.2.3 | C-sections |  |  |  |  |  |  |  |  |
| 1.4.3 | Other activities (JSY) |  |  |  |  |  |  |  |  |
| 1.4.3.1 | ASHA Incentive |  | No | 1917 | 13524 | 600 / 200 | 11.50 | 62.21 |  |
| 1.4.3.2 | Admin Cost (5%) |  | No |  |  |  | 1.54 | 8.25 |  |
| 1.5 | Maternal Death Audit Including Child Death Audit (both in institutions and community) |  | No | 350 | 670 | 750 | 2.63 | 4.88 |  |
| 1.6 | Other strategies/activities (please specify) ( Incentive for tracking of mothers who avail private facilities) |  | No |  | 3000 | 50 |  | 1.50 |  |
|  | Other - Co ordination Meeting on RTI/STI |  | No of meeting | 3 | 10 | 50000 | 1.50 | 5.00 |  |
| 1.6.1 | JSSK- Janani Shishu Surakhsha Karyakram |  |  |  |  |  |  |  |  |
| 1.6.1 | Mother and Child Care |  |  |  |  |  |  |  |  |
| 1.6.1.1 | Diagnostic / Laboratory expenses |  | No | 1800 | 18000 | 200 | 3.60 | 36.00 |  |
| 1.6.1.2 | Blood Transfusion |  | No | 180 | 1800 | 300 | 0.54 | 5.40 |  |
| 1.6.1.3 | Diet Normal Deliveries for 3 days |  | No | 1800 | 16200 | 100 per day | 5.40 | 48.60 |  |
|  | Diet for C.S for 7 days |  | No | 180 | 1800 | 100 per day | 1.26 | 12.60 |  |
| 1.6.2 | Drugs and Consumables |  |  |  |  |  |  |  |  |
| 1.6.2.1 | Drugs and Consumables for Normal Deliveries |  | No | 1620 | 16200 | 350 | 5.67 | 56.70 |  |
| 1.6.2.2 | Drugs and Consumables for Caesarean Deliveries |  | No | 180 | 1800 | 1600 | 2.88 | 28.80 |  |
| 1.6.4 | Others (Pl. specify)- Referral transport under JSSK for mothers & Sick newborns from Home to facility |  | No | 1980 | 19800 | 300 | 5.94 | 59.40 |  |
|  | Others (Pl. specify)- Referral transport under JSSK for mothers & Sick newborns from Facility to Home |  | No | 1980 | 19800 | 300 | 5.94 | 59.40 |  |
|  | Call Centres for JSSK |  |  |  |  |  |  | 10.00 |  |
|  | Sub-total Maternal Health (excluding JSY) |  |  |  |  |  | 40.32 | 340.78 |  |
|  | Sub-total JSY |  |  |  |  |  | 31.66 | 173.27 |  |
| 2. | CHILD HEALTH |  |  |  |  |  |  |  |  |
| 2.1 | IMNCI |  |  |  |  |  |  |  |  |
| 2.1.1 | Prepare detailed operational plan for IMNCI across districts |  |  |  |  |  |  |  |  |
| 2.1.2 | Implementation of IMNCI activities in districts |  |  |  |  |  |  |  |  |
| 2.1.3 | Monitor progress against plan; follow up with training, procurement, etc |  |  |  |  |  |  |  |  |
| 2.1.4 | Pre-service IMNCI activities in medical colleges, nursing colleges, and ANMTCs |  |  |  |  |  |  |  |  |
| 2.2 | Facility Based Newborn Care/FBNC (SNCU, NBSU, NBCC) |  |  |  |  |  |  |  |  |
| 2.2.1 | Prepare detailed operational plan for FBNC across districts (including training, BCC/IEC, drugs and supplies, etc.; cost of plan meeting should be kept). Operational cost of SNCU | 1 | No |  | 1 | 1000000 |  | 10.00 |  |
|  | Operatioonal cost of NBCC ( 23 existing and 21 newly proposed) | 23 | No | 10 | 44 | 20000 | 2.00 | 8.80 | included as per comment |
|  | Operatioonal cost of NBSU ( 2 existing and 5 newly proposed) | 2 | No | 1 | 5 | 175000 | 1.75 | 8.75 | included as per comment |
| 2.2.2 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |  |
| 2.3 | Home Based Newborn Care/HBNC |  |  |  |  |  |  |  |  |
| 2.3.1 | Prepare and disseminate guidelines for HBNC. |  |  |  |  |  |  |  |  |
| 2.3.2 | Prepare detailed operational plan for HBNC across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |  |
| 2.3.4 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |  |
| 2.4 | Infant and Young Child Feeding/IYCF |  |  |  |  |  |  |  |  |
| 2.4.1 | Prepare and disseminate guidelines for IYCF. |  |  |  |  |  |  |  |  |
| 2.4.2 | Prepare detailed operational plan for IYCF across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |  |
| 2.4.3 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  | 20000 / qtr | 0.20 | 0.80 |  |
| 2.5 | Care of Sick Children and Severe Malnutrition at facilities (e.g. NRCs, CDNCs etc.) |  |  |  |  |  |  |  |  |
| 2.5.1. | Prepare and disseminate guidelines. |  |  |  |  |  |  |  |  |
| 2.5.2 | Prepare detailed operational plan for care of sick children and severe malnutrition at FRUs, across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |  |
| 2.5.3 | Implementation of activities in districts. (JSSK)- Treatment cost of Sick new born |  | No | 180 | 1800 | 200 | 0.36 | 3.60 | Budget as per comment on JSSK |
| 2.5.4 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |  |
| 2.6 | Management of Diarrhoea, ARI and Micronutrient malnutrition |  |  |  |  |  |  |  |  |
| 2.7 | Other strategies/activities (please specify) |  |  |  |  |  |  |  |  |
| 2.8 | Infant Death Audit |  |  |  |  |  |  |  | Budget under MH |
| 2.9 | Incentive to ASHA under child health |  | No | 920 | 11500 | 250 | 2.30 | 28.75 |  |
|  | Sub-total Child Health |  |  |  |  |  | 6.61 | 60.70 |  |
| 3 | FAMILY PLANNING |  |  |  |  |  |  |  |  |
| 3.1 | Terminal/Limiting Methods |  |  |  |  |  |  |  |  |
| 3.1.1 | Orientation workshop and dissemination of manuals on FP standards & quality assurance of sterilisation services |  | Batches | 1 | 2 | 50000 | 0.50 | 1.00 |  |
| 3.1.1.1 | Prepare operational plan for provision of sterilisation services at facilities (fixed day) as well as camps , review meetings |  |  |  |  |  |  |  |  |
| 3.1.1.2 | Implementation of sterilisation services by districts(including fixed day services and PP sterilization) |  |  |  |  |  |  |  |  |
| 3.1.2 | Organise female sterilisation camps |  | No | 8 | 15 | 15000 | 1.20 | 2.25 | Target has been considered to be approprite |
| 3.1.3 | Organise NSV camps |  |  |  |  |  |  |  |  |
| 3.1.4 | Compensation for female sterilisation |  | No | 600 | 3400 | 1000 | 6.00 | 34.00 | Budget revised acoording to comment |
| 3.1.5 | Compensation for NSV Acceptance |  | No |  | 10 | 1500 |  | 0.15 |  |
| 3.1.6 | Accreditation of private providers to provide sterilisation services |  | No |  | 1 | 50000 |  | 0.50 | Green wood Hospital, Aizawl |
| 3.2 | Spacing Methods |  |  |  |  |  |  |  |  |
| 3.2.1 | IUD camps |  |  |  |  |  |  |  |  |
| 3.2.2 | Implementation of IUD services by districts (including fixed day services at SHC and PHC) |  |  |  |  |  |  |  |  |
| 3.2.2.1 | Provide IUD services at health facilities / compensation |  | No of Clients | 800 | 5000 | 20 | 0.16 | 1.00 |  |
| 3.2.2.2 | PPIUCD services |  | No of Clients | 450 | 3000 | 50 at each visit i.e 150 for 3 visits | 0.68 | 4.50 | Incentive to ASHA for retention of IUD |
| 3.2.3 | Accreditation of private providers to provide IUD insertion services |  |  |  |  |  |  |  |  |
| 3.2.4 | Social Marketing of contraceptives (includng delivery of contraceptive by ASHA at door step) |  |  |  |  |  |  |  |  |
| 3.2.5 | Contraceptive Update seminars |  |  |  |  |  |  |  |  |
| 3.3 | POL for Family Planning/ Others (including additional mobilty support to surgeon's team if req) |  | Teams | 4 | 10 | 20000 |  | 2.00 | Plse see text |
| 3.4 | Repairs of Laparoscopes |  |  |  |  |  |  |  |  |
| 3.5 | Other strategies/activities (please specify): Review meeting on family planning including QAC meeting at State and district level |  | No of State & Dists | 3 | 10 | 10000 | 1.20 | 4.00 | Quarterly meeting at State & Dists |
| 3.5.1 | Monitor progress, quality and utilisation of services (both terminal and spacing methods) including complications / deaths / failure cases. Note: cost of insurance / failure and death compensation NOT to be booked here |  | No of facility | 70 | 150 | 6000 | 4.20 | 9.00 |  |
| 3.5.2 | Performance reward if any |  |  |  |  |  |  | 7.84 | For Physical target, Plse ref the text |
| 3.5.3 | World Population Day’ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities |  |  |  |  |  |  | 9.00 | State, District, CHC & PHC level |
|  | Sub-total Family Planning (excluding Sterilisation Compensation and NSV Camps) |  |  |  |  |  | 7.78 | 40.09 |  |
|  | Sub-total Sterilisation Compensation and NSV Camps |  |  |  |  |  | 6.16 | 35.15 |  |
| 4 | ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH / ARSH |  |  |  |  |  |  |  |  |
| 4.1 | Adolescent services at health facilities |  |  |  |  |  |  |  |  |
| 4.1.1 | Disseminate ARSH guidelines.( Printing of guidelines) |  | Copy |  | 1500 | 200 |  | 3.00 |  |
| 4.1.2 | Establishment of new clinics at DH/SDH level |  | No | 2 | 5 | 100000 | 2.00 | 5.00 |  |
| 4.1.3 | Establishment of new clinics at CHC/PHC level |  | No | 10 | 29 | 100000 | 10.00 | 29.00 |  |
| 4.1.3.1 | Operating expenses for existing clinics |  | No | 1 | 5 | 4000 | 0.04 | 0.20 |  |
| 4.1.4. | Outreach activities including peer educators ( Youth Festival & Health Melas) |  | N0 | 3 | 9 | 300000 | 9.00 | 27.00 |  |
| 4.2 | School health programme |  |  |  |  |  |  |  |  |
| 4.2.1 | Prepare and disseminate guidelines for School Health Programme. Printing of Training Manual |  | Copy |  | 2000 | 150 |  | 3.00 |  |
|  | Printing referral card cum cumulative health card |  | copy |  | 20000 | 10 |  | 2.00 |  |
| 4.2.2 | Prepare detailed operational plan for School Health Programme across districts (cost of plan meeting should be kept) / Question Box activities |  |  |  |  |  |  |  |  |
| 4.2.3 | Implementation of School Health Programme by districts. (mobility of ANM, MO) |  |  |  |  |  |  | 4.90 |  |
| 4.2.4 | Monitor progress and quality of services. (School Health) |  | No |  | 5 | 57000/qtr |  | 2.28 |  |
| 4.3 | Other strategies/activities (please specify) Details of the Menstrual Hygiene project to be provided and budgeted under this head(referral support) |  |  |  | 2220 | 100 |  | 2.22 |  |
|  | Sub-total ARSH |  |  |  |  |  | 21.04 | 78.60 |  |
| 5 | URBAN RCH (focus on Urban slums) |  |  |  |  |  |  |  |  |
| 5.1 | Urban RCH Services |  |  |  |  |  |  |  |  |
| 5.1.1 | Identification of urban areas / mapping of urban slums |  |  |  |  |  |  |  |  |
| 5.1.2. | Prepare operational plan for urban RCH |  |  |  |  |  |  |  |  |
| 5.1.3 | Implementation of Urban RCH plan/ activities - Building rent, Electricity, Telephone, Water bill etc |  |  |  |  | 300000/qtr |  | 12.00 |  |
| 5.1.3.1 | Recruitment and training of link workers for urban slums |  |  |  |  |  |  |  |  |
| 5.1.3.2 | Strengthening of urban health posts and urban health centres |  |  |  |  |  |  |  |  |
| 5.1.3.3 | Provide RCH services (please specify) |  |  |  |  |  |  |  |  |
| 5.1.4 | Monitor progress, quality and utilisation of services. |  |  |  |  | 10000/ qtr |  | 0.40 |  |
| 5.1.5 | Other Urban RCH strategies/activities (please specify) - Salary of Support Staff |  | No |  | 25 | 6325 |  | 18.98 |  |
|  | Sub-total Urban Health |  |  |  |  |  | 0.00 | 31.38 |  |
| 6. | TRIBAL RCH |  |  |  |  |  |  |  |  |
| 6.1 | Tribal RCH services |  |  |  |  |  |  |  |  |
| 6.1.2 | Prepare operational plan for tribal RCH |  |  |  |  |  |  |  |  |
| 6.1.3 | Implementation of Tribal RCH activities |  |  |  |  |  |  |  |  |
| 6.1.4 | Monitor progress, quality and utilisation of services. |  |  |  |  |  |  |  |  |
| 6.1.5 | Other Tribal RCH strategies/activities (please specify) |  |  |  |  |  |  |  |  |
|  | Sub-total Tribal Health |  |  |  |  |  |  |  |  |
| 7 | PNDT Activities |  |  |  |  |  |  |  |  |
| 7.1 | Support to PNDT cell |  |  |  |  |  |  |  |  |
| 7.1.1 | Operationalise PNDT Cell |  |  |  |  |  |  | 3.50 |  |
| 7.1.2 | Orientation of programme managers and service providers on PC & PNDT Act |  |  |  |  |  |  | 0.50 |  |
| 7.2 | Other PNDT activities (please specify) |  |  |  |  |  |  |  |  |
|  | Sub-total PNDT activities |  |  |  |  |  | 0.00 | 4.00 |  |
| 8 | INFRASTRUCTURE AND HUMAN RESOURCES |  |  |  |  |  |  |  |  |
| 8.1 | Contractual Staff & Services |  |  |  |  |  |  |  |  |
| 8.1.1 | ANMs,supervisory nurses, LHVs |  | No |  | 428 |  |  | 555.66 |  |
|  | Normal Area |  | No |  | 57 | 9450 |  | 64.64 |  |
|  | Difficult Area |  | No |  | 122 | 10395 |  | 152.18 |  |
|  | Very difficult Area |  | No | 249 |  | 11340 | 338.84 |  |  |
| 8.1.2 | Laboratory Technicians, MPWs |  |  |  |  |  |  |  |  |
|  | Laboratory Technicians (Diploma) |  | No |  | 36 |  |  | 43.85 |  |
|  | Normal Area |  | No |  | 13 | 9600 |  | 14.98 |  |
|  | Difficult Area |  | No |  | 13 | 10200 |  | 15.91 |  |
|  | Very difficult Area |  | No | 10 |  | 10800 | 12.96 |  |  |
|  | Laboratory Technicians (Certificate) |  | No |  | 18 |  |  | 17.78 |  |
|  | Normal Area |  | No |  | 5 | 7500 |  | 4.50 |  |
|  | Difficult Area |  | No |  | 5 | 8125 |  | 4.88 |  |
|  | Very difficult Area |  | No | 8 |  | 8750 | 8.40 |  |  |
| A.8.1.3 | Specialists (Anaesthetists, Paediatricians, Ob/Gyn, Surgeons, Physicians, Dental Surgeons, Radiologist, Sonologist, Pathologist, Specialist for CHC ) |  | No |  | 9 |  |  | 50.00 |  |
|  | Normal Area |  | No |  | 6 | 44275 |  | 31.88 |  |
|  | Difficult Area |  | No |  | 2 | 48703 |  | 11.69 |  |
|  | Very difficult Area |  | No | 1 |  | 53573 | 6.43 |  |  |
|  | Dental Surgeons |  | No |  | 40 |  |  | 162.69 |  |
|  | Normal Area |  | No |  | 18 | 30250 |  | 65.34 |  |
|  | Difficult Area |  | No |  | 14 | 34375 |  | 57.75 |  |
|  | Very difficult Area |  | No | 8 |  | 41250 | 39.60 |  |  |
| A.8.1.4 | PHNs at CHC, PHC level / Staff Nurses |  | No |  | 237 |  |  | 416.55 |  |
|  | Normal Area |  | No |  | 77 | 12500 |  | 115.50 |  |
|  | Difficult Area |  | No |  | 73 | 15000 |  | 131.40 |  |
|  | Very difficult Area |  | No | 87 |  | 16250 | 169.65 |  |  |
| A.8.1.5 | Medical Officers at CHCs / PHCs |  | No |  | 55 |  |  | 229.35 |  |
|  | Normal Area |  | No |  | 20 | 30250 |  | 72.60 |  |
|  | Difficult Area |  | No |  | 20 | 34375 |  | 82.50 |  |
|  | Very difficult Area |  | No | 15 |  | 41250 | 74.25 |  |  |
| A.8.1.6 | Additional Allowances/ Incentives to M.O.s of PHCs and CHCs |  |  |  |  |  |  |  |  |
| A.8.1.7 | Others - Computer Assistants/ BCC Co-ordinator etc |  |  |  |  |  |  |  |  |
|  | Pharmacist |  | No |  | 28 |  |  | 34.88 |  |
|  | Normal Area |  | No |  | 18 | 10000 |  | 21.60 |  |
|  | Difficult Area |  | No |  | 3 | 10625 |  | 3.83 |  |
|  | Very difficult Area |  | No | 7 |  | 11250 | 9.45 |  |  |
|  | X-Ray Technician |  | No |  | 18 |  |  | 23.03 |  |
|  | Normal Area |  | No |  | 5 | 10000 |  | 6.00 |  |
|  | Difficult Area |  | No |  | 7 | 10625 |  | 8.93 |  |
|  | Very difficult Area |  | No | 6 |  | 11250 | 8.10 |  |  |
|  | BEE |  | No |  | 9 |  |  | 10.62 |  |
|  | Normal Area |  | No |  | 1 | 9000 |  | 1.08 |  |
|  | Difficult Area |  | No |  | 6 | 9750 |  | 7.02 |  |
|  | Very difficult Area |  | No | 2 |  | 10500 | 2.52 |  |  |
|  | Family Planning Counsellor |  | No |  | 2 | 12500 |  | 3.00 |  |
| A.8.1.8 | Incentive/ Awards etc. to SN, ANMs etc. |  |  |  |  |  |  |  |  |
| A.8.1.9 | Human Resources Development (Other than above) |  |  |  |  |  |  |  |  |
| A.8.1.10 | Other Incentives Schemes (Pl.Specify) |  |  |  |  |  |  |  |  |
| A.8.1.11 | Other activities (pl. specify) |  |  |  |  |  |  |  |  |
|  | Sub-total Infrastructure and Human Resources |  |  |  | 880 |  | 670 | 1547.39 |  |
| 9 | TRAINING (for each type of training, please provide the batch size in the rows below as applicable; in the physical target columns, pls put in the number of persons to be trained) |  |  |  |  |  |  |  |  |
| 9.1 | Strengthening of Training Institutions (SIHFW, ANMTCs, etc.) |  |  |  |  |  |  |  |  |
| 9.1.1 | Carry out repairs/ renovations of the training institutions |  |  |  |  |  |  |  |  |
| 9.1.2 | Provide equipment and training aids to the training institutions |  |  |  |  |  |  |  |  |
| 9.1.3 | Developing systems for monitoring & evaluations of training programmes. |  |  |  |  |  |  | 5.00 |  |
| 9.1.4 | Other activities (pl. specify) |  |  |  |  |  |  |  |  |
| 9.2 | Development of training packages |  |  |  |  |  |  |  |  |
|  | Development/ translation and duplication of training materials |  |  |  |  |  | 5.00 | 20.00 |  |
|  | Other activities (pl. specify) |  |  |  |  |  |  |  |  |
| 9.3 | Maternal Health Training |  |  |  |  |  |  |  |  |
| 9.3.1 | Skilled Attendance at Birth / SBA |  |  |  |  |  |  |  |  |
| 9.3.1.1 | Setting up of SBA Training Centres |  |  |  |  |  |  |  |  |
| 9.3.1.2 | TOT for SBA |  |  |  |  |  |  |  |  |
| 9.3.1.3 | Training of Medical Officers in Management of Common Obstetric Complications (BEmOC) |  | Batch | 3 | 10 | 39075 | 1.17 | 3.91 |  |
| 9.3.1.4 | Training of Staff Nurses in SBA |  | No | 15 | 68 |  | 4.13 | 18.74 | Unit of measure indicated in No due inconsistent batch size. |
| 9.3.1.5 | Training of ANMs / LHVs in SBA |  | No |  | 32 |  |  | 10.02 |  |
| 9.3.2 | EmOC Training |  |  |  |  |  |  |  |  |
| 9.3.2.1 | Setting up of EmOC Training Centres |  |  |  |  |  |  |  |  |
| 9.3.2.2 | TOT for EmOC |  |  |  |  |  |  |  |  |
| 9.3.2.3 | Training of Medical Officers in EmOC |  |  |  |  |  |  |  |  |
| 9.3.3 | Life saving Anaesthesia skills training |  |  |  |  |  |  |  |  |
| 9.3.3.1 | Setting up of Life saving Anaesthesia skills Training Centres |  |  |  |  |  |  |  |  |
| 9.3.3.2 | TOT for Anaesthesia skills training |  |  |  |  |  |  |  |  |
| 9.3.3.3 | Training of Medical Officers in life saving Anaesthesia skills |  |  |  |  |  |  |  |  |
| 9.3.4 | Safe abortion services training (including MVA/ EVA and Medical abortion) |  |  |  |  |  |  |  |  |
| 9.3.4.1 | TOT on safe abortion services |  |  |  |  |  |  |  |  |
| 9.3.4.2 | Training of Medical Officers in safe abortion (MTP) |  | Batch | 2 | 5 | 46000 | 0.92 | 2.30 |  |
| 9.3.5 | RTI / STI Training |  |  |  |  |  |  |  |  |
| 9.3.5.1 | TOT for RTI/STI training |  |  |  |  |  |  |  |  |
| 9.3.5.2 | Training of laboratory technicians in RTI/STI |  |  |  |  |  |  |  |  |
| 9.3.5.3 | Training of Medical Officers in RTI/STI |  | Batch |  | 1 | 138300 |  | 1.38 |  |
| 9.3.5.4 | Training of Staff Nurses in RTI/STI |  | Batch | 1 | 3 | 50600 | 0.51 | 1.52 | Unit of measure indicated in No due to inconsistent batch size |
| 9.3.5.5 | Training of ANMs / LHVs in RTI/STI |  | Batch | 1 | 3 | 50600 | 0.51 | 1.52 |  |
| 9.3.6 | BEmOC training |  |  |  |  |  |  |  |  |
| 9.3.7 | Other maternal health training (please specify) |  |  |  |  |  |  |  |  |
| 9.4 | IMEP Training |  |  |  |  |  |  |  |  |
| 9.4.1 | TOT on IMEP |  |  |  |  |  |  |  |  |
| 9.4.2 | IMEP training for state and district programme managers |  |  |  |  |  |  |  |  |
| 9.4.3 | IMEP training for medical officers |  |  |  |  |  |  |  |  |
| 9.4.4 | IMEP training for staff nurses |  | Batch | 2 | 10 | 48600 | 0.97 | 4.86 |  |
| 9.5 | Child Health Training |  |  |  |  |  |  |  |  |
| 9.5.1 | IMNCI & F-IMNCI Training (pre-service and in-service) |  |  |  |  |  |  |  |  |
| 9.5.1.1 | TOT on IMNCI (pre-service and in-service) |  |  |  |  |  |  |  |  |
| 9.5.1.2 | IMNCI Training for ANMs / LHVs |  | Batch |  | 4 | 218300 |  | 8.73 |  |
| 9.5.1.3 | IMNCI Training for Anganwadi Workers |  |  |  |  |  |  |  |  |
| 9.5.2 | F-IMNCI Training |  |  |  |  |  |  |  |  |
| 9.5.2.1 | TOT on F-IMNCI |  |  |  |  |  |  |  |  |
| 9.5.2.2 | F-IMNCI Training for Medical Officers |  |  |  |  |  |  |  |  |
| 9.5.2.3 | F-IMNCI Training for Staff Nurses |  | Batch | 2 | 12 | 123200 | 2.46 | 14.78 |  |
| 9.5.3 | Home Based Newborn Care / HBNC |  |  |  |  |  |  |  |  |
| 9.5.3.1 | TOT on HBNC |  |  |  |  |  |  |  |  |
| 9.5.3.2 | Training on HBNC for ASHA |  |  |  |  |  |  |  |  |
| 9.5.4 | Care of sick children and severe malnutrition at FRUs |  |  |  |  |  |  |  |  |
| 9.5.4.1 | TOT on Care of sick children and severe malnutrition |  |  |  |  |  |  |  |  |
| 9.5.4.2 | Training on Care of sick children and severe malnutrition for Medical Officers |  |  |  |  |  |  |  |  |
| 9.5.5 | Other child health training (please specify) |  |  |  |  |  |  |  |  |
| 9.5.5.1 | NSSK Training |  |  |  |  |  |  |  |  |
| 9.5.5.1.1 | TOT for NSSK |  |  |  |  |  |  |  |  |
| 9.5.5.1.2 | NSSK Training for Medical Officers |  |  |  |  |  |  |  |  |
| 9.5.5.1.3 | NSSK Training for SNs |  | Btach | 2 | 10 | 61000 | 1.20 | 6.10 |  |
| 9.5.5.1.4 | NSSK Training for ANMs |  | Batch | 3 | 5 | 61000 | 1.83 | 3.05 |  |
| 9.5.5.2 | Other Child Health training |  |  |  |  |  |  |  |  |
| 9.6 | Family Planning Training |  |  |  |  |  |  |  |  |
| 9.6.1 | Laparoscopic Sterilisation Training |  |  |  |  |  |  |  |  |
| 9.6.1.1 | TOT on laparoscopic sterilisation |  |  |  |  |  |  |  |  |
| 9.6.1.2 | Laparoscopic sterilisation training for doctors (teams of doctor, SN and OT assistant) |  | Team |  | 1 | 43550 |  | 0.44 |  |
| 9.6.2 | Minilap Training |  |  |  |  |  |  |  |  |
| 9.6.2.1 | TOT on Minilap |  |  |  |  |  |  |  |  |
| 9.6.2.2 | Minilap training for medical officers |  | Batch | 2 | 5 | 46000 | 0.92 | 2.30 |  |
| 9.6.3 | Non-Scalpel Vasectomy (NSV) Training |  |  |  |  |  |  |  |  |
| 9.6.3.1 | TOT on NSV |  |  |  |  |  |  |  |  |
| 9.6.3.2 | NSV Training of medical officers |  |  |  |  |  |  |  |  |
| 9.6.4 | IUD Insertion |  |  |  |  |  |  |  |  |
| 9.6.4.1 | TOT for IUD insertion |  |  |  |  |  |  |  |  |
| 9.6.4.2 | Training of Medical officers in IUD insertion |  |  |  |  |  |  |  |  |
| 9.6.4.3 | Training of staff nurses in IUD insertion |  |  |  |  |  |  |  |  |
| 9.6.4.4 | Training of ANMs / LHVs in IUD insertion |  | Batch | 1 | 5 | 37500 | 0.38 | 1.88 |  |
| 9.6.5 | Contraceptive update/ISD Training |  |  |  |  |  |  |  |  |
| 9.6.6 | Other family planning training (please specify) |  |  |  |  |  |  |  |  |
| 9.7 | Adolescent Reproductive and Sexual Health/ARSH Training |  |  |  |  |  |  |  |  |
| 9.7.1 | TOT for ARSH training |  |  |  |  |  |  |  |  |
| 9.7.2 | Orientation training of state and district programme managers |  |  |  |  |  |  |  |  |
| 9.7.3 | ARSH training for medical officers |  |  |  |  |  |  |  |  |
| 9.7.4 | ARSH training for ANMs/LHVs (staff nurse) |  | Batch | 3 | 12 | 104000 | 3.12 | 12.48 |  |
|  | ARSH Training for Councellors |  | Batch |  | 1 | 120750 |  | 1.21 |  |
| 9.7.5 | ARSH training for AWWs |  |  |  |  |  |  |  |  |
| 9.7.6 | Training of Masters Trainers under School Health |  | Batch |  | 1 | 55500 |  | 0.56 |  |
| 9.7.7 | Training of School Teacher under School Health |  | Batch | 8 | 15 | 127450 | 10.20 | 19.12 |  |
| 9.7.8 | Training of ANM/HW under School Health |  | Batch | 3 | 5 | 127450 | 3.82 | 6.37 |  |
| 9.8 | Programme Management Training (e.g. M&E, logistics management, HRD etc.) |  |  |  |  |  |  |  |  |
| 9.8.1 | Training of SPMSU staff (pls add rows to specify type of training) - Accounts Manager |  | No | 10 | 50 | 1280 | 0.13 | 0.64 |  |
| 9.8.2 | Training of DPMSU staff (pls add rows to specify type of training) - |  |  |  |  |  |  |  |  |
| 9.9 | Other training (pl. specify) -PHC/CHC Accounts Clerk Training |  | No | 13 | 66 | 1280 | 0.17 | 0.84 |  |
|  | Accounts training for HWs / ANMs |  | No | 90 | 400 | 1280 | 1.15 | 5.15 |  |
| A.9.10 | Training (Nursing) |  |  | 0 | 0 |  |  |  |  |
| A.9.10.1 | Strengthening of Existing Training Institutions/Nursing School (HR) |  |  |  |  |  |  |  |  |
| A.9.10.2 | New Training Institutions/School (Other strengthening) |  |  |  |  |  |  |  |  |
| A.9.11 | Training (Other Health Personnel's) |  |  | 0 | 0 |  |  |  |  |
| A.9.11.1 | Promotional Trig of health workers females to lady health visitor etc. |  |  |  |  |  |  |  |  |
| A.9.11.2 | Training of AMNs,Staff nurses,AWW,AWS |  |  |  |  |  |  |  |  |
| A.9.11.3 | Other training and capacity building programmes |  |  |  |  |  |  |  |  |
|  | Sub-total Training |  |  |  |  |  | 38.59 | 152.90 |  |
| 10 | PROGRAMME MANAGEMENT |  |  |  |  |  |  |  |  |
| 10.1 | Strengthening of State society/ State Programme Management Support Unit |  |  |  |  |  |  |  |  |
| 10.1.1 | Contractual Staff for SPMSU recruited and in position (Including HR, Management Cost, Mobility Support, Field Visits) |  | No |  | 34 |  |  | 103.33 | Salary RS. 78.33 lacs + Management, Mobility, Field Visit etc @ Rs.5 lacs/qtr i.e Rs.25 lacs |
|  | Contractual Staff Salary for School Health Programme at State |  |  |  |  |  |  | 10.92 |  |
| 10.2 | Strengthening of District society/ District Programme Management Support Unit |  |  |  |  |  |  |  |  |
| 10.2.1 | Contractual Staff for DPMSU recruited and in position (Including HR, Management Cost, Mobility Support, Field Visits) |  | No |  | 52 |  |  | 111.55 | Salary RS.83.55 lacs + Management, Mobility, Field Visit etc for 9 dists @ Rs.7 lacs/qtr i.e Rs.28 lacs |
| A.10.3 | Strengthening of Block PMU (Including HR, Management Cost, Mobility Support, Field Visits) |  | No |  | 66 |  |  | 103.70 | Salary RS. 95.70 lacs + Management, Mobility, Field Visit etc for Block @ Rs.8 lacs/year |
|  | Normal Area |  |  |  | 9 | 11250 |  | 12.15 |  |
|  | Difficult Area |  |  |  | 26 | 11875 |  | 37.05 |  |
|  | Very difficult Area |  |  | 31 |  | 12500 | 46.50 |  |  |
| A.10.4 | Strengthening (Others)-Office expenses etc |  |  |  |  | 200000/ qtr |  | 8.00 |  |
| A.10.5 | Audit Fees |  |  |  |  |  |  | 8.00 |  |
| A.10.6 | Concurrent Audit system |  |  |  |  |  |  | 10.00 |  |
| A.10.7 | Mobility Support, Field Visits to BMO/MO/Others |  |  |  |  |  |  |  |  |
|  | Sub-total Programme Management |  |  |  |  |  | 46.50 | 355.50 |  |
| 11 | VULNERABLE GROUPS |  |  |  |  |  |  |  |  |
| 11.1 | Other vulnerable communities not covered by Urban and Tribal RCH such as salt pan workers, migrants etc. |  |  |  |  |  |  |  |  |
| 11.2 | Services for Vulnerable groups |  |  |  |  |  |  |  |  |
| 11.2.1 | Mapping of vulnerable groups |  |  |  |  |  |  |  |  |
| 11.2.2 | Prepare operational plan for vulnerable groups (including infrastructure and human resources, training, BCC/IEC, equipment, drugs and supplies, etc.; cost of plan meeting should be kept). |  |  |  |  |  |  |  |  |
| 11.3 | Implementation of RCH activities |  |  |  |  |  |  |  |  |
| 11.4 | Other strategies/activities (please specify) |  |  |  |  |  |  |  |  |
|  | Sub-total Vulnerable Groups |  |  |  |  |  |  |  |  |
|  | TOTAL RCH II FLEXIPOOL |  |  |  |  |  | 831.04 | 2611.34 |  |
|  | TOTAL RCH II DEMAND SIDE |  |  |  |  |  | 37.82 | 208.42 |  |
|  | GRAND TOTAL |  |  |  |  |  | 868.86 | 2819.76 |  |

| ALLOCATION OF RCH FLEXIBLE FUNDS TO DISTRICTS 2012-13 (Rs. in lakhs) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Serchhip | Kolasib | Lunglei | Mamit (HF) | Saiha (HF) | Lawngtlai (HF) |
| Budget Head |  |  |  |  |  |  |  |  |  |
| 1 Maternal Health |  |  |  |  |  |  |  |  |  |
| (a) JSY | 21.41 | 50.3 | 22.41 | 10.37 | 12.86 | 21.81 | 10.8 | 12.62 | 10.69 |
| (b) Others | 32.78 | 34.15 | 34.15 | 31.42 | 31.42 | 34.15 | 32.78 | 31.83 | 27.32 |
| Sub total Maternal Health | 54.19 | 84.45 | 56.56 | 41.79 | 44.28 | 55.96 | 43.58 | 44.45 | 38.01 |
| 2 Child Health | 3.01 | 3.32 | 3.62 | 1.81 | 2.71 | 3.62 | 6.03 | 7.54 | 9.04 |
| 3 Family Planning |  |  |  |  |  |  |  |  |  |
| (a) Sterilization and IUD Compensation | 3.61 | 16.36 | 2.16 | 1.8 | 2.16 | 2.74 | 1.8 | 2.64 | 1.88 |
| (b) Others | 4.43 | 7.99 | 4.48 | 2.57 | 2.12 | 4.2 | 1.76 | 1.67 | 1.78 |
| Sub total Family Planning | 8.04 | 24.35 | 6.64 | 4.37 | 4.28 | 6.94 | 3.56 | 4.31 | 3.66 |
| 4 Adolescent Reproductive and Sexual Health | 5.15 | 6.19 | 7.73 | 4.64 | 4.64 | 7.73 | 4.64 | 4.64 | 4.64 |
| 5 Urban RCH | 8.85 | 10.77 |  |  |  | 5.38 |  |  |  |
| 6 Tribal RCH |  |  |  |  |  |  |  |  |  |
| 7 PNDT | 0.15 | 0.15 | 0.15 | 0.08 | 0.08 | 0.15 | 0.08 | 0.08 | 0.08 |
| 8 Infrastructure and Human Resources | 139.57 | 164.09 | 161.05 | 129.12 | 165.34 | 150.31 | 209.36 | 212.58 | 215.97 |
| 9 Training | 0.94 | 1.86 | 10.32 | 3.46 | 8.21 | 14.83 | 3.46 | 3.46 | 3.46 |
| 10 Programme Management | 26.18 | 26.18 | 24.72 | 23.27 | 23.27 | 23.27 | 23.27 | 23.27 | 21.82 |
| Grand Total RCH | 246.08 | 321.36 | 270.79 | 208.54 | 252.81 | 268.19 | 293.98 | 300.33 | 296.68 |