EXECUTIVE SUMMARY

The State of Mizoram highly appreciates the initiatives and activities taken up under the National Rural Health Mission through which the people have access to better Health Care facilities in terms of Infrastructure and better equipped and skilled manpower right at their own villages. During 2011-12, Mizoram was recognized as the ‘Most improved State in Health care among the Small States’ by Times of India Group.

The overall objectives/goals to be achieved in 2012-13 are as follows:

| Main Goals | Current Status | Proposed Goal for 2012-13 |
| --- | --- | --- |
| MMR | 72 (State HMIS 2010-11) | 65 |
| IMR | 37 (SRS 2010) | 35 |
| TFR | 2.9 (NFHS-3) | 2.8 |

The plan for the year 2012-13 is formulated keeping in mind the new guidelines and instructions made by the Government of India. The District plans which were submitted to the State on the 12th December 2011 went a long way in helping to form the current PIP.

The State Program Implementation plan recognizes the need of three most difficult districts in the state, namely Saiha, Lawngtlai and Mamit Districts, which are the districts that contribute most to the IMR, MMR and TFR of the state. New initiatives to address the needs of these districts are reflected in the PIP.

There will be decentralization of power to the Districts, especially in terms of rational deployment of Human resources with minimal interference from the Government who has already expressed their willingness in such a venture.

The main emphasis will be on monitoring and analysis of the implementation of the State Program. For this the State and District Monitoring committee will be made to act as per the guidelines. The State Program Unit will be responsible for the overall monitoring and strict implementation of guidelines received from the Government of India.

The State has 71 delivery points as per norms. The plan is to have at least 1 SBA trained staff and NSSK trained staff at these points and the setting up of Newborn Care Corners up to the PHC level and at least an indigenous Baby Warmer (to be made from RKS funds etc) and neonatal resuscitation kit up to the sub Centre level within 2012-13.

Incentives to the mother for each delivery worth Rs 300 in kind like Baby cloth etc. is proposed to be continued to be given to Mothers who deliver in both Government and Private facilities in certain difficult areas to reduce the labour load at District Hospitals so that 48 hours post delivery stay can be ensured.

JSSK for which the Government order was issued on 15th December 2011 has been stalled in implementation due to non availability of funds. It will be implemented in full swing immediately when fund is received.

More robust monitoring of the Infant and Maternal Death audits to ascertain their accountability and to cover all Infant and Maternal deaths within the prescribed time limits without fail, so that the State plans can be modified according to the needs of each District.

The State aims to reduce the disease burden under all Disease Control Programs. The State is very grateful for the improvement in Human resources and Infrastructure seen since the implementation of NRHM.

BUDGET SUMMARY

| SN | Main Heads | Components | Budget Amount (Rs in Lakh) |
| --- | --- | --- | --- |
| 1 | Human Resources | Contractual Remuneration for ANMs, Nurses, SNs, LHVs | 972.15 |
|  |  | Contractual Remuneration for LTs,MPWs | 61.63 |
|  |  | Contractual Remuneration of Specialists (Anesthetists, | 50.00 |
|  |  | Pediatricians, Ob/Gyn, Surgeons, Physicians, Dental |  |
|  |  | Surgeons, Radiologist, Sonologist, Pathologist, Specialist for CHCs.) |  |
|  |  | Medical Officers at CHCs / PHCs | 229.35 |
|  |  | Contractual Remuneration of PHNs at CHC, PHC level |  |
|  |  | Additional Allowances/ Incentives to M.O.s of PHCs and CHCs |  |
|  |  | Payment to Others - Computer Assistants/ BCC Co-ordinator/ Dental Surgeon/Pharmacist/X-Ray Technicians/BEE/ FP Counsellor etc | 235.04 |
|  |  | Incentive/ Awards etc. to SN, ANMs etc. |  |
|  |  | Human Resources Development (Other than above) |  |
|  |  | Other Incentives Schemes (Please Specify) |  |
|  |  | Strengthening of SHS /SPMU (Including HR, Management Cost, Mobility Support, Field Visits) | 100.93 |
|  |  | Strengthening of DHS/DPMU (Including HR, Management Cost, Mobility Support, Field Visits ) | 111.55 |
|  |  | Strengthening of Block PMU (Including HR, Management Cost, Mobility Support, Field Visits ) | 103.70 |
|  |  | Strengthening (Others) | 8.00 |
|  |  | Other Programme Management Costs (Audit Fees,Concurrent Audit etc.) | 18.00 |
|  |  | Mobility Support, Field Visits to BMO/MO/Others |  |
|  |  | Payment to AYUSH M.O.s |  |
|  |  | Payment to AYUSH Other Staffs |  |

| 2 | Training | Training under Maternal Health | 44.10 |
| --- | --- | --- | --- |
|  |  | Training under Child Health | 32.66 |
|  |  | Training under Family Planning Services | 4.62 |
|  |  | Strengthening Training Institutions |  |
|  |  | Development of training packages & Monitoring | 25.00 |
|  |  | IMEP Trainings | 4.86 |
|  |  | ARSH Training |  |
|  |  | Programme Management Training | 6.63 |
|  |  | Training (Nursing) |  |
|  |  | Training (Other Health Personnel) |  |
|  |  | Training for Cold Chain Handlers/refrigerator mechanics |  |
|  |  | Training of M.O.s /Other Staffs on R.I. |  |
| 3 | Infrastructure | Upgradation of CHCs, PHCs, Dist. Hospitals to IPHS | 1328.44 |
|  |  | Strengthening of District, Sub-divisional Hospitals, CHCs, |  |
|  |  | PHCs |  |
|  |  | New Constructions/ Renovation and Setting up CHCs, PHCs, |  |
|  |  | HSCs, |  |
|  |  | Construction (Others) |  |
|  |  | Minor civil works for operationalisation of FRUs |  |
|  |  | Minor civil works for operationalisation of 24 hour services |  |
|  |  | at PHCs |  |
|  |  | Civil Work under RNTCP |  |
|  |  | Other Civil Works |  |
| 4 | Procurement | Procurement of Drugs & Supplies | 300.00 |
|  |  | Procurement of Equipment | 501.15 |
|  |  | Procurement of Others |  |
| 5 | IEC/BCC | Development of State BCC/IEC strategy | 449.75 |
|  |  | Implementation of BCC/IEC strategy |  |
|  |  | Health Mela |  |
|  |  | Creating awareness on declining sex ratio issue |  |
|  |  | Other activities |  |

| 6 | Untied funds | Untied funds for,VHSC, SC CHC,PHC | 137.50 |
| --- | --- | --- | --- |
|  |  | Annual Maintenance Grants for CHCs, PHCs | 74.50 |
|  |  | Panchayati Raj Initiatives | 94.83 |
| 7 | ASHA | ASHA Payments under NRHM Additionalities | 109.56 |
|  |  | Selection & Training of ASHA |  |
|  |  | Procurement of ASHA Drug Kit |  |
|  |  | Incentive to ASHAs under JSY | 62.21 |
|  |  | Incentive under Family Planning Services |  |
|  |  | Incentive under Child Health | 28.75 |
|  |  | Incentive to ASHA's for motivating families for Sanitary |  |
|  |  | Toilets/Other Incentives |  |
|  |  | Awards to ASHA's/Link workers |  |
|  |  | ASHA Incentive under Immunisation |  |
|  |  | ASHA Incentive under NLEP |  |
|  |  | ASHA Incentive under NVBDCP |  |
|  |  | ASHA Incentive under NBCP |  |
|  |  | ASHA Incentive under RNTCP |  |
| 8 | RKS | Corpus grants to RKS | 110.00 |
| 9 | JSY | Home Deliveries | 12.88 |
|  |  | Institutional Deliveries | 98.19 |
| 10 | Sterlisation | Compensation for Male sterlisation | 0.15 |
|  |  | Compensation for Female sterlisation | 36.70 |
|  |  | NSV Camps |  |
|  |  | Female Sterlisation Camps | 2.25 |
|  |  | IUD Camps |  |
|  |  | Social Marketing of contraceptives |  |
|  |  | Repairs of Laparoscopes |  |
|  |  | Other Expenses | 39.32 |
| 11 | Referral Transport | Referral Transport (EMRI) | 658.88 |
| 12 | JSSK under MH | Total requirement of JSSK | 500.55 |
|  | Other Maternal Health activities | RCH Camps, Monitoring etc | 15.28 |

|  | JSSK under Child Health | Total requirement of JSSK | 23.50 |
| --- | --- | --- | --- |
|  | Other Child Health activities | Operationalization of SNCU, Monitoring etc | 10.80 |
|  | Other Components (please list) |  |  |
| 13 | Other RCH Activities | ARSH | 70.00 |
|  |  | Urban RCH | 31.38 |
|  |  | PNDT | 4.00 |
| 14 | Vulnerable Group | Tribal RCH |  |
|  |  | Vulnerable Groups |  |
| 15 | Other Mission activities | Research Studies, |  |
|  |  | New Initiatives | 60.40 |
|  |  | Support to other programmes | 163.50 |
|  |  | District Health Action Plan | 50 |
|  |  | Mainstreaming of AYUSH | 178.03 |
|  |  | MMU | 203.36 |
|  |  | SHSRC |  |
|  |  | School Health Programme | 92.33 |
|  |  | Health Insurance | 128.89 |
|  |  | External evaluation of infrastructure and programme |  |
|  |  | Planning , Implementation, Monitoring |  |
| 16 | PPP/NGO | NGO activities, PPP under NRHM Additionalities | 107.98 |
|  |  | Other NDCPs (RNTCP, NPCB etc) |  |
| 17 | Operational Cost (NDCPs) | Mobility, Review Meeting ,field visits, formats & reports, Communication etc for NDCPs | IDSP – 203.00 NLEP – 112.84 RNTCP – 413.28 NVBDCP – 1445.42 NPCB – 474.60 NIDDCP – 46.00 |
|  |  | Lab consumables, AMC etc for NDCPs |  |
| 18 | Financial aid/grant to Institutions (NDCPs) | Financial Support to Medical colleges |  |
|  |  | Financial Support to Referral Institutes |  |
|  |  | Financial Support to Sentinel sites |  |
| 19 | Other Components (please list) | HMIS | 197.37 |
| 20 |  | National Programme for prevention and control of Floursis | 0.40 |
| 21 |  | Immunisation | 159.47 |
|  |  | Direction & Admn. (Treasury Route) |  |
|  | TOTAL |  | 10784.26 |

Programee/Scheme wise summary

| Sl.No | Scheme/Programme | Proposed Amount (in crore) |
| --- | --- | --- |
| 1 | RCH Flexible Pool | 29.44 |
| 2 | NRHM Mission Flexible Pool | 48.54 |
| 3 | Immunisation and PPI Operation Cost | 1.59 |
| 4 | NIDDCP | 0.46 |
| 5 | IDSP | 2.03 |
| 6 | NVBDCP | 14.45 |
| 7 | NLEP | 1.13 |
| 8 | NPCB | 4.75 |
| 9 | RNTCP | 4.13 |
| 10 | National Programme for prevention and control of Floursis | 0.40 |
| 11 | Direction & Admn. (Treasury Route) |  |
| 12 | School Health | 0.92 |
|  | TOTAL (excluding Direction & Admn) | 107.84 |

CHAPTER-1: STATE SPECIPIC TARGETS FOR NEXT FIVE YEARS

A.  Outcome Indicators

| Indicators | Current status as on latest available data | Cumulative Target for next five year | 2012- 13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Maternal Mortality Ratio (MMR) | 68.82 ( HMIS 2011-12) | 35 | 65 | 60 | 55 | 45 | 35 |
| Infant Mortality Rate (IMR) | 37 (SRS 2010) | 18 | 35 | 32 | 25 | 20 | 18 |
| Total Fertility Rate (TFR) | 2.9 (NFHS-3) | 2.1 | 2.8 | 2.7 | 2.4 | 2.2 | 2.1 |
| Malaria Mortality Reduction Rate | 30 deaths (75%) | 5 | 22 | 16 | 11 | 8 | 5 |
| Kala Azar Mortality Reduction Rate | - | - | - | - | - | - | - |
| Dengue Mortality Reduction Rate | - | - | - | - | - | - | - |
| Cataract operations | 1200 | Yearly/Annual target was set by GOI, MOH&FW |  |  |  |  |  |
| Leprosy Prevalence Rate | 0.02 | 0.00 | 0.02 | 0.01 | 0.01 | 0.00 | 0.00 |
| Tuberculosis Cure Rate | 85% | 85% | 85% | 85% | 85% | 85% | 85% |

B.  Output Indicators

|  | Activity / Measurable indicator | Current status as on latest availablee data | Cumulative Targets for the 2nd Phase of NRHM (2012-17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012- 13 | 2013-14 | 2014-15 | 2015- 16 | 2016-17 |
| A | Maternal Health |  |  |  |  |  |  |
| 1 | Institutional Deliveries (%) | 83 | 85 | 87 | 90 | 92 | 95 |
| 2 | 24x7 Facilities (Sub-District/ 24*7 PHC) | 41 | 41 | 42 | 43 | 44 | 45 |
| 3 | Functional First Referral Units | 4 | 4 | 5 | 6 | 7 | 8 |
| B | Child health |  |  |  |  |  |  |
| 4 | Sick New Born Care Units | 1 | 1 | 1 | 1 | 2 | 2 |
| 5 | New Born Care Corners | 23 | 17 | 10 | 10 | 10 | - |
| 6 | Stabilization Units in FRUs | 2 | 5 | 3 | 3 | 3 | 3 |
| 7 | Full Immunization (%) | 60 | 90 | 91 | 92 | 93 | 95 |
| C | Population Stabilization |  |  |  |  |  |  |
| 8 | Male Sterilization | 0 | 10 | 12 | 13 | 14 | 15 |
| 9 | Female Sterilization | 1445 | 3400 | 3420 | 3450 | 3460 | 3500 |
| 10 | No. of IUD Insertions | 2090 | 5000 | 5100 | 5200 | 5300 | 5400 |
| D | Disease Control |  |  |  |  |  |  |
| 11 | Annualized New Smear Positive Detection Rate of TB (%) | 70 | 70 | 75 | 80 | 85 | 90 |
| 12 | Success Rate of New Smear Positive Treatment initiated on DOTS (%) | 85 | 86 | 87 | 88 | 89 | 90 |
| 13 | ABER for malaria (%) | 16.61 | 18.00 | 19.50 | 21.00 | 22.50 | 25.50 |
| 14 | API for malaria (per 1000 population) | 8.19 | 5.00 | 4.00 | 3.00 | 2.00 | 1.00 |

|  | Activity / Measurable indicator | Current status as on latest available data | Cumulative Targets for the 2nd Phase of NRHM (2012- 17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 15 | Annual New Case Detection Rate for Leprosy (per 1,00,000 population) |  |  |  |  |  |  |
| 16 | Cataract Surgeries performed | 1500 (35.5%) | 50% | 60% | 65% | 70% | 80% |
| E | Training |  |  |  |  |  |  |
| 19 | Doctors trained on EmOC | 10 | 1 | 1 | 2 | 2 | 2 |
| 20 | Doctors trained on LSAS | 10 | 1 | 1 | 2 | 2 | 2 |
| 21 | Doctors trained in NSV/ Conventional vasectomy |  | 1 | 1 | 1 | 1 | 1 |
| 22 | Doctors trained in Abdominal Tubectomy (Minilap) | 81 | 10 | 10 | 10 | 10 | 10 |
| 23 | Doctors trained in laparoscopic Tubectomy | 4 teams | 1 | 1 | 1 | 1 | 1 |
| 24 | Personnel trained in IMNCI | MO-127 ANM-775 | 120 | 120 | 120 | 120 | 120 |
| F | Community Processes |  |  |  |  |  |  |
| 25 | Functional VHSCs | 815 | 815 | 815 | 815 | 815 | 815 |
| 26 | ASHAs with Drug kits | 987 | 987 | 987 | 987 | 987 | 987 |
| 27 | ASHAs trained in 6th and 7th modules | 987 | 987 | 987 | 987 | 987 | 987 |
| G | Improved Management |  |  |  |  |  |  |
| 28 | Evaluation and Assessment of NRHM Activities | 9 | 9 | 9 | 9 | 9 | 9 |
| 29 | Cold Chain Management (number of functional ILR points) |  |  |  |  |  |  |  |  |  |  |
| H | Infrastructure |  |  |  |  |  |  |
| 30 | Construction of sub-centre buildings | 370 |  |  |  |  |  |
| 31 | Construction of PHC buildings | 57 |  |  |  |  |  |
| 32 | Construction of CHC buildings | 12 | 0 | 0 | 0 | 0 | 0 |
| 33 | Construction of District Hospital buildings | 8 | 0 | 0 | 0 | 0 | 0 |
| 34 | Construction of Other Hospital buildings | 0 | 0 | 0 | 0 | 0 | 0 |
| I | MMU and Referral Transport |  |  |  |  |  |  |
| 35 | No. Of Functional Mobile Medical Units | 9 | 9 | 9 | 9 | 9 | 9 |
| 36 | No. Of Emergency and Referral Transport vehicles | 0 | 12 | 12 | 12 | 12 | 12 |
| J | Operationalisation of MCTS |  |  |  |  |  |  |
| 37 | % of registration of pregnant women in MCTS | 76.6 | 80 | 82 | 85 | 90 | 95 |
| 38 | % of registration of children in MCTS | 56.4 | 70 | 78 | 85 | 90 | 95 |
| 39 | % of facilities (SC, PHC, CHC, DH & others) uploading data | NA | NA | NA | NA | NA | NA |
| 40 | % of facilities having internet connectivity | 5 | 10 | 15 | NA | NA | NA |
| 41 | % of data validated at State level | 5 | 10 | 15 | NA | NA | NA |
| K | Operationalisation of HMIS |  |  |  |  |  |  |
| 42 | % of facilities (SC, PHC, CHC, DH & others) uploading data | 5 | 10 | 15 | NA | NA | NA |
| 43 | % of districts uploading committing HMIS data within a week of reporting month/quarter | 5 | 10 | 15 | NA | NA | NA |

|  | Activity / Measurable indicator | Current status as on latest available data | Cumulative Targets for the 2nd Phase of NRHM (2012- 17) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Other Indicators |  |  |  |  |  |  |
| 44 | Collocation of AYUSH at health facilities | 8 DH | 9 CHC | 20 PHC | 15 PHC | 12 PHC | 10 PHC |

| L | Human Resources |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| L. 1 | Category | Number of Sanctioned post |  |  | Number of vacant post against sanctioned |  |  | Target for Filling up of vacant posts |  |  |  |  |  |
|  |  | R | C | Total |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | R | C | Total | 2012-13 |  |  | 2013-14 |  |  |
|  |  |  |  |  |  |  |  | R | C | Total | R | C | Total |
| 45 | Gynecologists | 7 | 2 | 9 | 0 | 2 | 2 |  |  |  |  |  |  |
| 46 | Pediatricians | 6 | 2 | 8 | 0 | 1 | 1 |  |  |  |  |  |  |
| 47 | Anesthetists | 3 | 2 | 5 | 0 | 1 | 1 |  |  |  |  |  |  |
| 48 | Other Specialists | 29 | 2 | 31 | 0 | 0 | 0 |  |  |  |  |  |  |
| 48 | Doctors | 152 | 55 | 207 | 0 | 15 | 15 |  |  |  |  |  |  |
| 49 | Staff Nurses | 402 | 231 | 633 | 6 | 0 | 6 |  |  |  |  |  |  |
| 50 | LHV | 85 | NA | 85 | 12 | NA | 12 |  |  |  |  |  |  |
| 51 | ANM | 241 | 295 | 536 | 64 | 9 | 73 |  |  |  |  |  |  |
| 45 | MPW | 263 | NA | 124 | 387 | 107 | - |  |  |  |  |  |  |
| 46 | Laboratory Technicians (D ) | 67 | 36 | 103 | 25 | 4 | 29 |  |  |  |  |  |  |
|  | Laboratory Technicians ( C ) | NA | 18 | 18 | NA | 8 | 8 |  |  |  |  |  |  |
| 47 | Pharmacists | 93 | 18 | 111 | 9 | 8 | 17 |  |  |  |  |  |  |
| 48 | Others:- Dental Surgeons | 28 | 40 | 68 | 0 | 18 | 18 |  |  |  |  |  |  |
|  | X-ray Tech | 44 | 18 | 62 | 7 | 3 | 10 |  |  |  |  |  |  |
|  | FP Counsellor | NA | 2 | 2 | NA | 0 | 0 |  |  |  |  |  |  |
|  | BEE | 14 | 9 | 23 | 0 | 0 | 0 |  |  |  |  |  |  |

| L. 2 | Category | New post Creation (as per IPHS) |  |  |  |  |  | Filling up of vacant posts |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012-13 |  |  | 2013-14 |  |  | 2012-13 |  |  | 2013-14 |  |  | 2014-15 |  |  |
|  |  | R | C | Total | R | C | Total | R | C | Total | R | C | Total | R | C | Total |
| 49 | Gynecologists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 50 | Pediatricians |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 51 | Anesthetists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 52 | Other Specialists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 53 | Doctors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 54 | Staff Nurses | 38 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 55 | LHV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 56 | ANM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 | MPW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 58 | Laboratory Technicians |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 59 | Pharmacists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 60 | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Information on Programme Management Units |  |  |  |  |
| --- | --- | --- | --- | --- |
| Level | No. of Regular Staff | No. of contractual Staff in important positions like Programme managers and Consultants who have been employed for their technical expertise | No. of contractual support staff such as programme assistants/ DEOs/ typists/ peons | Total Number of Staff in SPMU |
| SPMU | 8 | 5 | 18 | 31 |
| DPMU | 2 | 9 | 46 | 57 |
| BPMU |  |  | 66 | 66 |
| Total | 10 | 14 | 130 | 154 |

| CHAPTER 2: OUTCOME ANALYSIS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTIVITY* | Financial |  |  |  | Physical |  |  |  |
|  | 2010-11 |  | 2011-12 |  | 2010-11 |  |  |  |
|  | Amount Approved | Exp | Amount Approved | Exp | Expected Output | Achievements | Expected Output | Achievements |
| RCH Flexipool |  |  |  |  |  |  |  |  |
| Maternal Health | 21.48 | 13.27 | 28.48 | 6.55 |  |  |  |  |
| Child Health | 6.80 | 6.03 | 17.93 |  |  |  |  |  |
| Family Planning | 5.50 | 4.54 | 14.55 | 4.50 |  |  |  |  |
| ARSH | 12.60 | 6.58 | 63.28 |  |  |  |  |  |
| Urban RCH | 31.00 | 17.84 | 31.32 | 12.28 |  |  |  |  |
| Tribal RCH | - | - | - | - |  |  |  |  |
| PNDT & Sex Ratio | 1.40 | 1.40 | 2.40 | 1.20 |  |  |  |  |
| Infrastructure & HR | 419.50 | 373.96 | 1298.41 | 657.59 |  |  |  |  |
| Training | 180.66 | 120.44 | 184.95 | 28.20 |  |  |  |  |
| Program Management | 182.50 | 105.40 | 186.55 | 129.49 |  |  |  |  |
| Vulnerable Groups |  |  |  |  |  |  |  |  |
| JSY | 165.60 | 139.54 | 178.21 | 71.60 |  |  |  |  |
| Sterilisation & IUD compensation and NSV camps | 39.63 | 23.15 | 38.36 | 15.35 |  |  |  |  |
| Other Activities approved under RCH during 2010-11 such as PPP/NGO, Institutional Strengthening, IEC/BCC, Procurement | 537.21 | 435.62 |  |  |  |  |  |  |
| Mission Flexible Pool |  |  |  |  |  |  |  |  |
| ASHA Programme | 94.3 | 36.77 | 53.73 | 31.35 |  |  |  |  |
| Untied Fund | 138.25 | 139.53 | 138.75 | 137.55 |  |  |  |  |
| AMG | 71.5 | 40.17 | 77.50 | 65.30 |  |  |  |  |
| Hospital Strengthening | - | 1140 | - | - |  |  |  |  |
| New Construction/ Renovation and setting up | 592 | 968 | 123 | 151.64 |  |  |  |  |
| Corpus grants to HMS/RKS | 107.003.67 | 79.95 | 109.00 | 109.00 |  |  |  |  |
| DHAP | 32.00 | 20.03 | 50.00 | 28.96 |  |  |  |  |
| Panchayati Raj Initiative | 16.6 | - | - | - |  |  |  |  |
| Mainstreaming of AYUSH | - | - | 42.00 | 23.40 |  |  |  |  |
| IEC-BCC NRHM | 169.19 | 67.90 | 89.00 | 24.60 |  |  |  |  |
| Mobile Medical Units | 169.23 | 75.10 | 169.65 | 131.26 |  |  |  |  |
| Referral Transport | - | - | 69.60 | - |  |  |  |  |
| PPP/NGO | - | - | 6523 | 50.93 |  |  |  |  |
| Planning, Implementation and Monitoring | 57.74 | 3.67 | 99.65 | 37.79 |  |  |  |  |
| Procurement | 50.85 | 55.83 | 584.10 | 443.01 |  |  |  |  |
| Regional Drugs warehouses | - | - | 9.49 | - |  |  |  |  |
| New Initiatives/ Strategic Interventions |  |  |  |  |  |  |  |  |
| Health Insurance Scheme |  |  |  |  |  |  |  |  |
| Research, Studies, Analysis |  |  |  |  |  |  |  |  |
| State level health resources center (SHSRC) |  |  |  |  |  |  |  |  |
| Support services | - | - | 29.39 | 29.77 |  |  |  |  |
| Other expenditures |  |  |  |  |  |  |  |  |
| Immunization |  |  |  |  |  |  |  |  |
| Mobility support for Supervision and Monitoring at districts and State level. | 5.50 | 5.50 | 5.50 | 4.28 |  |  |  |  |
| Cold chain maintenance | 1.23 | 1.23 | 1.53 | 0.82 |  |  |  |  |
| Alternate Vaccine Delivery to Session sites | 10.32 | 7.18 | 10.32 | 8.02 |  |  |  |  |
| Focus on urban slum & underserved areas | 14.61 | 3.07 | 14.61 | 0.39 |  |  |  |  |
| Social Mobilization by ASHA /Link workers | 15.48 | - | 15.48 | 7.50 |  |  |  |  |
| Computer Assistants support at State/district level | 11.22 | 7.56 | 11.22 | 8.02 |  |  |  |  |
| Printing and dissemination of immunization cards, tally sheets, charts, registers, receipt book, monitoring formats etc. | 1.53 | 1.22 | 1.53 | - |  |  |  |  |
| Quarterly review meeting at State/District/Block level | 2.15 | 0.75 | 2.15 | 2.31 |  |  |  |  |
| District level Orientation for 2 days ANMs, MPHW,LHV | 2.65 | - | 0.79 | 0.79 |  |  |  |  |
| Trainings | 4.26 | 6.46 | 4.26 | 4.70 |  |  |  |  |
| To develop micro plan at sub-centre level and block level | 0.8 | 0.8 | 0.8 | 0.8 |  |  |  |  |
| For consolidation of micro plan at PHC/CHC level | - | - | - | - |  |  |  |  |
| POL for vaccine delivery from State to District and PHC/CHCs | 9.0 | 9.0 | 9.0 | 6.54 |  |  |  |  |
| Consumables for computer including provision for internet access | 0.43 | 0.47 | 0.43 | 0.33 |  |  |  |  |
| Red/Black/Zipper bags | 0.80 | - | 0.80 | 0.80 |  |  |  |  |
| Bleach/Hypochlorite solution |  |  |  |  |  |  |  |  |
| Twin Bucket |  |  |  |  |  |  |  |  |
| Disease Control Program |  |  |  |  |  |  |  |  |
| NVBDCP |  |  |  |  |  |  |  |  |
| Malaria | 419.5 | 344.27 | 413.00 | 200.64 |  |  |  |  |
| Filaria |  |  |  |  |  |  |  |  |
| Dengue/Chikungunya |  |  |  |  |  |  |  |  |
| Cash assistance for decentralized commodities | 17.35 | 17.30 | 15.00 | 7.30 |  |  |  |  |
| Commodity support by GoI | 280.28 | - | 373.72 | - |  |  |  |  |
| IDSP |  |  |  |  |  |  |  |  |
| Surveillance preparedness, training & staff salary | 84.90 | 38.14 | 92.92 | 44.47 |  |  |  |  |
| Outbreak investigation |  |  |  |  |  |  |  |  |
| Analysis & use of data |  |  |  |  |  |  |  |  |
| NPCB |  |  |  |  |  |  |  |  |
| Grant in aid (for Cataract Operations) | 22.50 | 26.00 | 22.50 | 22.50 |  |  |  |  |
| Vision Centre (50X50,000) | 2.50 | 2.50 | 2.50 | 2.48 |  |  |  |  |
| Medical Colleges (3X40) |  |  |  |  |  |  |  |  |
| Strengthening of District Hospital / Sub District Hospital |  |  |  |  |  |  |  |  |
| Eye Donation Centre (Non Recurring 3X1) | 1.00 | 1.00 | 1.00 | 1.00 |  |  |  |  |
| Remuneration (SBCS) & Staff Salary/ Other Activities/Post Requirement | 30.64 | 27.03 | 42.80 | 26.85 |  |  |  |  |
| IEC Activities (50X20 Thousand + SBCS 1 Lacs) | 7.83 | 9.56 | 10.00 | 5.09 |  |  |  |  |
| Proposal for Sutures /(Per Pieces 10.0) /Ophth. Equipments | 5.00 | 45.29 | 25.00 | 33.55 |  |  |  |  |
| NIDDCP |  |  |  |  |  |  |  |  |
| Establishment of IDD Control Cell | 36.00 | 5.30 | 26.99 | 2.50 |  |  |  |  |
| Establishment of IDD |  | 4.2 |  | 1.10 |  |  |  |  |
| Monitoring Lab |  |  |  |  |  |  |  |  |
| a)Health Education and Publicity |  |  |  |  |  |  |  |  |
| b) Salt Testing Kits supplies by GOI (3,84,000 No) |  |  |  |  |  |  |  |  |
| IDD surveys |  |  |  |  |  |  |  |  |
| NLEP |  |  |  |  |  |  |  |  |
| Contractual Services | 11.00 | 13.35 | 19.80 | 11.29 |  |  |  |  |
| Services through ASHA/USHA | 1.50 | 3.80 | 10.00 | 4.80 |  |  |  |  |
| Office expenses & Consumables | 1.50 | 4.69 | 2.05 | 2.18 |  |  |  |  |
| Capacity building | 5.00 | 1.88 | 2.80 | 0.58 |  |  |  |  |
| Behavioural Change Communication | 10.00 | 6.31 | 15.00 | 4.25 |  |  |  |  |
| POL/Vehicle operation & hiring | 5.00 | 6.22 | 4.10 | 4.16 |  |  |  |  |
| DPMR | 1.50 | 0.00 | 1.94 | 1.75 |  |  |  |  |
| Material & Supplies | 1.00 | 0.00 | 0.90 | 0.00 |  |  |  |  |
| Urban Leprosy Control | 0.50 | 0.00 | 0.20 | 0.00 |  |  |  |  |
| Supervision, Monitoring & Review | 3.00 | 0.03 | 2.62 | 0.00 |  |  |  |  |
| Cash assistance | 2.00 | 0.00 | 0.00 | 0.00 |  |  |  |  |
| NIPPCD |  |  |  |  |  |  |  |  |
| Training |  |  |  |  |  |  |  |  |
| Capacity building PHCs/CHCs & District Hospitals |  |  |  |  |  |  |  |  |
| Manpower at district level |  |  |  |  |  |  |  |  |
| Screening Camps |  |  |  |  |  |  |  |  |
| Hearing Aids 200 HI per district per year |  |  |  |  |  |  |  |  |
| Central Cell at State level |  |  |  |  |  |  |  |  |

CHAPTER 3: POLICY AND SYSTEMIC REFORMS IN STRATEGIC AREAS

| S. NO. | Strategic Areas | Target for Policy and Systemic reforms | New Policies should try to address the following issues |
| --- | --- | --- | --- |
| 1. | HR policies for Doctors, Nurses paramedical staff and programme management staff |  | As mentioned in the PIP guidelines, Contractual staff under NRHM regularization under the State Government was put up in the Mizoram State Health Mission, absorption of 25% of the contractual staff under NRHM has been resolved in meeting. |
| 2. | Accountability and Performance appraisal |  | Facility based monitoring; Incentive for both the HSP and the facility based on functioning. Performance appraisal against benchmarks, renewal of contracts based on performance. Incentives for performance above benchmark, special Incentives for difficult areas. |
| 3. | Policies on drugs, procurement system and Logistics management |  | Procurement will be done as per GOI guidelines, and implementation of ProMIS has been under process |
| 4. | Equipments |  | Availability of essential functional equipments in all Facilities, regular needs assessment. Timely indenting and procurement and identification of unused/faulty equipment, regular maintenance and MIS. |
| 5. | Ambulance Services and Referral Transport |  | This has been addressed under JSSK and Emergency referral scheme and from |

| 6 | Maintenance of Buildings. Sanitation, Water, Electricity, laundry, kitchen |  | 24 x 7 maintenance and round the clock plumbing, electrical, carpentry services, power backup, cleanliness and sanitation in PH facilities, upkeep of toilets, Electricity, clean linen, diet for pregnant women. |
| --- | --- | --- | --- |
| 7 | Diagnostics |  | It should be addressed under JSSK Scheme |
| 8 | Patients feedback and grievance redressal |  | Complaint box / Feedback box should be put up in each and every primary health care level |
| 9 | Private Public Partnership (PPP) |  | To supplement Govt effort in underserved area, partnership with mission hospital in Marpara PHC. Another newly established institution under border area (i.e Borapansury) by state Govt was decided by the state Health Mission to hand over to Autonomous District council for specific period as the state govt faced difficulty in posting manpower due to financial constraint presently. The area needs upliftment due to increase influx of population from other states. |
| 10 | Intersect oral convergence |  | There is a good effective coordination in supplying of clean water to Health institute with PHE Dept., school health programme, Adolescent health and IEC with Education Dept. Good relationship with AWW and other social welfare Dept etc. at present more effort in Maternal and child health activities with social welfare dept. like IMGSY, SABLA and MCTS etc. |
| 11 | Community mobilization |  | Active Community participation is acquired by sensitizing the public leader and religious leader with NGOs. Well organized strong VHSC meet regularly and social audit done regularly. PHC Doctors are mobilized to supervise VHS&NC. |
| 12 | IEC |  | More effort on IEC through public leaders and political leaders at various level i.e member of autonomous District council, village panchayat and NGOs especially targeting three backward District i.e Mamit, Saiha and Lawngtlai District. More effort to motivate District administrative personnel by giving more responsibilities within their District so as to increase public awareness on health care service and activities. |
| 13. | Civil Registration Sys tem (CRS) |  | 100% registration of births and deaths, capturing of births in private institutions, reliability to health data on institutional deliveries, sex ratio etc. |
| 14. | Supportive Supervision |  | For supervision of field activities more financial support for mobility is given to District authorities and also at block/PHC level. |
| 15. | Monitoring and Review |  | At present HMIS data cannot be operated in the state due to lack of IT facilities and problems in allocating various village under ministry web portal. Effort is under process with Central Government to overcome such difficulties. At present, PHC/Block level are informed to submit as before so as to have regular analysis of state performance in order to have regular and effective monitoring and supervision. State and District level committee are doing monitoring and evaluation at the District level. |
| 16 | Meetings of State Health Mission/Society/Dist rict Health Society |  | The State Health Mission has been organized regularly and the meetings for the District Health Society have been observed periodically. Review meeting, future road map and agenda have been followed up. |
| 17 | Medical Colleges (New Colleges and Upgradation of existing ones) |  | State Government after seeing health situation, in order to improve our present status, effort for establishing Medical College is under process. Besides this, up gradation of our existing Health institutions are under progress in order to strengthen NRHM activities. |
| 18 | Nursing Schools |  | Beside the existing one Government Nursing College and one Government GNM School and three private Nursing School with one regional institute under MOHFW named RIPANS – where Para medical courses are being conducted . GOI allowed the State to open 4 GNM school in different district. Construction of infrastructure being started from November 2011. When all these institutions are made functional it is expected that about 350 Nurses approx. will be provided by the State. The State will be able to export skilled manpower to other State and even to foreign countries. |
| 19 | Paramedical education |  | In order to improve quality of services and enhance activities regular training of Para medical staff like SBA, NSSK, IUCD, IMNCI, IMEP, RTI/STI etc. are regularly done. Besides these, in-service training in medical care, administration and nursing care are done by State Government. |
| 20 | Capacity building |  | As already stated above, in-service training are conducted for all Doctors and Para Medicals in Skill trainings and a centralized log is formulate under RCH as well as by different specific Health Programmes. |

- RCH Flexi Pool

RCH Monitorable indicators:

Quarterly targets both for High Focus districts and other districts and State total for RCH monitorable indicators should also be provided in the format below:

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A | Maternal Health |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.1 | % Pregnant women registered for ANC in the quarter | 72.8 | 76.9 | 21 | 22.5 | 21 | 22.5 | 21 | 22.5 | 21 | 22.5 | 85 | 90 |
| A.1.2 | % PW registered for ANC in the first trimester, in the | 1849 (46%) | 10155(56.6%) | 48 | 60 | 50 | 62 | 53 | 65 | 55 | 70 | 55 | 70 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
|  | quarter |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3 | Institutional deliveries (%) in the quarter | 1774 (59.6%) | 12183 (83%) | 62 | 85 | 63 | 86 | 65 | 88 | 75 | 90 | 75 | 90 |
| A.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.1 | % unreported deliveries in the quarter | 22% 9 | 17% | 30 | 20 | 25 | 15 | 20 | 10 | 15 | 10 | 15 | 10 |
| A.2.2 | % high risk pregnancies identified (a) % women having hypertension | 24 (0.59% against total ANC) | 248 (1.38% against total ANC) | 1 | 2 | 2 | 3 | 2.5 | 4 | 3 | 5 | 3 | 5 |
|  | (b) % women Having low Hb level | 5 (0.12%) | 56 (0.31%) | No Target |  |  |  |  |  |  |  |  |  |
| A.2.3 | % of Home Delivery by SBA (i.e. assisted by doctor/ nurse/ ANM) | 461 (35 %) | 1102 (44.6%) | 36 | 45 | 37 | 48 | 40 | 50 | 50 | 60 | 50 | 60 |
| A.2.4 | C-sections performed (%) (a) in Public facilities | 38 (2.14%) | 809 (7.9%) | 2.5 | 7.9 | 3 | 7.9 | 3 | 7.9 | 4 | 8 | 4 | 8 |
|  | (b) in private | 21 (13.8%) | 412 (21%) | 12 | 18 | 11 | 16 | 11 | 16 | 10 | 15 | 10 | 15 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
|  | accredited facilities |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5 | % of deliveries discharged after at least 48 hours of delivery (out of public institution deliveries) | 618 (34.8%) | 2949 (28.8%) | 37 | 37 | 38 | 38 | 39 | 39 | 40 | 40 | 40 | 40 |
| A.2.6 | % of still births | 30 (0.9%) | 123 (0.8%) | 0.8 | 0.7 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 |
| A.2.7 | %age of maternal deaths audited | 2 (100%) | 10 (100%) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| A.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.1 | % of 24x7 PHCs operationalised as per the GoI guidelines | 9 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |
| A.3.2 | % of FRUs operationalised as per the GoI guidelines (Current status and target indicated in absolute no.) | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 |
| A.3.3 | % of SCs doing More than 3 deliveries per month. ( status & target indicated in absolute no) | 0 | 37 | 2 | 4 | 2 | 4 | 3 | 5 | 2 | 5 | 9 | 18 |
| A.3.4 | % of PHCs/non FRU CHCs doing 10 deliveries per month | NA | NA | 0 | 0 | 1 | 5 | 1 | 4 | 1 | 2 | 3 | 10 |
| A.3.5 | % of FRUs (except DH) conducting 20 deliveries per month. | - | - | - | - | - | - | - | - | - | - | - | - |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A.3.6 | % ANMs/ LHVs/ SNs trained as SBA | 46.4 | 32.94 | 0 | 23 | 0 | 27 | 0 | 27 | 0 | 23 | 0 | 100 |
| A.3.5 | % doctors trained as EmOC . ( status & target indicated in absolute no) | 0 | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 (for lawngtlai Dist) |
| A.3.6 | % doctors trained as LSAS . ( status & target indicated in absolute no) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |
| A.4 | HR productivity |  |  |  |  |  |  |  |  |  |  |  |  |
| A.4.1 | % of LSAS trained doctors giving spinal anaesthesia | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70 |
| A.4.2 | Average no. of c-sections assisted by LSAS trained doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| A.4.3 | % of EmOC trained doctors conducting c-sections. | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70 |
| A.4.4 | Average no. of c- sections performed by EmOC trained doctor | 0 | 13 | 0 | 3 | 0 | 6 | 0 | 11 | 0 | 15 | 0 | 15 |
| A.4.5 | Average no. of deliveries performed by SBA trained SN/LHV/ANM | NA | 0 | State HMIS does not capture this data. It is expected to be in place in the coming year |  |  |  |  | 0 | 0 | 0 | 0 | 0 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| A.4.6 | % of SBA trained ANMs/SNs conducting deliveries | 75 | 90.6 | 75 | 100 | 75 | 100 | 80 | 100 | 80 | 100 | 80 | 100 |
| A.5 | Facility utilization |  |  |  |  |  |  |  |  |  |  |  |  |
| A.5.1 | % of FRUs conducting C- section | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| A.5.2 | Average no. of c- sections per FRU | 5 | 193 | 0 | 50 | 0 | 50 | 0 | 50 | 0 | 50 | 0 | 200 |
| A.5.3 | Average no. of MTPs performed in FRUs | 4 | 39 |  | 10 |  | 10 |  | 10 |  | 10 |  | 40 |
| A.5.4 | Average no. of deliveries per 24x7 PHCs per month |  | 11 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |
| A.5.5 | Average no. of MTPs performed per 24x7 PHC |  | 0.3 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.4 |
| A.5.6 | % of SC conducting at least 5 deliveries per month | 0 | 0 |  | - | - | - | - | - | - | - | - | - |
| B | Child Health |  |  |  |  |  |  |  |  |  |  |  |  |
| B.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| B.1.1 | Children 9-11 months age fully immunised (%)(Against estimated below 1 year) | 48 % (2688) | 60 % (13996) | 50 | 65 | 60 | 70 | 70 | 80 | 83 | 90 | 83 | 90 |
| B.1.2 | % children Breast fed within 1 hour of birth | 2592 (81%) | 12439 (85.6%) | 84 | 86 | 86 | 89 | 88 | 92 | 90 | 95 | 90 | 95 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| B.1.3 | % of low birth weight babies | 64 (2.42%) | 677 (5%) | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 |
| B.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| B.2.1 | %age of women receiving PP check up to 48 hrs to 14 days | 1082 (33.47% against Total delivery) | 9708 (66.26% against Total delivery) | 35 | 67 | 38 | 68 | 40 | 69 | 55 | 70 | 55 | 70 |
| B.2.3 | % drop out from BCG to measles | 260 (8%) | 1253 (8%) | 6 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 |
| B.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| B.3.1 | % of SNCUs Operationalised (Indicated in absolute no) |  | 0 |  |  |  |  |  |  |  | 1 |  | 1 |
| B.3.2 | % of stabilisation units operationalised | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 40 | 0 | 0 | 3 | 5 |
| B.3.3 | % of new born baby care corners operationalised | 0 | 0 | 9.5 | 28.5 | 9.5 | 28.5 | 9.5 | 28.5 | 4.7 | 14.5 | 0 | 21 |
| B.3.4 | % of personnel trained in IMNCI | 0 | 40.83 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 100% (120 Nos) |
| B.3.5 | % of personnel trained in F-IMNCI | 0 | 22.62 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 25 | 0 | 100% (144 Nos) |
| B.3.6 | % of personnel trained in NSSK | 0 | 11.86 | 0 | 26 | 0 | 26 | 0 | 22 | 0 | 26 | 0 | 100% (360 Nos) |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| B.4 | Facility utilization |  |  |  |  |  |  |  |  |  |  |  |  |
| B.4.1 | Average no. of children treated in SNCUs | 0 | 933 | 0 | 300 | 0 | 300 | 0 | 300 | 0 | 300 | 0 | 1200 |
| B.4.2 | Average no. of children treated in NBSUs | 0 | 120 | 0 | 45 | 0 | 45 | 0 | 45 | 0 | 45 | 0 | 180 |
| C | Family Planning |  |  |  |  |  |  |  |  |  |  |  |  |
| C.1 | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| C.1.1 | % of total sterilisation against ELA | 311 (78%) | 1445 (41%) | 79 | 79 | 79 | 79 | 79 | 79 | 80 | 80 | 80 | 80 |
| C.1.2 | % post partum sterilisation | 87 (44%) | 578 (38%) | 47 | 40 | 50 | 60 | 60 | 70 | 75 | 80 | 75 | 80 |
| C.1.3 | % male sterilizations | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 4 |
| C.1.4 | % of IUD insertions against planned | 265 (44%) | 2090 (42%) | 47 | 50 | 50 | 60 | 60 | 70 | 70 | 80 | 70 | 80 |
| C.1.5 | % IUD retained for 6 months | NA | NA | 65 | 75 | 70 | 80 | 75 | 85 | 80 | 90 | 80 | 90 |
| C.1.6 | % Sterilization acceptors with 2 children | NA | NA | 50 | 60 | 50 | 60 | 50 | 60 | 50 | 60 | 50 | 60 |
| C.1.7 | % Sterilisation acceptors with 3 or more children | NA | NA | 63 | 75 | 65 | 76 | 68 | 77 | 70 | 80 | 70 | 80 |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
| C.2 | Quality |  |  |  |  |  |  |  |  |  |  |  |  |
| C.2.1 | % of complications following sterilisation | 6 (2% out of female sterilization) | 30 (2% out of female Sterilization) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.3 | Outputs |  |  |  |  |  |  |  |  |  |  |  |  |
| C.3.1 | % doctors trained as minilap | - | 50 |  | 20 |  | 40 |  | 20 |  | 20 |  | 10 |
| C.3.2 | % doctors trained as NSV | - | - |  |  |  |  |  |  |  | 100% |  | 100% (1 No) |
| C.3.3 | % doctors trained as laparoscopic sterilisation | - | - |  |  |  |  |  | 100% |  |  | - | 100% (1 Team) |
| C.3.4 | % ANM/LHV/SN/MO trained in IUD insertion |  | 136% |  |  |  | 60 |  | 40 |  |  | - | 100% (50 Nos) |
| C.4 | HR productivity |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.1 | Average no. of NSVs conducted by trained doctors | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.4.2 | Average no. of minilap sterilisations conducted by minilap trained doctors | 4 | 11 | 40 | 240 | 40 | 240 | 40 | 240 | 40 | 240 | 160 | 960 |
| C.4.3 | Average no. of laparoscopic |  |  |  |  |  |  |  |  |  |  |  |  |

| SN. | INDICATOR | 2011-12 |  | 2012-13 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline (Apr-Nov 2011) |  | Q1 Target |  | Q2 Target |  | Q3 Target |  | Q4 Target |  | Annual Target |  |
|  |  | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total | HF Distts. | State total |
|  | sterilisations conducted by lap sterilisation trained doctors |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.4 | Average no. of IUDs inserted by MO trained in IUD insertion |  | 3 | 10 | 62 | 10 | 62 | 10 | 63 | 10 | 63 | 40 | 250 |
| C.4.5 | Average no. of IUDs inserted by MO trained in IUD insertion |  |  |  |  |  |  |  |  |  |  |  |  |
| C.4.6 | Average no. of IUDs inserted by SN/ LHV/ ANM trained in IUD insertion | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| C.5 | Facility utilisation |  |  |  |  |  |  |  |  |  |  |  |  |
| C.5.1 | Average no. of sterilizations performed in FRUs | 24 | 129 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 |
| C.5.2 | Average no. of sterilizations performed in 24x7 PHCs | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |

RCH FLEXIPOOL BUDGET SUMMARY:

| Sl.No | Components | FMR Code | Amount Proposed 2012-13 ( in lakhs) |
| --- | --- | --- | --- |
| 1 | Maternal Health including JSY | A.1 | 689.11 |
| 2 | Child Health | A.2 | 63.05 |
| 3 | Family Planning including Compensation | A.3 | 78.42 |
| 4 | Adolescent Reproductive and Sexual Health | A.4 | 70.00 |
| 5 | Urban RCH | A.5 | 31.38 |
| 6 | Tribal RCH | A.6 |  |
| 7 | PNDT & Sex Ratio | A.7 | 4.00 |
| 8 | Infrustructure and Human Resources | A.8 | 1548.17 |
| 9 | Training | A.9 | 117.87 |
| 10 | Programme Management | A.10 | 342.18 |
| 11 | Vulnerable Groups | A.11 |  |
| Total |  |  | 2944.18 |

I.MATERNAL HEALTH

GOAL: To reduce MMR from 72 (State HMIS 2010-11) to 65 in 2012-13 and to 35 by 2016-17

In order to achieve the target set for for the next 5 years various activities such as relocation of staff, up gradation of health facilities, training of health providers, IEC/BCC activities, outreach services, monitoring will be emphasized. The Maternal Death review findings will be prioritized and actions will be taken based on their findings. Priority will be given to low performing districts/High focus districts namely Saiha, Lawngtlai and Mamit districts.

| Year | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 (April to Nov) |
| --- | --- | --- | --- | --- | --- |
| MMR (State HMIS) | 58 | 20 | 50 | 72 | 68.82 |

Delivery Points

It may be  stated that the GOI benchmark for delivery points cannot apply whole heartedly to small states like Mizoram where there is sparse population and difficulty in transport due to the hilly terrain.

At present, there are 71 functional delivery points (as per GOI benchmark), 34 of which is DH/SDH/CHC/PHC, and 37 are sub-centers. They are :

| Functional Delivery Points List |  |  |
| --- | --- | --- |
| S no | District | Facility |
|  | Aizawl East |  |
| 1 |  | Saitual CHC |
| 2 |  | Sakawrdai CHC |
| 3 |  | Thingsulthliah 24*7 PHC |
| 4 |  | Darlawn 24*7 PHC |
| 5 |  | Khawruhlian 24*7 PHC |
| 6 |  | Phuaibuang 24*7 PHC |
|  | Aizawl West |  |
| 7 |  | Civil Hospital, Aizawl |
| 8 |  | Kulikawn Hospital |
| 9 |  | Lengpui PHC |
| 10 |  | Hmunpui SC |
|  | Champhai |  |
| 11 |  | Champhai DH |
| 12 |  | Ngopa CHC |
| 13 |  | Kawlkulh 24*7 PHC |
| 14 |  | Khawzawl 24*7 PHC |
| 15 |  | Hnahlan 24*7 PHC |
| 16 |  | Khawbung 24*7 PHC |
| 17 |  | Farkawn 24*7 PHC |
| 18 |  | Mimbung PHC |
| 19 |  | Tlangsam SC |
| 20 |  | N. Khawbung SC |
| 21 |  | Ruantlang SC |
| 22 |  | Hmunhmeltha SC |
| 23 |  | Melbuk SC |
| 24 |  | Ngur SC |
| 25 |  | Sesih SC |
| 26 |  | Khuangleng SC |
| 27 |  | Dungtlang SC |
| 28 |  | Samthang SC |
| 29 |  | Khuangthing SC |
| 30 |  | Dulte SC |
| 31 |  | Hliappui SC |
| 32 |  | Chhawrtui SC |
| 33 |  | Tualte SC |
| 34 |  | Ngaizawl SC |
| 35 |  | Vanzau SC |
| 36 |  | Sazep SC |
| 37 |  | Khankawn SC |
| 38 |  | Vaphai SC |
|  | Kolasib |  |
| 39 |  | Kolasib District Hospital |
| 40 |  | Vairengte CHC |
| 41 |  | Kawnpui 24*7 PHC |
| 42 |  | Saipum SC |
| 43 |  | Saiphai SC |
| 44 |  | Thingdawl SC |
| 45 |  | Bualpui SC |
| 46 |  | N. Hlimen SC |
| 47 |  | Zanlawn SC |
| 48 |  | Phaisen SC |
|  | Lawngtlai |  |
| 49 |  | Lawngtlai District Hospital |
| 50 |  | Chawngte CHC |
|  | Lunglei |  |
| 51 |  | Lunglei District Hospital |
| 52 |  | Tlabung SDH |
| 53 |  | Hnahthial CHC |
|  | Mamit |  |
| 54 |  | Mamit District Hospital |
| 55 |  | Kawrthah CHC |
| 56 |  | Marpara 24*7 PHC |
| 57 |  | West Phaileng 24*7 PHC |
| 58 |  | Kawrtethawveng PHC |
|  | Saiha |  |
| 59 |  | Saiha District Hospital |
|  | Serchhip |  |
| 60 |  | Serchhip District Hospital |
| 61 |  | Thenzawl CHC |
| 62 |  | North Vanlaiphai 24*7 PHC |
| 63 |  | Chhiahtlang SC |
| 64 |  | Keitum SC |
| 65 |  | Bungtlang SC |
| 66 |  | Mualpheng SC |
| 67 |  | Thentlang SC |
| 68 |  | Hmuntha SC |
| 69 |  | Hualtu SC |
| 70 |  | Lungchhuan SC |
| 71 |  | S. Chawngtui SC |

Of these delivery points,

53 have at least 1 Health Personnel Trained in SBA,

1 has at least 1 Health Personnel Trained in BEmOC

25 have at least 1 Health Personnel Trained in MTP

23 have at least 1 Health Personnel Trained in NSSK

Training for the remaining will be prioritized in the coming year.

Total functional delivery points in Public Health Facilities of Mizoram		Annexure A-I

State/UT-	Date as on -----

| S.No | Indicator | Number |  |
| --- | --- | --- | --- |
| 1 | Total No. of SCs | 370 |  |
| a | No. of SCs conducting >3 deliveries/month | 37 |  |
| 2 | Total No. of 24X7 PHCs | 41 |  |
| a | No. of 24X7 PHCs conducting > 10 deliveries /month | 13 |  |
| 3 | Total No. of any other PHCs | 16 |  |
| a | No. of any other PHCs conducting > 10 deliveries/ month | 2 |  |
| 4 | Total No. of CHCs ( Non- FRU)/SDH | 11 |  |
| a | No. of CHCs ( Non- FRU) conducting > 10 deliveries /month | 10 |  |
| 5 | Total No. of CHCs ( FRU) | - |  |
| a | No. of CHCs (FRU) conducting > 20 deliveries /month | - |  |
| b | No. of CHCs (FRU) conducting C-sections | - |  |
| 6 | Total No. of any other FRUs (excluding CHC-FRUs) | - |  |
| a | No. of any other FRUs (excluding CHC-FRUs) conducting > 20 deliveries /month | - |  |
| b | No. of any other FRUs (excluding CHC-FRUs) conducting C- sections | - |  |
| 7 | Total No. of DH | 8 |  |
| a | No. of DH conducting > 50 deliveries /month | 8 |  |
| b | No. of DH conducting C-section | 7 |  |
| 8 | Total No. of District Women And Children hospital (if separate from DH) | - |  |
| a | No. of District Women And Children hospital (if separate from DH) conducting > 50 deliveries /month | - |  |
| b | No. of District Women And Children hospital (if separate from DH) conducting C-section | - |  |
| 9 | Total No. of Medical colleges | 0 |
| a | No. of Medical colleges conducting > 50 deliveries per month | - |
| b | No. of Medical colleges conducting C-section | - |
| 10 | Total No. of Accredited PHF | NA |
| a | No. of Accredited PHF conducting > 10 deliveries per month | NA |
| b | No. of Accredited PHF conducting C-sections | NA |

| Report on Delivery points on KPI |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Sl no | Name and Type of Facility | Total deliveries in the institution (including CS)(Figures for S/C are available for October, 2011 only) | No. of CS (where applicable) | Total no of PW detected with Hb level 7gm and below | No of maternal deaths in the facility | Functional LR with NBCC | Functional OT | Functional BSU/BB | Availability of essential drugs | BMW | MO & Specialists posted | No of SN/ANM posted at facility |
| Aizawl East | 1 | Saitual CHC FRU | 20 | na | na | na | y | y | y | y | y | MO-2 | Sn-21 |
|  | 2 | Sakawrdai CHC | 10 | na | na | na | y | y | y | y | y | MO-1 | SN-6 |
|  | 3 | Thingsulthliah 24*7 PHC | 25 | na | na | na | y | n | n | y | y | MO-1 | SN-6 |
|  | 4 | Darlawn 24*7 PHC | 5 | na | na | na | y | n | n | y | y | MO-1 | SN-6 |
|  | 5 | Khawruhlian 24*7 | 12 | na | na | na | y | n | n | y | y | MO-1 | SN-4 |
|  | 6 | Phuaibuang 24*7 PHC | 4 | na | na | na | y | y | y | y | y | MO-1 | SN-4 |
| Aizawl West | 7 | Civil hospital, Aizawl FRU | 409 | 85 | na | 2 | y | y | y | y | y | MO-28,PG-68,Specialist-22 | S/N-203 |

|  | 8 | Kulikawn Hospital | 35 | na | Na | na | y | y | y | y | y | MO-2,Specialist-1 | SN -8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 9 | Lengpui CHC | 7 | na | na | na | y | n |  | y | y | MO-2 | SN-5 |
|  | 10 | Hmunpui SC | 0 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
| Champhai | 11 | Champhai DH | 65 | na | na |  | y | y | y | y | y | MO-7 | SN-24 |
|  | 12 | Ngopa CHC | 7 | na | na | na | y | y | n | y | y | MO-1 | SN-6 |
|  | 13 | Kawlkulh 24*7 PHC | 8 | na | na | na | Y | n | n | y | y | MO-1 | SN-4 |
|  | 14 | Khawzawl 24*7 PHC | 8 | na | na | na | y | n | n | y | y | MO-1 | SN-4 |
|  | 15 | Hnahlan 24*7 PHC | 8 | na | na | na | y(no NBCC) | n | n | y | y | MO-1 | SN-2 |
|  | 16 | Farkawn 24*7 PHC | 25 | na | na | na | y | n | n | y | y | MO-1 | SN-3 |
|  | 17 | Khawbung 24*7 PHC | 15 | na | na | na | y | n | n | y | y | MO-1 | SN-4 |
|  | 18 | MimbungPHC | 9 | na | na | na | y | n | n | y | y | na | SN-3 |
|  | 19 | Tlangsam SC | 3 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 20 | N. Khawbung SC | 1 | na | na | na |  | n | n | y | y | na |  |
|  | 21 | Ruantlang SC | 2 | na | na | na | y | n | n | n | y | na | H/W(F) - 2 |

|  | 22 | Hmunhmeltha SC | 0 | na | na | Na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 23 | Melbuk SC | 5 | na | na | na | n | n | n | y | y | na | H/W(M)-1 |
|  | 24 | Ngur SC | 3 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 25 | Sesih SC | 1 | na | na | na |  | n | n | y | y | na | H/W(F)-1 |
|  | 26 | Khuangleng SC | 1 | na | na | na |  | n | n | y | y | na | H/W(F)-1 |
|  | 27 | Dungtlang SC | 0 | na | na | na |  | n | n | y | y | na | H/W(F)-1 |
|  | 28 | Samthang SC | 0 | na | na | na | y | n | n | y | y | na | H/W(F) - 2 |
|  | 29 | Khuangthing SC | 4 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 30 | Dulte SC | 0 | na | na | na |  | n | n | y | y | na | H/W(F)-1 |
|  | 31 | Hliappui SC | 1 | na | na | na |  | n | n | y | y | na | H/W(F)-1 |
|  | 32 | Chhawrtui SC | 0 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 33 | Tualte SC | 1 | na | na | na | y | n | n | y | y | na | H/W(F)-1 |
|  | 34 | Ngaizawl SC | 1 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 35 | Vanzau SC | 1 | na | na | na | y | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
|  | 36 | Sazep SC | 0 | na | na | na | y | n | n | y | y | na | H/W(M)-1 |
|  | 37 | Khankawn SC | 1 | na | na | na | y | n | n | y | y | na | H/W(M)-1,H/W(F)-1 |
|  | 38 | Vaphai SC | 5 | na | na | na |  | n | n | y | y | na | H/W(M)-1, H/W(F)-1 |
| Kolasib | 39 | Kolasib District Hospital | 61 | na | na |  | y | y | y | y | y | MO-2 | SN-28 |
|  | 40 | Vairengte CHC | 30 | na | na | na | y | y | y | y | y | MO-2 | SN-5 |
|  | 41 | Kawnpui 24*7 PHC |  | na | na | na | y | n | n | y | y | MO-1 | S/N-5 |
|  | 42 | Saipum SC | 5 | na | na | na | n | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 43 | Saiphai SC | 0 | na | na | na | y | y | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 44 | Thingdawl SC | 0 | na | na | na | y | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 45 | Bualpui SC | 0 | na | na | na | y | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 46 | N. Hlimen SC | 0 | na | na | na |  |  | n | y | y | na |  |
|  | 47 | Zanlawn SC | 2 | na | na | na | y | n | y | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 48 | Phaisen SC | 0 | na | na | na |  |  | n | y | y | na | H/W(F)-1 |
| Lawngtlai | 49 | Lawngtlai District Hospital | 35 | na | na |  | y | y | y | y | y | MO-3, Specialist-1 | SN-10 |
|  | 50 | Chawngte CHC | 5 | na | na | na | y | n | y | y | y | MO-2 | S/N-7 |
| Lunglei | 51 | Lunglei District Hospital | 100 | 30 | na |  | y | y | y | y | y | MO-6, Specialist-2 | S/N-46 |
|  | 52 | Tlabung SDH | 13 | na | na | na | y | y | n | y | y | MO-2 | SN-6 |
|  | 53 | Hnahthial CHC | 12 | na | na | na | y | n | n | y | y | MO-2 | SN-9 |
| Mamit | 54 | Mamit District Hospital | 22 | 2 | na | 1 | y | y | y | y | y | MO-2,Specialist-1 | S/N- 11 |
|  | 55 | Kawrthah CHC | 10 | na | na | na | y | y | y | y | y | MO-2 | SN-6 |
|  | 56 | Marpara 24*7 PHC | 4 | na | na | na |  | n | n | y | y | MO-1 | S/N-4 |
|  | 57 | West Phaileng 24*7 PHC | 7 | na | na | na | y | n | n | y | y | MO-1 | SN-3 |
|  | 58 | Kawrtethawveng PHC | 9 | na | na | na | y | n | n | y | y | MO-1 | SN-2 |
| Saiha | 59 | Saiha District Hospital |  | 15 | na | na | y | y | y | y | y |  |  |
| Serchhip | 60 | Serchhip District Hospital | 45 | 5 | na | na | y | y | y | y | n | MO-3, Specialist-2 | S/N-23 |
|  | 61 | Thenzawl CHC | 20 | na | na | na | y | y | y | y | y | MO-2 | SN-8 |
|  | 62 | North Vanlaiphai 24*7 PHC | 8 | na | na | na | y | n | n | y | y | MO-1 | SN-3 |
|  | 63 | Chhiahtlang SC | 0 | na | na | na | y | n | n | n | y | na | H/W(F)-2 H/W(M)-2 |
|  | 64 | Keitum SC | 2 | na | na | na | y | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 65 | Bungtlang SC | 1 | na | na | na | y | n |  | n | y | na | H/W (F) - 1 |
|  | 66 | Mualcheng SC | 6 | na | na | na | n | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 67 | Thentlang SC | 0 | na | na | na | y | y | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 68 | Hmuntha SC | 0 | na | na | na | y | n | n | y | y | na | H/W F) - 2 |
|  | 69 | Hualtu SC | 2 | na | na | na | y | n | n | y | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 70 | Lungchhuan SC | 2 | na | na | na | y | n | n | n | y | na | H/W (F) - 1 H/W (M) - 1 |
|  | 71 | S. Chawngtui SC | 0 | na | na | na | N | N | n | N | y | na | H/W (F) - 1 H/W (M) - 1 |

FRU, 24*7 PHC and Sub Centre Operationalization

The State has 4 FRUs at Civil Hospital, Aizawl; Serchhip District Hospital; Lunglei District Hospital; Saiha District Hospital.

Plan is made for the setup of 4 more FRUs at 2 DHs, 1 SDH and 2 CHCs in the coming year at

- Kulikawn Hospital, Aizawl

- Kolasib District Hospital

- Champhai District Hospital

- Vairengte CHC, Kolasib District

The rationale behind this being that these centres already have at least one each of Gynaecologist/EmOC, Anaesthetist/LSAS, and Paediatrician/F-IMNCI already posted at these centres. Exception is for Champhai District hospital and Vairengte CHC where one Medical Officer each is currently under training for EmOC.at the time of writing.

Emphasis will be given to functional delivery points in terms of HR, Training, equipments etc. The Manpower and equipment status of DHs and CHCs designated to be FRUs

| District Hospitals to be designated as FRUs |  |  |  |
| --- | --- | --- | --- |
|  | Functioning | Under process | Gaps |
| District |  | Kolasib | Champhai |
|  | Name of Facility | Kolasib DH | Champhai DH |
| Sl. No. | Indicators |  |  |
| 1 | Sanctioned Bed Strength | 60 | 60 |
| 2 | No. of Functional Bed | 60 | 60 |
| 3 | Average Monthly OPD | 3032 | 1370 |
| 4 | Average Monthly IPD | 407 | 411 |
| 5 | Average Monthly institutional deliveries | 61 | 65 |
| 6 | Average Monthly C/Section | 4 | 4 |
| 7 | Number of Doctors with Specialization in |  |  |
|  | Obs & Gynae | 1 | 0 |
|  | Pediatrician | 0 | 0 |
|  | Anaesthetist | 1 | 1 |
| 8 | Doctors |  |  |
|  | MBBS | 2 | 7 |
| 9 | GNM | 28 | 24 |
| 10 | Pharmacist | 3 | 3 |
| 11 | Lab. Tech. | 4 | 5 |
| 12 | Radiographer | 0 | 3 |
| 13 | Functional Laboratory |  |  |
|  | Availability of Room | Y | Y |
|  | Functional Laboratory performing assured laboratory services of the Health Institutions. (YES/ NO) | Y | Y |
| 14 | Safe Blood Facility |  |  |
|  | Availability of Room | Y | Y |
|  | Whether Licensed (YES/ NO) | Y | Y |
|  | Blood Bag Refrigerators, 30 or 50 units of Blood. | Y (30) | Y (30) |
|  | Deep Freezers for freezing ice packs. | Y | Y |
|  | Cold chain boxes/Insulated Carrier boxes with ice packs. | Y | Y |
|  | Binocular Microscope | Y | Y |
|  | Bench top centrifuge. | Y | Y |
|  | Provision of backup Generator | Y | Y |
|  | Lab Technician trained in Blood safety, etc. looking after Blood Bank/ storage Centre | Y | Y |
|  | MO trained in Blood safety, etc. | Y | Y |
| 15 | Functional Labour Room |  |  |
|  | Availability of Room | Y | Y |
|  | Labour table with Mattress, pillow and Kelly’s pad | Y | Y |
|  | Examination Table with stirrup | Y | Y |
|  | Suction machine | Y | Y |
|  | Facility for Oxygen administration | Y | Y |
|  | Shadow less lamp | Y | Y |
|  | Sterilization equipment | Y | Y |
|  | 24-hour running water | Y | Y |
|  | Electricity supply | Y | Y |
|  | Attached toilet facilities | Y | Y |
|  | Emergency drug tray | Y | Y |
|  | Delivery kits, including those for normal delivery and assisted deliveries. | Y | Y |
| 16 | Functional Operation Theatre |  |  |
|  | Availability of Room | Y | Y |
|  | Availability of Room | Y | Y |
|  | Standard Surgical Set - I (Laparatomy) | Y | Y |
|  | Standard Surgical Set – II (Mini Laparatomy) | Y | Y |
|  | Standard Surgical Set – III (IUD Insertion) | Y | Y |
|  | Standard Surgical Set – IV (Vasectomy) | N | N |
|  | Standard Surgical Set – V (Normal Delivery) | Y | Y |
|  | Standard Surgical Set – VI (Vacumm Extractor) | Y | Y |
|  | Laproscope | Y | Y |
|  | Equipment for Anaesthesia | Y | Y |
|  | Diathermy machine | Y | Y |
|  | Table operation, hydraulic (Major) | Y | Y |
|  | Table operation, hydraulic Minor | Y | Y |
|  | Lamps shadowless (Ceiling) | Y | Y |
|  | Lamps shadowless (Portable) | Y | Y |
|  | Suction Apparatus | Y | Y |
|  | Stand with wheel for single basin | Y | Y |
|  | Dressing drum all sizes | Y | Y |
|  | Sterilizer | Y | Y |
|  | X-ray view box | Y | Y |
|  | Trolley for patients | Y | Y |
|  | Trolley for instruments | Y | Y |
|  | Wheel chairs | Y | Y |
| 17 | Newborn Care Facility |  |  |
|  | Availability of Room | Y | Y |
|  | Open care system on trolley with drawers, with radiant warmer, O2-provision | N | Y |
|  | Phototherapy unit, single head, high intensity | N | N |
|  | Resuscitator/ambu bag/self inflating bag, hand-operated, neonate, 500ml | Y | N |
|  | Resuscitator/ambu bag/self inflating bag, hand-operated, neonate, 250ml | Y | N |
|  | Laryngoscope set, neonate | Y | Y |
|  | Pump/Suction machine, portable, 220V, w/access | Y | Y |
|  | Pump/Suction machine, foot-operated | N | Y |
|  | Oxygen hood, S and M, set of 3 each, including connecting tubes | N | Y |
|  | Oxygen concentrator, elec 220V | Y | Y |
|  | Pulse oxymeter, bedside, neonatal | N | N |
|  | Infantometer, plexi, 3½ft/105cm | N | N |
|  | Monitor, vital sign, NIBP, HR, SpO2, ECG, RR, Temp | N | N |
|  | ECG unit, 3 channel, portable/SET | Y | N |
|  | X-Ray, mobile | Y | Y |
|  | Irradiance meter for phototherapy units | N | N |
|  | Oxygen Cylinder with flow meter | Y | Y |
|  | Weighing Scale, spring | Y | Y |
|  | Thermometer, clinical, digital, 32-34 0C | Y | Y |
|  | Light examination, mobile, 220-12 V | N | Y |
|  | Hub Cutter, syringe | Y | N |
| 22 | Referral Services avialable (YES/NO) | Y | Y |
| 23 | Waste Disposal System | Y | Y |

| ‘Delivery Point’ Community Health Centres to be upgraded to First Referral Units |  |  |  |
| --- | --- | --- | --- |
|  | Functioning | Under process | Gaps |
| Sl. No. | District | Aizawl West | Kolasib |
|  | Name of the Facility | Kulikawn | Vairengte |
|  | Indicators |  |  |
| 1 | Sanctioned Bed Strength | 60 | 30 |
| 2 | No. of Functional Bed | 60 | 30 |
| 3 | Average Monthly OPD | 1300 | 700 |
| 4 | Average Monthly IPD | 100 | 80 |
| 5 | Average Monthly institutional deliveries | 35 | 30 |
| 6 | Average Monthly C/Section | NA | NA |
| 7 | Number of Doctors with Specialization in |  |  |
|  | Obs & Gynea | 1 |  |
|  | EmOC | 1 | 1 |
|  | Pediatrician |  |  |
|  | F-IMNCI | 2 | 2 |
|  | Anaesthetist | 1 |  |
|  | LSAS | 1 | 1 |
| 8 | Doctors |  |  |
|  | MBBS | 3 | 2 |
|  | AYUSH |  |  |
| 9 | NURSE | 21 | 5 |
| 10 | Pharmacist | 2 |  |
| 11 | Lab. Tech. | 5 | 3 |
| 12 | Radiographer |  | 1 |
| 13 | Functional Laboratory |  |  |
|  | Availability of Room | Y | Y |
|  | Functional Laboratory performing assured laboratory services of the Health Institutions. (YES/ NO) | Y | Y |
| 14 | Safe Blood Facility |  |  |
|  | Availability of Room | N | Y |
|  | Blood Refrigerators, 30 or 50 units of Blood. |  | Y |
|  | Deep Freezers for freezing ice packs. |  | Y |
|  | Cold chain boxes/Insulated Carrier boxes with ice packs. |  | Y |
|  | Binocular Microscope | Y | Y |
|  | Bench top centrifuge. |  | Y |
|  | Provision of backup Generator |  | N |
|  | Lab Technician trained in Blood safety, etc. looking after Blood Bank/ storage Centre |  | Y |
|  | MO trained in Blood safety, etc. |  | Y |
| 15 | Functional Labour Room |  |  |
|  | Availability of Room | Y | Y |
|  | Labour table with Mattress, pillow and Kelly’s pad | Y | Y |
|  | Examination Table with stirrup | Y | N |
|  | Suction machine | Y | Y |
|  | Facility for Oxygen administration | N | Y |
|  | Shadow less lamp | N | N |
|  | Sterilization equipment | Y | Y |
|  | 24-hour running water | Y | Y |
|  | Electricity supply | Y | Y |
|  | Power back-up facility | Y | N |
|  | Attached toilet facilities | Y | Y |
|  | Emergency drug tray | Y | Y |
|  | Delivery kits, including those for normal delivery and assisted deliveries. | Y | Y |
| 16 | Functional Operation Theatre |  |  |
|  | Availability of Room | Y | Y |
|  | Standard Surgical Set - I (Laparatomy) | Y | N |
|  | Standard Surgical Set – II (Mini Laparatomy) | N | N |
|  | Standard Surgical Set – III (IUD Insertion) | Y | Y |
|  | Standard Surgical Set – IV (Vasectomy) | N | N |
|  | Standard Surgical Set – V (Normal Delivery) | Y | Y |
|  | Standard Surgical Set – VI (Vacumm Extractor) | Y | N |
|  | Laproscope | N | N |
|  | Equipment for Anaesthesia | N | N |
|  | General Equipment for operation Theatre | Y | N |
|  | Diathermy machine | N | N |
|  | Table operation, hydraulic (Major) | N | N |
|  | Table operation, hydraulic Minor | N | N |
|  | Lamps shadowless (Ceiling) | N | N |
|  | Lamps shadowless (Portable) | Y | Y |
|  | Suction Apparatus | Y | Y |
|  | Sterilizer |  |  |
| 17 | Newborn Care Facility |  | NBCC available |
|  | Availability of Room | N | N |
|  | Open care system on trolley with drawers, with radiant warmer, O2-provision | N | Y |
|  | Phototherapy unit, single head, high intensity | N | N |
|  | Resuscitator/ambu bag/self inflating bag, hand-operated, neonate, 500ml | N | N |
|  | Resuscitator/ambu bag/self inflating bag, hand-operated, neonate, 250ml | Y | Y |
|  | Laryngoscope set, neonate | N | Y |
|  | Pump/Suction machine, portable, 220V, w/access | Y | Y |
|  | Pump/Suction machine, foot-operated | Y | N |
|  | Oxygen hood, S and M, set of 3 each, including connecting tubes | N | N |
|  | Oxygen concentrator, elec 220V | Y | N |
|  | Irradiance meter for phototherapy units | N | N |
|  | Oxygen Cylinder with flow meter | Y | Y |
|  | Weighing Scale, spring | Y | Y |
|  | Hub Cutter, syringe | N | Y |
| 18 | Referral Services available (YES/NO) | Y | Y |
| 19 | Waste Disposal System | Y | Y |

Janani Suraksha Yojana

Under Janani Suraksha Yojana mothers are given incentives for institutional deliveries at all Public Health Institutions and in 10 Private institutions accredited to dispense JSY benefits. The following Private Institutions are accredited to dispense JSY benefits :

- Med–aim Adventist Hospital, Champhai

- Lairam Christian Medical Centre, Lawngtlai

- Christian Hospital, Serkawn, Lunglei

- Nazareth Hospital, Kolasib

- Aizawl hospital, Mission veng

- Seventh Day Adventist Hospital, Seventh Day Tlang

- Grace Nursing Home, Zarkawt

- Bethesda Hospital, Chaltlang

- New Life Hospital, Chanmari

- Presbyterian Hospital, Durtlang

. The Percentage of JSY beneficiaries out of the total institutional and home deliveries is as below.

| JSY Beneficiaries | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 (April to Nov) |
| --- | --- | --- | --- | --- | --- |
| % of JSY beneficiaries out of Institutional Deliveries | 62% | 93% | 79% | 72% | 60% |
| % of JSY beneficiaries out of home deliveries | 28% | 26% | 11% | 9.6% | 5.2% |

The percentage (%) of JSY beneficiaries out of home deliveries is less since most home deliveries are not eligible for JSY benefits.

JSY is being implemented in the state as per GOI guidelines. ASHAs who attend pregnant women for ANC, institutional delivery and PNC will be given incentives as per the guidelines. Estimate for JSY beneficiaries is calculated as below:

Estimated total no of live birth for 2012-13						: 23,000

Estimated no of JSY beneficiaries (70% of live birth)					:16,100

Estimated Institutional Beneficiaries (84% of JSY beneficiaries)		 		:13,524

Estimated Home Deliveries for BPL mothers including NMBS beneficiaries

(16% of Live birth)									: 2,576

Institutional deliveries out of beneficiaries

Rural (estimated 65%)								: 8790

Urban (estimated 35%)								: 4734

District Wise Estimated number of JSY beneficiaries

| District | Number of expected JSY beneficiaries |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aizawl West | Aizawl East | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Institution | 4200 | 2300 | 1600 | 812 | 763 | 2018 | 651 | 503 | 677 | 13524 |
| Home | 202 | 189 | 294 | 266 | 390 | 320 | 350 | 300 | 265 | 2576 |
| Total | 4402 | 2489 | 1894 | 1078 | 1153 | 2338 | 1001 | 803 | 942 | 16100 |

For budget estimate, please refer to relevant section.

NMBS

| I | II | III | IV | Total |
| --- | --- | --- | --- | --- |
| 300 | 300 | 300 | 300 | 1200 |

In compliance with the Hon’ble Supreme Court order dated 20th November, 2007 in the W.P. (C) No. 196 of 2001 (PUCL vs Union of India & others) National maternity Benefit Scheme (NMBS) will also be implemented for BPL pregnant women @ Rs 500/- per birth. They will receive NMBS money from the 3rd order of birth and the expenditure will be borne from JSY funds. The above calculation of home deliveries includes NMBS beneficiaries.

Quarter wise physical targets are as below:

Annexure A-III

| Institutional Deliveries in both Public and Private Institution |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Facility | Total number of estimated deliveries in the State in current FY (2011-12) | Total No. of deliveries Conducted in current month (Nov, 2011) | Cumulative No. of deliveries Conducted in Fy. Year (April, 2011- to current month) | No of C-sections Conducted in the current month (Nov, 2011) | Cumulative No. of C- sections Conducted in Fy. Year (April – Nov , 2011) | No. of Maternal Deaths Reported in Fy. Year (April, 2011- to current month) |
| Public Health Facilities | 16100 | 1,342 | 10,230 | 104 | 809 | 6 |
| Private Accredited Health Facilities | 3430 | 226 | 1,953 | 53 | 412 | 2 |
| Other Private Health Facilities | NA | NA | NA | NA | NA | 2 |
| TOTAL | 19530 | 1,568 | 12,031 | 157 | 1,221 | 10 |

Quality of Delivery Service

ANC, INC, PNC

| ANC (State HMIS April – November, 2011) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Total no. of pregnant women Registered for ANC | 3935 | 3,059 | 2307 | 1,555 | 1,689 | 2,080 | 1,266 | 1,088 | 974 | 17953 |
| No. registered within first trimester | 2,589 | 1,524 | 1646 | 1,082 | 642 | 894 | 653 | 554 | 571 | 10155 |

Activities:

- Counseling of newly married couples by ANMs & ASHAs for early registration

- Pregnancy test kit has been provided to ANMs & ASHAs for early diagnosis of pregnancy.

- Observing Village Health and Nutrition day as per GOI guidelines in all the Anganwadi Centres. Regular monitoring of VHND by Medical Officer I/C

- Tracking of pregnant mothers as per guidelines by ANMs & ASHAs up to 48 hrs after delivery. Monitoring of such activities is to be done regularly and budget kept under Monitoring.

- Incentive is proposed to be given to ASHAs for tracking of Mothers who avail private facilities @ Rs 50/- per case. Incentives will be given after 42 days of delivery

- Various services like

Urine test for albumin and sugar

Blood Hemoglobin test

Abdominal examination,

Blood Pressure Measurement

TT injection

Provision of IFA Tablets

Hemoglobinometer and N/10 is proposed to be procured and supplied to all Sub-Centres The HW/ANM posted in the Sub Centres will be trained at the nearest PHC in the use of hemoglobinometer. It has been suggested that RKS funds be used for the purchase of these materials, however many sub-centres do not have a hemoglobinometer till date. Therefore, procurement and distribution of these materials is proposed.

| INC (State HMIS) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Deliveries conducted at Public Institutions | 738 | 3797 | 1426 | 794 | 591 | 1049 | 558 | 625 | 652 | 10230 |
| No. of Deliveries at acctd Pvt Institutions | 1,293 | 137 | 0 | 0 | 152 | 371 | 0 | 0 | 0 | 1953 |
| Total no of institutional Deliveries | 2031 | 3934 | 1426 | 794 | 743 | 1420 | 558 | 625 | 652 | 12183 |

| Post Natal Care (April to November, 2011) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District | Aizawl E | Aizawl W | Champhai | Kolasib | Lawngtlai | Lunglei | Mamit | Saiha | Serchhip | Total |
| Total no of deliveries | 2200 | 4010 | 1660 | 989 | 1332 | 1822 | 931 | 970 | 738 | 14652 |
| Women receiving post partum check-up within 48 hours after delivery | 1157 | 3831 | 1013 | 877 | 748 | 1499 | 624 | 810 | 748 | 10952 |
| Women getting a post partum check up between 48 hours and 14 days | 2897 | 1931 | 1206 | 837 | 446 | 1358 | 391 | 245 | 393 | 9708 |
| PNC maternal complications attended | 11 | 0 | 3 | 0 | 6 | 0 | 15 | 0 | 5 | 40 |

Free and Cashless delivery under JSSK program is being implemented in the state. JSY is also implemented in all Government Health Facilities and 10 Private Hospitals have been accredited under JSY. (The names of the Private Facilities have been mentioned under JSY)

It may be mentioned that 106 sub-Centres are now capable and conducting deliveries. However only 37 of these can be classified as ‘Functional Delivery Points/delivery points as per GOI norms’ (kindly see list of Functional Delivery Points given before)

48 Hours Post delivery Stay: In some Hospitals in the State, most notably Civil Hospital, Aizawl, there is an acute shortage of beds. At a delivery rate of 350-450 per month and there are 21 beds. Due to this, most mothers are unable to stay for 48 hours after delivery. A new building for Obs & Gynae is being constructed, which is expected to be complete soon and will alleviate the situation.

In order to reduce delivery load of Civil Hospital Aizawl other Health facilities in Aizawl city will be promoted. The delivery load at the other Hospitals on the outskirts of the city namely, Kulikawn SDH, Falkawn Hospital, Ramhlun UHC, ITI UHC, Chawlhhmun UHC and Hlimen UHC is very low compared to Civil hospital Aizawl. IEC activities to increase the delivery loads could alleviate Civil Hospital Aizawl and the performance of post delivery 48 hours stay may increase substantially. Moreover, Post natal kits is not given at Civil Hospital, Aizawl and only those mothers who stay for 48 hours after delivery are given post natal kits.

Post natal kits to be given to mothers for institutional deliveries has been implemented since August 2010. It has been found to be effective and is proposed to be continued during 2012-13. The post natal kit worth is Rs 300/- per kit and will be distributed to the mothers in kind such as baby blanket/mosquito net/diaper etc. if they deliver in the health institutions. This will be in addition to other benefits like JSY, JSSK etc.

Budget under part B

Annexure A-IV

| Key Performance Indicators (KPIs) for Maternal Health( District Compiled Sheet) |  |  |
| --- | --- | --- |
|  | Estimated No. of Pregnancies in the year 2011-12 | 23,500 |
|  | Estimated No. of Deliveries in the year 2011-12 | 23,000 |
| S. N. | Key Performance Indicators for Maternal Health | Cumulative achievement for the current Fin. Yr.( April-November 2011 ) |
| 1 | Total No. of Registered pregnancies | 17,953 |
|  | Pregnancies registered within 12 weeks | 10,155 |
| 2 | Deliveries conducted at Institution | 12,183 |
|  | Public | 10,230 |
|  | Private | 1,953 |
| 3 | Total No of C-section | 1,221 |
|  | Public | 809 |
|  | Private | 412 |
| 4 | Tracking of severe Anaemia |  |
|  | Total No. of PW detected with Hb level below 7 gm | 56 |
| 5 | Total No. of Maternal Deaths | 10 |
|  | Public | 6 |
|  | Private | 2 |
|  | Home | 2 |

Mother and Child Health Card and Safe Motherhood Booklet

Safe Motherhood Booklet has been translated into the local language and will be supplied to all sub centres to be given along with MCP card after prior sensitization workshop and will be rolled out in the  1st quarter 2012-13

Availability of HR and Capacity Building

| Availability of District-Wise Human Resource in the State – Annexure A-V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of Posting and performance of EmOC trained doctor; Posting and performance of LSAS trained doctor. District; Name; Facility where posted; Performance; Name; Facility where posted; Performance. Aizawl West; Dr.Jeremy Vanramenga Pachuau; Civil Hospital, Aizawl FRU; Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly; Dr. Fabiola Kharkongar; Kulikawn SDH, Sub District Hospital; Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly. Aizawl East; Dr. J. Zolawmzuala; Saitual CHC, Community Health Centre; Dr. Lucy Lalsangpuii; Saitual CHC, Community Health Centre. Dr. Lalmalsawmi Khawlhring; Ramhlun UHC, Urban Health Centre. Champhai; Dr. Lalramengi (currently in training); Champhai DH District Hospital. Kolasib; Dr. C. Laldinpuii; Vairengte CHC, Community Health Centre; Dr. C. Lalrinchhana; Vairengte CHC Community Health Centre. Dr. Ramdinthari; Kawnpui PHC, Primary Health Centre. Lawngtlai; Dr. Vanlallawma Khiangte; Chawngte CHC, Community Health Centre; Dr. Lalrinfela; Lawngtlai DH, District Hospital. Lunglei; Dr. James Lalzuitluanga; Tlabung SDH, Sub District Hospital; Dr. Lalrengpuii Ralte; Hnahthial CHC, Community Health Centre. Dr. Isaac Lallawmsanga; Buarpui PHC, Primary Health Centre. Dr. Benjamin Malsawmtluanga; Bunghmun PHC, Primary Health Centre. Mamit; Dr. Freddie Lalrintluanga Chhangte; Kawrthah CHC, Community Health Centre; Dr. Saitluanga Sailo; Kawrthah CHC, Community Health Centre. Serhhip; Dr. Remlalnghaki; Thenzawl CHC, Community Health Centre; Dr. Christopher L Hmar; Thenzawl CHC, Community Health Centre. Saiha; Dr. Vabeilysa; Saiha District Hospital, FRU; CS done at an average of 15 per month. District | Availability(in position) of Specialist/PGMO, MO, and other Staff ( Give total Numbers available in the district) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Paediatrics |  | Anaesthetics |  | Gynaecology |  | No. of MO s | No of SNs | No of ANM s | MOs trained in LS AS | Mos trained in EmOC | No. of SBA Trained SNs/ ANMs | No. of LTs |
|  |  | Regul ar | Contra ctual | Regul ar | Con tract ual | Regul ar | Con tract ual |  |  |  |  |  |  |  |
| 1 | Aizawl East | - | - | - | - | - | - | 11 | 50 | 113 | 1 | 2 | SN -19 HW-13 | 7 |
| 2 | Aizawl West | 5 | 1 | 9 | 1 | 9 | 1 | 24 | 340 | 155 | 1 | 1 | SN-24 HW-21 | 23 |
| 3 | Champhai | - | - | 1 | - | - | - | 19 | 67 | 87 | -- | 1 (under training) | SN-10 HW-18 | 19 |
| 4 | Kolasib | - | - | 1 | - | 1 | - | 5 | 47 | 40 | 2 | 1(under training) | SN-13 HW-5 | 14 |
| 5 | Lawngtlai | 1 | - | - | - | - | - | 4 | 22 | 22 | 1 | 1 | SN-6 HW-11 | 8 |
| 6 | Lunglei | 1 | - | 1 | - | 1 | - | 23 | 170 | 105 | 3 | 1 | SN-28 HW-19 | 19 |
| 7 | Mamit | - | - | - | - | 1 | - | 13 | 35 | 25 | 1 | 1 | SN-8 HW-7 | 12 |
| 8 | Saiha | 1 | - | - | 1 | - | - | 8 | 20 | 32 | - | 1 | SN-7 HW-18 | 8 |
| 9 | Serchhip | 1 | - | - | 1 | 1 | - | 10 | 51 | 61 | 1 | 1 | SN-8 HW-7 | 1 |

Annexure A VI

| Posting and performance of EmOC trained doctor |  |  |  | Posting and performance of LSAS trained doctor |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| District | Name | Facility where posted | Performance | Name | Facility where posted | Performance |
| Aizawl West | Dr.Jeremy Vanramenga Pachuau | Civil Hospital, Aizawl FRU | Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly | Dr. Fabiola Kharkongar | Kulikawn SDH, Sub District Hospital | Procurement of necessary instrumentsfor Caesarean Section and Anaesthesia underway. Output is expected shortly |
| Aizawl East | Dr. J. Zolawmzuala | Saitual CHC, Community Health Centre |  | Dr. Lucy Lalsangpuii | Saitual CHC, Community Health Centre |  |
|  | Dr. Lalmalsawmi Khawlhring | Ramhlun UHC, Urban Health Centre |  |  |  |  |
| Champhai | Dr. Lalramengi (currently in training) | Champhai DH District Hospital |  |  |  |  |
| Kolasib | Dr. C. Laldinpuii | Vairengte CHC, Community Health Centre |  | Dr. C. Lalrinchhana | Vairengte CHC Community Health Centre |  |
|  |  |  |  | Dr. Ramdinthari | Kawnpui PHC, Primary Health Centre |  |
| Lawngtlai | Dr. Vanlallawma Khiangte | Chawngte CHC, Community Health Centre |  | Dr. Lalrinfela | Lawngtlai DH, District Hospital |  |
| Lunglei | Dr. James Lalzuitluanga | Tlabung SDH, Sub District Hospital |  | Dr. Lalrengpuii Ralte | Hnahthial CHC, Community Health Centre |  |
|  |  |  |  | Dr. Isaac Lallawmsanga | Buarpui PHC, Primary Health Centre |  |
|  |  |  |  | Dr. Benjamin Malsawmtluanga | Bunghmun PHC, Primary Health Centre |  |
| Mamit | Dr. Freddie Lalrintluanga Chhangte | Kawrthah CHC, Community Health Centre |  | Dr. Saitluanga Sailo | Kawrthah CHC, Community Health Centre |  |
| Serhhip | Dr. Remlalnghaki | Thenzawl CHC, Community Health Centre |  | Dr. Christopher L Hmar | Thenzawl CHC, Community Health Centre |  |
| Saiha | Dr. Vabeilysa | Saiha District Hospital, FRU | CS done at an average of 15 per month |  |  |  |
|  | Dr. Sangzuala | Went for further studies |  | Dr. Lalmuankimi | Went for further studies |  |
|  |  |  |  | Dr. Robert Lalfakzuala |  |  |

Maternal Health Trainings

- LSAS and EmOC Trainings:

The State has one II TIER training centre at Civil Hospital, Aizawl. There  There 2 trainers each for LSAS and EmOC Trainings. Training duration is of 4 weeks for LSAS and 9 weeks for EmOC at the State. The State Training Centre will be visited before training is conducted with a checklist to ensure functionality as per accreditation.

- BEmOC Training

BEmOC training is conducted at Civil Hospital, Aizawl. The State has 3 Trainers and the batch size is 2, with a training duration of 10 days. The training is given to doctors posted in PHCs with preference given to those posted in the High focus Districts and Functional Delivery Points.

- SBA Training

The State has 4 SBA Training Centres at

| Sl no | Training Centre | Batch Size |
| --- | --- | --- |
| 1 | Civil Hospital, Aizawl | 5 |
| 2 | Lunglei District Hospital | 2 |
| 3 | Kolasib District Hospital | 1 |
| 4 | Christian Hospital, Serkawn | 1 |

Training is conducted for ANMs and SNs with training duration of 21 days. The batch sizes are kept in accordance to the no. of deliveries conducted by the Training institution per month.

Re-accreditation of training centers is planned during the first two weeks of April, 2012, The Training centers will be checked every quarter to ensure functionality as per accreditation.

Note : The state could not achieve as per the Training plan for 2011-12 as there were unavoidable gaps where the Trainers took leave for various reasons and due to lack of funds.

d. Blood Storage Centre & Training

Taken up by Mizoram SACS in the State

e. MTP Training

The State has one II TIER training centre at Civil Hospital, Aizawl. There are 2 trainers and duration of 12 working days. The Training Centre will be visited and checked prior to every training to ensure functioning as per accreditation.

CAG guidelines will be made available at all Public Health Institutions dispensing this service.

f. RTI/STI Training

The State has 8 Training Centres at all the District Hospitals. Refresher Training for District Trainers is planned this year who in turn will train all untrained Medical Officers and Staff Nurses in all the districts.

| Progress of MH Trainings Annexure A VII |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Training | No. of Medical Colleges conducting training | No. of District Hospitals conducting training | Any other Facilities conducting training | No. of Master Trainers Trained | Target for NR HM period (up to 2012 ) | Achievement cumulative till March 2011 | Target for 2011- 12 | Achievement or Nos. trained in 2011- 12 (April 11-till December, 2011) * | Target for 2012- 13 | No. of trained MOs posted at facilities where their skills are being utilised - e.g. FRUs for LSAS & EmOC/ MTP; 24X7 PHCs for BeMOC/M TP; Facilities conducting delivery for SBA in the relevant column | Performance (Specify No. of deliveries, No. of C- section and No. of Spinal Anaesthesia, No. of MTPs, No. of any other complications attended in the relevant column) Cumulative since 2005 till date |
| LSAS | - | 1 (II TIER) | - | - | 11 | 12 | 2 | - | - | - | NA |
| EmOC | - | 1 (II TIER) | - | 2 | 10 | 4 | 6 | 5 | 2 | 1 | NA |
| BEmOC | - | 1 | - | 3 | 16 | - | 16 | 2 | 20 | 2 | NA |
| SBA | - | 3 | 1 | 20 (17 state trained) | SN-315 ANM-333 | SN-118 ANM-69 | SN-60 ANM-110 | SN-16 ANM-48 | SN-68 ANM-32 | NA | NA |
| MTP | - | 1 | - | 2 | MTP-90 | 79 | 4 | 2 | 6 | NA | NA |
| RTI/STI | - | 8 | - | 16 | MO-90 | MO-46 HW-770 | ANM-60 | - | MO-30 SN-90 | NA | NA |

Supervision, Monitoring and Quality Assurance.

The guidelines for QAC structure as per the guidelines for PIP cannot be followed in a small state like Mizoram due to lack of manpower. QAC cell which is already present at the State and District levels will be strengthened instead.

Timely review of RCH/NRHM Program activities should be carried out. The quality of HMIS at the State and Districts has seen an improvement. However, Data analysis and review of the program at the PHC level is not satisfactory. The PHC / CHC Health committee monitors the performance of SC under their jurisdiction and will submit the report. The PHC/ CHC health committee will monitor and evaluate the SC performance which will be submitted to the District, where it will be compiled and sent to the state. Tracking of pregnant mothers and Children will be done which will be monitored by State/District and concerned CHC/PHC.

Monitoring from State Level:

State level monitoring team was already constituted in 2010-11 under the chairmanship of Mission Director. The team consists of Program Officers of various vertical programs under NRHM, MIS Manager/ Consultant, Finance consultant Accounts Manager, Data Manager.

The Team will meet once in a month (date to be fixed), and ensure the dissemination of guidelines and manuals etc. Protocols for treatments will be adapted and disseminated to all Health facilities. The team will review and make suggestions on all maternal and Infant Death reports in the State, and monitor Accredited Private Health facilities to ensure implementation of national standards. The team will carry prescribed checklist for monitoring and submit the detail report to the State Mission Director. A copy of the monitoring report will be sent to each district with feedback and suggestion of improvement. Quarterly review meeting will be held at the State and District level. A proper record of all the findings and the actions taken will be kept.

Monitoring from District Level:

A District Level Joint Monitoring Team was already formed in 2010-11 to monitor various programs under NRHM in their respective district will be strengthened.

The team is headed by Chief Medical Officer of the respective districts and other team members consist of District Immunization Officer, District Program Manager, District Accounts Manager, District Data Manager etc. The team will carry prescribed checklist for monitoring and submit the detail report to the District Health Society meeting with a copy to the Mission Director. A copy of the monitoring report will be send to each CHC/PHC with feedback and suggestion for improvement. The feedback will be discussed at the CHC/PHC level during monthly meeting and corrective measures will be taken.

It will also review all cases of Maternal and Infant Deaths in the District, and submit the reports to the State. It will review all PHFs and ensure their functioning as per national standards. It will be involved in the review of all trainings and their implementation and other community and facility based interventions etc. QAC visits to facilities and report and discussion of these findings at all the monthly meetings. The District team will report to the State Monitoring and QAC team and pursue the State authorities for follow up.

A proper record of the findings and actions taken will be kept.

7. Integrated Outreach Camps

4 camps each has been proposed for 3 HF district

Detailed Budget for conducting one outreach camp

| Particulars | Amount in Rupees |
| --- | --- |
| Manpower: Gynaecologist Paediatrician Medical Officer Other Staff | 1,000/- 1,000/- 8,00/- 1,200/- Total : 4,000/- |
| Publicity Banner Sound System Local IEC requirements | 2,500/- |
| Camp arrangement Layout of services Generators Tents/ hiring Chairs | 4,000/- |
| Transport POL for specialists, Medical Officers, District Officers etc | 2,000 |
| Drugs & other Consumables | 5,000 |
| Contingency | 2,500 |
| TOTAL | 20,000 |

B. VHNDs

Village Health and Nutrition day is to be held at each Anganwadi Centers in each month. There are 1682 Anganwadi centres in the state. However, in some places, there are more than 5 Anganwadi Centres under the care of a single Health worker and cannot attend each and every VHND.

8. Maternal Death Review

Audit of maternal death as per GOI guidelines which will be review at State and District level. Incentive to ASHAs for death report @ Rs. 50/-, Incentive to 3 ANM/Staff Nurses etc for Field verification of maternal death @ Rs. 100/-, Incentive to 2 deceased family @ Rs. 200/- (Total incentive = Rs. 750/- per case) During 2011-12 till November maternal death report is only 10 numbers. It is therefore estimated that maternal death for the coming year is not more than 20. Also audit of child death will be reviewed at State and District level. Incentives to ASHA, audit team and deceased family will be given as per MH guidelines. Estimated of infant death is 650 nos and budgeted under Maternal Health.

The same incentive has also been proposed for Child Deaths.

Annexure A-IX

REPORTING FORMAT TO ASCERTAIN THE STATUS OF IMPLEMENTATION

Name of State: Mizoram

| SN. | Activity |  | Status / Remarks |
| --- | --- | --- | --- |
| 1 | Name, contact no. and e-mail address of State Nodal Officer for MDR | Dr. R. Lalthanga State Program Officer, RCH 0389 2328045 nrhmmizoram@yahoo.com |  |
| 2 | Number of medical/paramedical personnel trained or oriented on MDR | Medical College faculty | - |
|  |  | State officials (Directorate. SPMU, etc.) | All State program Officers |
|  |  | District Officials (CMO, DRCHO, DPMU, others) | 18 |
|  |  | Others including I/Cs of private hospitals | 2 |
|  |  | Block Officials (BMOs, BPMU, etc.) | - |
|  |  | MO I/Cs of public health facilities | 66 |
|  |  | ASHAs/ AWWs/ ANMs/ SHGs/ others | - |
| 3 | Constitution of Maternal Death Review Committee / Task Force as per GOI guidelines { Give no. at each level} | State Task Force (Yes/No) | Yes |
|  |  | Number of districts in the State | 9 |
|  |  | Number of districts where MDR Committee has been constituted) | 9 |
|  |  | Total number of health facilities (FRUs, DHs, private accredited hospitals) identified for FBMDR | 10 |
|  |  | Number of health facilities where FBMDR Committees has been constituted | Govt. order has been issued and is under process |
| 5 | Total number of MDs reported at the State level (April to the reporting month,2011-12) | Through CBMDR (Community Based MDR) | 10 |
|  |  | Through FBMDR (Facility Based MDR) | 0 |
| 6 | Total number of MDs reviewed by District MDR committees (CMO) (April to the reporting month, 2011-12) |  | 8 |
| 7. | Number of MDs reviewed by State Task Force out of total reported in column 4 |  | 8 |
| 8 | Causes of maternal deaths reported in column 4 (in numbers) |  |  |
| 8.1 | Haemorrhage |  | 2 |
| 8.2 | Sepsis |  | 3 |
| 8.3 | Abortion |  | - |
| 8.4 | Obstructed labour |  | - |
| 8.5 | Hypertensive disorders in pregnancy (includes eclampsia) |  | 2 |
| 8.6 | “Others” (include anaemia) |  | Uterine rupture-1 Retained placenta-1 others-1 |
| 9 | Analysis of MDR findings done by the State e.g. major causes of MDs (medical/systemic/others), geographical distribution- concentration in specific districts/blocks, whether conforming to the AHS High Mortality districts etc. | NA |  |
| 10 | Compliance with submission of State Monthly MDR Reports for April to the reporting month (2011-12); reasons for non- compliance. | - |  |

9. Comprehensive Abortion Care

Annexure A-X

Format for Performance on Comprehensive Abortion Care at State Level (April-September 2011)

Name of State/U.T:  Mizoram	          Number of districts in the State:  9

| SN | Indicator |  | Numbers |
| --- | --- | --- | --- |
| 1 | Number of districts where District Level Committee (DLC)* has not been constituted |  | 0 |
| 2 | Number of applications pending in the districts with the DLCs | For one year | - |
|  |  | More than one year | - |
| 3 | Is MVA equipment being procured and supplied to the districts? (Y/N) |  | None in the current year Supplied in 2009-10 |
| 4 | Are the drugs for MMA included in the essential drug list? (Y/N) |  | None in the current year |

1)	Indicators:

* As per MTP Act, Rules and Regulations 2002-2003

2)  Service Availability and Utilisation:

| Availability: Number of institutions providing services |  |  |  |  | Utilisation: Number of MTPs performed-any method |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Health Facility | Up to 12 weeks services | Up to 20 weeks services |  |  | Up to 12 weeks | 12 -20 weeks |
| Government (Total) | 61 | 8 |  |  | 239 | 20 |
| Private certified (Total) | - | - |  |  | - | - |
| “Delivery Points” providing services. |  |  |  |  |  |  |
| PHCs/non FRU CHCs | 24 | - |  |  | Data not available |  |
| FRUs (CHCs, SDH etc.) | 4 | - |  |  |  |  |
| DHs /DWH etc. | 8 | 8 |  |  |  |  |
| Medical Colleges | - | - |  |  |  |  |
| Private certified | - | - |  |  |  |  |

3)  Does the State have an IEC/BCC plan for MTP Services(Y/N) No

If yes, please indicate frequency/ periodicity of IEC/BCC activities

| SN | IEC/BCC Activity | Frequency/ periodicity |
| --- | --- | --- |
| 1 | Print | - |
| 2 | Audio | - |
| 3 | Video | - |
| 4 | Any Other (specify) | - |

Proposed Budget 2012-13:

| Area | Budget Head & Activity code | Unit Cost | Budget proposed in PIP 2012-13 |
| --- | --- | --- | --- |
| MMA Drugs | - | - | - |
| MVA/ EVA Equipments | - | - | - |
| MTP-Training MOs | - | 46,000/- | 2,30,000/- |
| MTP training of other field functionaries (counselling and post abortion care) | - | - | - |
| MTP-IEC/BCC activities | - | - | - |
| MTP: Monitoring and Supevision | Budgeted under Monitoring and supervision |  |  |

10. RTI/STI Services

STATUS OF STI/RTI SERVICES DELIVERY IN THE STATE

1.   Allocation of fund for STI/RTI services in the PIP:

Fund Allocated for the STI/RTI services in 2011-12:

| Activities | Fund allocated in the PIP (in Lacs) | Expenditure till date (inLacs) |
| --- | --- | --- |
| Training of ANMs (Training cost, printing of module, stationary, venue etc) | 1.19 | - |
| Monitoring and supervision of the facilities | - | - |
| Upgrading of infrastructure of the facilities (audio-visual privacy, examination facilities, speculum, gloves etc) | - | - |
| RPR test Kits | - | - |
| Colour coded STI/RTI drug kits | - | - |
| Total Budget in PIP | 1.19 | - |

- Coordination Meetings:

No coordination meeting has been organised yet in the current year regarding RTI/STI.

3.   Training:

a.   Training of the District Level trainer including District RCH Officer:

Training for District level trainer and training for 2 batches of Medical officer have been conducted at State level as well as 1 batch for MO at Lunglei district in the previous year. Orientation Training for Health workers have also been conducted in all the districts in collaboration with MSACS. 90% of the Laboratory Technicians have been trained in the State.

b.   Training of the Sub-district level Health Facilities staffs:

30 Medical Officers (remaining untrained) and 90 Staff Nurses covering all the sub-district level health facilities  are planned to be trained in the coming year.

Training Status of Sub-District Level Staffs:

| Cadre | Targe tfor 2011- 2012) | Cumulative Achievement (Since inception -till date) | Proposed numbers to be trained in 2012-13 | Timeline 2012-2013 (specify the number of providers to be trained in each quarter) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| MO | - | 46 | 30 | 30 |  |  |  |
| SN | - | - | 90 |  | 30 | 30 | 30 |
| ANM | - |  |  |  |  |  |  |

- Supply of STI/RTI colour Coded Drug Kits:

Colour coded drug kits have not been procured or distributed by the state. However, drugs (not colour coded) for RTI/STI have been procured and distributed along with the other essential drugs and supplied to each district.

4.   Implementation of STI/RTI Service Delivery:

Has the service delivery started at the sub district health facilities?

| Name of the District | Service Delivery Started (Yes/NO) | If No, Reasons why the Services have not started | Time Line when the Service will start |
| --- | --- | --- | --- |
| Aizawl East | Yes | - | - |
| Aizawl West | Yes | - | - |
| Champhai | Yes | - | - |
| Kolasib | Yes | - | - |
| Lawngtlai | Yes | - | - |
| Lunglei | Yes | - | - |
| Mamit | Yes | - | - |
| Saiha | Yes | - | - |
| Serchhip | Yes | - | - |

6.   Reporting Status on STI/RTI:

| Name of the district | Is this district reporting in HMIS/SIMS on STI/RTI (M-8, a,b column) | If not what is the reason and when the reporting will start |
| --- | --- | --- |
| Aizawl East | Yes | - |
| Aizawl West | Yes | - |
| Champhai | Yes | - |
| Kolasib | Yes | - |
| Lawngtlai | Yes | - |
| Lunglei | Yes | - |
| Mamit | Yes | - |
| Saiha | Yes | - |
| Serchhip | Yes | - |

7.   Monitoring of Services:

Has the each of the District has nodal person for STI/RTI (i.e RCH Officer)?

Number of monitoring visit conducted by the State and District level team for Service

Implementation:

| State /District Team | Number of Visit made to the District for program Implementation | Number of District Visited | Number of Sub-district health Facilities Visited |
| --- | --- | --- | --- |
| State RCH Officer/MH Officer | 4 trips | 9 | 25 PHC/CHC 70 SC |
| SPMU | 4 trips | 9 | 25 PHC/CHC 70 SC |
| District RCH Officer/ADMO in- charge of RCH Programme | 5 trips |  | 9 CHC, 57 PHC 360 SC |
| DPMU | 5 trips |  | 9 CHC, 57 PHC 360 SC |

11.Free Entitlements under JSSK

Government order for implementing JSSK has been issued, guidelines for implementing JSSK has also been disseminated to all districts. It can be started as soon as funds are received. Activities and budget has been worked out as follows:

| Activity | No of Expected Beneficiaries | Rate (Rs/Head) | Amount Proposed (in lakhs) | Remarks |
| --- | --- | --- | --- | --- |
| Referral Transport for PW and Sick Newborns |  |  |  |  |
| Transport from Motarable home to nearest Institutions and back on motorable roads (total mean distance of 40 km) @ Rs 20/km for mothers and sick newborns | 23500 mothers & 2350 sick newborns Total=25850 | 800.00 | 206.80 | Referral transport from Home to Facility @ Rs 20km taking into consideration difficult terrain per beneficiary i.e Rs.800/- per beneficiary. No of expected beneficiaries has been worked out for mothers and sick newborns and budget under Maternal Health components as per Child Health guidelines |
| Transport from Facility to Facility and Facility to Home for referred cases | 2350 | - | - | As per comment given by GOI in the approval of JSSK plan 2011-12, transport from Facility to facility is to be taken care by the state through its own ambulances. |
| Sub Total |  |  | 206.80 |  |
| Drugs & Consumables |  |  |  |  |
| Drugs and Consumables for Normal delivery | 21150 | 500 | 105.75 | Drugs and consumables estimated as per average local rate i.e Rs 500/- per delivery. |
| Drugs and Consumables including Blood Transfusions for C-section including high risk cases i.e 10% of total delivery | 2350 | 2500.00 | 58.75 | Estimated that total average cost for C-section is per local rate i.e rs.2,500/- |
| Drugs and Consumables including Blood Transfusions for Sick New born, Treatment etc | 2350 | 1000.00 | 23.50 | Budget has been calculated as per child health guidelines and budget will cover treatment, drugs, consumable etc and budget under child health. |
| Sub Total |  |  | 188.00 |  |
| Laboratory Expenses |  |  |  |  |
| Laboratory Expenses for Normal delivery | 21150 | 200.00 | 42.30 |  |
| Laboratory Expenses for C-Section including high risk cases | 2350 | 300.00 | 7.05 | Budget has been calculated @ Rs.300/- as per average rate in the state |
| Sub Total |  |  | 49.35 |  |
| Diet |  |  |  |  |
| Diet for Normal delivery for 3 days | 21150 | 100 per day i.e Rs300/- beneficiary | 63.45 | Budget has been calculated as approved for 2011-12 |
| Diet for C-Section including high risk case for 7 days | 2350 | 100 per day i.e Rs700/- beneficiary | 16.45 | Budget has been calculated as approved for 2011-12 |
| Sub Total |  |  | 79.90 |  |
| Grand Total |  |  | 524.05 |  |

12. Incentives under Maternal Health

| Incentives for | Reason for giving incentive | Amount/case (in rupees) |
| --- | --- | --- |
| ASHA | Community based Maternal Death Review | 50 |
|  | Janani Suraksha Yojana for complete ANC and institutional dleivery | Urban – 200 Rural - 600 |
| ANM/ SN | Community based Maternal Death Review | 100 |
| Deceased family | Community based Maternal Death Review | 200 |

II.CHILD HEALTH

GOAL: To reduce IMR from 37 (SRS 2010) to 18 by 2016-17

In order to achieve the target set for for the next 5 years various activities such as relocation of staff, up gradation of health facilities, training of health providers, IEC/BCC activities, outreach services, Child Death Review and monitoring will be emphasized. Priority will be given to low performing districts namely Saiha, Lawngtlai and Mamit districts.

.    Estimated Child Population (of the State/UT)

23000

Estimated live births per year

Estimated number of children under 5 years

1,42,665

2.    Situation Analysis (STATE/UT)

| Child Mortality | SRS 2007 | SRS 2008 | SRS 2009 | SRS 2010 | Trend Analysis |
| --- | --- | --- | --- | --- | --- |
| Neo Natal Mortality Rate (State HMIS) | - | - | 3 | 6 | Increasing trend |
| Infant Mortality Rate | 23 | 37 | 36 | 37 | Slight Increasing trend |
| Under Five Mortality (State HMIS) | 6 | 6 | 6 | 6 | Constant |

| Nutrition | NFHS 3 | CES* 2009 |
| --- | --- | --- |
| % of children age 6-35 months who are anaemia | 51.7 | NA |
| % of children (under 3 years) who are underweight | 21.6 | NA |
| % of children (under 3 years) who are severely wasted /SAM (< -3SD) | 9.2 | NA |

*Coverage Evaluation Survey

| Infant & Young Child Feeding | NFHS 3 | DLHS 3 | CES 2009 |
| --- | --- | --- | --- |
| Children age 6 months and above exclusively breastfed | 15.40 | 29.1 | 36.6 |

| Diarrhoea & ARI | NFHS 3 | DLHS 3 | CES 2009 |
| --- | --- | --- | --- |
| Children with Diarrhoea in the last 2 weeks who received ORS | 51.2 | 55.5 | 60.8 |
| Children with ARI or fever in the last 2 weeks who were given treatment at facilities. | 50.1 | 56 | 87.6 |
| itamin A Supplementation | NFHS 3 | DLHS 3 | CES 2009 |
| Percentage of children (age 9 months and above) received at least one dose of Vitamin A supplement | 42.2 | 75.5 | 65.4 |

|  | Newborn Care |  | Source : |
| --- | --- | --- | --- |
|  | Percentage of institutional deliveries | 83 | CES |
|  | Percentage of newborns with low birth weight | 4.6 | HMIS |
|  | Percentage of mothers staying for 48 hours at the facility | NA | CES |

3.1 Essential New born Care

At present, there are 71 Delivery Points (34 DH/SDH/CHC/PHC and 37 sub centres) in Mizoram, out of which 13 Delivery Points have Newborn Care Corners, and 23 Delivery Points have at least 1 health provider trained in NSSK. 21 Newborn Care Corners are proposed to be established and Training of 240 staff nurses and 120 ANMs in NSSK is proposed for 2012-13.

|  | S.No. |  |  |  | Name of the district |  |  | No. of existing delivery points |  |  |  | No. of NBCCs operational |  | NO. of NBCCs at Delivery points |  |  | No. of NBCCs proposed (2012-2013) |  | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | High Focus districts |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Lawngtlai |  |  | 2 |  |  |  | 3 |  |  | 1 |  | 1 |  |  |  |
|  |  |  |  |  | Mamit |  |  | 5 |  |  |  | 3 |  |  | - |  | 5 |  |  |  |
|  |  |  |  |  | Saiha |  |  | 1 |  |  |  | 1 |  |  | - |  | 1 |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Other districts |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Aizawl East |  |  |  | 6 |  |  | 4 |  |  | 4 |  | 2 |  | Proposal for NBCCs is for all Functional Delivery points where NBCC is not yet set up |  |
|  |  |  |  |  | Aizawl West |  |  |  | 3 |  |  | 1 |  |  | 1 |  | 2 |  |  |  |
|  |  |  |  |  | Champhai |  |  |  | 8 |  |  | 4 |  |  | 3 |  | 5 |  |  |  |
|  |  |  |  |  | Kolasib |  |  |  | 3 |  |  | 2 |  |  | 2 |  | 1 |  |  |  |
|  |  |  |  |  | Lunglei |  |  |  | 3 |  |  | 2 |  |  | 1 |  | 2 |  |  |  |
|  |  |  |  |  | Serchhip |  |  |  | 3 |  |  | 3 |  |  | 1 |  | 2 |  |  |  |
|  | Total |  |  |  |  |  |  |  | 42 |  |  | 23 |  |  | 13 |  | 21 |  |  |  |

|  | Name of the district |  | Total Units (NBCCs) proposed in 2012-2013 |  | 2012-13 |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 7 |  | 2 |  | 2 |  | 2 |  | 1 |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 14 |  | 4 |  | 4 |  | 3 |  | 3 |  |  |
|  | Total |  | 21 |  | 6 |  | 6 |  | 5 |  | 4 |  |  |

3.2 Care of sick newborn

At present, there is only one SNCU in Mizoram at Aizawl Civil Hospital. This is the only Hospital in Mizoram which qualifies according to the GOI guidelines i.e at least 3000 deliveries per year. It may be mentioned that the guidelines applicable for the big states can in no way be applied to the small states like Mizoram. One SNCU has therefore been proposed to be set up at Lunglei District Hospital during 2012-13 which will provide services to South Mizoram, and the existing SNCU at Civil Hospital, Aizawl will serve thenorthern part of Mizoram.

The state has 2 functioning NBSUs at present at Lunglei District Hospital and Kolasib District Hospital. NBSUs are proposed to be set up at the remaining 5 District Hospitals since manpower is readily available in these institutions.

Re-assessment of SNCU and NBSUs will be done on a 6 monthly basis as per the checklist provided in FBNC operational guidelines by the State and District Officials.

|  | S.No . |  | Name of the district |  | Existing SNCU (Yes/No) |  | If yes, date of operational ization |  | SNCU Proposed for 2012-2013 (Yes/No) |  | Timeline |  |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 |  | Aizawl West |  | Yes |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 |  | Lunglei |  | No |  | - |  | Yes ( 1 No) |  |  |  |  |  |  |  | 1 |  |  |  |
|  | Total |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*Only those units where patients are being admitted should be considered as functional units.

|  | S.No. |  | Name of the district |  | No. of existing NBSUs |  | No. of NBSUs proposed for 2012-13 2013 |  | Timeline |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | High Focus Districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Lawngtlai |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  |  |  | Mamit |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  |  |  | Saiha |  | - |  | 1 |  |  |  | 1 |  |  |  |  |  |  |
|  | Other districts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  | Champhai |  | - |  | 1 |  |  |  |  |  | 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Serchhip |  | - |  | 1 |  |  |  |  |  | 1 |  |  |  |  |
|  |  |  | Kolasib |  | 1 |  | - |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Lunglei |  | 1 |  | - |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  | 2 |  | 5 |  |  |  | 3 |  | 2 |  |  |  |  |

10. JSSK As per guidelines the cost of free drugs, diagnostics, treatment has been worked out and budgeted under Child Health. All other cost like transport has been budgeted under Maternal Health component. Please refer Maternal Health Section

3.3 Home Based New Born Care

As per the Home Based Newborn Care Operational Guidelines, ASHAs will visit homes to provide essential newborn care. All ASHAs in Mizoram have undergone training in Round 1 of module 6 & 7, Home based Newborn Care and will be practiced in full swing in the coming year.

It is proposed to give Incentives to ASHA for home visit . Budget is worked out below:

ASHA Incentive will be given on completion of home visits as per norms

3.4 Promoting IYCF practices

The Dept. of Social Welfare under ICDS is taking up IYCF in the State,. As regards to RCH, Two (2) Lactation Counselors have been appointed at Civil Hospital Aizawl on a pilot basis. They counsel all parents with newborns in the OPD in a separate Lactation Counseling Room, they also provide counseling to Pregnant Women in ANC and to all mothers in the Pre and post natal wards. This practice may be considered to be extended in the High Focus Districts.

IEC – refer to IEC Chapter Part B. of PIP

3.5, 3.6 Micronutrient supplementation and management of Children with malnutrition

Micronutrient Supplementation (Vitamin A and IFA Supplementation) to children 6-60 months and management of children with malnutrition have been taken up by the State Social Welfare Department under ICDS. Hence, No activities have not been planned by the Health Department to avoid duplication.

3.7 Integrated Management of Child hood and Neonatal Illnesses

IMNCI trainings for HWs, have been conducted covering 78% of all the Districts. 127 MOs and 775 Health Workers have been trained till date. . All the remaining untrained HWs will be trained in the coming year. Medical Officers and Staff Nurses are now given F-IMNCI training in lieu of IMNCI training. Trainings for LHVs is not conducted as the state does not have LHVs. All ASHAs in the State have been trained in module 6 & 7 1st round.

Pre service IMNCI has also been included in the syllabus at ANM and Nursing training Schools, namely:

- Health Worker Training School, Aizawl

- Mizoram College of Nursing, Aizawl

- Regional Institute Paramedical and Nursing Sciences, Aizawl

- Nursing School, Lunglei

3.8 Diarrhoea Management and ARI

As per guidelines Diarrhoea Management and ARI is on going activities. Procurement of ORS and Zinc tablets will be done and budgeted under part B. Reorientation  of health providers will be done during child health/ maternal health training and meetings. IEC- BCC activities focusing on hygiene, hand washing, preparation and use of ORS, feeding during a episode of diarrhoea and healthcare seeking behavior will also be taken up. ORS corners may be established in facilities but no separate budget is required.

4. 	Trainings:

Details of Child Health training plan may be seen in the training chapter.  As for supervision of post training, State and District level Monitoring team will take up during field visits. Training status is tabulated below as per prescribed format.

| Achievement in Child Health Training 2011- 2012 | IMNCI |  | F-IMNCI |  | NSSK |  | Total Numb er of ASHA s in the State | ASHA - Modul e 6 & 7 Round One | ASHA - Modul e 6 & 7 Round Two | ASHA - Modul e 6 & 7 Round Three | ASHA - Modul e 6 & 7 Round Three |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Prop osed | Achi eved | Prop osed | Ach ieve d | Pro pose d | Ach ieve d | 987 | Achieved |  |  |  |
| Number of Districts covered | 2 | 1 | 9 |  | 9 |  |  |  |  |  |  |
| AWW | - | - |  |  |  |  |  |  |  |  |  |
| ASHA | - | - |  |  |  |  |  |  |  |  |  |
| ANM | 48 | 49 |  |  |  |  |  |  |  |  |  |
| MPW (M) | - | - |  |  |  |  |  |  |  |  |  |
| LHV | - | - |  |  |  |  |  |  |  |  |  |

| Supervisor (M) | - | - |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | - | - | 36 | - | 480 | 76 |  |  |  |  |  |
| MO | - | - | 48 | 19 | - | - |  |  |  |  |  |
| Others | - | - |  |  |  |  |  |  |  |  |  |
| Total | 48 | 49 | 84 | 19 | 480 | 76 |  |  |  |  |  |

Budgeting for Child Health Trainings should be done under appropriate budget line.

4.1 IMNCI:

The State has at present, 2 active training sites at Saiha District Hospital and Aizawl Civil Hospital. There are 6 Master Trainers in Mizoram.

IMNCI trainings for health Personnel have been conducted covering 78% of all the Districts.

Status of IMNCI trainings

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of batches to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 150 |  | 127 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ANM |  | 1030 |  | 775 |  | 120 (4 batches) |  | 1 |  | 1 |  | 1 |  | 1 |  |  |
|  | LHV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | AWW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4.2 F-IMNCI

At present, training of F-IMNCI is done only at Civil Hospital, Aizawl and the state has 4 Master Trainers (2 state trained).

Medical Officers who have been trained in IMNCI will be trained in F-IMNCI for 5 days. Priority will be given to existing NBSU staff and for those planned for setting up of NBSU

Status of F IMNCI Training

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of providers to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 96 |  | 67 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SN |  | 36 |  | - |  | 144 (12 batch) |  | 3 |  | 3 |  | 3 |  | 3 |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

C. NSSK

The State has one Training Centre at Present at Aizawl Civil Hospital. 4 more District Centres where Paediatricians are in place are planned to be opened in the coming year.

All Health personnel in the Functional Delivery points will be  trained in NSSK with priority given to those already trained in SBA. Steps will be taken to ensure that both SBA and NSSK trained personnel are posted at delivery points.

Status of NSSK training

|  | Cadre |  | Cumulative Target (from inception to March 2012) |  | Cumulative Achievement (Since inception -till date) |  | Proposed numbers to be trained in 2012-13 |  | Timeline 2012-2013 (specify the number of batches to be trained in each quarter) |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MO |  | 120 |  | 87 |  | - |  |  |  |  |  |  |  |  |  |  |
|  | SN |  | 360 |  | 108 |  | 240 |  | 4 |  | 4 |  | 2 |  |  |  |  |
|  | ANM |  | 120 |  | - |  | 120 |  |  |  |  |  | 1 |  | 4 |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

D. ASHA training in module 6 & 7

All ASHAs in the State have been trained in Module 6 & 7 1st round.

Training Plan for ASHA Module 6 and 7

|  | Module 6 and 7 |  | Total training load, 2012- 2013 |  | To be achieved in |  |  |  |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | Round 1 |  |  |  |  |  |  |  |  |  |  |  | Details training plan under Mission Flexi pool |
|  | Round 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Round 3 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Round 4 |  |  |  |  |  |  |  |  |  |  |  |  |

E. Orientation on MCP card:

The MCP Card was translated into the local language and printed. No orientation or training has been conducted yet. MCP card will be used after sensitization workshop under the guidance of DPM and District RCH Officers.

F. Facility Based Management of children with SAM

All nutrition related works are taken up by the Social Welfare Department under ICDS.

G. SNCU training

1.   Training of health service providers posted at SNCU should be undertaken. A 4 days training programme (batch size 24), along with 12 days of Observer ship (batch size 4) at an identified facility is recommended.

2.   National Collaborative Centre at Kalawati Saran Children‟s Hospital (Delhi) and Regional

Collaborative Centre at ICH (Chennai), PGIMER Chandigarh, AMC (Dibrugarh), KEM Mumbai, Maulana Azad Medical College (Delhi) and IPGMER (Kolkata) should be contacted for assistance in training and any support required for newborn care units.

3.   State/UT needs to identify one Medical College in consultation with National/ State Collaborative Centre to coordinate with identified Regional Resource Centre and utilize their services for the purpose of capacity building, mentoring, operational research etc.

|  | SNCU training plan 4 days with batch size 24 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cadre |  | Total training |  | To be achieved in |  | Remarks |

|  |  |  | load 2012- 2013 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MOs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNCU Observer ship 12 days National/ Regional/ State Collaborative Centre batch size 4 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Cadre |  | Total training load 2012- 2013 |  | To be achieved in |  |  |  |  |  |  |  | Remarks |
|  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  |
|  | MOs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SNs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |  |  |  |  |

4. Miscellaneous:

- Dissemination of guidelines. -

FBNC guidelines are to be kept at all Newborn Stabilization Units and Sick Newborn Care Units. Charts given in FBNC guidelines may be adopted as protocol and made into chart books to be kept at all Newborn Stabilization Units and Sick Newborn Care Units etc.

Budget for dissemination of various guidelines refer to…

- Reporting Formats for Newborn Care Units: Orientation and sensitization regard;

- ing the various data collection will take place at the Quarterly review meetings.

- Budget for Quarterly Child Health Review Meeting refer to…

- Separate Strategy Proposal for High Focus Districts –

Saiha : Re-orientation training in IMNCI for ANMs in Saiha District is planned. The district has 55 ANMs who will be re trained in 2 batches at Civil Hospital, Aizawl.

5. Child Health Activities under NRHM

IEC, BCC –Child Health:

- Leaflets, wall writings, TV and Radio spots, endorsement by locally famous persons, short plays etc. Special emphasis to be given regarding sensitization of the community about the danger signs of ARI and Diarrhoea in children.

- Funding given under BCC/IEC

Infrastructure

Equipment

- Radiant Warmers -

- Dummies for F-IMNCI Training – 2

- Dummies for NSSK Training - 30

| 6. Human resources |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The detail of new contractual staff for child health (e.g SNCUs: MOS 4, 10 SNs, 4 support workers, 1 counsellor, 1 data entry operator and 1 part time lab technician), proposed in the PIP, should be specified. Cost should be budgeted under appropriate heads in NRHM |  |  |  |  |  |  |
| S.No. | Name of the district | Personnel to be hired (eg; Specialists, Medical officers, Staff nurses, Data operators, Dieticians, Cooks etc.) | No. of personnel to be hired | Unit cost (Monthly remuneration x no. of months) | FMR code | Remarks (eg. Facility where these personnel will be posted, if the staff is being hired fro NRCs or New born care units) |
| 7 | Budget for Child Health |  |  |  |  |  |
|  | Intervention | Unit cost | Physical targets proposed for 2012-13 | Proposed budget | FMR code | Remarks |
| 1 | Essential Newborn care |  |  |  |  |  |
|  | Cost for New NBCC | 85,000 | 21 | 1785000 |  | Budget under Part B |
|  | Operational cost (existing +new) | 20,000 |  |  |  | To operationalise from state budget |
| 2 | Sick Newborn Care |  |  | 0 |  |  |
|  | One time cost for new SNCUs | 41,00,000 | 1 | 4100000 |  | Budget under Part B |
|  | Operational cost for SNCUs (existing + new) | 10,00,000 | 1 | 1000000 | A.2.2.1 |  |
|  | One time cost for new NBSUs | 5,75,000 | 5 | 2875000 |  | Budget under Part B |
|  | Operational cost for NBSUs (existing + new) | 1,75,000 |  |  |  | To operationalise from state budget |
|  | Janani Shishu Suraksha Karyrakram (JSSK) | 1000 | 2200 | 2350000 | A.2.5.3 | Cost of free diagnostics, drugs, treatment |
|  | Intervention | Unit cost | PhysicalTargets proposed for 2012-2013 | Proposed budget | FMR code | Remarks |
| 3 | Home Based newborn Care |  | births |  |  |  |
|  | ASHA incentives | 250 | 11500 (50% of live birth) | 2875000 |  |  |
|  | Equipments, medications & Consumables for ASHA kit |  |  |  |  |  |
| 4 | Promotion of IYCF |  |  |  |  |  |
|  | Orientation programmes/Trainings |  | SWD |  |  |  |
|  | Other activities |  |  |  |  |  |
| 5 | Micronutrient Supplementation programme |  | SWD |  |  |  |
|  | Vitamin A |  |  |  |  |  |
|  | IFA |  |  |  |  |  |
| 6 | Management of children with SAM |  |  |  |  |  |
|  | One time cost for establishing new NRC | 2,00,000 (Indicative) | SWD |  |  |  |
|  | Operational cost for existing + new NRCs | 7,80,000/ unit/ year (Indicative) | SWD |  |  |  |
| 7 | IMNCI programme |  |  |  |  |  |
|  | Supplies, Logistics, Supportive supervision |  |  |  |  |  |
| 8 | Management of Diarrhoea and ARI |  |  |  |  |  |
| 9 | Trainings (Cost / Batch) |  |  |  |  |  |
|  | IMNCI (TOT) | 2,52,080 |  |  |  |  |
|  | IMNCI (HW) | 2,26,320 |  |  |  | To be planned for ANM, LHV not for AWWs |
|  | F-IMNCI (TOT) | 1,28,800 |  |  |  |  |
|  | F-IMNCI (MO-SN) | 2,83,360 |  |  |  |  |
|  | NSSK (TOT) | 93,840 |  |  |  |  |
|  | NSSK (HW) | 90,160 |  |  |  |  |
|  | Orientation on MCP card |  |  |  |  | Can be budgeted under MH/CH /Trainings |
|  | Facility Based Management of children with SAM |  |  |  |  |  |
|  | SNCU training |  |  |  |  |  |
|  | SNCU Observership |  |  |  |  |  |
| 10 | Miscellaneous |  |  |  |  |  |
|  | Rapid Assessment of SNCUs |  |  |  |  |  |
|  | Dissemination of guidelines |  |  |  |  |  |
|  | Quarterly reviews |  |  |  |  |  |
|  | Intervention | Unit cost | Physical Targets proposed for2012-2013 | Proposed budget | FMR code | Remarks |
| 11 | Infant Death Review |  |  |  |  |  |
|  | Orientation of programme managers on reporting formats for newborn care units and NRCs |  |  |  |  |  |
|  | Operational Research |  |  |  |  |  |
| 12 | Other costs |  |  |  |  | These costs are only to be listed here ; budget to be included under appropriate budget heads |
|  | IEC-BCC :Child Health |  |  |  |  | Plse ref relevant section |
|  | Hiring of new contractual staff for CH |  |  |  |  |  |
|  | Child Health Equipments |  |  |  |  |  |
|  | Procurement of drugs &supplies for CH |  |  |  |  | Plse ref relevant section |

III. FAMILY PLANNING

GOAL: To reduce TFR  from 2.9 (NFHS-3) to 2.1 by 2016-17

Family planning performance has not been convincing but it is to be mentioned that there are high resistance from the apex body of the church and NGOs against advocacy of family planning in any form. But when there is stiff resistance there are also increasing percentage of unmet needs as per NFHS but a declining figure in DLHS-2 to DLHS-3. There is a correlation of female sterilization with unmet needs. As female sterilization goes down there is growing percentage of unmet needs as indicated in NFHS (1-3).  This could be the failure of service delivery. However DLHS shows the percentage of female sterilization is growing as such the % of total unmet need is declining. Emphasis will be made in the financial year to cover more unmet needs and promote more of Pills and Condom distribution which is easy and IUD insertion through health workers. The contribution of ASHA in family planning is also worth mentioning, they act as community distributors of contraceptives. Birth rate and TFR shows a growing trend. Much efforts need to be undertaken to reduce TFR and delay of marriage and meeting of unmet need are challenge the state has to undertake so that population growth can be controlled.

|  | 1998-99 |  | 2005-06 |  | 2002-04 |  | 2007-08 |  | 2009-10 |  | 2010-11 | 2011-12 (upto Nov) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | NFHS-2 |  | NFHS-3 |  | DLHS-2 |  | DLHS-3 |  | STATE HMIS |  | STATE HMIS | STATE HMIS |
| FAMILY PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |
| Any Method (%) | 57.7 |  | 59.9 |  | 53.8 |  | 53.9 |  | 49.04 |  | 47 | 29.4 |
| Any Modern method (%) | 57.1 |  | 59.6 |  | 52.6 |  | 53.1 |  | 49.04 |  | 47 | 29.4 |
| Male Sterilization (%) | 0.1 |  | 0.0 |  | 0.1 |  | 0.2 |  | 0.04 |  | 0.04 | 0 |
| Female Sterilization (%) | 45.4 |  | 42.9 |  | 39.2 |  | 35.9 |  | 24 |  | 24 | 13.4 |
| Pill (%) | 5.4 |  | 10.6 |  | 5.9 |  | 11.6 |  | 5 |  | 6 | 3.8 |
| IUD (%) | 5.4 |  | 4.7 |  | 4.9 |  | 4.3 |  | 15 |  | 13 | 10.7 |
| Condom (%) | 0.9 |  | 1.4 |  | 2.3 |  | 1.2 |  | 3 |  | 4 | 1.5 |
| Total Unmet need (%) | 15.5 |  | 17.3 |  | 25.0 |  | 16.7 |  | NA |  | NA | NA |

CONTRACEPTIVE USE

PROPOSED ACTIVITIES FOR 2012-13

State: Mizoram

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD/Target | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 1 | FAMILY PLANNING MANAGEMENT |  |  |  |  |  |  |  |
| 1.1 | Review meetings on Family Planning performance and initiatives at the State and district level (periodic; including QAC meetings)) | NR | Quarterly | Quarterly | Q I,II, III & IV | Quarterly at State & Dists |  | Budget under M&E |
| 1.2 | Monitoring and supervisory visits to districts/ facilities | NR | 100 facilities | 81 facilities | Q I,II, III & IV | 100 facilities | 9.00 |  |
| 1.3 | Orientation workshops on technical manuals of FP viz. standards, QA, FDS approach, SOP for camps, Insurance etc. | NR | 3 batches | - | Q II | 2 batches | 1.00 | - |
| 2 | SPACING METHOD (Providing of IUD services by districts) |  |  |  |  |  |  |  |
| 2.1 | Plan for providing FDS (Fixed Day Static) IUD services at health facilities in districts (at least 2 days in a week at SHC and PHC level) – number of facilities to be provided | - | - | - | Q I,II, III & IV | 9 CHCs, 2 SHD & 40 PHC atleast 2 days in a week | - |  |
| 2.2 | No. of IUD camps in districts | NR | - | - | - | - | - | - |
| 2.3 | Compensation for IUD | NR | 5000 | 2090 | Q I,II, III & IV | 5000 | 2.50 | Rate increase from Rs.20 to 50/- |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 2.4 | Plan for strengthening PPIUCD services | NR | - | - | Q I,II, III & IV | 6612 Clients | 8.38 | Budget for retention of IUD – Please see write up below this table |
| 3 | TERMINAL/LIMITING METHODS ( Providing sterilisation services in districts) |  |  |  |  |  |  |  |
| 3.1 | Plan for facilities providing FEMALE sterilisation services on fixed days at health facilities in districts (number of facilities) | NA | 9 CHC & 41 PHC once in a month | 8 CHC & 24 PHC | Monthly | 9 CHC & 41 PHC once in a month | - | Separate budget not requred |
| 3.2 | Plan for facilities providing NSV services on fixed days at health facilities in districts (number of facilities) | - | - | - | - | - | - | IEC activities will be emphasised |
| 3.3 | Number of FEMALE Sterilisation camps in districts. | NR | 25 | 11 | Q I,II, III & IV | 15 camps | 2.25 |  |
| 3.4 | Number of NSV camps in districts. | NR | - | - | - | - | - | - |
| 3.5 | Compensation for sterilisation (female) | NR | 3520 | 1445 | Q I,II, III & IV | 3400 | 36.70 |  |
| 3.6 | Compensation for sterilisation NSV (male) | NR | 10 | 0 | Q I,II, III & IV | 10 | 0.15 | - |
| 3.7 | Additional mobility support to surgeon’s team (if required) | NR | 10 teams | 2 teams | Q I,II, III & IV | 10 teams | 2.00 | - |
| 3.8 | Accreditation of private centres/ NGOs for sterilization services (number accredited) | 3 | 1 | 1 | Q II | 1 | - | - |

|  |  | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) |  | PLAN NED |  | ACHI EVE D |  | WORK PLAN |  |  | SCHEDU LED/ Trg. LOAD |  | BUDGET (In lakhs) |  | REMA RKS |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2011-12 |  |  |  | 2012-13 |  |  |  |  |  |  |  |  |
| 3.9 |  | Plan for post partum sterilisation | NR |  | 1520 |  | 578 |  | Q I,II, III & IV |  |  | 1600 |  | - |  |  |  |
| 4 |  | SOCIAL MARKETING OF CONTRACEPTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 |  | Delivery of contraceptives by ASHA at door step | NR |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 4.2 |  | Any other social marketing activity for family planning | NR |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 5 |  | FAMILY PLANNING TRAINING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 |  | IUD Insertion training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.1 |  | TOT for IUD insertion | 25 |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 5.1.2 |  | Training of Medical officers in IUD insertion | 83 |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 5.1.3 |  | Training of staff nurses in IUD insertion | 37 |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 5.1.4 |  | Training of ANMs / LHVs in IUD insertion | 603 |  | 30 |  | 41 |  | - |  |  | 50 |  | 1.88 |  | - |  |
| 5.1.5 |  | Refresher training in IUD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 |  | PPIUCD training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.1 |  | TOT for PPIUD insertion | - |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| 5.2.2 |  | Training of Medical officers in PPIUD insertion | - |  | - |  | - |  | - |  |  | - |  | - |  | - |  |
| SN. |  | STRATEGY / ACTIVITY |  |  | Cumulati ve achievem ent (as on 31st March 2011) |  | PLAN NED |  | ACHI EVE D |  | WORK PLAN | SCHEDU LED/ Trg. LOAD |  | BUDGET (In lakhs) |  | REMA RKS |  |  |  |
|  |  |  |  |  |  |  | 2011-12 |  |  |  | 2012-13 |  |  |  |  |  |  |  |  |
| 5.2.3 |  | Training of staff nurses in PPIUD insertion |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |
| 5.3 |  | Laparoscopic Sterilisation Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3.1 |  | TOT on laparoscopic sterilisation |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |
| 5.3.2 |  | Laparoscopic sterilisation training for service providers (gynaecologists /surgeons) |  |  | 4 teams |  | 1 team |  | - |  | - | 1 team |  | 0.44 |  | - |  |  |  |
| 5.3.3 |  | Refresher training (if required) |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |
| 5.4 |  | Minilap Training for MOs/ MBBS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4.1 |  | TOT on Minilap |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |
| 5.4.2 |  | Minilap training for service providers (medical officers) |  |  | 81 |  | 4 |  | 2 |  | - | 10 |  | 2.30 |  | - |  |  |  |
| 5.4.3 |  | Refresher training (if required) |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |
| 5.5 |  | Non-Scalpel Vasectomy (NSV) Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5.1 |  | TOT on NSV |  |  | - |  | - |  | - |  | - | - |  | - |  | Cases are very few and hence not proposed training in NSV |  |  |  |
| 5.5.2 |  | NSV training for medical officers |  |  | - |  | - |  | - |  | - | - |  | - |  |  |  |  |  |
| 5.5.3 |  | Refresher training (if required) |  |  | - |  | - |  | - |  | - | - |  | - |  |  |  |  |  |
| 5.5 |  | No. of Contraceptive Update trainings for health providers in the districts |  |  | - |  | - |  | - |  | - | - |  | - |  | - |  |  |  |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 5.7 | Other family planning trainings (please specify) |  |  |  |  |  |  |  |
| 6 | „World Population Day‟ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities. | NR |  | 9 dist Hqrs | - | State, Dist & CHC/PHC | 9.00 |  |
| 7 | BCC/ IEC activities - Campaigns/ melas / print/ audio/ video materials for family planning | NR |  |  |  |  |  | Budget under part B of IEC |
| 8 | PROCUREMENT of DRUGS/MATERIALS |  |  |  |  |  |  |  |
| 8.1 | NSV Kits | - | - | - | - | - | - |  |
| 8.2 | IUD insertion Kits | - | - | - | Q II | 450 | 4.50 | Budget under procurement |
| 8.3 | Minilap Set | - | 65 | - | Q III | 41 | 4.10 |  |
| 8.4 | Procurement/ repair of laparoscopes | - | - | - | Q III | 8 nos | 40.00 |  |
| 8.5 | Provision for buffer stock for (subject to maximum of 25% of last year‟s utilisation): |  |  |  |  |  |  | To be procured by state |
|  | IUDs |  |  |  |  |  |  |  |
|  | Tubal Rings |  |  |  |  |  |  |  |
|  | Condom |  |  |  |  |  |  |  |
|  | OCPs |  |  |  |  |  |  |  |
|  | ECPs |  |  |  |  |  |  |  |

| SN. | STRATEGY / ACTIVITY | Cumulati ve achievem ent (as on 31st March 2011) | PLAN NED | ACHI EVE D | WORK PLAN | SCHEDU LED/ Trg. LOAD | BUDGET (In lakhs) | REMA RKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2011-12 |  | 2012-13 |  |  |  |
| 9 | Other innovatory schemes for promoting FP at State or district level | NR |  |  |  |  |  |  |
| 10 | Performance based rewards to institutions and providers for FP performance at State and district level | NR | For HF dists |  | - | Plan for service providers, institutions, Districts | 7.84 |  |

COMPENSATION TO CLIENTS FOR RETENTION OF IUD:

As per the findings of NFHS-3, Infant mortality rate of previous birth interval 2-3 years is only 21 whereas <2 years is 64. In this connection, it has been considered that retention of IUD will be effective to promote birth spacing as well as reduction of IMR.  Since all the government institutions keeps proper records for monitoring and implementation will not be a problem. Therefore, the State Planning Team has proposed to implement incentive to clients for retention of IUD atleast upto 2 years in all government health facilities. It is suggested that mothers who avail IUD services during March, 2011 be included in this scheme for motivation of new clients 2012-13

The proposed rate of compensation are as follows:

- Retention for 1 year			Rs.100/- per client

- Retention for 2 year			Rs. 200/- per Client

Calculation of Budget

1.Estimated number of clients 1 year retention		=  4841 nos  X Rs.100 = Rs 4,84,100/-

2.Estimated number of clients 2 years retention		= 1771 nos X Rs. 200/- = Rs. 3,54,200/-

. 											Total fund requirement = Rs.8,38,300/-

# Performance Based Reward:

# As proposed performance based reward was approved for 2011-12 for 3 high focus district namely Lawngtlai, Saiha and  MamitIt is learnt that this has been motivating the 3 districts and in turn it will result improvement in services delivery. For the year 2012-13 it is proposed to extend performance reward to services providers, institutions wise and district wise covering not only HF districts but  for all other districts. Reward will be disbursed in kinds as follows:

- Reward to Services providers to be disbursed at District Level:

# 1st Prize		= Rs.8,000/-

# 2nd Prize		= Rs.6,000/-

# 3rd Prize		= Rs.4,000/-

# Total		=Rs.18,000/-

# Total for 9 districts = Rs.18,000/- X 9 = Rs.1,62,000/-

- Reward to Institutions i.e SDH/CHC/PHC to be disbursed at District Level:

# 1st Prize		= Rs.10,000/-

# 2nd Prize		= Rs.8,000/-

# 3rd Prize		= Rs.6,000/-

# Total		=Rs.24,000/-

# Total for 9 districts = Rs.24,000/- X 9 = Rs.2,16,000/-

- Reward to S/C level to be disbursed at District Level:

# 1st Prize		= Rs.10,000/-

# 2nd Prize		= Rs.8,000/-

# 3rd Prize		= Rs.6,000/-

# Total		=Rs.24,000/-

# Total for 9 districts = Rs.24,000/- X 9 = Rs.2,16,000/-

- Reward to District Level:

# 1st Prize		= Rs.80,000/-

# 2nd Prize		= Rs.60,000/-

# 3rd Prize		= Rs.50,000/-

# Total		=Rs.1,90,000/-

Family Planning Counselor: 2 existing Family Planning Counselors in 2 biggest Hospitals i.e Aizawl and Lunglei Civil Hospital will be reengaged.

Budget for this under Human resources.

IV. ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH

Adolescent is a phase of rapid physical growth, psycho-social development and sexual transformation. Adolescent comprise of approximately 22% of the total population.  They are critical to the success of any reproductive and sexual health. District hospitals and CHC/PHC are planned to arrange clinic in the same OPD in the afternoon. The contribution made by the State AIDS control Society towards Adolescent Reproductive and Child Health is worth mentioning. Though detailed data for measuring Adolescents health are not available, yet it may be stated that the health status of Adolescent has been improving since the initiative taken by various department such as NRHM, MSAC, Social welfare , Sport and Youth services, Education etc.  During 2011-12 Question box activities were taken up during school health campaigns. In such a way that Students asked any questions about their problems without mentioning their name and all the questions were answered. Question box activities are found to be very effective and successful and therefore proposed to continue in 2012-13.  IEC/BCC activities towards knowledge of RTI/STI, HIV/AIDS and harmfulness of marriage during teenage is badly needed . Adolescent friendly services also need to be improved in order to motivate them to access health services..

| Activity | Status as on 01.04.2012 | Planned for 2011- 12 | Achievement against Plan till 31.12.11 | Plan for 2012-13 |
| --- | --- | --- | --- | --- |
| State Level Training of Trainers (3 days) | - | - | 4 | - |
| Translation of Training Modules | - | - | Already translated | - |
| Printing of Training Modules for MO and ANM/LHV | - | - | Printing done | 1500 C |
| Helpline for ARSH | - | - | - | Establish in DHs |
| Peer Educators Trained | - | - | - | - |
| Any other Activity (Please Specify) | - | - | - | - |

It may be noted that information cannot be furnished as per prescribed format as activities have not been taken up as per PIP guidelines. Most of the activities indicated in the following table are new initiatives to be undertaken in Mizoram. It is therefore proposed to take up activities as per guidelines from 2012-13

Checklist for ARSH Activities

ARSH Training

| District | Training Status as on 01.04.11 |  |  | Training Planned for 2011-12 |  |  | Achievement Against Plan Till 31.12.2011 |  |  | Planning for 2012- 13 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M O | ANM/ LHV | Counsel lor | MO | ANM/ LHV | Couns ellor | MO | ANM/ LHV | Couns ellor | M O | ANM/ LHV | Coun sellor |
|  | MO-99, ANM-637 |  |  | ANM-60 |  |  |  |  |  |  |  |  |
|  | - |  |  |  |  |  |  |  |  |  |  |  |

Note: Budget for ARSH training under Training Chapter.

Adolescent Friendly Health Clinic (AFHC)

| Total Districts | Total DH | Total DH with Functional AFHC | Planned in 2011-12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in DH in 2012-13 |
| --- | --- | --- | --- | --- | --- |
| 9 | 8 | 5 | - |  | 3 DH, 2 SDH |

Note:  During 2012-13 AFHC  will be established in 3DH and 2 SDH.  Necessary equipment such as Projector, TV, Examination table, Chair etc will be needed. Renovation /extension of room for AFHC will also be done.

AFHC in CHC and PHC

| Total Districts | Total CHC | Total CHC with Functional AFHC | Planned in 2011- 12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in CHC in 2012- 13 |
| --- | --- | --- | --- | --- | --- |
| 9 | 9 | - | - | - | 9 |
| Total Districts | Total PHC | Total PHC with Functional AFHC | Planned in 2011- 12 | Achievement Against Plan for 2011-12 till 31.12.11 | Planned AFHC in PHC in 2012- 13 |
| 9 | 57 |  |  | - | 9 CHC & 20 PHC |

OUTREACH ACTIVITIES

| Total Number of Outreach Sessions | In-School 2011-12 |  | Out-of-School 2011-12 |  | Planned with In-School 2012-13 |  | Planned with Out- of-School 2012-13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female | Male | Female | Male | Female |
| Direct in schools |  |  |  |  |  |  |  |  |
| Direct in colleges |  |  |  |  |  |  |  |  |
| VHNDs |  |  |  |  | Plan in 50% of AWW i.e 841 centers |  |  |  |
| School Health Team |  |  |  |  |  |  |  |  |
| Mobile Medical Unit |  |  |  |  | MMUalready in placed in all districts to address Adolescent |  |  |  |
| Teen Clubs |  |  |  |  | To in 100 Schools & 10 all colleges |  |  |  |
| Youth clubs/Gymnasium |  |  |  |  |  |  |  |  |
| SHGs |  |  |  |  |  |  |  |  |
| Vocational Training Centres |  |  |  |  |  |  |  |  |
| Youth Festivals |  |  |  |  | Will be organized in 8 district capital |  |  |  |
| Health Mela |  |  |  |  |  |  |  |  |
| Others |  |  |  |  |  |  |  |  |

Note: Youth festival and Health mela will be clubbed and organized in all district capitals. In the festival different activities such as Games & Sport, Musical Drama related to adolescent health, Solo & Beat contest etc will be conducted. Posters and audio visual will be displayed to address adolescent health. Clinics will also be opened during festival/mela.

| Peer Educators | Identified in 2011-12 |  | Trained in 2011-12 |  | To be Identified in 2012-13 |  | To be Trained in 2012- 13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female | Male | Female | Male | Female |

Activities planned with peer educators

| Activities planned with peer educators | Timeline | Remarks |
| --- | --- | --- |

Note: There is no separate plan for peer educator as ASHA can play the same role

SCHEME  FOR  PROMOTION  OF  MENSTRUAL  HYGIENE  AMONG  ADOLESCENT GIRLS (10-19 YRS) IN RURAL AREAS

In formation regarding seledted districts for implementation of Menstrual Hygien Scheme has not been received. As such separate  plan has not been formulated for 2012-13

SCHOOL HEALTH: Separate plan for school health included in the part B of PIP.

# V. URBAN RCH

# Goal & Objective: To improve the health status of urban poor community by provision of integrated primary health care services.

| S.No. | Name of cities identified for implementing UHPs. In the State PIPs. Under Urban RCH, so far | Major urban health strategies/activities carried out under Urban RCH so far, city-wise | Urban health strategies/activities as proposed now in the State PIP under Urban RCH, city- wise | Brief on activities being supported by external agencies |
| --- | --- | --- | --- | --- |
| 1 | Aizawl – 4 UHCs | Ref write up below |  |  |
| 2 | Lunglei- 1 UHC | Ref write up below |  |  |

As mentioned in previous year PIP, Aizawl and Lunglei Cities have been taken up under urban Health RCH programme since 2004. In addition to the existing health facilities, 4 UHCs in Aizawl and 1 UHC in Lunglei were established to address poor community.

The existing Health facilities in the two cities other than Urban Health Centres are:

| Health Facilities | No of Facilities |  |
| --- | --- | --- |
|  | Aizawl | Lunglei |
| Government Hospital | 4 (State Hospital, Kulikawn Hospital & Falkawn Hospital, TB Hospital) | 1 |
| Sub Centre | 53 | 14 |
| Mission Hospital | 2 | 1 |
| Other Private Hospital | 7 | - |

Health care services delivery has been provided to the urban poor community through 4 UHCs in Aizawl city and 1 UHC in Lunglei. All these UHCs are located in the outskirt of the cities to make easily accessible health care services for targeted group. As per provisional data 2011 (Census of India) urban population in Mizoram comprises of 51.51% of the total population and the population of Aizawl and lunglei  is 264645 and 58339 respectively.  It can be stated that urban population growth rate will increse every year due to  Socia economic and Educational factors. Provision of assured and credible primary health services in urban areas is a priority considering rapid mushrooming growth of urban population. A large number of families have been migrated to city every year due to the above reasons stated.

The existing UHCs in Aizawl and Lunglei are useful to ensure provision of assured and credible health services in urban areas especially to slum/ poor people dwelling in the outskirt of the cities.  All UHCs except ITI UHC ( Aizawl East) were established in rented buildings. UHCs are providing round the clock services and operationalised as PHC/CHC. It has been experienced that UHCs are very useful and beneficial especially for urban poor community who are not able to access other government / private health facilities as they are providing all RCH activities as delivered in PHCs. UHCs also greatly promote ANC registration, Immunization, institutional delivery, breast feeding and reducing unmet needs. In addition to these, OPD are opened in the UHCs for the general out Patients. Not only mothers but general patients have been admitted for treatment. Considering the experiences of the significant roles played by UHCs for promoting urban poor community, it is proposed to continue urban health programme during 2012-13

The Approximate population coverage of each UHCs are: 1) Chawlhhmun UHC (Aizawl ‘W’)- 31000 2) ITI UHC (Aizawl ‘E’)-32000 3) Hlimen UHC (Aizawl ‘S’)- 27000 4) Ramhlun UHC- 56700. 5) Hrangchalkawn UHC-22000.

The average monthly Performance of UHCs are tabulated below:

| Indicators | Chalhhmun UHC | ITI UHC | Hlimen UHC | Ramhlun UHC | Hrangchalkawn UHC |
| --- | --- | --- | --- | --- | --- |
| No of Deliveries conducted | 9 | 8 | 6 | 16 | 6 |
| No of Out patients attended | 310 | 140 | 2019 | 200 | 150 |
| No of Female sterilized | 5 | 3 | Nil | 7 | 3 |
| No of IUD insertion done | 4 | 2 | 11 | 4 | 3 |
| No of JSY beneficiaries | 7 | 5 | 5 | 10 | 4 |

Activities to be carried out by UHCs are mentioned below:

1.Ensure timely and full ANC & PNC

2. Promote Institutional Delivery

3. Provide all FP services mentioned in the relevant chapter

4. Provide all Child Health services mentioned in the relevant chapter

5. Implement JSY & JSSK as per guidelines

6. Outreach camps

6. All other functions as provided in PHCs

Other Activities which need budget under Urban Health are
1. Reengagement of Support Staff ( Other staff budgeted under HR)

2.Building Rent for 4 UHCs ( 4 out 5 UHCs are in rented building)

3.Maintenance of UHC such as, Eletricity bill, Water bill, Indane Gas, Telephone bill etc

# Staff already recruited and on the roll are mentioned below:

| Category of Staff | No of staff per centre | Total no of Staff for 5 UHCs |
| --- | --- | --- |
| Medical Officer | 1 | 5 |
| Staff nurses | 4 nos | 20 |
| ANM/HW | 3 nos | 15 |
| Laboratory Technician | 1 no | 5 |
| Helpers / Support staff | 4 nos | 25 |

Note :

# 1) The above contractual staff already in place will be reengaged. Salary of contractual staff except Support staff is budgeted under the budget head of Human resources.

2) No proposal for engagement of Link workers as ASHA already in place can play the roll of link worker.

# VI. Tribal Health

The entire State of Mizoram is Tribal dominated area. 2001 census reveals that Tribal population is 94.46% out of the total population. It may be stated in this connection that all the RCH II strategic interventions in Mizoram are for promoting the health status of Tribal population. So, specific activities need not be taken up for Tribal health as RCH normal/ routine activities cover scheduled tribe and other castes.

VII. PC & PNDT and Gender Mainstreming:

Goal & Objective: To maintain equality between male and female in the society.

Strategies & Activities: As mentioned in the previous PIPs, gender discrimination is not a big problem and social evil in Mizoram. PNDT Act has been implemented in the state since RCH I to maintain the good relationship and rights of male and female / gender discrimination in the Society. Regular checking of records of diagnostic laboratories with ultra sound machines and regular monitoring of sex ratio at birth from records of birth registration in the health institutions will be done. Reorientation of Proramme managers medical officers and paramedics on the PNDT Act will also be conducted as convenient at state as well as district level. Other activities such as IEC /BCC activities to address the gender issue, Audit of facilities by QAC. Budget has been allocated for operationalization of PNDT cell ( this include IEC/BCC activities) and monitoring of facilities. However, a big amount of budget need not to allocate as monitoring can be done by state and districts officers during visit of Hospitals/PHC/CHC.

VIII. TRAINING:

Skill development of health professional to provide quality services to the clients is one of the main objectives of NRHM. It is a well know fact that considerable improvement is possible in the workforce of the department by improving skills of the existing staff. As regard human resources development, the training activity in the department need more strengthen so that its contribution in capacity building is much more focused. At present there is no medical Colleges and State Institute of Health and Family welfare in the state for which Medical Officers are sent to outside the state to undergo training in EmoC and LSAS. Civil Hospital Aizawl is the only  training centre for Medical Officers in the state, other district hospitals are identified only to train other staff with small batch sizes.   Since the launch of NRHM, various trainings related to Maternal health, Child health, Family planning and Adolescent health have been conducted at the state and district levels. The batch size of training such as RTI/STI and SBA varies from district to district depending upon the case load, number of facilities and staff. The qualities of services being provided have also been very much improved which is possible as some health personnel have undergone various training in IMNCI, SBA etc.  Staff those who have undergone various training are indicated in the table below. However, there are still a number of staff to be trained in different MH,CH,FP etc related trainings. In order to attain further improvement in service delivery, it has been planned that training of staff will be continued during 2012-13. Physical target has been worked out as tabulated below.

# Proposed Training during 2012-13

| Name of Training | Staff & No to be trained During 2012-13 | Current Status |  | Training Centre |  | No. of participants/ batch | No. of Batches | Duration (in Days) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SBA | Staff Nurse (68) |  | 134 |  | CH, Aizawl | 5 | 8 | 21 Days |
|  |  |  |  |  | CH, Lunglei | 2 | 10 | 21 Days |
|  |  |  |  |  | DH, Kolasib | 1 | 8 | 21 Days |
|  | HW / ANMs ( 32) |  | 117 |  | CH, Aizawl | 5 | 4 | 21 Days |
|  |  |  |  |  | DH, Kolasib | 1 | 2 | 21 Days |
|  |  |  |  |  | Christian Hosp, Serkawn | 1 | 10 | 21 Days |
| EmOC | Medical Officer 1) |  | 10 |  | GMC, Guwahati & Civil Hospital Aizawl | 1 | 1 | 112 Days |
| BEmOC | Medical Officer (20) |  | - |  | Civil Hospital Aizawl | 2 | 10 | 10 Days |
| LSAS | Medical Officer (1) |  | 10 |  | RIMS Imphal | 1 | 1 | 126 Days |
| RTI/STI | Medical Officer (30) |  | 46 |  | Civil Hospital Aizawl | 30 | 1 | 2 Days |
|  | SN (90) |  | - |  |  | 30 | 3 | 1 day |
| MTP | Medical Officer (10) |  | 81 |  | Civil Hospital Aizawl | 2 | 5 | 12 Days |
| IMNCI | ANM/HW (120) |  | 775 |  | Civil Hospital Aizawl, | 30 | 4 | 8 Days |
| F-IMNCI | SN (144) |  | 0 |  | Civil Hospital Aizawl | 12 | 12 | 5 days |
| NSSK | SN ( 240) |  | 108 |  | Civil Hospital Aizawl | 24 | 15 | 2 days |
|  | ANM/HW (120) |  | 0 |  | Civil Hospital Aizawl | 24 | 5 | 2 days |
| MiniLap Tubectomy | Medical Officer (10) |  | 81 |  | Civil Hospital Aizawl | 2 | 5 | 12 Days |
| Alternative Training Methodology in IUCD | Health Worker/ ANM (50) |  | 603 |  | Civil Hospital Aizawl | 10 | 5 | 3 Days |
| IMEP | SN (300) |  | 0 |  | State & District | 30 | 20 | 1 day |

# ESTIMATED BUDGET FOR TRAININGS

# Maternal health Training

# 1. (i)Skilled Birth Attendants Training for Staff Nurses (Aizawl)

1. Target Load			= 40

2. No of Batches		= 8

3. Participants per batch	=5

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 5 | 42,000 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 5 Lectures | 1 | 3,000 |
| Incidental expenditure | 250 | - | 5 | 1,250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 5 | 21,000 |
| Institutional Overhead (15% of above) |  |  |  | 13,850 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 5 | 3,000 |
| Total |  |  |  | Rs. 1,09,300/- |

# Budget for 8 batches = 8X Rs. 1,09,300/- = Rs.8,74,400/-

# Quarter Wise – No of Batches to be trained

| SBA(Aizawl) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 3 | 3 | 2 | - |

# 1. (ii)Skilled Birth Attendants Training for Health Workers(Aizawl)

1. Target Load			= 20

2. No of Batches		= 4

3. Participants per batch	=5

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 5 | 42,000 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 5 Lectures | 1 | 3,000 |
| Incidental expenditure | 250 | - | 5 | 1,250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 5 | 21,000 |
| Institutional Overhead (15% of above) |  |  |  | 13,850 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 5 | 3,000 |
| Total |  |  |  | Rs. 1,09,300/- |

# Budget for 4 batches = 4X Rs. 1,09,300/- = Rs.4,37,200/-

# Quarter Wise – No of Batches to be trained

| SBA(Aizawl) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | - |  | 1 | 3 |

# 1. (iii) Skilled Birth Attendants Training for Staff Nurses(Lunglei district)

1. Target Load			= 20

2. No of Batches		= 10

3. Participants per batch	= 2

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 21 | 2 | 8,400 |
| Institutional Overhead (15% of above) |  |  |  | 7,800 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 2 | 1,200 |
| Total |  |  |  | Rs. 62,300/- |

# Budget for 10 batches = 10X Rs. 62,300/- = Rs.6,23,000/-

# Quarter Wise – No of Batches to be trained

| SBA(Lunglei) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 2 | 3 | 3 | 2 |

# 1. (iv) Skilled Birth Attendants Training for Staff Nurses (Kolasib district)

1. Target Load			=8

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 8 batches = 8X Rs. 47,100/- = Rs.3,76,800/-

# Quarter Wise – No of Batches to be trained

| SBA(Kolasib) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 2 | 2 | 2 | 2 |

# 1. (v) Skilled Birth Attendants Training for  Health Workers (Kolasib district)

1. Target Load			=2

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 2 batches = 2X Rs. 47,100/- = Rs.94,200/-

# Quarter Wise – No of Batches to be trained

| SBA(Kolasib) | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | - | 1 | 1 | - |

# 1. (vi) Skilled Birth Attendants Training for Health Workers (Christian Hospital, Serkawn)

1. Target Load			=10

2. No of Batches		=10

3. Participants per batch	= 1

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 1 | 8,400 |
| Honorarium of Resources Person | 600 | 21 | 2 | 25,200 |
| Honorarium of Co Trainer | 600 | 4 Lectures | 1 | 2,400 |
| Incidental expenditure | 250 | - | 2 | 250 |
| Working Lunch, Tea & Snacks | 200 | 21 | 1 | 4,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 1 | 600 |
| Total |  |  |  | Rs. 47,100/- |

# Budget for 10 batches = 10X Rs. 47,100/- = Rs.4,71,000/-

# Quarter Wise – No of Batches to be trained

| Christian Hospital, Serkawn | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health workers | I | II | III | IV |
|  | 2 | 3 | 3 | 2 |

# 2. EmOC Training for Medical Officer(at GMC, Guwahati)

1. Target Load			= 1

2. No of Batches		= 1

3. Participants per batch	= 1

4. Duration of Training	= 16 weeks (112 Days)

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 112 | 1 | 78,400 |
| Training Cost (including Honorarium to tertiary centre faculty) |  |  |  | 22,000 |
| Honorarium to District Faculty | 600 | 70 | 2 | 75,600 |
| TA (Actual Airfare, POL) | 20000 | - | 1 | 25,000 |
| Total |  |  |  | Rs. 2,01,000/- |

# Quarter Wise – No of Batches to be trained

| EmOC | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | 1 | - | - |

# 3. Basic Emergency Obstetric Care (BEmOC)

1. Target Load			= 20

2. No of Batches		= 10

3. Participants per batch	= 2

4. Duration of Training	= 10days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 10 | 2 | 14,000 |
| Honorarium of Resources Person | 600 | 10 | 2 | 12,000 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 10 | 2 | 4,000 |
| Institutional Overhead (15% of above) |  |  |  | 4,575 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 39,075/- |

# Budget for 3 batches = 10 X Rs. 39,075/- = Rs.3,90,750/-

# Quarter Wise – No of Batches to be trained

| BEmOC | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I |  | III | IV |
|  | 2 | 3 | 3 | 2 |

# 4. LSAS for Medical Officer(at RIMS, Imphal)

1. Target Load			= 1

2. No of Batches		= 1

3. Participants per batch	= 1

4. Duration of Training	= 18 weeks (126 Days)

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 126 | 1 | 88,200 |
| Honorarium to Resource Person | 500 | 126 | 2 | 1,26,000 |
| Working Lunch | 100 | 126 | 1 | 12,600 |
| Training Materials | 1000 |  | 1 | 1,000 |
| Administrative expense @ 10% |  |  |  | 22,000 |
| TA (Actual Airfare, POL) | 20000 | - | 1 | 20,000 |
| Total |  |  |  | Rs. 2,69,800/- |

# Quarter Wise – No of Batches to be trained

| LSAS | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | - | 1 | - |

5.(i) RTI/STI Training for Medical Officer

1. Target Load			= 30

2. No of Batches		=1

3. Participants per batch	= 30

4. Duration of Training	= 2 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 2 | 30 | 42,000 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4800 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 2 | 30 | 12000 |
| Venue Hiring | 500 | 2 |  | 1000 |
| Institutional Overhead (15% of above) |  |  |  | 11000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 2000 | - | 30 | 60,000 |
| Total |  |  |  | Rs. 1,38,300/- |

# Quarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | 1 | - | - | - |

5. (ii) RTI/STI Training for Staff Nurses

1. Target Load			= 90

2. No of Batches		=3

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 4 | 2400 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4200 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 50,600/- |

# Budget for 3 batches = 3 X Rs.50,600/- = Rs.1,51,800/-

# Quarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | - | 3 | - | - |

5. (iii) RTI/STI Training for Health Workers

1. Target Load			= 90

2. No of Batches		=3

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 4 | 2400 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4200 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 50,600/- |

# Budget for 3 batches = 3 X Rs.50,600/- = Rs.1,51,800/-

# Quarter Wise – No of Batches to be trained

| RTI/STI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | - | 3 | - |

6. MTP Training for Medical Officer

1. Target Load			= 6

2. No of Batches		= 3

3. Participants per batch	= 2

4. Duration of Training	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 12 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 12 | 2 | 4,800 |
| Institutional Overhead (15% of above) |  |  |  | 5,500 |
| TA (POL) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 46,000/- |

# Budget for 3 batches = 3X Rs. 46000/- = Rs.1,38,000/-

# Quarter Wise – No of Batches to be trained

| MTP | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | 2 | 1 | - |

7. IMNCI Training for Health Workers

1. Target Load			= 120

2. No of Batches		= 4

3. Participants per batch	= 30

4. Duration of Training	= 8 Days

| Components | Rate/day (Rs) | No of days | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 8 | 30 | 96,000 |
| Honorarium of Resources Person | 600 | 8 | 4 | 19,200 |
| Incidental expenditure | 250 | - | 30 | 7,500 |
| Working Lunch, Tea & Snacks | 200 | 8 | 30 | 48,000 |
| Venue Hiring | 500 | 8 |  | 4,000 |
| Institutional Overhead (15% of above) |  |  |  | 25,600 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 2,18,300/- |

# Budget for 4 batches = 4 X Rs. 2,18,300/- = Rs. 8,73,200/-

# Quarter Wise – No of Batches to be trained

| IMNCI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | 1 | 1 | 1 | 1 |

# 8. F-IMNCI Training for Staff Nurses

1. Target Load			=144

2. No of Batches		= 12

3. Participants per batch	= 12

4. Duration of Training	= 11 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 11 | 12 | 52,800 |
| Honorarium of Resources Person | 600 | 11 | 2 | 13,200 |
| Incidental expenditure | 250 | - | 12 | 3,000 |
| Working Lunch, Tea & Snacks | 200 | 11 | 12 | 26,400 |
| Venue Hiring | 500 | 11 |  | 5,500 |
| Institutional Overhead (15% of above) |  |  |  | 15,100 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 12 | 7,200 |
| Total |  |  |  | Rs.1,23,200 /- |

# 12 Batches x Rs. 1,23,200/- = Rs.14,78,400/-

# Quarter Wise – No of Batches to be trained

| F-IMNCI | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurses | I | II | III | IV |
|  | 3 | 3 | 3 | 3 |

# 9(i). NSSK Training for Staff Nurses

1. Target Load			=240

2. No of Batches		=10

3. Participants per batch	= 24

4. Duration of Training	= 2 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 2 | 24 | 19,200 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4,800 |
| Incidental expenditure | 250 | - | 24 | 6,000 |
| Working Lunch, Tea & Snacks | 200 | 2 | 24 | 9,600 |
| Venue Hiring | 500 | 2 |  | 1,000 |
| Institutional Overhead (15% of above) |  |  |  | 6,000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 24 | 14,400 |
| Total |  |  |  | Rs.61,000 /- |

# 10 Batches x Rs. 61,000/- = Rs. 6,10,000/-

# Quarter Wise – No of Batches to be trained

| NSSK | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 4 | 4 | 2 | - |

# 9(ii). NSSK Training for Health Workers

1. Target Load			=120

2. No of Batches		=5

3. Participants per batch	= 24

4. Duration of Training	= 2 Days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 2 | 24 | 19,200 |
| Honorarium of Resources Person | 600 | 2 | 4 | 4,800 |
| Incidental expenditure | 250 | - | 24 | 6,000 |
| Working Lunch, Tea & Snacks | 200 | 2 | 24 | 9,600 |
| Venue Hiring | 500 | 2 |  | 1,000 |
| Institutional Overhead (15% of above) |  |  |  | 6,000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 24 | 14,400 |
| Total |  |  |  | Rs.61,000 /- |

# 5 Batches x Rs. 61,000/- = Rs. 3,05,000/-

# Quarter Wise – No of Batches to be trained

| NSSK | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | - | 1 | 4 |

10. MiniLap Tubectomy Training for Medical Officer

1. Target Load			= 6

2. No of Batches		= 3

3. Participants per batch	= 2

4. Duration of Training	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 12 | 2 | 16,800 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 2 | 500 |
| Working Lunch, Tea & Snacks | 200 | 12 | 2 | 4,800 |
| Institutional Overhead (15% of above) |  |  |  | 5,500 |
| TA (POL) | 2000 | - | 2 | 4,000 |
| Total |  |  |  | Rs. 46,000/- |

# Budget for 3 batches = 3X Rs. 46000/- = Rs.1,38,000/-

# Quarter Wise – No of Batches to be trained

| Minilap Tubectomy | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Medical Officer | I | II | III | IV |
|  | - | 2 | 1 | - |

11. Laparoscopic Sterilisation Training

1. Target Load			= 1 Team

2. No of Batches		= 1

3. Participants per batch	= 3

4. Duration of Training	= 12days

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees(Gynaecologist) | 700 | 12 | 1 | 8,400 |
| DA for Other trainees | 400 | 12 | 2 | 9,600 |
| Honorarium of Resources Person | 600 | 12 | 2 | 14,400 |
| Incidental expenditure | 250 | - | 3 | 750 |
| Working Lunch, Tea & Snacks | 200 | 12 | 3 | 7,200 |
| Institutional Overhead (15% of above) |  |  |  | 6,050 |
| TA (POL ) | - | - | - | 3,200 |
| Total |  |  |  | Rs. 43,550/- |

# Budget for 1 batches = 1X Rs. 43,550/- = Rs.43,550/-

# Quarter Wise – No of Batches to be trained

| Lap Sterilisation | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
|  | I | II | III | IV |
|  |  | - | 1 | - |

12. Alternative Training Methodology in IUCD for Health Workers

1. Target Load			= 50

2. No of Batches		= 5

3. Participants per batch	= 10

4. Duration of Training	= 3 days

| Components | Rate/day (Rs) | No of days | No of Participants | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 3 | 10 | 12,000 |
| Honorarium of Resources Person | 600 | 3 | 3 | 5,400 |
| Incidental expenditure | 250 | - | 10 | 2,500 |
| Working Lunch, Tea & Snacks | 200 | 3 | 10 | 6,000 |
| Venue Hiring | 500 | 3 |  | 1,500 |
| Institutional Overhead (15% of above) |  |  |  | 4,100 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 10 | 6000 |
| Total |  |  |  | Rs. 37,500/- |

# Budget for5 batches = 5X Rs. 37,500/- = Rs.1,87,500/-

Quarter Wise – No of Batches to be trained

| Alternative Methodology in IUCD | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Health Workers | I | II | III | IV |
|  | - | 3 | 2 | - |

13. IMEP Training for Staff Nurses

1. Target Load			= 300

2. No of Batches		=10

3. Participants per batch	= 30

4. Duration of Training	= 1 Day

| Components | Rate/day (Rs) | No of days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 30 | 12,000 |
| Honorarium of Resources Person | 600 | 1 | 1 | 600 |
| Incidental expenditure | 250 | - | 30 | 7500 |
| Working Lunch, Tea & Snacks | 200 | 1 | 30 | 6000 |
| Venue Hiring | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) |  |  |  | 4000 |
| TA (Actual Maxi Cap / Bus Fare, Taking average ) | 600 | - | 30 | 18,000 |
| Total |  |  |  | Rs. 48,600/- |

# Budget for 10 batches = 10 X Rs.48,600/- = Rs.4,86,000/-

# Quarter Wise – No of Batches to be trained

| IMEP | No of Batches |  |  |  |
| --- | --- | --- | --- | --- |
| Staff Nurse | I | II | III | IV |
|  | 3 | 7 | - | - |

# PUBLIC PRIVATE PARTNERSHIP & MNGO

# Goal: To improve the health status of the population of underserved/ difficult area through PPP.

Notes: 2 MNGOs cover 4 districts namely Aizawl, Champhai, Lunglei and Lawngtlai. Only Marpara PHC in mamit district is operationalized as PPP mode.

Public Private Partnership (PPP) has been implemented in the state w.e.f 2005-06 under RCH II program. 2(two) Mission Hospital namely Christian Hospital Serkawn run by Baptist Church of Mizoram in Lunglei district and Presbyterian Hospital Durtlang run by Mizoram Synod in Aizawl district were identified for Mother NGOs to cover 2 districts each. Christian Hospital Serkawn is functioning as MNGO in Lunglei and Lawngtlai districts and Presbyterian Hospital Durtlang is looking after Aizawl and Champhai districts. It has been proposed that the existing two MNGOs will continue their services to promote RCH programme.

As mentioned in the previous RCH II PIP, Marpara PHC under Mamit district has been operationalised in collaboration with Presbyterian Hospital Durtlang (biggest Mission Hospital in the state) . Marpara is located in the west of Mizoram (Mamit dist) .It is one of the remote and hard to reach areas. Marpara PHC covers 2 S/C, 6 villages with a population of around 7600. Due to its remoteness and bad climatic condition many service providers used to refuse to work in this area. Thus, the inhabitants in this area are still lacking good health care delivery system due to its location and non availability of dedicated staff and health infrastructure. In such a situation. The Mission Hospital agreed to extend its services in this area keeping its Mission for the backward people in mind.

As approved by Government of India, MOU was signed during 2008-09 and the contract is 5 years commencing from 1st July, 2008. The State Health Society under RCH II Program provides all necessary funding for staff salaries, maintenance of health infrastructure, all equipment etc required for comprehensive health care delivery through the Mission Hospital. As implementation of  PPP has been found successful, It is planned to continue during 2012-2013. The Mission hospital is services provider, and responsible for recruitment of staff, operationalization of PHC and provide necessary services in accordance with existing norms and instruction issue by the State Health Society.

The District being covered under PPP & MNGO are 1) Aizawl 2) Champhai 3) Lunglei 4) Lawngtlai and Marpara PHC under Mamit District

Budget for MNGOs and PPP under Mission Flexipool

HUMAN RESOURCES:

As per instruction issued by the Government of India, difficult areas have been identified and accordingly the whole state of Mizoram was identified and categorized into three groups as follows – Category A soft area/normal area, category B difficult area, category C very difficult area. It is proposed to reengage all the existing contractual staff.

# Clarification of Categorization:

- Very difficult are: These areas do not have regular power supply, running water supply and good educational institutions. The places remain inaccessible at least about 6 months during monsoon season. Accommodation facilities could not be provided to all medical and paramedical workers in these areas.

- Difficult area	: These areas are connected by unmetalled roads only, but cab be accessed most of the time except during the peak monsoon season. They are having slightly better power supply although with regard to running water and accommodation facilities, it is still difficult to provide them.

- Normal/Soft area: They are all weather road and reachable by vehicle throughout the year.

Existing Human resources and proposed pay for 2012-13. Sl.No; Category of staff; No of Staff; Approved pay as per ROP 2011-12; % Increase; Total Salary per Month; Salary for 1 year. 1; Specialist. Normal Area; 6; 38500; 15%; 44275; 3187800. Difficult area; 2; 42350; 15%; 48703; 1168860. Very Difficult Area; 1; 46585; 15%; 53573; 642873. Sub Total; 9; 4999533. 2; Medical Officer. Normal Area; 20; 24200; 25%; 30250; 7260000. Difficult area; 20; 27500; 25%; 34375; 8250000. Very Difficult Area; 15; 33000; 25%; 41250; 7425000. Sub Total; 55; 22935000. 3; Dental Surgeon (BDS). Normal Area; 18; 22000; 37.50%; 30250; 6534000. Difficult area; 14; 26400; 30.21%; 34375; 5775000. Very Difficult Area; 8; 28600; 44.23%; 41250; 3960000. Sub Total; 40; 16269000. 4; Staff Nurse. Normal Area; 77; 10000; 25%; 12500; 11550000. Difficult area; 73; 11000; 36%; 15000; 13140000. Very Difficult Area; 87; 12000; 35%; 16250; 16965000. Sub Total; 237; 41655000. 5; Pharmacist. Normal Area; 18; 8000; 25%; 10000; 2160000. Difficult area; 3; 8500; 25%; 10625; 382500. Very Difficult Area; 7; 9000; 25%; 11250; 945000. Sub Total; 28; 3487500. 6; X-ray tech. Normal Area; 5; 8000; 25%; 10000; 600000. Difficult area; 7; 8500; 25%; 10625; 892500. Very Difficult Area; 6; 9000; 25%; 11250; 810000. Sub Total; 18; 2302500. 7; BEE. Normal Area; 1; 6000; 50%; 9000; 108000. Difficult area; 6; 6500; 50%; 9750; 702000. Very Difficult Area; 2; 7000; 50%; 10500; 252000. Sub Total; 9; 1062000. 8; ANM. Normal Area; 57; 9000; 5%; 9450; 6463800. Difficult area; 122; 9900; 5%; 10395; 15218280. Very Difficult Area; 249; 10800; 5%; 11340; 33883920. Sub Total; 428; 55566000. 10; Laboratory Technician (Diplonma). Normal Area; 13; 8000; 20%; 9600; 1497600. Difficult area; 13; 8500; 20%; 10200; 1591200. Very Difficult Area; 10; 9000; 20%; 10800; 1296000. Sub Total; 36; 4384800. 11; Laboratory Technician (Certificate). Normal Area; 5; 6000; 25%; 7500; 450000. Difficult area; 5; 6500; 25%; 8125; 487500. Very Difficult Area; 8; 7000; 25%; 8750; 840000. Sub Total; 18; 1777500. 12; FP Counsellor. Normal Area; 2; 15000; 5%; 15750; 378000. Sub Total; 2; 378000. G.Total; 154816833.

| PROGRAMME MANAGEMENT SUPPORT UNIT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STATE PROGRAMME MANAGEMENT UNIT |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff | No of Staff | Approved pay as per ROP 2011-12 |  | Increase % |  | Total Salary per Month |  | Salary for 1 year |  |
| 1 | Medical officer ( i/c of Maternal Health, Child Health, Family Planning and ARSH) | 4 | 35000 |  | 25% |  | 43750 |  | 2100000 |  |
| 2 | Consultant HMIS | 1 | 20000 |  | 25% |  | 25000 |  | 300000 |  |
| 3 | State Finance Manager | 1 |  |  |  |  | 55000 |  | 660000 |  |
| 4 | Consultant Finance | 1 | 20000 |  | 25% |  | 25000 |  | 300000 |  |
| 5 | NGO Coordinator | 1 | 12000 |  | 25% |  | 15000 |  | 180000 |  |
| 6 | Manager MiS | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 7 | Admi. Officer | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 8 | Accounts manager | 1 | 18000 |  | 25% |  | 22500 |  | 270000 |  |
| 9 | Asst. Engineer | 2 | 22000 |  | 25% |  | 27500 |  | 660000 |  |
| 10 | Junior engineer | 9 | 9000 |  | 25% |  | 11250 |  | 1215000 |  |
| 11 | Accountant | 1 | 10000 |  | 25% |  | 12500 |  | 150000 |  |
| 12 | Statistical Assistant | 1 | 9500 |  | 25% |  | 11875 |  | 142500 |  |
| 13 | Accounts Clerk/ Financial Assistant | 3 | 9000 |  | 25% |  | 11250 |  | 405000 |  |
| 14 | DEO | 3 | 8000 |  | 25% |  | 10000 |  | 360000 |  |
| 15 | Driver | 1 | 5500 |  | 25% |  | 6875 |  | 82500 |  |
| 16 | Helper | 3 | 5500 |  | 15% |  | 6325 |  | 227700 |  |
|  | Grand Total | 34 |  |  |  |  |  |  | 7592700 |  |
| DISTRICT PROGRAMME MANAGEMENT UNIT |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff |  |  | No of Staff |  | Approved pay as per ROP 2011-12 | Increase % | Salary per Month |  | Salary for 1 year |  |
| 1 | District DPM |  |  | 9 |  | 18500 | 25% | 23125 |  | 2497500 |  |
| 2 | DEO |  |  | 9 |  | 8500 | 15% | 10625 |  | 1147500 |  |
| 3 | Project Asst/NGO Coordinator |  |  | 1 |  | 12000 | 25% | 15000 |  | 180000 |  |
| 4 | Accounts Manager |  |  | 18 |  | 9500 | 25% | 11875 |  | 2565000 |  |
| 5 | Stat Asst |  |  | 1 |  | 9500 | 25% | 11875 |  | 142500 |  |
| 6 | Executive Asst |  |  | 9 |  | 8500 | 25% | 10625 |  | 1147500 |  |
| 7 | Junior Engineer |  |  | 4 |  | 9000 | 25% | 11250 |  | 540000 |  |
| 9 | Section Asst |  |  | 1 |  | 9000 | 25% | 11250 |  | 135000 |  |
|  | TOTAL |  |  | 52 |  |  |  |  |  | 8355000 |  |
| BLOCK MANAGEMENT SUPPORT UNIT |  |  |  |  |  |  |  |  |  |  |  |
|  | Category of Staff |  |  | No of Staff |  | Approved pay as per ROP 2011-12 | Increase in % | Salary per Month |  | Salary for 1 year |  |
|  | ACCOUNTS CLERK IN CHC/PHC |  |  |  |  |  |  |  |  |  |  |
| 1 | Normal Area |  |  | 9 |  | 9000 | 25% | 11250 |  | 1215000 |  |
| 2 | Difficult area |  |  | 26 |  | 9500 | 25% | 11875 |  | 3705000 |  |
| 3 | Very Difficult Area |  |  | 31 |  | 10000 | 25% | 12500 |  | 4650000 |  |
|  | Total |  |  | 66 |  |  |  |  |  | 9570000 |  |

| DETAIL BUDGET RCH II: 2012-13 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (States to provide details for high focus districts and for the State total) |  |  |  |  |  |  |  |  |
| S. No. | Budget Head | Unit of Measure | PHYSICAL TARGET (where applicable) |  | Rate (Rs./Unit) | BUDGET (RS. LAKHS) |  | Remarks / Justification |
|  |  |  | Total Annual |  |  | Total Annual Budget (Rs. Lakhs) |  |  |
|  |  |  | High focus districts | State Total |  | High focus districts | State Total |  |
| 1 | MATERNAL HEALTH |  |  |  |  |  |  |  |
| 1.1 | Operationalise facilities (only dissemination, meetings and quality assurance) |  |  |  |  |  |  |  |
| 1.1.1 | Operationalise FRUs |  |  |  |  |  |  |  |
| 1.1.1.1 | Organise dissemination workshops for FRU guidelines |  |  |  |  |  |  |  |
| 1.1.1.2 | Prepare plan for operationalisation across districts (cost of plan meeting should be kept) |  |  |  |  |  |  |  |
| 1.1.1.3 | Monitor progress and quality of service delivery | No of visit | 10 trips | 30 trips | 10000 | 1.00 | 3.00 |  |
| 1.1.2 | Operationalise 24x7 PHCs |  |  |  |  |  |  |  |
| 1.1.2.1 | Prepare plan for operationalisation across districts (cost of plan meeting should be kept) |  |  |  |  |  |  |  |
| 1.1.2.2 | Monitor progress and quality of service delivery |  |  |  |  |  |  |  |
| 1.1.3 | Operationalise Safe abortion services (including MVA/ EVA and medical abortion)at health facilities |  |  |  |  |  |  |  |
| 1.1.3.1 | Prepare plan for operationalisation across districts (priortise facilities for safe abortion services; cost of plan meeting should be kept) |  |  |  |  |  |  |  |
| 1.1.3.2 | Monitor progress and quality of service delivery | No of visit | 15 trips | 50 trips | 5000 | 0.75 | 2.50 |  |
| 1.1.4 | Operationalise RTI/STI services at health facilities |  |  |  |  |  |  |  |
| 1.1.4.1 | Prepare plan for operationalisation across districts (priortise facilities for RTI/STI services; cost of plan meeting should be kept) |  |  |  |  |  |  |  |
| 1.1.4.2 | Monitor progress and quality of service delivery. |  |  |  |  |  |  |  |
| 1.1.5 | Operationalise sub-centres | No of visit | 25 trips | 100 trips | 1000 | 0.25 | 1.00 |  |
| 1.1.5.1 | Prepare plan for operationalising services at sub-centres (for a range of RCH services including antenatal care and post natal care; cost of plan meeting should be kept) |  |  |  |  |  |  |  |
| 1.1.5.2 | Monitor quality of service delivery and utilisation including through field visits |  |  |  |  |  |  |  |
| 1.2 | Referral Transport (home to facility, interfacility, dropback) |  |  |  |  |  |  |  |
| 1.3 | Integrated outreach RCH services |  |  |  |  |  |  |  |
| 1.3.1 | RCH Outreach Camps in un-served/ under-served areas (state should focus on facility based services and outreach camps to be restricted to areas without functional health facilities) |  | 12 | 12 | 20000 | 2.40 | 2.40 |  |
| 1.3.2. | Monthly Village Health and Nutrition Days |  |  |  |  |  |  |  |
| 1.3.2.1 | Monitor quality of services and utilisation |  |  |  |  |  |  |  |
| 1.4. | Janani Suraksha Yojana / JSY |  |  |  |  |  |  |  |
| 1.4.1 | Dissemination of JSY guidelines to districts and sub-districts |  |  |  |  |  |  |  |
| 1.4.2 | Implementation of JSY by districts. |  |  |  |  |  |  |  |
| 1.4.2.1 | Home deliveries | No | 1040 | 2576 | 500 | 5.20 | 12.88 |  |
| 1.4.2.2 | Institutional deliveries |  |  |  |  |  |  |  |
| 1.4.2.2.1 | Rural | No | 1917 | 8790 | 700 | 13.42 | 61.53 |  |
| 1.4.2.2.2 | Urban | No |  | 4734 | 600 |  | 28.40 |  |
| 1.4.2.2.3 | C-sections |  |  |  |  |  |  |  |
| 1.4.3 | Other activities (JSY) |  |  |  |  |  |  |  |
| 1.4.3.1 | ASHA Incentive | No | 1917 | 13524 | 600 / 200 | 11.50 | 62.21 |  |
| 1.4.3.2 | Admin Cost (5%) | No |  |  |  | 1.54 | 8.26 |  |
| 1.5 | Maternal Death Audit (both in institutions and community) | No | 350 | 670 | 750 | 2.63 | 4.88 |  |
| 1.6 | Other strategies/activities (please specify) ( Incentive for tracking of mothers who avail private facilities) | No |  | 3000 | 50 |  | 1.50 |  |
| 1.6.1 | JSSK- Janani Shishu Surakhsha Karyakram |  |  |  |  |  |  |  |
| 1.6.1 | Mother and Child Care |  |  |  |  |  |  |  |
| 1.6.1.1 | Diagnostic / Laboratory expenses | No | 2115 | 23500 | 200 / 300 | 4.45 | 49.35 |  |
| 1.6.1.2 | Blood Transfusion |  |  |  |  |  |  |  |
| 1.6.1.3 | Diet (3 days for Normal Delivery and 7 days for Caesarean) | No | 2115 | 23500 | 300 / 700 | 7.22 | 79.90 |  |
| 1.6.2 | Drugs and Consumables |  |  |  |  |  |  |  |
| 1.6.2.1 | Drugs and Consumables for Normal Deliveries | No | 1900 | 21150 | 500 | 9.50 | 105.75 |  |
| 1.6.2.2 | Drugs and Consumables for Caesarean Deliveries | No | 220 | 2350 | 2500 | 5.50 | 58.75 |  |
| 1.6.4 | Others (Pl. specify)- Referral transport under JSSK for mothers & Sick newborns | No | 2320 | 25850 | 800 | 18.56 | 206.80 |  |
|  | Sub-total Maternal Health (excluding JSY) |  |  |  |  | 52.26 | 515.83 |  |
|  | Sub-total JSY |  |  |  |  | 31.66 | 173.28 |  |
| 2. | CHILD HEALTH |  |  |  |  |  |  |  |
| 2.1 | IMNCI |  |  |  |  |  |  |  |
| 2.1.1 | Prepare detailed operational plan for IMNCI across districts |  |  |  |  |  |  |  |
| 2.1.2 | Implementation of IMNCI activities in districts |  |  |  |  |  |  |  |
| 2.1.3 | Monitor progress against plan; follow up with training, procurement, etc |  |  |  |  |  |  |  |
| 2.1.4 | Pre-service IMNCI activities in medical colleges, nursing colleges, and ANMTCs |  |  |  |  |  |  |  |
| 2.2 | Facility Based Newborn Care/FBNC (SNCU, NBSU, NBCC) |  |  |  |  |  |  |  |
| 2.2.1 | Prepare detailed operational plan for FBNC across districts (including training, BCC/IEC, drugs and supplies, etc.; cost of plan meeting should be kept). Operational cost of SNCU | No |  | 1 | 1000000 |  | 10.00 |  |
| 2.2.2 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |
| 2.3 | Home Based Newborn Care/HBNC |  |  |  |  |  |  |  |
| 2.3.1 | Prepare and disseminate guidelines for HBNC. |  |  |  |  |  |  |  |
| 2.3.2 | Prepare detailed operational plan for HBNC across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |
| 2.3.4 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |
| 2.4 | Infant and Young Child Feeding/IYCF |  |  |  |  |  |  |  |
| 2.4.1 | Prepare and disseminate guidelines for IYCF. |  |  |  |  |  |  |  |
| 2.4.2 | Prepare detailed operational plan for IYCF across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |
| 2.4.3 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  | 20000 / qtr | 0.20 | 0.80 |  |
| 2.5 | Care of Sick Children and Severe Malnutrition at facilities (e.g. NRCs, CDNCs etc.) |  |  |  |  |  |  |  |
| 2.5.1. | Prepare and disseminate guidelines. |  |  |  |  |  |  |  |
| 2.5.2 | Prepare detailed operational plan for care of sick children and severe malnutrition at FRUs, across districts ( cost of plan meeting should be kept). |  |  |  |  |  |  |  |
| 2.5.3 | Implementation of activities in districts. (JSSK) | No | 190 | 2350 | 1000 | 1.90 | 23.50 |  |
| 2.5.4 | Monitor progress against plan; follow up with training, procurement, etc. |  |  |  |  |  |  |  |
| 2.6 | Management of Diarrhoea, ARI and Micronutrient malnutrition |  |  |  |  |  |  |  |
| 2.7 | Other strategies/activities (please specify) |  |  |  |  |  |  |  |
| 2.8 | Infant Death Audit |  |  |  |  |  |  |  |
| 2.9 | Incentive to ASHA under child health | No | 920 | 11500 | 250 | 2.30 | 28.75 |  |
|  | Sub-total Child Health |  |  |  |  | 4.40 | 63.05 |  |
| 3 | FAMILY PLANNING |  |  |  |  |  |  |  |
| 3.1 | Terminal/Limiting Methods |  |  |  |  |  |  |  |
| 3.1.1 | Orientation workshop and dissemination of manuals on FP standards & quality assurance of sterilisation services | Batches | 1 | 2 | 50000 | 0.50 | 0.10 |  |
| 3.1.1.1 | Prepare operational plan for provision of sterilisation services at facilities (fixed day) as well as camps , review meetings |  |  |  |  |  |  |  |
| 3.1.1.2 | Implementation of sterilisation services by districts(including fixed day services and PP sterilization) |  |  |  |  |  |  |  |
| 3.1.2 | Organise female sterilisation camps | No | 8 | 15 | 15000 | 1.20 | 2.25 |  |
| 3.1.3 | Organise NSV camps |  |  |  |  |  |  |  |
| 3.1.4 | Compensation for female sterilisation | No | 600 | 3400 | 1000 / 1500 | 6.50 | 36.70 |  |
| 3.1.5 | Compensation for NSV Acceptance | No |  | 10 | 1500 |  | 0.15 |  |
| 3.1.6 | Accreditation of private providers to provide sterilisation services | No |  | 1 | 50000 |  | 0.50 | Green wood Hospital, Aizawl |
| 3.2 | Spacing Methods |  |  |  |  |  |  |  |
| 3.2.1 | IUD camps |  |  |  |  |  |  |  |
| 3.2.2 | Implementation of IUD services by districts (including fixed day services at SHC and PHC) |  |  |  |  |  |  |  |
| 3.2.2.1 | Provide IUD services at health facilities / compensation | No of Clients | 800 | 5000 | 50 | 0.40 | 2.50 | Rate increase from Rs.20/- to Rs50/- |
| 3.2.2.2 | PPIUCD services | No of Clients | 825 | 6612 | 100 / 200 | 1.24 | 8.38 | Incentive to clients for retention of IUD |
| 3.2.3 | Accreditation of private providers to provide IUD insertion services |  |  |  |  |  |  |  |
| 3.2.4 | Social Marketing of contraceptives (includng delivery of contraceptive by ASHA at door step) |  |  |  |  |  |  |  |
| 3.2.5 | Contraceptive Update seminars |  |  |  |  |  |  |  |
| 3.3 | POL for Family Planning/ Others (including additional mobilty support to surgeon's team if req) | Teams | 4 | 10 | 20000 |  | 2.00 |  |
| 3.4 | Repairs of Laparoscopes |  |  |  |  |  |  |  |
| 3.5 | Other strategies/activities (please specify): |  |  |  |  |  |  |  |
| 3.5.1 | Monitor progress, quality and utilisation of services (both terminal and spacing methods) including complications / deaths / failure cases. Note: cost of insurance / failure and death compensation NOT to be booked here | No of facility | 70 | 150 | 6000 | 4.20 | 9.00 |  |
| 3.5.2 | Performance reward if any |  |  |  |  |  | 7.84 | For Physical target, Plse ref the text |
| 3.5.3 | World Population Day’ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities |  |  |  |  |  | 9.00 | State, District, CHC & PHC level |
|  | Sub-total Family Planning (excluding Sterilisation Compensation and NSV Camps) |  |  |  |  | 7.14 | 39.07 |  |
|  | Sub-total Sterilisation Compensation and NSV Camps |  |  |  |  | 6.90 | 39.35 |  |
| 4 | ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH / ARSH |  |  |  |  |  |  |  |
| 4.1 | Adolescent services at health facilities |  |  |  |  |  |  |  |
| 4.1.1 | Disseminate ARSH guidelines.( Printing of guidelines) | Copy |  | 1500 | 200 |  | 3.00 |  |
| 4.1.2 | Establishment of new clinics at DH/SDH level | No | 2 | 5 | 100000 | 2.00 | 5.00 |  |
| 4.1.3 | Establishment of new clinics at CHC/PHC level | No | 10 | 29 | 100000 | 10.00 | 29.00 |  |
| 4.1.3.1 | Operating expenses for existing clinics |  |  |  |  |  |  |  |
| 4.1.4. | Outreach activities including peer educators ( Youth Festival & Health Melas) | N0 | 3 | 9 | 300000 | 9.00 | 27.00 |  |
| 4.2 | School health programme |  |  |  |  |  |  |  |
| 4.2.1 | Prepare and disseminate guidelines for School Health Programme. |  |  |  |  |  |  |  |
| 4.2.2 | Prepare detailed operational plan for School Health Programme across districts (cost of plan meeting should be kept) / Question Box activities | No | 30 | 120 | 5000 | 1.50 | 6.00 |  |
| 4.2.3 | Implementation of School Health Programme by districts. |  |  |  |  |  |  |  |
| 4.2.4 | Monitor progress and quality of services. |  |  |  |  |  |  |  |
| 4.3 | Other strategies/activities (please specify) Details of the Menstrual Hygiene project to be provided and budgeted under this head |  |  |  |  |  |  |  |
|  | Sub-total ARSH |  |  |  |  | 22.50 | 70.00 |  |
| 5 | URBAN RCH (focus on Urban slums) |  |  |  |  |  |  |  |
| 5.1 | Urban RCH Services |  |  |  |  |  |  |  |
| 5.1.1 | Identification of urban areas / mapping of urban slums |  |  |  |  |  |  |  |
| 5.1.2. | Prepare operational plan for urban RCH |  |  |  |  |  |  |  |
| 5.1.3 | Implementation of Urban RCH plan/ activities - Building rent, Electricity, Telephone, Water bill etc |  |  |  | 300000/qtr |  | 12.00 |  |
| 5.1.3.1 | Recruitment and training of link workers for urban slums |  |  |  |  |  |  |  |
| 5.1.3.2 | Strengthening of urban health posts and urban health centres |  |  |  |  |  |  |  |
| 5.1.3.3 | Provide RCH services (please specify) |  |  |  |  |  |  |  |
| 5.1.4 | Monitor progress, quality and utilisation of services. |  |  |  | 10000/ qtr |  | 0.40 |  |
| 5.1.5 | Other Urban RCH strategies/activities (please specify) - Salary of Support Staff | No |  | 25 | 6325 |  | 18.98 |  |
|  | Sub-total Urban Health |  |  |  |  | 0.00 | 31.38 |  |
| 6. | TRIBAL RCH |  |  |  |  |  |  |  |
| 6.1 | Tribal RCH services |  |  |  |  |  |  |  |
| 6.1.2 | Prepare operational plan for tribal RCH |  |  |  |  |  |  |  |
| 6.1.3 | Implementation of Tribal RCH activities |  |  |  |  |  |  |  |
| 6.1.4 | Monitor progress, quality and utilisation of services. |  |  |  |  |  |  |  |
| 6.1.5 | Other Tribal RCH strategies/activities (please specify) |  |  |  |  |  |  |  |
|  | Sub-total Tribal Health |  |  |  |  |  |  |  |
| 7 | PNDT Activities |  |  |  |  |  |  |  |
| 7.1 | Support to PNDT cell |  |  |  |  |  |  |  |
| 7.1.1 | Operationalise PNDT Cell |  |  |  |  |  | 3.50 |  |
| 7.1.2 | Orientation of programme managers and service providers on PC & PNDT Act |  |  |  |  |  | 0.50 |  |
| 7.2 | Other PNDT activities (please specify) |  |  |  |  |  |  |  |
|  | Sub-total PNDT activities |  |  |  |  | 0.00 | 4.00 |  |
| 8 | INFRASTRUCTURE AND HUMAN RESOURCES |  |  |  |  |  |  |  |
| 8.1 | Contractual Staff & Services |  |  |  |  |  |  |  |
| 8.1.1 | ANMs,supervisory nurses, LHVs | No |  | 428 |  |  | 555.66 |  |
|  | Normal Area | No |  | 57 | 9450 |  | 64.64 |  |
|  | Difficult Area | No |  | 122 | 10395 |  | 152.18 |  |
|  | Very difficult Area | No | 249 |  | 11340 | 338.84 |  |  |
| 8.1.2 | Laboratory Technicians, MPWs |  |  |  |  |  |  |  |
|  | Laboratory Technicians (Diploma) | No |  | 36 |  |  | 43.85 |  |
|  | Normal Area | No |  | 13 | 9600 |  | 14.98 |  |
|  | Difficult Area | No |  | 13 | 10200 |  | 15.91 |  |
|  | Very difficult Area | No | 10 |  | 10800 | 12.96 |  |  |
|  | Laboratory Technicians (Certificate) | No |  | 18 |  |  | 17.78 |  |
|  | Normal Area | No |  | 5 | 7500 |  | 4.50 |  |
|  | Difficult Area | No |  | 5 | 8125 |  | 4.88 |  |
|  | Very difficult Area | No | 8 |  | 8750 | 8.40 |  |  |
| A.8.1.3 | Specialists (Anaesthetists, Paediatricians, Ob/Gyn, Surgeons, Physicians, Dental Surgeons, Radiologist, Sonologist, Pathologist, Specialist for CHC ) | No |  | 9 |  |  | 50.00 |  |
|  | Normal Area | No |  | 6 | 44275 |  | 31.88 |  |
|  | Difficult Area | No |  | 2 | 48703 |  | 11.69 |  |
|  | Very difficult Area | No | 1 |  | 53573 | 6.43 |  |  |
|  | Dental Surgeons | No |  | 40 |  |  | 162.69 |  |
|  | Normal Area | No |  | 18 | 30250 |  | 65.34 |  |
|  | Difficult Area | No |  | 14 | 34375 |  | 57.75 |  |
|  | Very difficult Area | No | 8 |  | 41250 | 39.60 |  |  |
| A.8.1.4 | PHNs at CHC, PHC level / Staff Nurses | No |  | 237 |  |  | 416.55 |  |
|  | Normal Area | No |  | 77 | 12500 |  | 115.50 |  |
|  | Difficult Area | No |  | 73 | 15000 |  | 131.40 |  |
|  | Very difficult Area | No | 87 |  | 16250 | 169.65 |  |  |
| A.8.1.5 | Medical Officers at CHCs / PHCs | No |  | 55 |  |  | 229.35 |  |
|  | Normal Area | No |  | 20 | 30250 |  | 72.60 |  |
|  | Difficult Area | No |  | 20 | 34375 |  | 82.50 |  |
|  | Very difficult Area | No | 15 |  | 41250 | 74.25 |  |  |
| A.8.1.6 | Additional Allowances/ Incentives to M.O.s of PHCs and CHCs |  |  |  |  |  |  |  |
| A.8.1.7 | Others - Computer Assistants/ BCC Co-ordinator etc |  |  |  |  |  |  |  |
|  | Pharmacist | No |  | 28 |  |  | 34.88 |  |
|  | Normal Area | No |  | 18 | 10000 |  | 21.60 |  |
|  | Difficult Area | No |  | 3 | 10625 |  | 3.83 |  |
|  | Very difficult Area | No | 7 |  | 11250 | 9.45 |  |  |
|  | X-Ray Technician | No |  | 18 |  |  | 23.03 |  |
|  | Normal Area | No |  | 5 | 10000 |  | 6.00 |  |
|  | Difficult Area | No |  | 7 | 10625 |  | 8.93 |  |
|  | Very difficult Area | No | 6 |  | 11250 | 8.10 |  |  |
|  | BEE | No |  | 9 |  |  | 10.62 |  |
|  | Normal Area | No |  | 1 | 9000 |  | 1.08 |  |
|  | Difficult Area | No |  | 6 | 9750 |  | 7.02 |  |
|  | Very difficult Area | No | 2 |  | 10500 | 2.52 |  |  |
|  | Family Planning Counsellor | No |  | 2 | 15750 |  | 3.78 |  |
| A.8.1.8 | Incentive/ Awards etc. to SN, ANMs etc. |  |  |  |  |  |  |  |
| A.8.1.9 | Human Resources Development (Other than above) |  |  |  |  |  |  |  |
| A.8.1.10 | Other Incentives Schemes (Pl.Specify) |  |  |  |  |  |  |  |
| A.8.1.11 | Other activities (pl. specify) |  |  |  |  |  |  |  |
|  | Sub-total Infrastructure and Human Resources |  |  | 880 |  | 670 | 1548.17 |  |
| 9 | TRAINING (for each type of training, please provide the batch size in the rows below as applicable; in the physical target columns, pls put in the number of persons to be trained) |  |  |  |  |  |  |  |
| 9.1 | Strengthening of Training Institutions (SIHFW, ANMTCs, etc.) |  |  |  |  |  |  |  |
| 9.1.1 | Carry out repairs/ renovations of the training institutions |  |  |  |  |  |  |  |
| 9.1.2 | Provide equipment and training aids to the training institutions |  |  |  |  |  |  |  |
| 9.1.3 | Developing systems for monitoring & evaluations of training programmes. |  |  |  |  |  | 5.00 |  |
| 9.1.4 | Other activities (pl. specify) |  |  |  |  |  |  |  |
| 9.2 | Development of training packages |  |  |  |  |  |  |  |
|  | Development/ translation and duplication of training materials |  |  |  |  | 5.00 | 20.00 |  |
|  | Other activities (pl. specify) |  |  |  |  |  |  |  |
| 9.3 | Maternal Health Training |  |  |  |  |  |  |  |
| 9.3.1 | Skilled Attendance at Birth / SBA |  |  |  |  |  |  |  |
| 9.3.1.1 | Setting up of SBA Training Centres |  |  |  |  |  |  |  |
| 9.3.1.2 | TOT for SBA |  |  |  |  |  |  |  |
| 9.3.1.3 | Training of Medical Officers in Management of Common Obstetric Complications (BEmOC) | Batch | 3 | 10 | 39075 | 1.17 | 3.91 |  |
| 9.3.1.4 | Training of Staff Nurses in SBA | No | 15 | 68 |  | 4.13 | 18.74 | Unit of measure indicated in No due inconsistent batch size. |
| 9.3.1.5 | Training of ANMs / LHVs in SBA | No |  | 32 |  |  | 10.02 |  |
| 9.3.2 | EmOC Training |  |  |  |  |  |  |  |
| 9.3.2.1 | Setting up of EmOC Training Centres |  |  |  |  |  |  |  |
| 9.3.2.2 | TOT for EmOC |  |  |  |  |  |  |  |
| 9.3.2.3 | Training of Medical Officers in EmOC | No | 1 | 1 | 201000 |  | 2.01 |  |
| 9.3.3 | Life saving Anaesthesia skills training |  |  |  |  |  |  |  |
| 9.3.3.1 | Setting up of Life saving Anaesthesia skills Training Centres |  |  |  |  |  |  |  |
| 9.3.3.2 | TOT for Anaesthesia skills training |  |  |  |  |  |  |  |
| 9.3.3.3 | Training of Medical Officers in life saving Anaesthesia skills | No |  | 1 | 269800 |  | 2.70 |  |
| 9.3.4 | Safe abortion services training (including MVA/ EVA and Medical abortion) |  |  |  |  |  |  |  |
| 9.3.4.1 | TOT on safe abortion services |  |  |  |  |  |  |  |
| 9.3.4.2 | Training of Medical Officers in safe abortion (MTP) | Batch | 2 | 5 | 46000 | 0.92 | 2.30 |  |
| 9.3.5 | RTI / STI Training |  |  |  |  |  |  |  |
| 9.3.5.1 | TOT for RTI/STI training |  |  |  |  |  |  |  |
| 9.3.5.2 | Training of laboratory technicians in RTI/STI |  |  |  |  |  |  |  |
| 9.3.5.3 | Training of Medical Officers in RTI/STI | Batch |  | 1 | 138300 |  | 1.38 |  |
| 9.3.5.4 | Training of Staff Nurses in RTI/STI | Batch | 1 | 3 | 50600 | 0.51 | 1.52 | Unit of measure indicated in No due to inconsistent batch size |
| 9.3.5.5 | Training of ANMs / LHVs in RTI/STI | Batch | 1 | 3 | 50600 | 0.51 | 1.52 |  |
| 9.3.6 | BEmOC training |  |  |  |  |  |  |  |
| 9.3.7 | Other maternal health training (please specify) |  |  |  |  |  |  |  |
| 9.4 | IMEP Training |  |  |  |  |  |  |  |
| 9.4.1 | TOT on IMEP |  |  |  |  |  |  |  |
| 9.4.2 | IMEP training for state and district programme managers |  |  |  |  |  |  |  |
| 9.4.3 | IMEP training for medical officers |  |  |  |  |  |  |  |
| 9.4.4 | IMEP training for staff nurses | Batch | 2 | 10 | 48600 | 0.97 | 4.86 |  |
| 9.5 | Child Health Training |  |  |  |  |  |  |  |
| 9.5.1 | IMNCI & F-IMNCI Training (pre-service and in-service) |  |  |  |  |  |  |  |
| 9.5.1.1 | TOT on IMNCI (pre-service and in-service) |  |  |  |  |  |  |  |
| 9.5.1.2 | IMNCI Training for ANMs / LHVs | Batch |  | 4 | 218300 |  | 8.73 |  |
| 9.5.1.3 | IMNCI Training for Anganwadi Workers |  |  |  |  |  |  |  |
| 9.5.2 | F-IMNCI Training |  |  |  |  |  |  |  |
| 9.5.2.1 | TOT on F-IMNCI |  |  |  |  |  |  |  |
| 9.5.2.2 | F-IMNCI Training for Medical Officers |  |  |  |  |  |  |  |
| 9.5.2.3 | F-IMNCI Training for Staff Nurses | Batch | 2 | 12 | 123200 | 2.46 | 14.78 |  |
| 9.5.3 | Home Based Newborn Care / HBNC |  |  |  |  |  |  |  |
| 9.5.3.1 | TOT on HBNC |  |  |  |  |  |  |  |
| 9.5.3.2 | Training on HBNC for ASHA |  |  |  |  |  |  |  |
| 9.5.4 | Care of sick children and severe malnutrition at FRUs |  |  |  |  |  |  |  |
| 9.5.4.1 | TOT on Care of sick children and severe malnutrition |  |  |  |  |  |  |  |
| 9.5.4.2 | Training on Care of sick children and severe malnutrition for Medical Officers |  |  |  |  |  |  |  |
| 9.5.5 | Other child health training (please specify) |  |  |  |  |  |  |  |
| 9.5.5.1 | NSSK Training |  |  |  |  |  |  |  |
| 9.5.5.1.1 | TOT for NSSK |  |  |  |  |  |  |  |
| 9.5.5.1.2 | NSSK Training for Medical Officers |  |  |  |  |  |  |  |
| 9.5.5.1.3 | NSSK Training for SNs | Btach | 2 | 10 | 61000 | 1.20 | 6.10 |  |
| 9.5.5.1.4 | NSSK Training for ANMs | Batch | 3 | 5 | 61000 | 1.83 | 3.05 |  |
| 9.5.5.2 | Other Child Health training |  |  |  |  |  |  |  |
| 9.6 | Family Planning Training |  |  |  |  |  |  |  |
| 9.6.1 | Laparoscopic Sterilisation Training |  |  |  |  |  |  |  |
| 9.6.1.1 | TOT on laparoscopic sterilisation |  |  |  |  |  |  |  |
| 9.6.1.2 | Laparoscopic sterilisation training for doctors (teams of doctor, SN and OT assistant) | Team |  | 1 | 43550 |  | 0.44 |  |
| 9.6.2 | Minilap Training |  |  |  |  |  |  |  |
| 9.6.2.1 | TOT on Minilap |  |  |  |  |  |  |  |
| 9.6.2.2 | Minilap training for medical officers | Batch | 2 | 5 | 46000 | 0.92 | 2.30 |  |
| 9.6.3 | Non-Scalpel Vasectomy (NSV) Training |  |  |  |  |  |  |  |
| 9.6.3.1 | TOT on NSV |  |  |  |  |  |  |  |
| 9.6.3.2 | NSV Training of medical officers |  |  |  |  |  |  |  |
| 9.6.4 | IUD Insertion |  |  |  |  |  |  |  |
| 9.6.4.1 | TOT for IUD insertion |  |  |  |  |  |  |  |
| 9.6.4.2 | Training of Medical officers in IUD insertion |  |  |  |  |  |  |  |
| 9.6.4.3 | Training of staff nurses in IUD insertion |  |  |  |  |  |  |  |
| 9.6.4.4 | Training of ANMs / LHVs in IUD insertion | Batch | 1 | 5 | 37500 | 0.38 | 1.88 |  |
| 9.6.5 | Contraceptive update/ISD Training |  |  |  |  |  |  |  |
| 9.6.6 | Other family planning training (please specify) |  |  |  |  |  |  |  |
| 9.7 | Adolescent Reproductive and Sexual Health/ARSH Training |  |  |  |  |  |  |  |
| 9.7.1 | TOT for ARSH training |  |  |  |  |  |  |  |
| 9.7.2 | Orientation training of state and district programme managers |  |  |  |  |  |  |  |
| 9.7.3 | ARSH training for medical officers |  |  |  |  |  |  |  |
| 9.7.4 | ARSH training for ANMs/LHVs |  |  |  |  |  |  |  |
| 9.7.5 | ARSH training for AWWs |  |  |  |  |  |  |  |
| 9.8 | Programme Management Training (e.g. M&E, logistics management, HRD etc.) |  |  |  |  |  |  |  |
| 9.8.1 | Training of SPMSU staff (pls add rows to specify type of training) - Accounts Manager | No | 10 | 50 | 1280 | 0.13 | 0.64 |  |
| 9.8.2 | Training of DPMSU staff (pls add rows to specify type of training) - |  |  |  |  |  |  |  |
| 9.9 | Other training (pl. specify) -PHC/CHC Accounts Clerk Training | No | 13 | 66 | 1280 | 0.17 | 0.84 |  |
|  | Accounts training for HWs / ANMs | No | 90 | 400 | 1280 | 1.15 | 5.15 |  |
| A.9.10 | Training (Nursing) |  | 0 | 0 |  |  |  |  |
| A.9.10.1 | Strengthening of Existing Training Institutions/Nursing School (HR) |  |  |  |  |  |  |  |
| A.9.10.2 | New Training Institutions/School (Other strengthening) |  |  |  |  |  |  |  |
| A.9.11 | Training (Other Health Personnel's) |  | 0 | 0 |  |  |  |  |
| A.9.11.1 | Promotional Trig of health workers females to lady health visitor etc. |  |  |  |  |  |  |  |
| A.9.11.2 | Training of AMNs,Staff nurses,AWW,AWS |  |  |  |  |  |  |  |
| A.9.11.3 | Other training and capacity building programmes |  |  |  |  |  |  |  |
|  | Sub-total Training |  |  |  |  | 21.45 | 117.87 |  |
| 10 | PROGRAMME MANAGEMENT |  |  |  |  |  |  |  |
| 10.1 | Strengthening of State society/ State Programme Management Support Unit |  |  |  |  |  |  |  |
| 10.1.1 | Contractual Staff for SPMSU recruited and in position (Including HR, Management Cost, Mobility Support, Field Visits) | No |  | 34 |  |  | 100.93 | Salary RS. 75.93 lacs + Management, Mobility, Field Visit etc @ Rs.5 lacs/qtr i.e Rs.25 lacs |
| 10.2 | Strengthening of District society/ District Programme Management Support Unit |  |  |  |  |  |  |  |
| 10.2.1 | Contractual Staff for DPMSU recruited and in position (Including HR, Management Cost, Mobility Support, Field Visits) | No |  | 52 |  |  | 111.55 | Salary RS.83.55 lacs + Management, Mobility, Field Visit etc for 9 dists @ Rs.7 lacs/qtr i.e Rs.28 lacs |
| A.10.3 | Strengthening of Block PMU (Including HR, Management Cost, Mobility Support, Field Visits) | No |  | 66 |  |  | 103.70 | Salary RS. 95.70 lacs + Management, Mobility, Field Visit etc for Block @ Rs.8 lacs/year |
|  | Normal Area |  |  | 9 | 11250 |  | 12.15 |  |
|  | Difficult Area |  |  | 26 | 11875 |  | 37.05 |  |
|  | Very difficult Area |  | 31 |  | 12500 | 46.50 |  |  |
| A.10.4 | Strengthening (Others)-Office expenses etc |  |  |  | 200000/ qtr |  | 8.00 |  |
| A.10.5 | Audit Fees |  |  |  |  |  | 8.00 |  |
| A.10.6 | Concurrent Audit system |  |  |  |  |  | 10.00 |  |
| A.10.7 | Mobility Support, Field Visits to BMO/MO/Others |  |  |  |  |  |  |  |
|  | Sub-total Programme Management |  |  |  |  | 46.50 | 342.18 |  |
| 11 | VULNERABLE GROUPS |  |  |  |  |  |  |  |
| 11.1 | Other vulnerable communities not covered by Urban and Tribal RCH such as salt pan workers, migrants etc. |  |  |  |  |  |  |  |
| 11.2 | Services for Vulnerable groups |  |  |  |  |  |  |  |
| 11.2.1 | Mapping of vulnerable groups |  |  |  |  |  |  |  |
| 11.2.2 | Prepare operational plan for vulnerable groups (including infrastructure and human resources, training, BCC/IEC, equipment, drugs and supplies, etc.; cost of plan meeting should be kept). |  |  |  |  |  |  |  |
| 11.3 | Implementation of RCH activities |  |  |  |  |  |  |  |
| 11.4 | Other strategies/activities (please specify) |  |  |  |  |  |  |  |
|  | Sub-total Vulnerable Groups |  |  |  |  |  |  |  |
|  | TOTAL RCH II FLEXIPOOL |  |  |  |  | 824.45 | 2731.55 |  |
|  | TOTAL RCH II DEMAND SIDE |  |  |  |  | 38.56 | 212.63 |  |
|  | GRAND TOTAL |  |  |  |  | 863.01 | 2944.18 |  |

2012 – 2013  NRHM - PIP FOR  SCHOOL HEALTH PROGRAMME (SHP)

FOR THE STATE OF MIZORAM

INTRODUCTION : The School Health programme (SHP)  of Mizoram has not been incorporated under the programme implementation plan (PIP) of NRHM and funded  through State Plan and Non-Plan fund and   the beneficiaries are only from the Government run Primary schools student of classes 1-IV till 2010-2011. Hence, the proposal was chalked out to cover from class I – XII  as per the guidelines of the NRHM for the State in phase manner to be completed within 3 years starting from 2011 – 2012. The current proposal is for the 2nd phase of the planned activity for School Health Programme in Mizoram.

- Brief on the Programme:

School Health programme is a program for school health service under National Rural  Health Mission, which has been necessitated and launched in fulfilling the vision of NRHM to provide effective health care to population throughout the country. It also focuses on effective integration of health concerns through decentralized management at district with determinant of health like sanitation, hygiene, nutrition, safe drinking water, gender and social concern.

2.	Rationale for School Health Programme:

The School Health programme is the only public sector programme specifically focused on school age children. Its main focus is to address the health needs of children, both physical and mental, and in addition, it provides for nutrition interventions, yoga facilities and counseling. It responds to an increased need, increases the efficacy of other investments in child development, ensures good current and future health, better educational outcomes and improves social equity and all the services are provided for in a cost effective manner.

- Components of School Health Program:

Health service provision:

•Screening, health care and referral:

⁰Screening of general health, assessment of Anaemia / Nutritional status, visual 	acuity, 	hearing problems, dental check up, common skin conditions, Heart defects, 	physical disabilities, learning disorders, behavior problems, etc.

⁰Basic medicine kit will be provided to take care of common ailments prevalent 	among young school going children.

⁰Referral Cards for priority services at District / Sub- District hospitals.

•Immunisation:

⁰As per national schedule

⁰Fixed day activity

⁰Coupled with education about the issue

•Micronutrient ( Vitamin A & IFA ) management:

⁰Weekly supervised distribution of Iron – Folate tablets coupled with education about the issue.

⁰Administration of Vitamin A in needy cases.

•De- Worming

⁰As per national guidelines

⁰Biannually supervised schedule

⁰Prior IEC

⁰Siblings of students also to be covered

Health promoting Schools

⁰Counseling services

⁰Regular practice of Yoga, Physical education, health education

⁰Peer leaders as health educators.

⁰Adolescent health education- existing in few places

⁰Linkages with the out of school children

⁰Health clubs, Health cabinets

⁰First Aid room / corners or clinics.

•Capacity building

•Monitoring& Evaluation

•Mid Day Meal

- The strategy suggested for the programme:

For the state of Mizoram the strategy of Option - 1 has been selected from amongst the various options from the guideline of the School Health Programme to be implemented in the state. A framework for continuing  the programme has been chalked out wherein the ANM is to be spared once a week for school Health only as there will be MPW (male) or second ANM to support her at the health sub centre. The Multi Purpose worker male would be entrusted for exclusive boys senior basic school.Wherever possible the he indicative costing of the programme has been formulated so as to continue the  programme in the year 2012-13.

Based on a cascading training strategy involving Health and Education Departments TOTs will take place at State and District levels and teachers will be oriented on the programme so that they internalize the core values and strategies of the programme. Apart from the teachers screening the children, area ANMs/MPWs will visit one school every week on an average for detailed screening and treatment of minor ailment and required referral. In addition, a Medical Officer will also visit one school per week for additional screening, treatment and referral.

Inferring from the indicative costing, it has been proposed that the programme may be taken up in a phased manner covering 20% schools in the first year and 40% schools each in second and third year. The proposed cost of implementation so phased can then be met out of RCH – II Flexible Pool/ Mission Flexible Pool.

5.   Management structure for effective management

Management structure has been provided for in the guidelines at state, and District levels.

The NRHM convergence mechanism will apply to this programme as well. The involvement of State Health Mission and District Health Mission has been ensured by placing the School Health Programme  management committees under the overall Supervision/ Guidance of these overarching structures.

In addition, emphasis has been placed at making these management committees multi–departmental involving the functionaries of various related departments/ organizations such as Education, Rural Development, Public Health Engineering (PHED)

Various School Health Promotion Committees recommended at the State, District, Block and School levels will formed.

School Health Coordinator on Contract basis at the State and District levels has been provided to support the programme in the areas of Coordination monitoring and evaluation.

- Plan for Monitoring :

These management committees have been proposed in a manner that they bring in convergence between related departments/ organizations. The main convergence required in the programme is between the Ministry of Health & Family Welfare (MOHFW) Ministry of Rural Development (MRD) MHRD will be partner in capacity building. IEC, monitoring and evaluation. MRD needs to take case of water, safety Education, Sanitation Education and garbage disposal waste management. The MOHFW will take care of screening, Health care Services, Immunization, Referral micronutrient, management, Health Education, capacity Building, monitoring and evaluation etc.

7.   Cost of implementing the strategy will include :

- Cost training and Orientation at all levels mobility support to functionaries and incentives to them for carrying out this additional work.

- Fixed costs such as hardware and medical supply, IEC, printing of training manual, additional manpower provisioning at State and District Health Society levels for monitoring and evaluation.

- Provisioning of School Health Co-ordinator, 1 each at the State and District Health Society level for Programme Coordination, monitoring and evaluation.

The indicative cost for the Programme including the three components mentioned above is estimated at approximately l`.5228176  in the 1st year,  `.92,33,132   in the 2nd year,  ` 89,84,937  in the 3rd year and

` 102,27,330  from 4th year onwards.onward.

ENCLOSED	1) Indicative Costing for major activities under School Health Programme as proposed as per the guidelines of NRHM-PIP. From pages 1-7

2) NRHM-PIP guidelines on School Health Programme (SHP)

INDICATIVE COSTING FOR MAJOR ACTIVITIES UNDER SCHOOL HEALTH PROGRAMME

INTRODUCTION: For calculation of the indicative costing for the major activities under school Health programme following are the data of the state (Mizoram)-

- No.of districts:			-		       9

- No. of ANMs			-		1440

- No. of Schools			-	               3700

- No.of students			-	          289032

- No.of blocks			-		     30

1     Common costs for all options

- Personel cost during 2012 – 13  at the state Health society

|  |  |  |  | Monthly per state | Annual per state |
| --- | --- | --- | --- | --- | --- |
| 1. |  | Renumeration to school Health Programme coordinator (1 post ) MBA/ Master of social work ( with experience in training and outreach society work |  | `25,000 | `3,00,000 |
|  |  | Mobility support to the school Health coordinator |  | ` 5,000 | ` 60,000 |
|  |  | TOTAL |  | ` 30,000 | ` 3, 6 0,000 |
| 2.2. | Remuneration to School Health Programme(SHP)Medical Officer (MO) MBBS |  | ` 25,000 |  | ` 3,00,000 |
|  | Mobility support to the MO |  | ` 5,000 |  | ` 60,000 |
|  | TOTAL |  | ` 30,000 |  | `3,60,000 |
| 2.3. | Remunaration to SHP Dental Surgeon(BDSc)1 post |  | ` 25,000 |  | ` 3,00,000 |
|  | Mobility support to the Dental Surgeon |  | ` 5,000 |  | ` 60,000 |
|  | TOTAL |  | ` 30,000 |  | ` 3,60.000 |
| 3.4. | Remuneration to SHP Staff Nurse(BSc Nursing/GNM 1 post |  | ` 10,000 |  | ` 1,20,000 |
|  | Mobility support to the Staff Nurse |  | ` 2,000 |  | ` 24,000 |
|  | TOTAL |  | `12,000 |  | ` 1,44,000 |
| 55 | Remuneration to SHP Ophthalmic Assistant (OA) |  | ` 8,000 |  | ` 72,000 |
|  | Mobility support to the SHP –OA |  | ` 2,000 |  | ` 24,000 |
|  | TOTAL |  | ` 10,000 |  | ` 96,000 |
|  | GRAND TOTAL |  | ` 82,000 |  | `13,20,000 |

- Additional manpower requirement at the District Health Society

|  |  |  | Monthly Per District | Annual Per District | For 4 Districts |
| --- | --- | --- | --- | --- | --- |
| 1. | Renumeration to the school Health Programme coordinator (1 post): ((Master of Social Work with commerce background at +2 level and experience in training and outreach social work). The Coordinator will coordinate school Health programme and also the fund flow for the programme.He/She will also assist the district Accounts Manager in releasing funds and maintaining the Accounts for the SHP. District Accounts Manager will look after the over all accounting of school Health programme in the district. |  | ` 15,000 | ` 1,80,000 | `. 7,20,000 |
| 2. | Mobility support to the School Health coordinator |  | ` 5,000 | ` 60,000 | `. 2,40,000 |
|  | TOTAL AT DISTRICT LEVEL | ` 20,000 |  | ` 2,40,000 | `. 9,60,000 |  |

| Cost of hiring school Health coordinator at the District Health Society level as per phasing of coverage of Districts: |  |  |  |
| --- | --- | --- | --- |
| 20% District (1st year) | 40% District (2nd year)2012-13 | 40% District (3rd year) | 100% District ( 4th year onwards) |
| ` 48,0000 | ` 96,0000 | ` 96,0000 | ` 2,40,0000 |

- Hardware and Medical supply ( for phasing of 3700  Schools) per annum

|  |  | 1st year | 2nd year (2012-13) onwards |
| --- | --- | --- | --- |
| 1. | One time capital cost Weighing scale (Rs.500) and height measurement equipment ( wall mounted) (Rs.100) and sneller’s chart for bigger schools (` 80) | ` 680 | NIL |
| 2. | Student health cards referral cards, 2 registers per year | ` 535 | ` 535 |
| 3. | Medical kit | ` 140 |  |
| 4. | IFA tablet | ` 547 | ` 547 |
| 5. | Albendazole | ` 250 | ` 250 |
| 6. | Spectacles @ Rs.125/- being revised to Rs 200 per 250 students – cost may be borne by NBCP |  | ` 200 |
| 7. | Travel cost for referral (1% of all screened Rs.100/- per referral) | ` 250 | ` 250 |
| 8. | Total cost for one School | ` 2,402 | ` 1,707 |
| 9. | Total cost for 3700 Schools in Mizoram. | ` 88,87,400 | ` 63,15,900 |

| Phasing of cost incurred on Hardware and Medical supply Estimates for state of Mizoram |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 1 st year (20%) | 2nd year (40%) 2012-13 | 3rd year (40%) | 4th year onwards per year |
| No. of each School | 740 | 1480 | 1480 | 3700 |
| Expenditure in 3 year for new units taken up for the first time | `17,77,480 (with capital expenditure) | `35,54,960 (with capital expenditure) | `35,54,960 (with capital expenditure) |  |
| Expenditure from 4th year onwards |  |  |  | `63,15,900 |
| Total Expenditure | ` 1777480 | ` 35,54,960 | ` 35,54,960 | `63,15,900 |

- Printing of Training Manual ( for  3700  schools @ unit cost of Rs. 100 per copy )

| Phasing of printing and supply of training manual |  |  |  |
| --- | --- | --- | --- |
| 1st year(20%) 740 schools | 2nd year (2012-13) (40%)1480 schools | 3rd year(40%) 1480 schools | 4th year (100%) `3,700 |
| `74,000 | `1,48,000 | `1,48,000 | `3,70,000 |

- IEC  cost with phasing for the State of Mizoram based on the no. of Schools to be covered each year.

|  | Cost for 1st year | Cost for 2nd year (2012 – 13) | Cost for 3rd year | Cost from 4th year onwards |
| --- | --- | --- | --- | --- |
|  | No. of schools (20%) 740 | No. of schools ( 40%) 1480 | No. of schools (40%) 1480 | No. of schools (100%) 3700 |
| Posters ( 4 each school @ Rs.10/- each) | ` 29,600 | ` 59,200 | ` 59,200 |  |
| Leaflet: 170 per school @ Rs. 0.30 each | ` 37,740 | ` 75,480 | ` 75,480 |  |
| Repeat requirement of posters |  | ` 29,600 | ` 88,800 |  |
| Repeat requirement of Leaflets |  | ` 37,740 | ` 1,13,220 | ` 1,88,700 |
|  | ` 67,340 | ` 2,02,020 | ` 3,36,700 | ` 1,88,700 |

2.Cost of A Option 1

Teachers screen students on a continuous basis and ANMs and a Doctor visit the schools for treatment of minor ailments and referral

A.1. STATE LEVEL TRAINING OF MASTER TRAINERS FROM DISTRICTS AT SIHFW( 1 BATCH )

Cost of Training of Participants from Districts

There are 9 Districts in the State 18 participants would be trained at the State level 1 from DIET (Education Dept) and I MO from Health Dept .

|  | Per day cost/ person | Total per day 18person | Total for 18persons for 5 days | Total for Mizoram state | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Honorarium | `500 | `9,000 | `1,62,000 | `1,62,000 |  |  |  |
| Refreshment | ` 50 | ` 900 | `16,200 | ` 16,200 |  |  |  |
| Stationary | ` 20 | ` 360 | `6,480 | `6,480 |  |  |  |
| Total | ` 570 | ` 10,260 | `184800 | `184680 | `36,936 | ` 73872 | `73872 |

Consisting of 2 personnel from each District trained for 5 days)

A.2	DISTRICT LEVEL – Training of  Block trainiers at DIET (District Institute of  Education & Training) for 3 days; 1 batch of 20 trainees from 10 blocks in the District.

| - Cost of engaging 2 Master trainers (Who have been trained at State Level) for imparting training to Block level trainers |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Per day cost per person | Total per day all persons | Total all days | Total 9 District | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| Honorarium | ` 300 | `600 | ` 1,800 | ` 16,200 |  |  |  |
| Refreshment | `50 | `100 | ` 300 | ` 2,700 |  |  |  |
|  | ` 350 | `700 | ` 2,100 | ` 18,900 | ` 3,780 | `7,560 | `7,560 |

| II. Cost of training trainees from Block within the Districts (10 blocks have been taken for calculation purposes ) for 2 days, 2 persons from each block need to be trained. 1 from BRC (Block Resource centre of education Department) and 1 doctor from CHC/PHC. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Phasing |  |  |
|  | Per day cost/person | Total per day all persons | Total all days | Total 9 districts | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| TA/DA | ` 200 | ` 4,000 | ` 8,000 | `72,000 |  |  |  |
| Refreshment | `50 | `1,000 | ` 2,000 | `18,000 |  |  |  |
| Stationary | `20 | ` 400 | ` 800 | ` 7,200 |  |  |  |
|  | ` 270 | ` 5,400 | `10,800 | `97,200 | ` 19,440 | `38,880 | ` 38,880 |

| - Cost of engaging 2 Master trainers who have been trained at District level (1 from BRC and 1 Doctor from CHC/PHC) for 2 days. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Phasing |  |  |
|  | Per day cost/person | Total per day(2 persons) | Total all days (2 daysx8 batches=16 days. | Total for Mizoram (30Blocks) | 20% (1st year) | 40% (2nd year) 2012-13 | 40%(3rd year) |
| Honorarium | `200 | `400 | `6,400 | `1,92,000 |  |  |  |
| Refreshment | ` 50 | `100 | `1,600 | ` 48,000 |  |  |  |
| Stationary | `20 | ` 40 | ` 640 | ` 19,200 |  |  |  |
|  | `270 | ` 540 | `8,640 | `2,59,200 | ` 51,840 | `1,03,680 | `1,03,680 |

| ii. Cost of training Teachers from Schools in the Block (2 teachers from each School)As there are approximately 500 schools in a District, there would be 150 Schools in a block. Thus 300 teachers @ 2 teachers per school need to be trained. The BRC can take a batch of 40 teachers, 8 batches would be needed to cover 300 teachers. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Phasing |  |  |
|  | Per day cost person | Total per day (40 persons) | Total all days (2 daysx8 batches=16 days. | Total 26 blocks for Mizoram | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| TA/DA | `100 | `4,000 | ` 64,000 | `19,20,000 |  |  |  |
| Refreshment | ` 50 | ` 2,000 | ` 32,000 | `9,60,000 |  |  |  |
| Stationary | ` 20 | ` 800 | `12,800 | ` 384000 |  |  |  |
| Total | `170 | ` 6,800 | `1,08,800 | ` 3264000 | `6,52,800 | `13,05,600 | `13,05,600 |

- If 1 ANM can cover 1 school in a day, it will take 211 days to cover 211 schools in a block.

- Thus time taken to cover 211 schools by 15 number of ANMs will be 14 days

- One Doctor from CHC/PHC will also visit one school per week. As there are 32 weeks in a school session 32 such visit will be possible

| - Orientation of ANMs for SHP in Block CHC for 2 days: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Block level ANMs | District level | Mizoram State level | Phasing |  |  |
|  | Each ANM each day | Each ANM for 2 days | For 30 in a Bloc for 2 days | For 300 ANMs in a District (2 days) | 9 District of Mizoram | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| TA/DA | `100 | ` 200 | `6,000 | ` 60,000 | ` 5,40,000 |  |  |  |
| Refreshment | ` 50 | ` 100 | ` 3,000 | ` 3,000 | ` 27,000 |  |  |  |
| Stationary | ` 20 | ` 40 | ` 1,200 | ` 12,000 | ` 108,000 |  |  |  |
| Total | `170 | ` 340 | `10,200 | ` 1,02,000 | ` 675,000 | `1,35,000 | `27,0000 | `270000 |

| II. Mobility support to ANMs to visit Schools |  |  | Phasing |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Per day | For 14 working days | 20% (1st year) | 40% (2nd year) 2012-13 | 40% (3rd year) |
| For 1 ANM each day | ` 100 | `1,400 |  |  |  |
| For 6 ANM in a block | `600 | `8,400 |  |  |  |
| For 90 ANMs in a District | ` 9,000 | `1,26,000 |  |  |  |
| For 1440 ANM in the State | ` 14,400 | `2,01,600 |  |  |  |
| Total | ` 24,100 | `3,37,400 | `67,480 | ` 1,34,960 | `1,34,960 |

| III . INCENTIVE TO ANMs FOR COVERING EACH SCHOOL Phasing |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | For 14 working days | 20%(1st year) | 40%(2nd year) 2012-13 | 40%(3rd year) |
| Incentive to 1 ANM for covering 1 school | ` 100 |  |  |  |
| Incentive to 1 ANM for 14 schools in a year. | ` 1,400 |  |  |  |
| Incentive to 6 ANMs in a Block for covering 14 schools in a year. | ` 8400 |  |  |  |
| . Incentive to 90 ANMs in a District in a year for covering 14 schools in Block. | ` 16,800 |  |  |  |
| Incentive to 90 ANMs in a District in a year for covering 14 schools in Block. | ` 2,52,000 |  |  |  |
| For 1440 ANMs in the State | ` 20,16,000 | `4,03,200 | `8,06,400 | `8,06,400 |

Incentive to Doctor

A doctor from Block CHC/any PHC will visit one school per week to cover 32 schools per annum. The selection of school will be based on the screening reports submitted by ANMs

|  | Phasing |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Per Visit | For 32 Visits | For 30 blocks in Mizoram | 20% (1st year) | 40% (2nd year) 2012-13 |  | 40% (3rd year) |
| Incentive to 1 Doctor to visit 1 school per week (32 weeks are available during school session | ` 300 | ` 9,600 | ` 2,88,000 | ` 57,600 | ` 1,15,200 |  | ` 1,15,200 |
| Mobility support to Doctors to visit schools | ` 500 | ` 16,000 | ` 4,80,000 | ` 96,000 | ` 1,92,000 |  | ` 1,92,000 |
| TOTAL EXPENDITURE | ` 800 | ` 25,600 | ` 7,68,000 | ` 1,53,600 | ` 3,07,200 | ` 3,07,200 |  |

| GRAND TOTAL OF EXPENDITURE ON OPTION - I | YEAR - I | YEAR – 2 (2012-13) | YEAR – 3 | YEAR – 4 ONWARDS |
| --- | --- | --- | --- | --- |
|  | ` 52,28,176 | ` 92,33,132 | ` 89,84,937 | ` 102,27,330 |

OPTION– I  has been selected out of the various options, hence the calculation cost Indicative Costing for Major Activities Under School Health Programme of 2012 – 2013  for 2nd  year Grand Total  Amount of `92,33,132 may be incurred from as per  School Health Programme (SHP) – Programme Implementation Plan (PIP) NRHM guideline.  All expenditures are to be budgetted under RCH – NRHM Management Costs.

B 	MISSION FLEXI POOL

B.i CORE ACTIVITIES

Non Negotiable components:

For certain components, the allocation of funds has to be made as per pre-determined norms and the States cannot deviate from them. These non negotiable components are- Village Health and Sanitation Committee Funds, Untied Funds for different levels of facilities, Annual Maintenance Grants to health facilities, Rogi Kalyan Samiti Funds and ASHA training and drug kits. The norms for allocation of funds under non negotiable components are as under:

♦   Facility level funds:

| Levels of facility | Annual Maintenance Grant | Untied Funds (UF) | RKS Grants (RKS) |
| --- | --- | --- | --- |
| Sub-centre | Rs. 10,000 | Rs. 10,000 | — |
| PHC | Rs. 50,000 | Rs. 25,000 | Rs. 1,00,000 |
| CHC/SDH | Rs. 1,00,000 | Rs. 50,000 | Rs. 1,00,000 |
| DH | — | — | Rs. 5,00,000 |

- Village Health and Sanitation Committee Funds: Rs 10,000 per year

- ASHA : Rs 10,000 per ASHA per year for training and drug kits

- The State may ensure that the untied fund, RKS and AMG Grant will be provided to the facilities
on the basis of utilization of funds of the previous financial year.

B.i.a ASHA (Accredited Social Health Activist) :

It was a great privilege for rural poor communities to have ASHA identified and selected from among themselves to work in their own villages, and had warmly welcomed the initiatives undertaken in NRHM programme, to revive their involvements in health care services for their own interest and benefits.

PRESENT SITUATION :-

- At present, there are 987 ASHA in Mizoram against a population of 10.91 lakhs (Census 2011)

- ASHA 1 to 7th modules, ASHA documentary - video clip and Flip charts are available in Local languages at all the Districts.

- ASHA Resource Centre not yet established and ASHA facilitator not yet selected in Mizoram till date.

- There is no separate ASHA coordinator at the state as well as District.

- Refresher cum 2nd Round State level ToT of ASHA Mod 6&7 was conducted during 9th to 16th Sept, 2011. All the essential training Kits/materials were utilised during ToT.

- During the 2nd round of ToT for ASHA 6th&7th Module, Field practice was organised at Aibawk Village which is 30 KMs away from the Training site for practice session on Nutritional counselling.

- Practice session, Recap/role play and Evaluation test was conducted each day during Training.

- There are 2 qualified trainers for the state and there are 4 identified District trainers. The two State trainers had undergone 2nd round National level ToT at Gadchiroli, Nagpur during 18th to 25th August, 2011.

- 2nd Round 6th and 7th Module Training for ASHA at the District level will be conducted during 4th Quarter 2011-12.

ASHAs being selected by the concern Village Health Sanitation and Nutrition Committee, guided by the President of Village Council. ASHA trainings are being organized for their improvement of skills and capacity buildings, with cooperatives supports of VHSNC to provide all necessary helps and assistances to Health Workers, for further reductions of mortality and morbidities in their respective villages.

As there is no ASHA facilitator in the State as well at the District, supervision and monitoring is done by DPMSU at the District level. Every VHSNC were informed to purchase ASHA diary from VHSNC fund and their daily activities were recorded in their dairy. But If VHSNC purchase ASHA diary then there is least chance of having uniformity, so it would be wise to procure and distribute diary centrally from the state. The expenditure may be booked under VHS&NC. ASHA monthly report form is prepared at the district level to have maximum involvement in terms of health care delivery system.

Selection of PHC/CHC level ASHA Facilitator and District ASHA Coordinator will help for effective implementation of ASHA program. .

The selection criteria for ASHA Facilitator and District ASHA Coordinator are as follows:-

ASHA Facilitator:

- ASHA Facilitator must be a woman in the age group of 25- 45 years.

- At least Cl-X Standard pass ,for existing ASHAs, otherwise class 12 pass knowing local language and good communication skills, having experience of social work.

- Honorarium of Rs. 1000/- pm Plus incentive, DA @ Rs. 200/- per day for 15 days etc.

District ASHA Coordinator:-

- District ASHA Coordinator must be women having good communication skills and education at least Graduate level with experience of working in social sector or PG in social science..

- Honorarium of Rs. 8000/- pm

Job responsibilities of the ASHA Facilitator and ASHA Coordinator are as follows:-

- ASHA Facilitator should support the activities of ASHA within the area and give support at any time

- She will support and monitor VHSNC Meeting in the area and submit all the activities of ASHA at the higher level.

- She should maintain her diary properly for documentation and further utilization for claiming any incentives/compensation to the higher authority.

- The District ASHA Coordinator will look after all the activities of ASHA as well as ASHA Facilitators within the district through PHC / CHC / Sector level meeting.

- She should monitor, supervise and evaluate the ASHA Program and submit all the required information to CMO through the DPMSU.

ACTION PLAN ON ACCREDITED SOCIAL HEALTH ACTIVIST

| Sl. No. | Issues in Planning in ASHA | Current Status | Activities to be undertaken to achieve targets | Outputs to be achieved | Time Frame for 2012-13 |
| --- | --- | --- | --- | --- | --- |
| 1 | Training | 1-5 modules for 987 ASHAs completed, 1st round 6&7 mod training was completed and 2nd round 6&7 Mod ToT has been completed as well. The 2nd round ASHA training is due to start in 4th qtr of 11 - 12. | 3rd round ToT for 6th and 7th module and 5 days training of ASHAs each for 3rd and 4th round in 6& 7th module will be held. Re orientation for all ASHAs which may be conducted during the ASHA quarterly review meeting. | Improvement of skills and capacity building. | 2nd Qtr |
| 2 | Replenishment of ASHA Drugs | Pregnancy test kit, RDK, ASHA packages, Drugs and supplies are being provided for all the ASHAs on Half yearly basis | Collect the required quantity of ASHA kits with register and deliver them (twice a year) | Strengthening service delivery at the the villages | 1st Qtr |
| 3 | New initiatives | At present there is no District ASHA Coordinator and ASHA facilitator at the district level. | Selection of District ASHA Coordinator @Rs 8000/-pm Selection of ASHA facilitator @ 1000/- per month + incentives per visit, DA etc. @ Rs.200/- per day for maximum 15 days a month | Strengthening support mechanism of ASHA | 1st Qtr |
| 4 | ASHA Rest House | ASHA Rest House is not available at any level during 2011-12 | Identify a specific ward/room lying vacant at the delivery points at DH/CHC/PHC level. Basic expenditure would be met out of RKS fund | Strengthening of ASHA support mechanism. | 2nd Qtr |

| 5 | Review meeting for ASHA | No specific routine followed so far | Quarterly one day review meeting at the PHC/CHC level/sector level | Strengthening support mechanism of ASHA | 2-4th Qtr |
| --- | --- | --- | --- | --- | --- |
| 6 | Review meeting for District ASHA Coordinator | There is no District ASHA Coordinator during 2011-12 | Quarterly review meeting at the State level (plan for 3 qtr as selection will take 1 qtr) | Strengthening support mechanism of ASHA | 2-4th Qtr |
| 7 | Review meeting for ASHA Facilitator | There is no ASHA Facilitator during 2011-12 | Quarterly review meeting at the District level (plan for 3 qtr as selection will take 1 qtr) | Strengthening support mechanism of ASHA | 2-4th Qtr |
| 8 | Observation of ASHA Conference | Not yet observed so far | ASHA Conference may be observed on the date when NRHM was launched. | To increase Motivational level of ASHA | 1st Qtr |
| 9 | Quarterly AMG meeting | Half yearly meeting held during 2011-12 | Review of the overall ASHA programmes at the state level. Specific districts will be allotted to the AMG members and field visits will be done accordingly. | Strengthening support mechanism of ASHA | 1-4th Qtr |

BUDGET PLAN ON ASHA FOR 2012-2013

District wise information

| Name of District | Proposed ASHA Target | Selected / In place ASHA | Status of ASHA trained |  |  |  |  |  |  | Number of ASHA dropped out (left work) | Drug kits distributed to ASHA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Mod-1 | Mod-2 | Mod-3 | Mod-4 | Mod5 | Mod 6 (1st round) | Mod 7 |  |  |
| Aizawl E | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | Module 7 training will be held during 4th Qtr 2011-12 | Not Available | 124 |
| Aizawl W | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 |  |  | 119 |
| Kolasib | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  |  | 75 |
| Mamit | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 |  |  | 62 |
| Serchhip | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 |  |  | 54 |
| Champhai | 122 | 122 | 122 | 122 | 122 | 122 | 122 | 122 |  |  | 122 |
| Lunglei | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 |  |  | 186 |
| Lawngtlai | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 |  |  | 174 |
| Saiha | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 |  |  | 71 |
| TOTAL | 987 | 987 | 987 | 987 | 987 | 987 | 987 | 987 |  |  | 987 |

| BUDGET PLAN FOR 3rd ROUND STATE LEVEL ASHA ToT ON MOD 6&7 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons | No. of days | Total budget |
| TA for trainees (to and fro) | Saiha District | 600/ | 2 |  | 2400 |
|  | Lawngtlai | 550/ | 2 |  | 2200 |
|  | Lunglei | 330/ | 2 |  | 1320 |
|  | Serchhip | 200/ | 2 |  | 800 |
|  | Champhai | 350/ | 2 |  | 1400 |
|  | Mamit | 200/ | 2 |  | 800 |
|  | Kolasib | 150/ | 2 |  | 600 |
| DA | Trainees (18 from Districts + 4 State trainers) | 150/- per day | 22 | 8 days | 26,400/- |
|  | DA for Mothers and Driver on Field practice | 100/- per head | 8 mothers + 1 driver + 1 helper | 1 day | 1000 |
|  | Supporting staff | 100/- | 2 | 8 days | 1600 |
| Honorarium | Resource persons/State Trainers | 500/- | 4 | 8 days | 16,000 |
| TA/DA Total |  |  |  |  | 54,520/- |

| Material | Training material : notepad, pen, folder, Chart paper, marker pen etc. | 80/- per head | 22 |  | 1760 |
| --- | --- | --- | --- | --- | --- |
| Banner | Banner to put up at the training Hall | 700/- |  |  | 700 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 80/- per head | 35 | 8 days | 22400 |
| Hall Rent | Hall rent at the state training site | 500/- |  | 8 days | 4000 |
| Mobility | Transportation for field practice (Hirer of Bus) | 3000/- (to and fro) |  | 1 day | 3000 |
| TOTAL |  |  |  |  | 86,380/- |
| Grand Total : Rs. 86,380/- (Rupees Eighty six thousand three hundred and eighty) only. |  |  |  |  |  |

| Budget Plan for 3rd round and 4th round training of ASHA at PHCs/CHC at District level |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total No. of District - 9 |  |  |  |  |
| Sl.No | Particulars |  | Amount | Remarks |
| 1 | DA @ Rs. 200/day for (5+5) = 10 days x 987 ASHA's | Rs.200 x10 daysx987 | 19,74,000 | Inclusive of refreshment, etc. |
| 2 | TA @ Rs. 150x4days x 987 participants. | 150x4x987 | 5,92,200 |  |
| 3 | Hall Rent @ Rs. 500 /day | 500x10daysx9 | 45,000 | 9 Districts |
| 4 | Training Material @ Rs. 80/participants for 3rd round | 80x987 | 78960 |  |
| 5 | Training Material @ Rs. 80/participants for 4th round | 80x987 | 78960 |  |
| 6 | Training manual for trainers @ 150/- per trainer | 150 per trainerx24 trainer | 3600 |  |
| 7 | DA for Trainers/resource persons @ Rs. 200/trainer | 200x2trainersper batchx33batchx10 days | 132000 |  |
| 8 | Honororium of Resource person (District/ASHA trainer)@ 300x33batchx10daysx2trainers | 300x33batchx10daysx2trainers | 198000 |  |
| 9 | Honorarium For six Full time State Trainers @Rs 6000/- per month for 6month | 6000x6x6 | 2,16,000 |  |
| Total |  |  | 33,18,720 |  |

Grand Total: 33,18,720/- (Rupees thirty three lakh eighteen thousand seven hundred and twenty) only

| Budget Plan for Drug Kits refilling : |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. of times proposed to refill in a year : Half yearly |  |  |  |  |
| Sl.No | Particulars | Frequency | Unit Cost | Total Amount |
| 1 | ASHA Drug kits replenishment | Half yearly | Rs. 600 per ASHA | 600x 987 x 2 = 11,84,400 |

Grand Total: 11,84,400/- (Rupees eleven lakh eighty four thousand and four hundred) only.

| Selection of District ASHA Coordinator and ASHA Facilitator : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. of District ASHA Coordinator to be selected : 9 No. of ASHA Facilitator to be selected : 66 |  |  |  |  |  |
| Honorarium for the 1st Quarter has not been counted as it will be engaged for the selection, recruitment and induction training for District ASHA Coordinator and ASHA Facilitator |  |  |  |  |  |
| Sl.No | Particulars | No. of manpower | Honorarium per month | Unit Cost | Total Amount |
| 1 | Selction of District ASHA Coordinator | 9 | 8000 | 8000x9x9 | 648000 |
| 2 | Selction of ASHA Facilitator | 66 | 1000 + incentives @200x15 days = 4000 | 4000x9x66 | 2376000 |

INDUCTION Training for District ASHA Coordinator and ASHA Facilitator: 4 days each Induction training will be held at the state level.

| BUDGET PLAN FOR INDUCTION TRAINING OF DISTRICT ASHA COORDINATOR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons | No. of days | Total budget |
| TA for DAC (to and fro) | Saiha District | 600/- | 1 |  | 1200 |
|  | Lawngtlai | 550/- | 1 |  | 1100 |
|  | Lunglei | 330/-) | 1 |  | 660 |
|  | Serchhip | 200/- | 1 |  | 400 |
|  | Champhai | 350/- | 1 |  | 700 |
|  | Mamit | 200/- | 1 |  | 400 |
|  | Kolasib | 150 | 1 |  | 300 |
| DA | DA for DAC from all the Districts | 150/- per day | 9 | 4 days | 5400 |
| Honorarium | Resource persons/Trainers | 500/- per day | 4 | 4 days | 8000 |
| TA/DA Total |  |  |  |  | 18,160/- |

|  | Training material : notepad, pen, folder etc. | 60/- per head | 9 |  | 540 |
| --- | --- | --- | --- | --- | --- |
| Banner | Banner to put up at the training Hall | 700/- |  |  | 700 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 80/- per head | 15 | 4 days | 4800 |
| Hall Rent | Hall rent at the state training site | 500/- |  | 4 days | 2000 |
|  |  |  |  | TOTAL | 26,200/- |
| Grand Total: Rs. 26,200/- (Rupees Twenty Six thousand Two hundred ) only. |  |  |  |  |  |

| BUDGET PLAN FOR INDUCTION TRAINING OF ASHA FACILITATOR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons | No. of days | Total budget |
| DA | DA for ASHA Facilitator from all the PHC/CHC | 100/- per day | 66 | 4 days | 26400 |
|  | DA for supporting staff | 100/- per day | 2 | 4 days | 800 |
| Honorarium | Resource persons/Trainers | 300/- per day | 2 | 4 days | 2400 |
| TA/DA Total |  |  |  |  | 29,600/- |
|  | Training material : notepad, pen, folder etc. | 60/- per head | 9 |  | 540 |
| Banner | Banner to put up at the training Hall | 700/- |  |  | 700 |
| Training Manual | Training manual for all the 66nos of ASHA Facilitators | 150/- per manual | 100(66 copies for the AF and remaining 34 copies for ARC) |  | 15000 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 80/- per head | 15 | 4 days | 4800 |
| Hall Rent | Hall rent at the state training site | 500/- |  | 4 days | 2000 |
|  |  |  |  | TOTAL | 52,640/- |
| Grand Total : Rs. 52,640/- (Rupees Fifty Two Thousand Six Hundred and forty) only. |  |  |  |  |  |

| Action Plan for Review meeting of ASHA/DAC/ASHA Facilitator : |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. of times proposed to be held : Quarterly |  |  |  |  |
| The quarterly review meeting for ASHAs can also be used as a platform for refresher training for all the module training of ASHAs that are held in the state. |  |  |  |  |
| Sl.No | Particulars | Frequency | Remarks |  |
| 1 | Review meeting for ASHA at PHC/CHC level | Quarterly | The details budgeting is as below: |  |
| 2 | Review meeting for District ASHA Coordinator at State Level | Quarterly |  |  |
| 3 | Review meeting for ASHA Facilitator at District Level | Quarterly | No TA/DA is proposed as ASHA Facilitators will attend the district level meeting one day out of the proposed 15 days field trip |  |
| 4 | AMG Review Meeting at state level | Quarterly | The details budgeting is as below: |  |
| 5 | Field visit of AMG members | Half yearly |  |  |

| REVIEW MEETING FOR ASHA AT PHC/CHC LEVEL (57 PHCs+9 CHCs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements |  |  | Rate (in Rupees) |  | No. of ASHAs per PHC/CHC |  |  |  | Frequency |  |  |  | Amount |  |  |
| TA / DA for ASHAs | Quarterly review meeting |  |  | 200/- per ASHAs |  | 200 x 987x 4 |  |  |  | 4 Quarters |  |  |  | 789600 |  |  |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. |  |  | 50/- per head |  | 50x 987x 4 |  |  |  | 4 Quarters |  |  |  | 197400 |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  | 9,87,000/- |  |  |
| REVIEW MEETING FOR ASHA FACILITATOR AT DISTRICT LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head | Particulars/Requirements |  |  |  | Rate (in Rupees) |  |  | No. of persons |  |  |  | Frequency |  |  |  | Amount |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. |  |  |  | 50 per head |  |  | 70 |  |  |  | 3 Quarters |  |  |  | 10,500 |
| DA/TA for ASHA Facilitators | 200 per ASHA Facilitator |  |  |  | 200 X 66 X 3 |  |  | 66 |  |  |  | 3 Q |  |  |  | 39600 |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL |  |  |  | 50,100/- |
| REVIEW MEETING FOR DISTRICT ASHA COORDINATOR AT STATE LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head | Particulars/Requirements | Rate (in Rupees) |  |  |  |  |  |  | No. of persons |  |  |  | Frequency |  |  | Amount |
| TA / DA for DAC | Quarterly review meeting | Average TA, based on actuals, Rs.1000/- + DA of Rs. 200/- per day =1200/- per DAC |  |  |  |  |  |  | 9 |  |  |  | 3 quarters |  |  | 1200 x 9 x 3 = 32400 |
| Banner | Banner to put up at the meeting Hall | 700 |  |  |  |  |  |  |  |  |  |  | 3 Quarters |  |  | 2100 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 80 per head |  |  |  |  |  |  | 13 |  |  |  | 3 Quarters |  |  | 3120 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 37,620/- |
| REVIEW MEETING FOR ASHA MENTORING GROUP AT STATE LEVEL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head | Particulars/Requirements |  | Rate (in Rupees) |  |  |  | No. of persons |  |  |  | Frequency |  |  |  | Amount |  |
| TA/DA for AMG members | Quarterly review meeting |  | 200/- per members |  |  |  | 15 |  |  |  | 4 Quarters |  |  |  | 12,000 |  |
| Banner | Banner to put up at the meeting Hall |  | 700 |  |  |  |  |  |  |  | 4 Quarters |  |  |  | 2800 |  |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. |  | 80 per head |  |  |  | 15 |  |  |  | 4 Quarters |  |  |  | 4,800 |  |
| Field exposure for AMG members | Hirer of Bus for field visit |  | 3000 per trip |  |  |  |  |  |  |  | 4 |  |  |  | 1,80,000 |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  | 1,99,600/- |  |

Budget requirement of ASHA under Home Based New Born Care:

The incentives for ASHAs for home visits under HBNC have been calculated @ 250 which is an approved rate of GoI. It is mandatory for ASHAs to make a series of home visits under HBNC component which will be budgeted under Part A : Child Health.

Procurement of Mucus Extractor:

As mucous extractor will be provided to ASHAs after completion of 4th round of 6th and 7th module training. The budget is proposed under HBNC part of Child Health (part –A)

Incentive for ASHA under Immunization:

As the GoI has approved Rs 100 per ASHA for ensuring full immunization, the budget plan for full immunization under immunization head is as follows. This budget will be reflected under Part C.(Immunisation)

Action plan  for ASHA Conference:

There are 987 Accredited Social Health Activist (ASHA) in Mizoram. ASHAs are the grass root and voluntary public workers who played one of the most essential role in achieving the aims and goals of NRHM. Due to their hard work and the success that they have achieved, ASHA Conference will be organize and observe for one day at each District on the day when NRHM was launched, i.e 12th April (from 12th April, 2012 onwards). On this day, different ASHAs from all the Villages will be sharing their success stories so that everyone could gain something from someone’s experience. This can motivate and challenge them to perform better.

On this day, the ASHAs would portray through short play/drama an awareness relating to mothers and pregnant women, the advantages of delivering in hospitals or delivery under the guidance of trained personnel and the importance of regular check-up and treatment after delivery. The ASHAs may share their successful history as an ASHA. Also, best ASHA will be awarded based on performance reported by the concerned CMO, CHO/HS and VHSNC members on grading system. The grading system format will be supplied by the District. The programme will be covered through Media local channels to create awareness in the community about ASHA.

| DETAIL BUDGET PLAN FOR ASHA CONFERENCE ON 12th April 2012 AT EACH DISTRICT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons per District | No. of days | Total Amount |
| TA/DA for ASHAs (to and fro) | Transportation cost and fooding | 200 per ASHAs | 110x9 | 2 | 3,96,000 |
| DA for ASHA |  | 100 per ASHA | 110x9 | 1 | 99,000 |
| DA for Supporting staff |  | 100/- per head | 5x9 | 1 | 4500 |
| Banner | Banner to put up at the conference Hall | 700/- |  |  | 700 |
| Refreshments | Lunch packages, Dinner, Mineral water, Tea/coffee etc. | 150/- per head | 110x10x9 | 1 | 14,85,000 |
| Hall Rent | Hall rent at the District HQ | 500x9 |  |  | 4500 |
|  |  |  |  | TOTAL | 19,89,700/- |
| Grand Total : Rs. 19,89,700/- (Rupees Nineteen lakh eighty nine thousand and seven hundred) only. |  |  |  |  |  |

*Consolidated budget for ASHAs:

| Sl. No. | Activity | Unit Cost | Physical Targets | Amount Proposed |
| --- | --- | --- | --- | --- |
| Mission Flexible Pool |  |  |  |  |
| B.1 | ASHA |  |  |  |
| 1 | 3rd Round state level ASHA TOT on 6th & 7th modules | 3926.00 | 22 | 86,380.00 |
| 2 | 3rd and 4th round training of ASHAs in 6th & 7th modules | 1681.22 | 987 x 2 = 1974 | 33,18,720.00 |
| 3 | Replenishment of drugs and articles | 600.00 | 987 x 2 = 1974 | 11,84,400.00 |
| 4 | Honorarium of District ASHA Coordinator | 8000.00 | 9 | 6,48,000.00 |
| 5 | Honorarium + Incentive of ASHA Facilitators | Rs.1000/- consolidated+ Rs. 200/per visit x 15 visits | 66 | 23,76,000.00 |
| 6 | Induction training of District ASHA Coordinator | 26200.00 | 1 | 26,200.00 |
| 7 | Induction training for ASHA Facilitator | 797.58 | 66 | 52,640.00 |
| 8 | Review meeting for ASHA at PHC/CHC level | 3738.64 | 66 X 4 = 264 | 9,87,000.00 |
| 9 | Review meeting for ASHA Facilitator at District level | 16700.00 | 3 | 50,100.00 |
| 10 | Review meeting for District ASHA Coordinator at State level | 12540.00 | 3 | 37,620.00 |
| 11 | Review meeting of AMG at State and field visit | 4990.00 | 4 | 1,99,600.00 |
| 12 | Observation of ASHA Conference at the District level | 41078.00 | 9 | 19,89,700.00 |
|  |  |  | Total : | 109,56,369/- |

Overall Total : Rs. 109.00 lakhs

B.i.b: Village Health Sanitation and Nutrition Committee:

NRHM in Mizoram constitute 815 VHSNC approximately in over thousand villages and provision of untied grants were given to them by the year 2008.

a.	Village Health Sanitation Committee were constituted since September 2007 and this Committee were rename last year as Village Health Sanitation and Nutrition Committee and the same notification was issued in last year.

b.	VHSC sensitization training was organised in the year 2007 ending. Orientation for planning process and capacity building of community leaders/PRIs in Village Level Planning / Village Health Sanitation and Nutrition Committee is a must as most of the members will be new as there is going to be an election next month. Therefore, 2 days TOT for orientation of VHSC members  2012-13 and 3 days Orientation Training of VHSC Members at districts level is plan and the budget for all Districts is given below.

c.	Untied fund for the VHSNC were utilised for sanitation of each villages and for observation of VHND day every month, unspent balances is hardly seen from their side.

d.	Details of major activity for which VHSNC fund has been utilized in 2011-12: Ussually @ Rs 500/-  is spent for Village Sanitation every month from the month of April- September, bi-monthly from the month of October- March. Apart from observation of VHND day @ Rs 200/- every month, the rest of the money is kept for contingency/ Emergency etc.

e.	As the training for Village Health Plan was not given till date, Village Health Plan is not prepared for the year 2011-12

f.	There is no Block system in Mizoram, Block wise details of meetings held for VHSNC in 2011-12 is not available

g.	Good Convergence with Village Council members & ICDS were observed at the grassroot level in regards to immunization, ANC, PNC and in terms of Health Education, Nutrition etc.

h.  NGO/SHG help in mobilization of children and Pregnant mother in immunization, ANC,PNC et cVHSNC

Progress made is indicated in the following format:

| Activity | Cumulative Achievements so far |
| --- | --- |
| No. of Revenue Villages | 815 |
| Number of Village Health Sanitation & Nutrition committees constituted ( specify if panchayat level) | 815 |
| No. of Joint Account opened | Not known |
| Total funds released to VHSCs (Rs in lakh) | 811.00 lakhs |
| Total amount spent by VHSCs so far | 811.00 lakhs |
| Total unspent balance | Nil |
| Number of VHSNC utilized less than 50% of fund (in 2010-11) | Nil |
| No of VHSCs members trained | All needs to be trained as election is going to held in February. |
| No. of Village Health Plan Prepared | nil |

Total fund proposed for VHSC is 81.5 lakhs

B.i.c Untied Fund:

To enhance functionality, administrative and financial autonomy of various field units provision of untied funds have been made under NRHM. Following issues pertaining to Untied Funds have been highlighted in assessments and feedbacks:

- Utilization of untied fund at various levels of health facilities enumerated as follows,	untied fund is used for the institution needs like water connection , electricit bulb, electric fan, Gas connection, emergency medicine etc..

- Apart from the above mentioned subject, the major areas of fund utilization are for emergency referal, for helping the down troden in attaining health.

- There is no health facilities utilizing less than 50 % of untied funds in the year 2010-11 and 2011-12 .

- Lots of improvements have been observed in the health facilities as a result of untied funds for e.g previously there was no provision of running water in the CHC/PHC and S/C. Since, Untied Fund was provided there is the provision of running water.

- Innovative and best practices adopted: Gas connection was avail in most of the S/C, PHC/CHC sterilisation was easier

- No training/workshops was conducted in 2011-12 for PRI members in regards of untiedfund, only VHSC meeting were organised (at sub center level)

- Since, there was no Training/ Workshop on Untied fund issue. Related issue/ constraints  with utilization of untied fund is observed in the State of Mizoram. Thereby, training/ workshop is budgeted here as we are in dire needs for further improvement.

| Cumulative achievements so far should be indicated in the following format: i |  |  |  |  |  | (Rs in lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Facility level | Number of facilities in position as per norm | Number of facilities received untied fund (2011-12) | Total amount released so far | Total amount utilized | No of Facilities that have utilized less than 50 % of then-funds in 2010-11 | Unspent balance |
| Untied Fund for SCs | 370 | 370 | 370 lakhs | 37 lakhs | NA | Nil |
| Untied fund for the facility below PHC & above SC |  |  |  |  |  |  |
| Untied Fund for PHCs | 57 | 57 | 14.25 | 14.25 | NA | Nil |
| Untied Fund for CHCs | 9 | 9 | 4.5 | 4.5 | NA | Nil |
| Untied Fund for SDH | 3 | 3 | 1.5 | 1.5 | NA | Nil |
| Untied Fund forDH |  |  |  |  |  |  |

The total budget for Untied Fund is Rs. 57.25 lakhs

B.i.d Annual Maintenance Grant:

Annual Maintenance Grants is given to the health facilities for proper maintenance of physical infrastructure to ensure quality services at various levels. To improve the facilities continuously through regular maintenance and repair works AMG funds should be effectively utilized. The issues pertaining to AMG which require a deeper look are:

- Annual Maintenance Grant is used for  immediate Institutional needs like Sanitation, cleaning, fencing of institutional areas, maintenance of the institutional itself etc.

- There is no health facilities who utilizes less than 50 % of Annual Maintenance Grant in 2010-11and 2011-12.

- Improvements made in the health facilities as a result of AMG: the annual maintenance    grant help the institutions in re-novation of the institutions who receives the grant, lots of improvement seen on the outward and  inward cleanliness.

| Facility level | Number of facilities in position as per norm | Number of facilities situated in Govt. Building | Number of facilities received AMG in 2011-12 | Total amount released so far | Total amount utilized | No of Facilities that have utilized less than 50 % of then-funds in 2010-11 | Unspent balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AMG for SCs | 370 | 370 | 30.30 | 30.30 | 30.30 | Nil | Nil |
| AMG for the facility below PHC & above SC |  |  |  |  |  |  |  |
| AMG for PHCs | 57 | 57 | 23 | 23 | 23 | Nil | Nil |
| AMG for CHCs | 9 | 9 | 9 | 9 | 9 | Nil | Nil |
| AMG for SDH | 3 | 3 | 3 | 3 | 3 | Nil | Nil |
| AMG for DH |  |  |  |  |  |  |  |

In the PIP of 2012-13 details of strategies/activities to tackle above mentioned issues and other issues highlighted in assessment of utilization of Annual Maintenance Grant should be given.

Total fund proposed for Annual Maintenance Fund is Rs.77.5 lakhs

B.i.e Rogi Kalyan Samiti:

The Rogi Kalyan Samiti as the pivot of facility based planning and community involvement. RKS’s have contributed to local level leadership and need based decision making. So, far 8 district hospitals, 3 Sub-divisional hospitals, 9 CHCs, and 57 PHC’s facilities have a registered RKS in place.

- RKS District Hospital, Sub Divisional Hospital,Community Health Centre and Primary Health Centre,was constituted in most of Govt.Health facilities except State Referral Hospital,  Falkawn.

- All RKS constituted facilities are functional.

- Before the inception of RKS society in Mizoram all the Health Facilities are facing problems in  maintaining their Hospitals in terms of infrastucture, manpower, logistics etc.

- Major heads under which RKS funds are being utilized: As mentioned above funds is used for maintenance of  their own District Hospital, Sub Divisional Hospital, Community Health Centre and Primary Health Centre, buying of emergency drugs and other hospital requirements.RKS fund is also used as revolving fund. Another utilisation of fund is Ambulance PoL

- Non of the Facilities utilized less than 50 % of RKS fund in 2010-11 & 2011 -12.

- RKS facilitate all Health Programmes under their Jurisdiction and sometimes they organised Health camp. They also mobilised local community to avail the health facility available.

- RKS sensitization training is given at every Induction Training of Medical Officer’s and other staff training. Capacity building of RKS members training cum workshop was conducted in May 2011 for RKS members to revitalize the expectations of RKS in 2011-20 12.

- Status of RKS meetings: Executive Meeting is organised almost every month in most of the District Hospital, SubDivisional Hospital,Community Health Centre and Primary Health Centre but Governing body meeting twice in a year is almost impossible due to the non-availability of Chaiman at the local area as per the norms of guidelines.

- Sharing of success stories and best practices : Due to retention of User’s charges by RKS Society, Civil Hospital Aizawl can generate lots of employment leading to the achievement of attaining ‘ISO 9001:2008 Certification of Approval’ from Indian Register Quality Systems. This approval is subject to continued  satisfactory maintenance of the Quality Management System of the Hospital (Organisation) to the above Standard which is monitored by IRQS. RKS fund is also used as revolving fund which means that a poor patient was admitted in the hospital who does not effort medication and treatment, RKS fund was used in advance for his treatment and this was again re-embursed from RSBY fund and from Mizoram Health Care scheme / Health Insurance scheme. Apart of RKS fund is also used as poor fund that is to buy medicine for poor patient.

- Monitoring Format has been developed and send to all District Health Society to monitor their own District Hospital, Sub Divisional Hospital,Community Health Centre and Primary Health Centre in their Jurisdiction and to send the report back to the state then only review of functioning of RKS will be possible.

- For further improvement of RKS Society in Mizoram a study tour outside Mizoram is budgetted in Table 1, District Training of Trainers for District wise RKS society in Table 2, 1 day, DH, CHC, PHC RKS members Orientation Training   2012-13 Table 3.

Details of status and activities to be undertaken on above mentioned issues should be given in the PIP. Information on cumulative amount released to Rogi Kalyan Samitis and amount utilized so far is summarized in the following format:

(Rs in lakh)

| Facility | Number of RKS | Total amount released so far | Total amount utilized | No of Facilities that have utilized less than 50 % of then-funds in 2010-11 | Unspent balance |
| --- | --- | --- | --- | --- | --- |
| District Hospital | 8 | 40 | 40 | Nil |  |
| Sub Divisional Hospital | 3 | 3 | 3 | Nil |  |
| Community Health Centres | 9 | 9 | 9 | Nil |  |
| Primary Health Centres | 57 | 57 | 57 | Nil |  |
| Other health facilities (Please Specify) |  |  |  | Nil |  |

Facility wise list of RKS meetings held in 2011-12:

| Health Facilities | Number of RKS meetings held in 2011-12 | Target for 2012-13 |
| --- | --- | --- |
| DH Level | 60 | 112 |
| SDH Level | 18 | 28 |
| CHC Level | 67 | 126 |
| PHC Level | 500 | 798 |
| Any other | nil | nil |

ADDITIONAL  BUDGET , OTHER THAN CORPUS  FUND FOR RKS :

Table 1+2+3 = Rs 34,30,680/-

(Rs Thirty four lacs, Thirty thousand Six hundred and Eighty only)

Total fund budget for RKS is :

- 8 DH @ Rs. 5 lakhs per DH		= Rs 40 lakhs

- 9 CHC@Rs. 1 lakhs per CHC		= Rs 9 lakhs

- 3 SDH @ Rs. 1 lakh per SDH		= Rs 3 lakhs

- 57 PHC @ Rs 1 lakhs per PHC		= Rs 57 lakhs

Total			= Rs 109 lakhs

B.ii HEALTH CARE INFRASTRUCTURE:

Civil Constructions

All infrastructure proposals both for new construction and expansion shall be based on both facility and area mapping exercise and not just a district wise allocation exercise. The need of the underserved areas has to be taken into consideration and strengthening of facilities in close contiguity needs to be discouraged unless justified by a heavy case load. Therefore the focus should be on consolidation and need based expansion supplemented with a HR plan. A bird's eye view of available infrastructure should be given in the following format:

| States Requirement of Infrastructure | DH | SDH | CHC | PHC | SHC |
| --- | --- | --- | --- | --- | --- |
| Existing Facilities | 8 | 3 | 9 | 57 | 370 |
| Shortfall |  | 6 | 0 | 0 | 84 |
| Mapping of facilities undertaken | Y | Y | Y | Y | Y |
| Requirement of new facilities after mapping exercise | 0 | 3 | 0 | 0 | 84 |

Upgradation of Private Facility

Presbyterian Hospital, Durtlang is the biggest Mission Hospital in Mizoram. Their contribution for promotion of Community Health is worth mentioning. They requested financial support under NRHM and submitted plan to state Health Society for upgradation of Maternity Wing. It is considered that their proposal could not be funded from NRHM. However, Their proposal for the same has been included n this PIP for reference and the GoI is requested to seek other funding sources.

Proposal for upgradation of

Maternity WING (OB & GYN. DEPT.)

in Presbyterian Hospital, Durtlang.

Submitted to :

The Director,

Hospital & Medical Education,

Directorate of Hospital & Medical Education,

Govt. of Mizoram.

Submitted by :

The Director,

Presbyterian Hospital,

Durtlang.

Total cost of the Project : ` 40,456,800.00

Proposal for upgradation of Maternity WING

(OB & GYN. DEPT.)

in Presbyterian Hospital, Durtlang.

ORGANISATION PROFILE :

a)	Name of the Organisation 		:	Presbyterian Hospital, Durtlang.

b)	Address				:	Durtlang, Aizawl, Mizoram - 796025

Phone					:	0389-2361122/2361222/2361183

Fax					:	0389-2361185

E-mail					:	synodhospital@gmail.com.

c)	Name & Designation of Chief

functionary 				:	Dr. Lalremthanga, Director.

d)	Name of other key functionaries 	:	1)	Rev. Zosangliana Colney,

Executive Secretary i/c Hospital.

Phone : 0389-2316436/2325110

2)	Dr. Vanlalruata,

Medical Superintendent,

Presbyterian Hospital, Durtlang.

Phone :0389-2361418/2361188

3)	Lalchhungliana,

Manager,

Presbyterian Hospital, Durtlang.

Phone : 0389-2361183

e)	Registration details 			:	Societies Registration Act XXI of 1860

Registration No. & date		:	SR 15 of 3rd September, 1987.

f)	FCRA No.				:	304330005

g)	Activities in brief :

The Presbyterian Hospital at a glance : The Presbyterian Hospital at Durtlang is a 300 bedded Multispeciality General Hospital, Registered under Registrar of Societies Act XXI of 1860 and managed by the Mizoram Presbyterian Church Synod. It was started in 1928 with the following foundations :-

i)	To care for all the sick and needy at all times without discrimination of creed, race or social status.

ii)	To train quality nurses with strong Christian principles.

The Hospital has been working very closely with the Department of Health & Family Welfare, Govt. of Mizoram in implementing various projects such as :-

1.	Running a PHC in the Indo-Bangladesh border under the PPP mode since 2008.

2.	Running Mobile Medical Unit (MMU) for the Aizawl West District.

3.	Treatment Centre for Tuberculosis patients under RNTCP.

4.	Eye donation centre under SBCS.

5.	MNGO for 2 districts covering 27 villages.

6.	Mizoram State AIDS Control Society :-

(1)	10 bedded Community Care Centre.		(2)	Drop in Centre

(3)	ICTC						(4)	PPTCT

Hospital statistics for the year 2010 :-

–	Staff details :

Doctor				:	29

Nursing Staff			:	170

Allied Health Professionals	:	22

Others				:	124

Total				:	345

–	Number of beds		:	300 beds in General Wards

30 beds in Community Care Centre.

–	Number of OPD attendance	:	66584

–	Number of Admissions		:	14135

–	Admissions rate			:	25.77%

–	Bed occupancy rate			:	88.87%

–	Average length of stay		:	7.37 days

–	Delivery rate				:	4.68/day

The Maternity Wing (ob & gyn. dept.) :

The Maternity Ward has the following facilities :-

i)	Obstetrics Ward				:	26 beds

ii)	Labour Room					:	3 Delivery beds

3 First stages beds.

iii)	Gynae Ward					:	25 beds

iv)	Neonatology Ward				:	10 beds

v)	Operation room				:	1 with 1 operation table.

Statistics for the year 2010 are as follows :-

i)	Number of deliveries				:	1739

ii)	Number of still births				:	17

iii)	Number of Caesarian section			:	488

Neonatology Ward (Nursery) :

i)	Total admissions				:	366

ii)	Total Number of deaths 	Neonates 	:	44

Infant		:	Nil

Staff detail in the Maternity Ward :

No. of Doctors	:	2 Specialists

1 Medical Officer

Obs. Ward		:	1 Sister

13 Staff Nurses

3 Ward Auxiliaries

Gynae Ward		:	1 Sister

5 Staff Nurses

2 Ward Auxiliaries

Neonatology Ward	:	1 Sister

5 Staff Nurses

1 Ward Auxiliaries

Source of fund last three years :

Name of Agency		:	NEC, Shillong

Name of the Project		: 	Support for procurement of equipments and machineries

for establishment of 6 bedded ICU.

Amount received		:	Rs. 229.52 lakhs

Year				:	2007 - 2009.

Banking details :

1)	SBI, Aizawl 		:	A/C No. 10763500761

SBI, Bawngkawn	:	A/C No. 40717893836

MRB, Durtlang : A/C No. 1791

PROJECT PROFILE

Title of the Project	:	Upgradation of the Maternity Wing (OB & Gynae Dept) in Presbyterian Hospital, Durtlang.

Aims & Objectives	:	To reduce the Infant Mortality Rate (IMR) of Mizoram from 36 to 30 by the year 2012.

The Mizoram Scenario	:	The Infant Mortality Rate (IMR) of Mizoram is 36/1000 live births (SRS 2009), and the National Goal is to bring down this rate to 30/1000 live births by the year 2012. When compared to other North East States, Mizoram has the 2nd highest IMR, next to Assam.

If Mizoram is to achieve the National Goal by the year 2012, it has to make an all-out-effort to up-scale its activities and up-grade it existing facilities. In order to achieve this goal the following points need to be considered earnestly.

Project goal 	:	1.	Increase the number of beds in the Maternity Wards, so that more patients can be admitted for Hospital deliveries.

2.	Improve the Labour Wards by increasing beds and improve facilities so as to render quality care during deliveries.

3.	Upgrade the existing Neonatology Ward so as to improve service delivery and thereby decreasing neonatal deaths.

PROPOSAL FOR THE UPGRADATION OF THE MATERNITY WING

(ob & gyn. dept.), PRESBYTERIAN HOSPITAL :

The Presbyterian Hospital has well established facilities namely Maternity Ward, Neonatology Ward and Labour Room and desires to improve them in order to achieve the required goal, it is therefore proposed to upgrade the existing facilities in the following :-

1.	Increase number of beds available for mothers :

The Hospital has only 26 beds for delivery, as there is no room for additional beds in the present building, it is proposed to build a new maternity ward that will have 40 beds, so that more patients can be admitted for Safe Institutional Deliveries.

(See attached plan).

2.	Upgrade the Neonatology Ward :

The present Neonatology Ward can accommodate 10 beds, in an extremely congested atmosphere, there was no provision for such a ward in the present structure but provision was made purely out of necessity by internal re-structuring, as the need was acute and urgent.

It is therefore proposed to build a new Neonatology Ward which will house 20 beds and will have all the necessary equipments for care and resuscitation of neonates and infants.

3.	Upgrade the Labour Room :

The Labour Room has only 3 delivery beds and three first stage beds and these prove to be too small and congested in view of the increasing demand.

It is therefore proposed to build a new Labour room which will have the following :-

i)	First stage beds		:	20

ii)	Delivery beds			:	5

4.	Upgrade the Operation Room :

The Operation Room can accomodate only one table and in view of the presence of two specialist doctors this prove to be insufficient. It is therefore proposed to enlarge the operation room so as to accomodate 2 operating tables.

The Proposal :

In order to achieve all the above upgradation it is proposed to build a new Maternity Wing with grants from the Govt. of India and contributions from the hospital which will be a two storied structure and will have enough space for all the above mentioned facilities including Patient’s Ramp, Lift and Air conditioning.

The dimensions of the new building will be 150 ft. x 54 ft. and it will be an RCC building and will have the following :-

(1)	40 bedded Maternity Ward

(2)	20 bedded Gynaecology Ward

(3)	20 bedded Neonatology Ward

(4)	Labour Room

(5)	Operation Theatre

(6)	Ramp

(7)	Lift

Equipments :

In order to run the facilities and render quality service the following equipments will be required

I	For the Labour Room :

(1)	Fetal Monitors - 10

(2)	Delivery beds – 5

II	For the Operation Rooms :

(1)	Operation Tables - 2

(2)	Oxygen Concentrator - 1

(3)	Anaesthesia Machines - 2

III	For the Neonatology Ward :

(1)	Incubators - 2

(2)	Neonatal Ventilators - 2

(3) 	Infant Warmers - 10

(4)	Phototherapy Units - 10

Costing :

I	The cost of the building as calculated from the rates of the Mizoram State PWD, 2007 is Rs. 2,00,00,000.00 (Rupees 2 crores only).

II	The cost of the equipments are as follows :

- Cost of Equipments for Labour room :-

| Sl. No. | Name of Equipment | Unit Price in ` | Name of supplier | Total in ` |
| --- | --- | --- | --- | --- |
| 1 | Delivery beds - 5 nos. | 180,000.00 | A.K. Care | 900,000.00 |
| 2 | Fetal Monitors- 10 nos. | 350,000.00 | A.K. Care | 3,500,000.00 |

- Cost of Equipments for Neonatology Ward :-

| Sl. No. | Name of Equipment | Unit Price in ` | Name of supplier | Total in ` |
| --- | --- | --- | --- | --- |
| 1 | Incubators – 2 nos. | 1,100,000.00 | Wipro GE | 2,200,000.00 |
| 2 | Neonatal Ventilators – 2 nos. | 1,690,000.00 | Maquet | 3,380,000.00 |
| 3 | Infant Warmers - 10 nos. | 150,000.00 | Wipro GE | 1,500,000.00 |
| 4 | Phototherapy Units – 10 nos. | 50,000.00 | Wipro GE | 500,000.00 |

- Cost of Equipments for Operation Theatre :-

| Sl. No. | Name of Equipment | Unit Price in ` | Name of supplier | Total in ` |
| --- | --- | --- | --- | --- |
| 1 | Operation Tables - 2 nos. | 970,000.00 | AK Care | 1,940,000.00 |
| 2 | Oxygen Concentrator - 1 no. | 4,500,000.00 | AK Care | 4,500,000.00 |
| 3 | Anaesthesia Machines - 2 nos. | 625,000.00 | Wipro GE | 1,250,000.00 |

Total cost of the equipments 	:	` 	19,670,000.00

Add 4% VAT 	: 	` 	786,800.00

Cost of building	:	` 	20,000,000.00

Grand Total	:	` 	40,456,800.00

Funding :

The following is the proposed funding for the upgradation of the Maternity Wing :-

i)	Grant from Govt. of India	:	`  	38,700,000.00

(Rupees Three hundred and eighty seven lakhs)

ii)	Hospital’s contribution :

1)	All the required staff will be from the Hospital Staff.

2)	7.5% for internal water supply and sanitary installations ` 12,20,421/-

3)	3% for contingencies ` 4,88,168/-

(Total of 2 & 3 = ` 17,56,800/- approximately)

iii)	Subsidised rates :

BPL families who come for deliveries would be accorded 50% reduction from the prevailing hospital rates.

Respectfully submitted by

(Dr. LALREMTHANGA)

Director,

Presbyterian Hospital.

| CIVIL WORKS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl.no | Type of construction | No | Rate (Rs inlakh) | Amount (Rs in lakh) |
| Reconstruction of SC |  |  |  |  |
| SAIHA |  |  |  |  |
| 1 | Tuipui Ferry SC | 1 | 7.65 |  |
| 2 | Miepu SC | 1 | 7.65 |  |
| 3 | Tongkolong SC | 1 | 7.65 |  |
| 4 | Tuipang SC | 1 | 7.65 |  |
| 5 | Zero point Clinic | 1 | 7.65 |  |
|  |  |  | 38.25 | 38.25 |
| AIZAWL 'W' |  |  |  |  |
| 1 | Vaivakawn SC | 1 | 6.33 |  |
| 2 | Hmunpui SC | 1 | 6.33 |  |
| 3 | Ailawng SC | 1 | 6.33 |  |
| 4 | Tachhip SC | 1 | 6.33 |  |
| 5 | Sailam SC | 1 | 6.33 |  |
| 6 | Thiak SC | 1 | 6.33 |  |
|  |  |  | 37.98 | 37.98 |
| AIZAWL 'E' |  |  |  |  |
| 1 | Phullen SC | 1 | 6.33 |  |
| 2 | N. Serzawl SC | 1 | 6.33 |  |
| 3 | Sakawrdai SC | 1 | 6.33 |  |
| 4 | Khawlian SC | 1 | 6.33 |  |
| 5 | Khawruhlian SC | 1 | 6.33 |  |
|  |  |  | 31.65 | 31.65 |
| SERCHHIP |  |  |  |  |
| 1 | Sailulak Sc | 1 | 6.24 |  |
| 2 | E. Lungdar SC | 1 | 6.24 |  |
| 3 | Sialhau SC | 1 | 6.24 |  |
| 4 | Ngentiang SC | 1 | 6.24 |  |
| 5 | N. Vanlaiphai SC | 1 | 6.24 |  |
| 6 | Chhingchhip | 1 | 6.24 |  |
|  |  |  | 37.44 | 37.44 |
| LAWNGTLAI |  |  |  |  |
| 1 | Lawngtlai- I SC | 1 | 7.49 |  |
| 2 | College Veng SC | 1 | 7.49 |  |
| 3 | Hmunlai SC | 1 | 7.49 |  |
| 4 | Vathuampui SC | 1 | 7.49 |  |
|  |  |  | 29.96 | 29.96 |

| KOLASIB |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Tumpui SC (III type) | 1 | 12.86 |  |
| 2 | Hortoki SC (III type) | 1 | 12.86 |  |
| 3 | Salem SC Clinic (III type) | 1 | 12.86 |  |
|  |  |  | 38.58 | 38.58 |
| LUNGLEI |  |  |  |  |
| 1 | Muallianpui SC (Assam type) | 1 | 6.95 |  |
| 2 | Tuisenchhuah SC (assam Type) | 1 | 6.95 |  |
| 3 | Farm Veng SC (Assam Type) | 1 | 6.95 |  |
| 4 | Vaisam SC (Assam Type) | 1 | 6.95 |  |
| 5 | Tiperaghat SC (Assam Type) | 1 | 6.95 |  |
| 6 | Chawilung SC (assam Type) | 1 | 6.95 |  |
| 7 | Dibligarh SC (Assam type) | 1 | 6.95 |  |
| 8 | Tuipui 'D' SC (Assam Type) | 1 | 6.95 |  |
| 9 | Ramlaitui SC (Assam Type) | 1 | 6.95 |  |
| 10 | Kawlhawk SC (assam Type) | 1 | 6.95 |  |
| 11 | Thenhlum SC (Assam Type) | 1 | 6.95 |  |
|  |  |  | 76.45 | 76.45 |
| CAMPHAI |  |  |  |  |
|  | SC (7 to be constructed) | 7 | 6.43 |  |
|  | 6 Clinics | 6 | 6.43 |  |
|  | 10 SC need to be renovated @ 50,000 | 10 | 5.00 |  |
|  |  |  | 88.59 | 88.59 |
| AIZAWL 'E' |  |  |  |  |
| 1 | Phullen SC Qtr | 1 | 6.8 |  |
| 2 | Sakawrdai SC Qtr | 1 | 6.8 |  |
| 3 | Khawlian SC Qtr | 1 | 6.8 |  |
| 4 | Darlawn | 1 | 6.8 |  |
| 5 | Suangpuilawn | 1 | 6.8 |  |
| 6 | Khawruhlian | 1 | 6.8 |  |
| 7 | Phuaibuang | 1 | 6.8 |  |
| 8 | Thingsulthliah | 1 | 6.8 |  |
| 9 | Saitual | 1 | 6.8 |  |
|  |  |  | 61.2 | 61.2 |
| AIZAWL 'W' |  |  |  |  |
| 1 | Maubuang SC Qtr | 1 | 6.8 |  |
| 2 | W' Lungdar SC Qtr | 1 | 6.8 |  |
| 3 | Tachhip SC Qtr | 1 | 6.8 |  |
| 4 | Sateek SC Qtr | 1 | 6.8 |  |
| 5 | khawrihnim SC Qtr | 1 | 6.8 |  |
| 6 | Sumsuih SC Qtr | 1 | 6.8 |  |
| 7 | Reiek SC Qtr | 1 | 6.8 |  |
| 8 | Sialsuk SC Qtr | 1 | 6.8 |  |
|  |  |  | 54.4 | 54.4 |

| SERCHHIP |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Chawngtui SC | 1 | 6.24 |  |
| 2 | District ware house needed for reconstruction | 1 | 20 |  |
|  |  |  | 26.24 | 26.24 |
| LAWNGTLAI |  |  |  |  |
| 1 | Lawngtlai DH (IV type) for MO | 1 | 16.32 |  |
| 2 | Lawngtlai DH (III type) for Staff Nurse | 1 | 10.32 |  |
| 3 | CMO Compound Lawngtlai (IV type) for SMO | 1 | 16.32 |  |
|  |  |  | 42.96 | 42.96 |
| KOLASIB |  |  |  |  |
| 1 | Buhchangphai (I Type) | 1 | 6.74 |  |
| 2 | Zanlawn (I Type) | 1 | 6.74 |  |
| 3 | Pangbalkawn (I Type) | 1 | 6.74 |  |
|  |  |  | 20.22 | 20.22 |
| LUNGLEI |  |  |  |  |
| 1 | Haulawng PHC Quarters Building | 1 | 9.59 |  |
| 2 | Bunghmun PHC Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
| 3 | Buarpui PHC Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
| 4 | Pangzawl PHC Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
| 5 | Cerhlun PHC Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
| 6 | S. Vanlaiphai Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
|  |  |  | 57.54 | 57.54 |
| CAMPHAI |  |  |  |  |
|  | 8 SC qtrs need to be constructed | 1 | 6.92 |  |
|  | 15 SC Qtrs needed to be reconstructed | 1 | 6.92 |  |
|  |  |  | 13.84 | 13.84 |
| MAMIT |  |  |  |  |
| 1 | Zawlnuam | 1 | 6.65 |  |
| 2 | Rawpui | 1 | 6.65 |  |
| 3 | Parvatui | 1 | 6.65 |  |
| 4 | W. Phaileng | 1 | 6.65 |  |
| 5 | Tuipuibari | 1 | 6.65 |  |
| 6 | Phuldungsei | 1 | 6.65 |  |
| 7 | Silsuri | 1 | 6.65 |  |
|  |  |  | 46.55 | 46.55 |
| Reconstruction of PHC |  |  |  |  |
| AIZAWL 'E' |  |  |  |  |
| 1 | Darlawn | 1 | 92.2 |  |
| 2 | Phuaibuang | 1 | 92.2 |  |
|  |  |  | 184.4 | 184.4 |
| MAMIT |  |  |  |  |
| 1 | Kanhmun PHC | 1 | 91.89 | 91.89 |

| LUNGLEI |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Haulawng PHC | 1 | 103.41 | 103.41 |
|  | Construction of Staff Quarters |  |  |  |
| LUNGLEI |  |  |  |  |
| 1 | Type II Qtrs at Bunghmun PHC | 1 | 9.59 |  |
| 2 | Type II Qtrs at Buarpui PHC |  | 9.59 |  |
| 3 | Type II Qtrs at Pangzawl PHC | 1 | 9.59 |  |
| 4 | Cerhlun PHC Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
| 5 | S. Vanlaiphai Staff Nurse Qtrs (II Type) | 1 | 9.59 |  |
|  |  |  | 47.95 | 47.95 |
| Kolasib |  |  |  |  |
| 1 | Kawnpui (III Type) | 1 | 8.53 |  |
| 2 | Bairabi (III Type) | 1 | 8.53 |  |
| 3 | Bukpui (IV Type) for MO | 1 | 8.53 |  |
| 4 | Bukpui (II Type) | 1 | 8.53 |  |
|  |  |  | 34.12 | 34.12 |
| MAMIT |  |  |  |  |
| 1 | Kanhmun | 1 | 8.53 |  |
| 2 | Damdiai Type II Qtr | 1 | 8.53 |  |
| 3 | Kanhmun Type II Qtr | 1 | 8.53 |  |
| 4 | Zawlnuam Type II Qtr | 1 | 8.53 |  |
| 5 | Phuldungsei Type II Qtr | 1 | 8.53 |  |
| 6 | Marpara Type II Qtr | 1 | 8.53 |  |
| 7 | Kanhmun 2 Type II Qtr | 1 | 8.53 |  |
| 8 | W. Phaileng Type III Qtr | 1 | 8.53 |  |
|  |  |  | 68.24 | 68.24 |
| Construction of Water Storage |  |  |  |  |
| LUNGLEI |  |  |  |  |
| 1 | Cherhlun | 1 | 6.52 |  |
| 2 | Lungsen | 1 | 6.52 |  |
| 3 | Chipphir | 1 | 6.52 |  |
| 4 | Buangpui | 1 | 6.52 |  |
|  |  |  | 26.08 | 26.08 |
| MAMIT |  |  |  |  |
| 1 | Kawrtethawveng | 1 | 5.8 | 5.8 |
| ASHA Rest room at |  |  |  |  |
| LUNGLEI |  |  |  |  |
| 1 | Haulawng (Assam Type) | 1 | 4.5 |  |
| 2 | Lungsen (Assam Type) | 1 | 4.5 |  |
| 3 | Tawipui (Assam Type) | 1 | 4.5 |  |
| 4 | Hnahthial SDH (Assam Type) | 1 | 4.5 |  |
| 5 | Tlabung SDH (Assam Type) | 1 | 4.5 |  |
| 6 | Pangzawl (Assam Type) | 1 | 4.5 |  |
| 7 | Cherhlun (Assam Type) | 1 | 4.5 |  |
| 8 | Near CMO Office 2 Storey building | 1 | 4.5 |  |
|  |  |  | 36 | 36 |

| AIZAWL 'W' |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Sairang PHC | 1 | 4.1 |  |
| 2 | Reiek PHC | 1 | 4.1 |  |
| 3 | Aibawk PHC | 1 | 4.1 |  |
| 4 | Sialsuk PHc | 1 | 4.1 |  |
| 5 | Kanghmun PHC | 1 | 4.1 |  |
| 6 | Falkawn Hospital | 1 | 4.1 |  |
| 7 | Kulikawn SDH | 1 | 4.1 |  |
|  |  |  | 28.7 | 28.7 |
|  |  | TOTAL |  | 1328.44 |

| COST APPRAISAL FOR THE WORK "CONSTRUCTION OF 50 BEDDED DISTRICT HOSPITAL, KHAWZAWL, UNDER NRHM, MIZORAM" |  |  |
| --- | --- | --- |
| Sl.no. | Item | Estimated Amount |
| Hospital Complex |  |  |
| 1 | Hospital Building (refer annexure-I) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 10,68,55,671.00 |
| 2 | Motuary Block (refer annexure-II) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 60,20,118.00 |
| 3 | Service Block (refer annexure-III) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 17,75,228.00 |
| Residential Complex |  |  |
| 4 | Type-I Quarter (refer annexure-IV) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,41,33,844.00 |
| 5 | Type-II Quarter (refer annexure-V) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,05,53,894.00 |
| 6 | Type-III Quarter (refer annexure-VI) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,03,14,011.00 |
| 7 | Type-IV Quarter (2nos. Of G+3 blocks) (refer annexure-VII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,38,96,216.00 |
| 8 | Type-V Quarter (refer annexure-VIII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 55,74,335.00 |
| 9 | Total 'A' (1+2+3+4+5+6+7+8)= | Rs. 16,91,23,317.00 |
| 10 | Adding 10% for escalation of prices on total 'A' over SOR 2007 of Mizoram= | Rs. 1,69,12,331.70 |
| 11 | Total 'B' (9+10)= | Rs. 18,60,35,648.70 |
| Additional Works |  |  |
| 12 | Boundary wall (LS)= | Rs. 1,00,00,000.00 |
| 13 | External development Work (Internal road work, Earthwork, Retaining wall etc.= | Rs. 1,00,00,000.00 |
| 14 | Landscaping work (LS)= | Rs. 10,00,000.00 |
| 15 | Underground water tank (LS)= | Rs. 10,00,000.00 |
| 16 | Internal Decoration (LS)= | Rs. 1,20,00,000.00 |
| 17 | Fire Fighting Works (LS)= | Rs. 5,00,000.00 |
| 18 | Total 'C' (12+13+14+15+16+17)= | Rs. 3,45,00,000.00 |
| 19 | Total 'D' (Total'B'+Total 'C')= | Rs. 22,05,35,648.70 |
| 20 | Adding contingency @ 3% on Total 'D'= | Rs. 66,16,069.46 |
| 21 | Total 'E' (total'D'+20)= | Rs. 22,71,51,718.16 |
| Consultancy Charges |  |  |
| 22 | Consultancy Charges@ 5% on total'D'= | Rs. 1,10,26,782.44 |
| 23 | Adding service charge on consultancy charge @ 12.36% on '22'= | Rs. 24,25,892.14 |
| 24 | Total of Consultancy Charges=Total'F' (22+23)= | Rs. 1,34,52,674.57 |
| Sale Tax |  |  |
| 25 | Addind Sale Tax @ 5.6% on Total 'E'= | Rs. 1,27,20,496.22 |
| Project Cost (Phase-I) |  |  |
| 26 | Total Cost of Project (total'E+total'F'+25)= | Rs. 25,33,24,888.95 |
| 27 | Phase-II= | Rs. 12,37,47,000.00 |
| 28 | Total (Phase-I+II) | Rs. 37,70,71,888.95 |

| COST APPRAISAL FOR THE WORK "CONSTRUCTION OF 100 BEDDED DISTRICT HOSPITAL, SERCHHIP, UNDER NRHM, MIZORAM" |  |  |
| --- | --- | --- |
| Sl.no. | Item | Estimated Amount |
| Hospital Complex |  |  |
| 1 | Hospital Building (refer annexure-I) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 12,65,22,746.00 |
| 2 | Motuary Block (refer annexure-II) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 61,10,161.00 |
| 3 | Service Block (refer annexure-III) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 18,01,780.00 |
| Residential Complex |  |  |
| 4 | Type-I Quarter (refer annexure-IV) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,85,89,771.00 |
| 5 | Type-II Quarter (refer annexure-V) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,34,49,710.00 |
| 6 | Type-III Quarter (refer annexure-VI) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,51,59,077.00 |
| 7 | Type-IV Quarter (refer annexure-VII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,40,19,546.00 |
| 8 | Type-V Quarter (refer annexure-VIII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,07,35,638.00 |
| 9 | Total 'A' (1+2+3+4+5+6+7+8)= | Rs. 20,63,88,429.00 |
| 10 | Adding 10% for escalation of prices on total 'A' over SOR 2007 of Mizoram= | Rs. 2,06,38,842.90 |
| 11 | Total 'B' (9+10)= | Rs. 22,70,27,271.90 |
| Additional Works |  |  |
| 12 | Boundary wall (LS)= | Rs. 1,00,00,000.00 |
| 13 | External development Work (Internal road work, Earthwork, Retaining wall etc.= | Rs. 1,00,00,000.00 |
| 14 | Landscaping work (LS)= | Rs. 10,00,000.00 |
| 15 | Underground water tank (LS)= | Rs. 10,00,000.00 |
| 16 | Internal Decoration (LS)= | Rs. 1,00,00,000.00 |
| 17 | Fire Fighting Works (LS)= | Rs. 5,00,000.00 |
| 18 | Total 'C' (12+13+14+15+16+17)= | Rs. 3,25,00,000.00 |
| 19 | Total 'D' (Total'B'+Total 'C')= | Rs. 25,95,27,271.90 |
| 20 | Adding contingency @ 3% on Total 'D'= | Rs. 77,85,818.16 |
| 21 | Total 'E' (total'D'+20)= | Rs. 26,73,13,090.06 |
| Consultancy Charges |  |  |
| 22 | Consultancy Charges@ 5% on total'D'= | Rs. 1,29,76,363.60 |
| 23 | Adding service charge on consultancy charge @ 12.36% on '22'= | Rs. 16,03,878.54 |
| 24 | Total of Consultancy Charges=Total'F' (22+23)= | Rs. 1,45,80,242.14 |
| Sale Tax |  |  |
| 25 | Addind Sale Tax @ 5.6% on Total 'E'= | Rs. 1,49,69,533.04 |
| Project Cost (Phase-I) |  |  |
| 26 | Total Cost of Project (total'E+total'F'+25)= | Rs. 29,68,62,865.24 |
| 27 | Phase II= | Rs. 17,58,86,000.00 |
|  | Total Phase (I+II)= | Rs. 47,27,48,865.24 |

| COST APPRAISAL FOR THE WORK "CONSTRUCTION OF 50 BEDDED DISTRICT HOSPITAL, HNAHTHIAL, UNDER NRHM, MIZORAM" |  |  |
| --- | --- | --- |
| Sl.no. | Item | Estimated Amount |
| Hospital Complex |  |  |
| 1 | Hospital Building (refer annexure-I) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 12,21,65,682.00 |
| 2 | Motuary Block (refer annexure-II) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 68,82,665.00 |
| 3 | Service Block (refer annexure-III) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 20,29,578.00 |
| Residential Complex |  |  |
| 4 | Type-I Quarter (refer annexure-IV) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,61,58,905.00 |
| 5 | Type-II Quarter (refer annexure-V) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,20,66,029.00 |
| 6 | Type-III Quarter (refer annexure-VI) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,17,91,776.00 |
| 7 | Type-IV Quarter (refer annexure-VII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 1,58,87,232.00 |
| 8 | Type-V Quarter (refer annexure-VIII) (Civil, Sanitary, Water supply, Electrification & Site Development work) | Rs. 63,73,011.00 |
| 9 | Total 'A' (1+2+3+4+5+6+7+8)= | Rs. 19,33,54,878.00 |
| 10 | Adding 10% for escalation of prices on total 'A' over SOR 2007 of Mizoram= | Rs. 1,93,35,487.80 |
| 11 | Total 'B' (9+10)= | Rs. 21,26,90,365.80 |
| Additional Works |  |  |
| 12 | Boundary wall (LS)= | Rs. 1,00,00,000.00 |
| 13 | External development Work (Internal road work, Earthwork, Retaining wall etc.= | Rs. 1,00,00,000.00 |
| 14 | Landscaping work (LS)= | Rs. 10,00,000.00 |
| 15 | Underground water tank (LS)= | Rs. 10,00,000.00 |
| 16 | Internal Decoration (LS)= | Rs. 1,20,00,000.00 |
| 17 | Fire Fighting Works (LS)= | Rs. 5,00,000.00 |
| 18 | Total 'C' (12+13+14+15+16+17)= | Rs. 3,45,00,000.00 |
| 19 | Total 'D' (Total'B'+Total 'C')= | Rs. 24,71,90,365.80 |
| 20 | Adding contingency @ 3% on Total 'D'= | Rs. 74,15,710.97 |
| 21 | Total 'E' (total'D'+20)= | Rs. 25,46,06,076.77 |
| Consultancy Charges |  |  |
| 22 | Consultancy Charges@ 5% on total'D'= | Rs. 1,23,59,518.29 |
| 23 | Adding service charge on consultancy charge @ 12.36% on '22'= | Rs. 27,19,094.02 |
| 24 | Total of Consultancy Charges=Total'F' (22+23)= | Rs. 1,50,78,612.31 |
| Sale Tax |  |  |
| 25 | Addind Sale Tax @ 5.6% on Total 'E'= | Rs. 1,42,57,940.30 |
| Project Cost (Phase-I) |  |  |
| 26 | Total Cost of Project (total'E+total'F'+25)= | Rs. 28,39,42,629.39 |
| 27 | Phase-II= | Rs. 12,37,47,000.00 |
| 28 | Total (Phase-I+II) | Rs. 40,76,89,629.39 |

The total budget for Serchhip District Hospital, Hnahthial SDH and Khawzawl SDH amounting to Rs 9826.62 lakhs, However the funding shall sought from other sources.

Budget reconstruct 1 District Hosptal and 2 Sub-District Hospital:

- Serchhip District Hospital 		: Rs. 4727.48 lakhs

- Hnanthial SDH				: Rs. 4076.89 lakhs

- Khawzawl SDH			: Rs. 3770.71 lakhs

The total amount proposed during 2012 – 13 for civil construction is Rs 1328.44 lakhs

B.iii MOBILE MEDICAL UNITS

There are 9 (nine) Mobile Medical Units in Mizoram comprising of three vehicles in each unit totalling 27 vehicles. Each unit is provided with ultasound, X-ray, ECG and Semi – Auto-analysers. The MMU team consists of Specialists Doctors, Laboratory Technicians, Pharmacist, Nurses, etc. and the team usually go for outreach programme 2 to 4 times in a month.  Many cases of cancer, stones, TB and other felt deseases are detected during the outreach clinics. Several minor operations are also conducted and  many cases are being referred to District Hospitals for further investigations and treatment.  Mizoram, being a hilly terrain with undesirable (Kacha) road conditions especially during the monsoon, the vehicles suffer from speedy wear and tear and the fuel consumption is astronomical resulting in huge financial expenditure towards the frequent repairing and change of vehicle parts, including the tyres.  Besides, the poor villagers are not in a position to purchase the prescribed medicines during the outreach clinics which necessitates provision of free medicines. Hence, the budget for MMUs is placed in the table below for the smooth and successful functioning .

| BUDGET FOR MAINTENANCE OF MMU FOR 2012-2013 Table :- |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Post |  | Approved AS per PIP 2011-2012 |  | Manpower Currently Existing | Anticipated Nos | Proposed Pay |  |  |  |  | Budget Requirement for 1 month |
|  |  |  | Nos | Salary per mth |  |  | Normal/ Soft Area |  | Difficult area |  | Very Difficult area |  |
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 | 10 |
| Manpower |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | MO |  | 9 | 35000 | 9 | 6 | 35000 |  |  |  |  | 210000.00 |
|  |  |  |  | 38500 |  | 3 |  |  | 38500 |  |  | 115500.00 |
| 2 | Staff Nurse |  | 9 | 10000 | 9 | 6 | 10000 |  |  |  |  | 60000.00 |
|  |  |  |  | 11000 |  | 3 |  |  | 11000 |  |  | 33000.00 |
| 3 | Lab tech |  | 9 | 8000 | 9 | 6 | 8000 |  |  |  |  | 48000.00 |
|  |  |  |  | 8500 |  | 3 |  |  | 8500 |  |  | 25500.00 |
| 4 | X-ray Tech |  | 9 | 8000 | 9 | 6 | 8000 |  |  |  |  | 48000.00 |
|  |  |  |  | 8500 |  | 3 |  |  | 8500 |  |  | 25500.00 |
| 5 | Phatmacist |  | 9 | 8000 | 9 | 6 | 8000 |  |  |  |  | 48000.00 |
|  |  |  |  | 8500 |  | 3 |  |  | 8500 |  |  | 25500.00 |
| 6 | Driver |  | 27 |  | 27 | 18 | 5500 |  |  |  |  | 49500.00 |
|  |  |  |  |  |  | 9 |  |  | 5500 |  |  | 49500.00 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 738000.00 |
|  | Total Budget requirement for 1 year |  |  |  |  |  |  |  |  |  |  | 8856000.00 |
|  | IN LAKHS |  |  |  |  |  |  |  |  |  |  | 88.56 |
| 7 | AMC for X-Ray in MMU@ Rs. 60000 per machine per year |  |  |  |  |  |  |  |  |  |  | 5.4 |
| 8 | AMC for Untra Sound Machine in MMU @ Rs. 60000 per machine per year |  |  |  |  |  |  |  |  |  |  | 5.5 |
| 9 | Maintenance of Vehicle @ Rs 3 lakhs per district per year |  |  |  |  |  |  |  |  |  |  | 27 |
| 10 | POL @ Rs 2.5 lakhs per district per year |  |  |  |  |  |  |  |  |  |  | 23 |
| 11 | Drugs and reagent @ 6 lakhs per district per year |  |  |  |  |  |  |  |  |  |  | 54 |
|  | Total Requirement for MMU Maintenance (Rs in Lakhs) |  |  |  |  |  |  |  |  |  |  | 203.36 |

TOTAL BUDGET FOR MMU:  Rs 203.36 lakhs

The year-wise summary performance of MMUs in the state is presented in the table below : -

Table : Year – wise Performance of Mobile Medical Units, Mizoram

| Sl. No | Year | No.of outreach clinic | No.of patients examined | No.of patients referred | TYPE & NO. OF INVESTIGATIONS |  |  |  |  |  | Financial Achievement (In Rs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Urine test | X-Ray | USG | Renal Stone | Cancer | Bladder |  |
| 1. | 2008-2009 | 175 | 39007 | 364 | 3863 | 1841 | 969 | 2 |  | 1 | 17,74,483 |
| 2. | 2009-2010 | 131 | 24023 | 356 | 2372 | 885 | 1318 | 32 | 3 | 2 | 81,54,151 |
| 3. | 2010-2011 | 162 | 36588 | 573 | 2530 | 1230 | 887 | 17 | 1 |  | 75,10,004 |

NEW INITIATIVES/STRATEGIC INTERVENTION/INNOVATION

108 EMERGENCY PATIENT TRANSPORT WITH HELP LINE

Emergency Patient Transport Services:

At present there is neither Emergency Response Service nor Private Service Providers for transport/ referral facilities. This is a major hindrance in patients getting access to tertiary care in times of emergency even in the urban areas.

The State proposes to set up help line with 22 ambulances for all 8 districts to cater to the need of patients in terms of transporting them from their residence in case of emergencies, free of cost. Apart from other medical emergencies, priority will also be given to complicated pregnancies, and severely ill children. For accessing the Emergency Patient Transport Services and for catering to the queries of people on health issues, it is proposed to set up a centralized call center. Through this initiative, health information can be made available and accessible 24x7 to all callers.

The State proposes to link up with GVK EMRI (Emergency Management and Research Institute) for providing the above services. The State proposes to set up the service in two phases. The first phase is planned from April’12 to June ’12 and the second phase from December’12 to March’13.  In the first phase, it may be initiated on a pilot basis in the 2 districts, namely Aizawl and Serchhip to be scaled up to all the 8 districts.

- Implementation Plan

| Coverage | Ambulance Plan |
| --- | --- |
| Phase I – Aizawl, Serchhip | 5ALS+5BLS |
| Phase II – Champai, Lawngtlei, Mamit, Saiha, Kolkasib and Lunglei | 5ALS+5BLS |
| Phase III- OTHER Rural Areas | 2BLS |
| Total | 22 |

ALS ambulances will be provided with facility for catering to cardiac emergencies since the number of such patients cites an increasing trend. The Advance Life Saving Ambulance will have the following equipments:

Table: Required Equipments

| Items | Qty. |
| --- | --- |
| PATIENTS HANDLING SYTEMS |  |
| Automatic Loading Stretcher | 1 No. |
| Head Immobilization System | 1 No. |
| Folding Stretcher | 1 No. |
| Scoop Stretcher | 1 No. |
| Vacuum Splint Kit | 1 No. |
| Anti shock trousers (Imported) | 1 No. |
| EMERGENCY EQUIPMENTS |  |
| Automatic Suction Pump | 1 No. |
| Mouth to Mouth Respirator | 1 No. |
| Resuscitation Bag for Adults & Children | 1 No. |
| Resuscitation Kit (Imported) | 1 No. |
| Defibrillator/ Monitor/ Pacer. | 1No. |

BLS Ambulance will have the following equipments (besides other BLS Equipment)

| Sl. No | Particulars | BLS Model (in Lakhs) |
| --- | --- | --- |
| 1 | Basic Price (bare vehicle - BSIII) | 6.50 |
| 2 | Fabrication including AC & Stickers | 1.25 |
| 3 | Defibrillator | Not provided for BLS |
| 4 | AED | 0.65 |
| 5 | Monitor | Not provided for BLS |
| 7 | Insurance & Registration | 0.12 |
| 8 | AVLT/ VMD (Vehicle Mounted Device) | 0.23 |
| 9 | Standard BLS Medical Equipment (as per list attached separately) | 1.00 |
|  | TOTAL | 9.75* |
|  | Ambulance Station – (Space to be provided by GoMizoram – Room + Toilet Provision) | 3.50 |

* (and consumables to be stocked separately)

- Ambulance Deployment Plan

Phase – I

| SN | District | Population | Density | Area (Sq.Kms) | No of Ambulance (1st phase/Total) |
| --- | --- | --- | --- | --- | --- |
| 1 | Aizawl | 404054 | 113 | 3577 | 8/ 8 |
| 2 | Champai | 125370 | 39 | 3185 | 0/ 1 |
| 3 | Kolasib | 83054 | 60 | 1382 | 0/ 1 |
| 4 | Lawngtlai | 117444 | 46 | 2557 | 0/ 2 |
| 5 | Lunglei | 154094 | 34 | 4538 | 0/ 3 |
| 6 | Mamit | 85757 | 28 | 3025 | 0/ 1 |
| 7 | Saiha | 56366 | 40 | 1399 | 0/ 1 |
| 8 | Serchhip | 64875 | 46 | 1421 | 2/ 2 |

^2 ambulances in total would be launched (1st phase) as backup/ buffer for replacement for repair and maintenance work undertaken for regular ambulances.

- The government of Mizoram would bear all non-recurring and recurring expenditure.

- All physical infrastructure - movable & immovable assets - and licensed software acquired and created for with the GOVERNMENT OF MIZORAM funds will become the property of Government of Mizoram.

- GVK EMRI will utilize the government funds with transparency and efficiency.

- GVK EMRI will Operationalize 12 ambulances (including 2 back up ambulances) for in 1st Phaze and run Emergency Response Centre.

- GVK EMRI will provide

  - Senior Management guidance from Hyderabad

  - Processes and Protocols

  - Technology (ERS application software)

  - Innovation

  - And fund these costs as a private philanthropy

- Project financial estimates

| Activity | Rs. In Lakhs |
| --- | --- |
| Non-recurring Expenditure (1st Phase) |  |
| Ambulances |  |
| 6 ALS @ Rs. 14.35 Lakh (average cost) | 86.10 |
| 6 BLS @ Rs. 9.75 Lakh (average cost) | 58.50 |
| IT Infrastructure | 200.00 |
| Temporary ERC (assuming Space Provided by GoMizoram – 3000 sq ft X Rs 1500 per sq ft) | 45.00 |
| Sub Total – Non-recurring expenditure | 389.60 |
| Recurring Expenditure for 1 year (based on 1.32 Lakhs per ambulance) & Assuming balance 10 Ambulances are Launched in the 6th Month of Launching 1st batch of 12 Ambulances | 269.28 |
| Total amount | 658.88 |
| Amount for first phase (12+10 Ambulance of Rs. XXX.XX Lakh + Rs 200 lakhs for temporary ERC) |  |

^to be provided post clarification and based on feedback once we have agreed norms available post discussion with NRHM.
~ Tentative Costing has been provided which are subject to change based on actuals (may be reduced in-case we plan to operationalize 10 ambulances for 1st Financial Year).

If the Government of Mizoram Plans to Operationalize remaining 10 ambulances in the 1st year, Non Recurring Expenditure may be updated for ambulance cost accordingly.

The first phase will consist of procurement of ambulances, setting up of IT Infrastructure, Temporary ERC. The project is envisaged to take off from next financial year hence recurring cost has not been budgeted under the first phase. Assumption is considered that all ambulances shall be procured by GVK EMRI and Launched in 10+2 with 10 Operational and 2 Backup Ambulances (for repair and maintenance).

Recurring Expenditure

The recurring expenditure is estimated @ Rs. 1.32 lakhs per ambulance (approximately) for 1st year and is towards Staff Salaries, Fuel Costs, Repairs and Maintenance, Medical Consumables, Ambulance Mobile telephone expense, Uniforms, Vehicle Insurance, Training, Annual maintenance, Support Staff salaries, Marketing Expenses, Traveling Costs, Admin Expenses (Telephone/ Electricity/ Housekeeping/ Security/ office expenses). Additional head count for balance 10 Ambulances and related cost may be added later.

The recurring expenditure is expected to increase by 10% for cost of expenditure on such accounts each year including Salary.

Apportionment Cost towards Project Oversight, Monitoring Protocols and Process Implementation by GVK EMRI  will be @ 10% of Opex.

Proposed Activities:

- Signing of PPP agreement and release of Funds

- Obtaining 108 connectivity

- Allocation of Temporary Site for Emergency Response Centre & Office.

- Allocation of Temporary Site for  Training facility / Hostel

- Provide Hospitals / Police Stations / Fire Stations data

- Provide GIS Maps

- Provide Telephone subscribers data

- Provide Ambulance Segments  data

- Provide Safety and Security (Police protection) to Ambulances and Staff

- Provide Insurance coverage for Staff procedure with participation of senior officials from GVK EMRI. (OR)

- GVK EMRI will follow exact CVC guidelines for all procurement / purchases for the project.

- GVK EMRI solicits participation of senior government officials in the procurement process to ensure adherence to the CVC guidelines and transparency in the process.

- If the project envisages launch within five months from the date of signing the agreement, GVK EMRI

- would place purchase orders on repeat order i.e. adhering to immediate last purchase orders which were finalized for other states and to identified vendors selected by GVK EMRI for following items:

- Site Preparation to set up temporary ERC

- IT equipment

- Ambulance

- Any other item necessary for commissioning, etc.

Responsibilities as enlisted above to be agreed upon based on discussion before signing the agreement.

Table B (): Proposed Activities

| Sl No. | Action Item |
| --- | --- |
| 1 | Signing of PPP Agreement Letter of Intent, Release of Pre Operational Expenses, Allocation of Temporary building for Emergency Response Centre. |
| 2 | 3 Digit Toll free Number (1-0-8) Obtaining Toll free number, Commissioning PRI Lines, Hunting facility, Commissioning of PSTN lines, Telecom Service Providers connectivity, back up from alternate Telecom Service Provider. Other communication equipment - Wireless communication with Police, Fire , Internet connectivity, Intranet, GSM Mobiles for ambulances, Fax, EPABX. |
| 3 | Ambulance Procurement ( First Phase Vehicles ) Bare Vehicle, Fabrication, fitting of Medical Equipment. |
| 4 | Site Preparation Civil works, Electrical Cabling , Data Network Cabling, Generator & UPS Server Room, Office Infrastructure. |
| 5 | I T Infrastructure Hardware procurement, Third party Software procurement , Installation & Configuration of Servers and Data Storage devices, Desktops for COs & Dos, Telecom service provider’s components. |
| 6 | Recruitment & Training Communication Officers (CO), Dispatch Officers (DO), Emergency Medical Technicians (EMT), doctors (ERCP), Leadership Positions (COO and others) & Support Staff. Medical check-up for ERC and ambulance personnel, provide EMTs & Pilots with uniforms, issue ID cards, medical insurance coverage, Training |
| 7 | Data Collection and entry – Demographics of State, upload GIS Maps, Hospitals Information, Police data, Fire data. Ambulance segmentation, base location of ambulances, allocation of EMTs and Pilots to ambulances/ familiarize them to field operations |
| 8 | Partners Meet Government Partners ( Medical Police, Fire & other agencies), Healthcare Partners, Telecom Service Providers – availability of 108 facility from all the telecom service providers |
| 9 | Testing Mechanism Testing of PRI & PSTN lines, Testing of Hunting facility, Testing of 3 digit call routing, Testing of Pop ups on CO’s & DO’s application, Testing of Soft Phone facility at CO & DO application, Testing of Dispatches from DO application, GIS Maps on Dispatcher application |
| 10 | Promotion and awareness Awareness Programs through electronic and print media, Road Shows, Press Meet, Hoardings, Banners, Posters, Stickers, fliers, etc |
| 11 | Pilot run & Inauguration of Phase I |

Some considerations to be noted:

Notes:

- Cost for Medical Equipments are tentative and may vary by 5% - 10% based on actual;

- Prices considered for IT Infrastructure are taking Nortel EPABX and Server/ Generator/UPS/Software Licenses requirements are accordingly calculated. This is in view of integration issues of ERC Software Application;

- Regarding ERC Infrastructure, Land and Building are to be provided by the Government;

- Lead Time for Procurement of IT Equipment is 8 Weeks from date of PO Release.

Note: This is just a preliminary estimate, on confirmation of firm up numbers, the final estimation will be prepared.

B.V  HUMAN RESOURCES

Key Guidelines for Human Resources including Programme Management Staff

The most important aspect in this section is the plan for augmentation of the human resources in the next 5 years. For sustainable human resource development, policy reforms for restructuring of deployment and more from contractual to regular employees should be expedited. The State is thus requested to present the plan for creation of new posts & filling up of regular posts under the State Government so that the contractual appointments can be slowly reduced and a sustainable HR structure developed.

Provision of human resource should be based on gap analysis with adequate / incentivized provision for difficult and hard to reach areas. Following issues in provision of human resources continue to need attention:

- Capacity and skill development of the human resource both contractual and permanent.

- Filling up of existing vacancies by the State Government

Efforts and roadmap to address these issues should be elaborated in the PIP.

B.vi PROGRAMME MANAGEMENT:

The state health society for Mizoram functions as follows, there are three committees at the state level and one committee each at all the districts. At the state level there is a State Health Mission which is chaired by the Hon’ble Chief Minister, Governing Body which is chaired Chief Secretary and an Executive Committee which is chaired by the Principal Secretary, Health.

The State Programme Management Unit is headed by the Mission Director and under the umbrella of NRHM , all programme divisions converge. The SPMSU hires key personnel on a contractual basis for planning, monitoring and implementation of the programme.

At the district level the state constitute a district Health Society which is under the Chairmanship of the District Commissioner. The DHS is the main implementing functionaries of NRHM programme.

Mizoram administrative arrangement cannot be functioned as they state administrative setup followed, therefore the state does not follow the administrative setup of block. However, the CHC/PHC is taken as an administrative unit and the state employs Accounts Clerk to assist in programme and financial management in all the PHC/CHC.

High focus districts

Mizoram identifies three districts namely Lawngtlai, Mamit and Saiha as a high focus high priority districts as the overall performance of these three districts is comperatively low in terms of health infrastructure and service delivery. Priority is given to these three districts  in all areas – Human resource, infrastructure etc. The necessary budgeting is reflected in relevant chapters of the State Programme Implementation Plan 2012-13.

| Information on Programme Management Units |  |  |  |  |
| --- | --- | --- | --- | --- |
| Level | No. of Regular Staff | No. of contractual Staff in important positions like Programme managers and Consultants who have been employed for their technical expertise | No. of contractual support staff such as programme assistants/ DEOs/ typists/ peons | Total Number of Staff in SPMU |
| SPMU | 6 | 15 | 19 | 34 |
| DPMU | 0 |  | 52 | 52 |
| BPMU | 0 |  |  | 66 |
| Total | 6 | 15 | 71 | 152 |

B.vii INNOVATIONS

Some local problems that emerge as priority in the Block/District Action Plans may require innovative solutions. Such innovative measures may be supported under NRHM. States should provide the details of innovations and suggest cost as per need.

B.viii. FUNDS FOR IMPACT ASSESSMENT OF NRHM AND ASSESSMENT OF VARIOUS COMPONENTS:

Continuous assessment and evaluation of the program is important to keep us focused and do the necessary course corrections swiftly. States must propose an amount from NRHM Flexipool for evaluation and assessment activities of NRHM and components like ASHA, VHSCs, RKS, etc. Reputed medical, Public Health, Management and Research Institutes should be identified for such evaluation/assessments and should be accredited with the Government of India. Only such accredited institutes may be allowed to take up the assessment work.

National Rural Health Mission is now implemented for five years in the State of Mizoram. The state now proposes to assess the impact the Mission has in various fields of Health Care delivery.

For this purposes s technical expertise will be sought by engaging professionals in various subject. These  expert will work closely with the State government and NRHM. Formats will be designed and the assessment result will be printed and distributed to all stakeholders with advice on how to improve the mission

The state there fore proposes Rs 50 lakhs for impact assessment

Bix. ADDITIONAL FUNDS FOR COMMUNICABLE DISEASES:

States should analyze and identify areas/ Districts that have a high burden of communicable diseases. The additional funds required to tackle the same should be budgeted for in the NRHM Mission Flexipool. Detailed information should be provided under the concerned disease control program. A summary of information should be provided under this section.

B.x. ACTIVITIES TAKEN UP WITH SUPPORT UNDER OTHER PROGRAMMES:

Activities taken up with support under other programmes such as Donor Partners, Minority Development, Finance Commission Award, Labour, DONER and any other scheme etc. to be clearly reflected in this section. Similarly details of PPP activities, Health Insurance scheme and any other district innovation funds being solicited, details need to be spelt out in this Part.

Bxi. State Health Resource Centre (SHRC)

SHRC has not been proposed for 2012-13

B xii. PROCUREMENT

Proposed Procurement of Drugs and Equipments for the year 2012-13 are tabulated below:

Procurement of Drugs:

| Name of the facility | Rates per facility (Rs) | No of Facility | Amount (lakhs) |
| --- | --- | --- | --- |
| Sub-Center | 20000 | 370 | 74 |
| Primary Health center | 300000 | 57 | 171 |
| CHC/SDH | 500000 | 11 | 55 |
| TOTAL |  |  | 300 |

The total requirement for the procurement of drugs is  Rs. 300 lakhs

| Procurement of Equipments |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | MATERNAL HEALTH |  |  |  |
| Sl.No | Item | Quantity | Unit Cost (Rs) | Amount (Rs) |
| 1 | Boyles apparatus | 15 | 2,00,000 | 30,00,000 |
| 2 | X RayMachine | 5 | 5,80,000 | 29,00,000 |
| 3 | Ultrasonography | 10 | 5,25,000 | 52,50,000 |
| 4 | Binocular microscope | 20 | 20,500 | 4,10,000 |
| 5 | Labour Bed | 100 | 25,000 | 25,00,000 |
| 6 | Vaccum Aspirator | 30 | 20,000 | 6,00,000 |
| 7 | Backup Generator | 10 | 2,00,000 | 20,00,000 |
| 8 | Shawdowless Lamp | 70 | 1,10,000 | 77,00,000 |
| 9 | Delivery kit | 350 | 5,000 | 17,50,000 |
| 10 | Examination Table | 20 | 25,000 | 5,00,000 |
| 11 | Oxygen Concentrator | 2 | 2,00,000 | 4,00,000 |
| 12 | Diathermy Machine | 7 | 3,45,000 | 24,15,000 |
| 13 | Suction Machine | 7 | 20,000 | 1,40,000 |
| 14 | Operation Table | 20 | 20,000 | 4,00,000 |
| 15 | Weighing Scale Baby | 300 | 1,500 | 4,50,000 |
| 16 | Surgical set for CS | 20 | 10,000 | 2,00,000 |
| 17 | Post natal kits @ Rs.300/- | 1,000 | 300 | 3,00,000 |
|  | SUB-TOTAL |  |  | 3,09,15,000 |
|  | CHILD HEALTH |  |  |  |
|  | Equipments for NBCC |  |  |  |
| Sl.No | Name of Equipments | Quantity | Unit Cost(Rs.) | Amount(Rs.) |
| 1 | Establishment of SNCU | 1 | 41,00,000 | 41,00,000 |
| 2 | Establishment of NBSU | 5 | 5,75,000 | 28,75,000 |
| 3 | Establishment of NBCC | 21 | 85,000 | 17,85,000 |
|  | SUB-TOTAL |  |  | 87,60,000 |
|  | FAMILY PLANNING |  |  |  |
| Sl.No | Name of Equipments | Quantity | Unit Cost(Rs.) | Amount(Rs.) |
| 1 | IUD Kits | 450 | 1000 | 4,50,000 |
| 2 | Mini Lap Set | 41 | 10,000 | 4,10,000 |
| 3 | Laparoscope | 8 | 5,00,000 | 40,00,000 |
|  | SUB-TOTAL |  |  | 48,60,000 |
|  | IMEP |  |  |  |
| Sl.No | Name of Equipments | Quantity | Unit Cost(Rs.) | Amount(Rs.) |
| 1 | Bio degradable bags | 3,00,000 | 6 | 18,00,000 |
|  | SUB-TOTAL |  |  | 18,00,000 |
|  | GRAND TOTAL |  |  | 4,63,35,000 |

Purchase order for 140 KWp Solar Power Plant

140 KWp Solar Power Plant to be installed in the premises Health Services Dept., Government of Mizoram as enclosed The project may be implemented in associations with the local Services provider

Total Project Cost:	Rs. 378.0 Eacs

Subsidy from MNRE:	Rs. 340.2 Eacs

Funding from the Beneficiary:	Rs. 37.8 Lacs

Terms and conditions:

After the receipt of MNRE sanction letter, we will release 10% advance payment to Gautarn Polymers.

| SI.No. |  | Proposed Location of Projects | Capacity |
| --- | --- | --- | --- |
| 1. |  | Community Health Centre, Saitual, Mizoram | 2 KWp |
| 2. |  | Community Health Centre, Sakawrdai, Mizoram | 2 KWp |
| 3. |  | Community Health Centre, Hnahthial, Mizoram | 2 KWp |
| 4. |  | Community Health Centre, Chawngte, Mizoram | 2 KWp |
| 5. |  | Community Health Centre, Thenzawl, Mizoram | 2 KWp |
| 6. |  | Community Health Centre, Vairengte, Mizoram | 2 KWp |
| 7. |  | Community Health Centre, Kawrthah, Mizoram | 2 KWp |
| 8. |  | Community Health Centre, Biahte, Mizoram | 2 KWp |
| 9. |  | Community Health Centre, Ngopa, Mizoram | 2 KWp |
| 10. |  | Sub-District Hospital Tlabung, Mizoram | 2 KWp |
| 11. |  | Primary Health Centre, Thingsulthliah, Mizoram | 2 KWp |
| 12. |  | Primary Health Centre, Suangpuilawn, Mizoram | 2 KWp |
| 13. |  | Primary Health Centre, Darlawn, Mizoram | 2 KWp |
| 14. |  | Primary Health Centre, Khawruhlian, Mizoram | 2 KWp |
| 15. |  | Primary Health Centre, Phullen, Mizoram | 2 KWp |
| 16. |  | Primary Health Centre, Phuaibuang , Mizoram | 2 KWp |
| 17. |  | Primary Health Centre, Lengpui, Mizoram | 2 KWp |
| 18. |  | Primary Health Centre, Sairang, Mizoram | 2 KWp |
| 19. |  | Primary Health Centre, Reiek , Mizoram | 2 KWp |
| 20. |  | Primary Health Centre, Aibawk , Mizoram | 2 KWp |
| 21. |  | Primary Health Centre, Sialsuk , Mizoram | 2 KWp |
| 22. |  | Primary Health Centre, Kanghmun, Mizoram | 2 KWp |
| 23. |  | Primary Health Centre, Cherhlun, Mizoram | 2 KWp |
| 24. |  | Primary Health Centre, Lungsen, Mizoram | 2 KWp |
| 25. |  | Primary Health Centre, Tawipui, Mizoram | 2 KWp |
| 26. |  | Primary Health Centre, Chhipphir, Mizoram | 2 KWp |
| 27. |  | Primary Health Centre, Haulawng, Mizoram | 2 KWp |
| 28. |  | Primary Health Centre, Bunghmun S, Mizoram | 2 KWp |
| 29. |  | Primary Health Centre, Buarpui, Mizoram | 2 KWp |
| 30. |  | Primary Health Centre, Chhuarlung, Mizoram | 2 KWp |
| 31. |  | Primary Health Centre, Chakhang , Mizoram | 2 KWp |
| 32. |  | Primary Health Centre, Phura , Mizoram | 2 KWp |
| 33. |  | Primary Health Centre, Tuipang, Mizoram | 2 KWp |
| 34. |  | Primary Health Centre, S. Lungpher, Mizoram | 2 KWp |
| 35. |  | Primary Health Centre, Bualpui NG, Mizoram | 2 KWp |
| 36. |  | Primary Health Centre, Borapansury, Mizoram | 2 KWp |
| 37. |  | Primary Health Centre, Sangau, Mizoram | 2 KWp |
| 38. |  | Primary Health Centre, Chhingchhip, Mizoram | 2 KWp |
| 39. |  | Primary Health Centre, N. Vanlaiphai, Mizoram | 2 KWp |
| 40. |  | Primary Health Centre, Khawlailuang, Mizoram | 2 KWp |
| 41. |  | Primary Health Centre, Lungdar E, Mizoram | 2 KWp |
| 42. |  | Primary Health Centre, Ngentiang, Mizoram | 2 KWp |
| 43. |  | Primary Health Centre, Phuldungsei , Mizoram | 2 KWp |
| 44. |  | Primary Health Centre, W. Phaileng, Mizoram | 2 KWp |
| 45. |  | Primary Health Centre, Lungdai, Mizoram | 2 KWp |
| 46. | Primary Health Centre, Kawnpui, Mizoram |  | 2 KWp |
| 47. | Primary Health Centre, Bilkhawthlir, Mizoram |  | 2 KWp |
| 48. | Primary Health Centre, Kawrtethawveng Mizoram |  | 2 KWp |
| 49. | Primary Health Centre, Zawlnuam, Mizoram |  | 2 KWp |
| 50. | Primary Health Centre, Kanhmun, Mizoram |  | 2 KWp |
| 51. | Primary Health Centre, Marpara, Mizoram |  | 2 KWp |
| 52. | Primary Health Centre, Rawpuichhip, Mizoram |  | 2 KWp |
| 53. | Primary Health Centre, Khawzawl, Mizoram |  | 2 KWp |
| 54. | Primary Health Centre, Khawhai, Mizoram |  | 2 KWp |
| 55. | Primary Health Centre, Kawlkulh, Mizoram |  | 2 KWp |
| 56. | Primary Health Centre, Rabung, Mizoram |  | 2 KWp |
| 57. | Primary Health Centre, Sialhawk, Mizoram |  | 2 KWp |
| 58. | Primary Health Centre, NE Khawdungsei, Mizoram |  | 2 KWp |
| 59. | Primary Health Centre, Mimbung, Mizoram |  | 2 KWp |
| 60. | Primary Health Centre, Bungzung, Mizoram |  | 2 KWp |
| 61. | Primary Health Centre, Bukpui, Mizoram |  | 2 KWp |
| 62. | Primary Health Centre, Chawngte, Mizoram |  | 2 KWp |
| 63. | Primary Health Centre, Vanlaiphai, Mizoram |  | 2 KWp |
| 64. | Primary Health Centre, Khawbung, Mizoram |  | 2 KWp |
| 65. | Primary Health Centre, Pangzawl, Mizoram |  | 2 KWp |
| 66. | Primary Health Centre, Sesih, Mizoram |  | 2 KWp |
| 67, | Primary Health Centre, Farkawn, Mizoram |  | 2 KWp |
| 68. | Primary Health Centre, Hnahlan, Mizoram |  | 2 KWp |
| 69. | Primary Health Centre, Bungtlang , Mizoram |  | 2 KWp |
|  | Total |  | 140 KWp |

Proposed Fund for 140 KWp Solar Power Plant is Rs. 37.8 lakhs

B xiii. DISTRICT PLANS

Each District have prepared district plan since 2006-07 and for 2012 – 13 the District has submitted their respective district plan too. Appraisal of Distrcit health action plan was conducted at the state level where the district plan was appraised for its technical aspect and their financial implications. The distrcts modified their plan accordingly and submitted the final district plan to the State Health Society. The finalized district plan is thus incorporated into the State Plan

The state again propose Rs 5 Lakhs each for each district amountiong to Rs 45 Lakhs and Rs 5 lakhs for the state.The Final proposal for preparation of action plan is Rs 50 Lakhs.

B xiv. MAINSTREAMING OF AYUSH

AYUSH MAN POWER:

|  | Component | Engaged in 2012-13 | Proposed during 2012-13 |  |  |
| --- | --- | --- | --- | --- | --- |
| Manpower | Institution | Number | Number |  | Amount (Rs. In Lakhs) |
| AYUSH Doctors (Hom. & Ayur.) | PHCs | Nil | nil |  | nil |
|  | CHCs | 2 nos. | 7 nos. |  | 37.80 |
|  | DHs | 8 nos. | nil |  | 33.60 |
| Paramedical Staff (Staff Nurse/ Pharmacist) | PHCs | Nil | nil |  | nil |
|  | CHCs | Nil | nil |  | nil |
|  | DHs | Nil | S/N | Pharmacist | 53.76 |
|  |  |  | 40 | 8 |  |
| Driver | State AYUSH Offis | nil | 1no. |  | 0.78 |
| IV Grade | CHCs DHs | Nil Nil | 9 nos. 20 nos. |  | 05.94 13.20 |
| Total Amount |  |  |  |  | 145.08 |

| Sl. No. | Name of Post | Level of Co-locations | Unit cost (wherever applicable) per month | Physical Target / Expected output | Proposed Amount per annum (Rs. In lakh) |
| --- | --- | --- | --- | --- | --- |
| 1 | Medical Officer (AYUSH) | 9- CHCs(IPD) 8- DHs (10 bedded Hospital) | Rs. 35,000/- Rs. 35,000/- | 9 8 | 37.80 33.60 |
| 2 | Pharmacist | PHCs(OPD) CHCs(IPD) 8 -DHs (10 bedded Hospital) | Rs. 8,500/- | nil nil 8 | nil nil 08.16 |
| 3 | Staff Nurse | CHCs(IPD) 8- DHs (10 bedded Hospital) | Rs. 9,500/- | nil 40 | 45.60 |
| 4 | IV Grade | 9- CHCs(IPD) 8- DHs (10 bedded Hospital) | Rs. 5,500/- Rs. 5,500/- | 9 20 | 05.94 13.20 |
| 5 | Driver | State AYUSH Office | Rs. 6,500/- | 1 | 0.78 |
| TOTAL |  |  |  |  | 145.08 |

(Rupees two hundred seven lakhs and six thousand) only

Training of AYUSH Manpower:

| Name of Training | Category | Trained till date | Proposed in the year 2012-13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No. Of Batches | Duration | Training Load | Financial (Rs. in Lakh) |
| Induction training for 20 nos. of Medical Officer AYUSH under mainstreaming of AYUSH - Health Services in the state - NRHM - Other National Programme | Medical Officer (AYUSH) | Nil | 2 | 3 days | 10+10 | 2.00 |
| Continuing Medical Education (CME) for 20 nos. of M.O.(AYUSH) | Medical Officer (AYUSH) | Nil | 4 | 4 days | 20 | 6.00 |
| TOTAL AMOUNT |  |  |  |  |  | 8.00 |

AYUSH Medicines for allocated facilities:

There are 12 AYUSH OPD/Dispensaries under NRHM which is functional till date. Medicines for allocated facilities are provided by Department of AYUSH Government of India till today. However, due to non-existence of AYUSH Medicines Shop/Pharmacy in Mizoram, these medicines supplied by Department of AYUSH is not sufficient for one year as it is supply free of cost to the patient. Therefore, Rs. 5.00 lakhs per unit for purchase of medicine is essential.

Place of allocated Dispensary/OPD for supply of medicine:

| AYUSH Facilities allocated (OPD/Clinic) | Place of Allocated | Medicine/ Drug Required | Amount (Rs. In lakh) |
| --- | --- | --- | --- |
| District Hospital | - Civil Hospital, Aizawl | Hom. & Ayur. | 10.00 |
|  | - Civil Hospital, Lunglei | Hom. & Ayur. | 10.00 |
|  | - Civil Hospital, Kolasib | Homoeopathic | 5.00 |
|  | - Civil Hospital, Champhai | Homoeopathic | 5.00 |
|  | - Civil Hospital, Mamit | Homoeopathic | 5.00 |
|  | - Civil Hospital, Serchhip | Homoeopathic | 5.00 |
|  | - Civil Hospital, Saiha | Homoeopathic | 5.00 |
|  | - Civil Hospital, Lawngtlai | Homoeopathic | 5.00 |
| CHC | 9. CHC, Saitual | Homoeopathic | 5.00 |
|  | 10. CHC, Tlabung | Homoeopathic | 5.00 |
|  | - CHC, Chawngte | Homoeopathic | 5.00 |
|  | - CHC, Thenzawl | Homoeopathic | 5.00 |
| TOTAL | 12 OPD / Clinic |  | 70.00 |

Support Required from Department of AYUSH for PIP 2012-13:-

Co-location under NRHM:

| S.No. | Centre | One time assistance |  | Recurring assistance |  |  | Total Amount (Rs. In lakhs) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. Of Units | Amount (Rs. In lakhs) | New Units | Old Units | Cumulative Amount (Rs. In lakhs) |  |
| 1 | PHC | nil | nil | nil | Nil | nil | nil |
| 2 | CHC | 2 | 25.00 | 7 | 2 | 2.00 | 2.00 |
| 3 | DH | 8 | 30.00 | nil | 8 | 3.20 | 3.20 |
| Total |  |  |  |  |  |  | 5.20 |

Upgradation of AYUSH Hospitals:

| S.No. | Centre | One time assistance |  | Recurring assistance |  |  | Total Amount (Rs. In lakhs) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. Of Units | Amount (in lakhs) | New Units | Old Units | Cumulative Amount (in lakhs) |  |
| Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil |

Upgradation of AYUSH Dispensaries:

| S.No. | Centre | One time assistance |  | Recurring assistance |  |  | Total Amount |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. Of Units | Amount | New Units | Old Units | Cumulative Amount |  |
| Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil |

- Establishment of Programme Management Unit (AYUSH):

| Sl.No. | State | Onetime assistance | Recurring assistance | Total Amount (Rs. In lakhs) |
| --- | --- | --- | --- | --- |
|  | Mizoram | 01.72 lakhs | Manpower @ 6.90 lakhs Contingency @ 0.10 lakh | 07.00 lakhs |

- Procurement of Essential Drugs for AYUSH Hospitals and Dispensaries

| Sl.No. | Unit | Stream | Recurring assistance | Total Amount (Rs. In lakhs) |
| --- | --- | --- | --- | --- |
| 1 | 2 Units Aizawl & Lunglei | Ayurvedic | 0.50x2 | 01.00 |
| 2 | 19 units:- - Civil Hospital, Aizawl - Civil Hospital Lunglei - Civil Hospital Kolasib - Civil Hospital Champhai - Civil Hospital Serchhip - Civil Hospital Mamit - Civil Hospital Lawngtlai - Civil Hospital Saiha - CHC Kawrthah - CHC Chawngte - CHC Saitual - CHC Thenzawl - CHC Sakawrdai - CHC Ngopa - CHC Khawzawl - CHC Hnahthial - CHC Vairengte - CHC Biate - Tlabung | Homoeopathic | 0.25x19 | 04.75 |
| TOTAL |  |  |  | 05.75 |

SUMMARY OF PROPOSED FUND FOR THE YEAR 2012-13:-

| Sl. No. | Name of Scheme / Activity | Amount Required (Rs. In lakhs) |
| --- | --- | --- |
| 1 | AYUSH Manpower | 145.08 |
| 2 | Training of AYUSH Manpower | 08.00 |
| 3 | AYUSH Medicines for Allocated Facilities | 70.00 |
| 4 | Co-location under NRHM | 05.20 |
| 5 | Upgradation of AYUSH Hospitals | nil |
| 6 | Upgradation of AYUSH Dispensaries | Nil |
| 7 | Establishment of Programme Management Unit (AYUSH) | 07.00 |
| 8 | Procurement of Essential Drugs for AYUSH Hospitals and Dispensaries | 05.75 |
| TOTAL AMOUNT |  | 178.03 lakhs |

(Rupees one hundred seventy eight lakh and three thousand) only

B.xv  I.E.C/BCC NRHM  IN MIZORAM

I.E.C/BCC NRHM  IN MIZORAM

History: In Mizoram Mini State Health Education Bureau was created in the State Health Directorate in the year 1977 headed by Health Education Officer, one LDC and a Peon. In addition to the routine duties, School Health Programme was taken up under this Bureau though the School Health Programme was switched over to MCH Programme in the year 1985. The Mini State Health Education Bureau was amalgamated with Mass Education and Media Wing in March 1988, which is presently known as State Mass Education and Media Wing (SMEMW) headed by State Mass Education and Media Officer (SMEMO) & Health Education Officer (HEO) within the Directorate of Health Services (DHS) at the State. Before, the inception of NRHM in 2005and till 2009 this SMEM Wing was looking after all the IEC and Health Education programmes.

Apart from this, some of the State vertical programmes have their own IEC consultants for e.g. RNTCP, NVBDCP and there is no integrated mechanism of IEC of various programmes. Though, a Medical Officer Grade I was notified in charge of IEC under NRHM, since the inception of NRHM in 2005, the charge of this duty was not hand over till recently i.e. since 2010.

The overall situation in the State is as follows:

Present Scenario of State Mass Education and Media Wing at the State & Districts Level:

The present position of staff under SMEM Wing of Health & Family Welfare Department of Mizoram is as shown below:-

Table 1. MAN POWER AT STATE LEVEL

| SL no. | Name of post | No. of post | Post fill | Post Vacant |
| --- | --- | --- | --- | --- |
| 1 | SMEMO | 1 | 1 |  |
| 2 | HEO | 2 | 2 |  |
| 3 | EE | 5 | 5 | - |
| 4 | Assistant Editor | 1 | 1 | - |
| 5 | Artist Cum Photographer | 1 | 1 | - |
| 6. | Projectionist | 2 | 1 | 1 |
| 7 | UDC | 1 | 1 | - |
| 8. | LDC | 1 | 1 | - |
| 9. | Peon | 1 | 1 | - |

At present the State Mass Education and Media Wing are looking after a health magazine in Mizo language known as ‘HRISELNA’

Table 2.MAN POWER AT THE DISTRICT LEVEL

| Sl.No. | Name of Districts | No. of IEC Staff post created and filled up |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | HEO | DEMO | Dy.DEMO | BEE | HE | Projectionist |
| 1 | Aizawl ‘E’ | - | 1 | - | 4 | - | - |
| 2 | Aizawl ‘W’ | - | - | - | 2 | - | - |
| 3 | Lunglei | - | - | - | 1 | 2 | - |
| 4 | Saiha | - | - | - | 1 | - | 1 |
| 5 | Serchhip | - | - | 1 | 2 | - | - |
| 6 | Kolasib | - | - | 1 | 2 | - | - |
| 7 | Champhai | - | - | - | 3 | 2 | - |
| 8 | Mamit | - | - | - | 1 |  | - |
| 9 | Lawngtlai | - | - | - | 1 | - | - |
|  | TOTAL |  | 1 | 2 | 17* | 4 | 1 |

*out of 17 BEE 9 are Contractual BEE from NRHM, rest of the BEE & HE are State Contract.

As of today, the ability of districts to plan, chart out contents, chalk out the strategies and choose appropriate media for communication is very much limited. The district media cell is without Media Officers and Block Extension Educators (BEEs). Contractual Manpower i.e. BEE’s recruited by NRHM & State government are posted haphazardly without any strategy/objectives on IEC as we have seen in table 2. Due to this problem most of the programme are planned at the state level and the local specific issues do not appear in the presentations. Another important issue is proper training, which is a must for effective quality of presentation was lacking till the year before. Since, this problem was identified, few training were organized for IEC personnel in the state. To have more effective BCC we need to train our IEC personnel more rigorously than before with field practice for the adequacy, effectiveness and acceptability of messages and choice of communication channels.

SITUATION ANALYSIS:

One of the major challenges in IEC related activities in the state of Mizoram, as in most other states of India, has been the lack of a master plan and integrated strategies towards Behaviour Change Communication (BCC). Each vertical programme has been organizing its own IEC materials and events and there has been very little collaboration between different segments of the Health Department. Similarly, the level of joint thinking with related Departments like Social Welfare, PHE and Rural Development. This result in the following difficult situations:-

1.	Too many messages on the same issues from too many sources, which confuse people

2.	Resource duplication

3.	Some vitals aspects of Behaviour Change being left out for lack of resources – either human or financial.

BCC/IEC BUREAUS

Integrated BCC Strategy for the Health Sector

NRHM gives an opportunity to address this situation and work towards an integrated BCC strategy for the Health Sector. The Department of Health Family Welfare, Government of Mizoram would, therefore like to undertake the following activities:-

1.	Access technical assistance towards doing a Communication Needs Assessment (CNA) Study

2.	Design an integrated BCC Strategy on the basis of the findings of the CNA Study

3.	Develop communication materials and packages on the basis of that strategy.

4.	Identify suitable agencies – including different arms of the Health Department, other related Departments and NGOs / CBOs.

This systematic approach will optimize the impact of the Intra Communication Flow Chart which was already projected in the earlier years. The CNA, the integrated BCC strategy, the communication packages and materials and the partnership with different agencies including NGOs will feed into the Flow Chart in the following ways:-

a.	Will determine the specific communication needs of different areas

b.	Will determine the messages that should go

c.	Will identify the best channels / modes of communication to use

d.   Will optimize resources – both financial and human – through minimizing  duplication

ORGANIZATIONAL STRUCTURE

The BCC/IEC BUREAU will be one of the Section of State Programme Management Support Unit (SPMSU) as per the guidelines of National Rural Health Mission: Institutional Setup at State level.

Objectives and Strategy

•	Designing an Integrated BCC Strategy for the health sector on the basis of Communication Needs Assessment

•	Strengthen IEC/BCC Section at State & Districts level by engaging professional on contract basis/short term consultancies.

•	Strengthening of District IEC Section with AV Aids and Training Aids.

•	Intra-sectoral coordination of IEC experts of different vertical programmes into one IEC programmes at state level.

•	Media Advocacy on issues related to MCH by Institutional Delivery; Breast feeding, Immunization etc. and promotion of healthy life style.

The Mission Director, NRHM will be the administrative head of the IEC/ BCC Section.  He will be assisted by Officer’s expert in BCC and IEC of various disciplines.

Hierarchy IEC/BCC Section:

DIRECTOR / MISSION DIRECTOR

STATE IEC OFFICER

STATE IEC CONSULTANT (2),

DISTRICT IEC OFFICER (9),

BLOCK EXTENSION EDUCATOR (CHC= 9)

HEALTH EDUCATOR (PHC =57)

HW / ASHA

IEC BUREAU AT THE STATE HEADQUARTER:

- State IEC Officer

- State IEC Consultant

- Editor – Audio Visual

- Video Cameramen / Photographer

- Computer Operator /DEO

- Helper

DIVISIONS OF THE IEC/ BCC

The Section, will accomplishes its functions to plan, formulate and strengthen Health Education / Behavior Change Communication in the state through multipurpose activities which are performed by various technical divisions. Each division will be headed by an officer well trained in his /her respective field. These Divisions are:-

- Editorial & Media Division

- Training & Health Education Services Division

- Behavior Research & Evaluation Division

1. EDITORIAL & MEDIA DIVISION

The Editorial Division of this section will be one of its primary divisions. It will be mainly responsible for producing printed health education and educated material for various health programmes. The Editorial Division will maintain liaison with All India Radio and Doordarshan Kendra, for providing background material on health programmes. The functions of the division are:

- To produce journals or NRHM news letter in Mizo for continuing education of Health Workers and general public.

- To produce ‘type’ health education materials like pamphlets, folders, handbills, posters, flash cards, charts for use of Health Workers and general public.

- To provide media services to different divisions of the section like Research and Evaluation, School Health Education and Training.

- To provide media services to all sections of Directorate of Health Services and its attached institutions regarding printed material and broadcast media.

- To prepare draft articles, speeches, messages for dignitaries of the Directorate of Health Services and of the Ministry.

- To prepare script and dispatch them to All India Radio Stations and Doordarshan Kendra based on the basis of seasonal diseases.

- To pretest ‘type’ health education material.

- To coordinate work with different units of the Information and Broadcasting division for the production of campaign material in local languages on different health subjects.

- To participate in training programmes on print media, Radio/ T.V. and communication for health education.

- To supervise individual assignments of the trainees for production of printed and broadcast material.

The Media Division will be mainly responsible for producing health education and publicity material for carrying out health education programmes in the state on scientific lines by disseminating the latest and correct information to the people about health and prevention of disease; and thereby creating awareness among the people and motivating them for desired changes in health behavior.

(a) Exhibitions

On an average, 5 exhibitions are to be organize every year on different areas of health and family welfare to educate the people on different aspects of health. Assistance is to be given to different official/non-official organizations in planning, production and use of exhibition media in health education programmes. Besides organizing exhibitions, exhibition material will also be loaned to the organizations working in the field of health education. They will participate in a number of State fairs to publicize the programmes and achievements on behalf of the Department.

(b) Photo Services

Photographic coverage will be done for the support of health programmes of the Directorate of Health Services, and Health & Family Welfare Dept. These photographs are to be used in the health publicity/educational material. A Photo Library will be maintained to provide ready reference of the photographic coverage.

(c) Audio-Visual Activities

Realizing the significant role of the A.V. Aids in disseminating health message to the masses, the Section will maintain a Film Library. Different health topics for teaching and educational purposes will also be made available. These can be loaned to Agencies to spread all over the state for carrying health messages to the people.

The Media Division should be well equipped with modern gadgets such as film projectors, slide projectors, T.V. Camera, etc.

2. TRAINING & HEALTH EDUCATION SERVICES DIVISION

Training will constitutes a major function of this section. The training programme itself with the help of various specialists available in the section and institution to organize courses for different categories of personnel such as ASHA, Multi Purpose Workers, Block Extension Educators, District Health Extension Educators, Nursing Staff, Social Workers, Social Scientists and Teachers. Much emphasis will be laid on to supervised field programmes for the trainees in order to develop skills in extension education and to integrate the theoretical aspects of health education with the field operations.

The objectives of the Training Division are to:-

1. To provide training in health education through short-term training programmes to equip the participants to work as health educator.

2. To prepare and standardize training curricula etc. for the training of various categories of health education personnel.

3. To organize orientation training programmes for ASHA, Multi Purpose Workers, Block Extension Educators, District Health Extension Educators, Nursing Staff, Social Workers, Social Scientists and teachers.

The Health Education Services Division will work for the growth and development of health education services in the state and will be apart of the National Health Programmes campaign.

It will also maintain to facilitate, support and assists for training of personnel, organizing workshops, seminars, and supply of equipment. The Division will have a close liaison with all Health Education Department in the States and will provide technical guidance to carry out health education activities.

3. BEHAVIOURAL RESEARCH AND EVALUATION DIVISION

The knowledge of people's behaviour forms an essential component of health education. To understand why people behave the way they do and to develop better ways and means to change them, it is essential to study the people's knowledge, their health practices and attitudes towards various health problems and programmes. With this view in mind, the Behavioral Research and Evaluation Division will establish with the objective to understand and promote behavioural research activities and behavioural change communication in the state. The functions of the Division are:-

1. 	 To conduct studies in various components of society and social forces related to health behaviour.

2. 	 To conduct problem-oriented studies to help in the effective implementation of various public health programmes.

3. 	 To initiate health related behavioral studies in cooperation/coordination with agencies, universities and other allied organizations.

4. 	 To strengthen social sciences and research methods components in various in-service training programmes of this section

5.	To conduct evaluation studies of the various training programmes, methods and media and other service activities.

6.	 To assist or carry out health education research and  other research oriented activities at the State level.

7. 	To disseminate health education research information to IEC section and various other allied institutions at the State level.

The Division will conducted field studies in the areas of National Malaria Eradication Programme, Maternity & Child Health and Family Welfare, JSY, Institutional delivery Sexually Transmitted Diseases, Environmental Sanitation, Food practices and medical care, etc. One of the major functions of the Division will be to produce technical papers and circulate them to other institutions that may use these for developing the research component of health education. Training in research methods will be another significant function of the Division.

The Field Study and Demonstration Centre of this section will be field laboratories to try various methods and media of health education which can be adopted elsewhere. These Centres provide opportunities for various Divisions of the Bureau to undertake field trials, conduct research, test and develop methods and media, and train various categories of personnel in actual field situations.

Health education work is carried out in the area especially in the rural areas, Sub- centre, Primary Health Centre, Community Health Centre, Hospitals, etc. A number of projects are to be carried out from time to time. The field training will be provides in different situations to various categories of trainees.

IEC SECTION AT THE DISTRICT

DISTRICT HEALTH SOCIETY would have BCC sub committee to make BCC plan and implementation.

District I.E.C Officer

DEMO

Deputy DEMO

BEE

ANM / ASHA / NGO

IEC SECTION AT THE DISTRICT HEADQUARTERS:

- District  IEC Officer

- Video Cameramen /Photographer

- Helper

FUNCTIONS OF DISTRICT I.E.C SETION

The District I.E.C Officer will be the convener of the BCC Sub-committee; the office may be in the District Health Society or CMO Office. Main functions will be to carry out the BCC activities in planning, implementation and supervision of their respective Districts. DEMO & Deputy Demo will help and support District IEC Officer in planning, implementation and supervision of BCC activities.

BEE and the Health Management Team:

Functions:-

# Support the District IEC subcommittee in all its functions.

# Implement the district IEC plan as appropriate for the block.

# Implement on the job capacity building of ASHAs/, Dais, ANMs, AWWs, MPWs 			in Interpersonal communication and other forms of BCC in synergy with the DTC.

# Collect feedback from the field on the campaigns, initiatives and interactions with 			the community.

# Help the district design context specific messages and material.

# Maintain necessary block-level databases, especially tracking the beneficiaries of 			different schemes for using them in advocacy

Competencies:-

- Co-ordinating tasks, prioritizing, organizing and problem solving; using different media, including mass media.

- Facilitating and monitoring health communication activities.

- Working with different groups - low literacy/ gender/ ethnicity/ school children / adolescents/ youth/ elders.

- Negotiation counselling and consensus building;

VILLAGE & HAMLET LEVEL

At the village level the BCC work will be integrated with all health planning and implementation work needs to be integrated through the statutory village health & sanitation committee, ANM, Anganwadi workers and the trainers of ASHAs, besides themselves carrying out BCC activities, will provide technical support to these committees. At the hamlet level the women’s health committee and /or the self help groups play the role of communicators along with the ASHA. The ANMs and the ASHA trainers and ASHA will together provide training and support to the local community based organizations and the village health & sanitation committees.

- Health Worker’s:

Function:-

- Carry out the planned health communication activities

- Collect feedback from the community and share it with the Supervisors

- Train and support the ASHAs in carrying out IEC / BCC activities.

Competencies:-

- Participatory Rural Appraisal

- Counseling and consensus building.

- Using basic communication aids

- ASHA’s:

Function:-

- Play a proactive or supportive role as necessary to disseminate health messages

- Undertake community mobilization

- Network with women's groups/ SHGs and involve them in advocacy

- Share local knowledge with ANMs, Supervisors help them understand the target audiences and learn out about the local context and culture.

Competencies:-

- Working with different groups.

- Using basic communication aids.

- Motivating, mobilizing and engaging people.

- Village Health and Sanitation Committees:

Function:-

- Integrate BCC into health plans by identifying key behaviours that need to be addressed.

- Support activities and provide leadership for changes.

- Play a proactive role to disseminate health messages and engage with community on building understanding current behaviours and needs for changes.

- Undertake collective action that involves many individuals and families to support or catalyze changed behaviour.

Competencies:-

- Understanding of issues, current behaviours and need for changes.

- Understand powers and influence of their office and learn how to exercise it to  support BCC.

- Understand needs and methods of social mobilization.

IMPLEMENTATION FRAMEWORK FOR BCC

IEC BUREAU HIERARCHY AT THE STATE LEVEL:

DIRECTOR / MISSION DIRECTOR

STATE IEC OFFICER

STATE IEC CONSULTANT (2),

DISTRICT IEC OFFICER (9)

BLOCK EXTENSION EDUCATOR (CHC= 9)

HEALTH EDUCATOR (PHC)

HW / ASHA

MANPOWER AT THE STATE LEVEL:

- State IEC Officer

- State IEC Consultant

- Editor - Printing/Audio Visual

- Video Cameramen /Photographer

- Computer Operator

- Helper

IEC SECTION HIERARCHY AT THE DISTRICT LEVEL:

District I.E.C Officer

DEMO

Deputy DEMO

BEE

ANM / ASHA / NGO

MANPOWER AT THE DISTRICT HEADQUARTER:

- District  IEC Officer

- Video Cameramen / Photographer

- Helper.

Table 3. MANPOWER REQUIREMENT AT THE DISTRICT/CHC/PHC

| Sl. No | Name of District | DHQ | CHC | PHC |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | Dist. IEC Officer | 3-BEE | 5-BEE |
| 2 | Aizawl West | Dist. IEC Officer | - | 6-BEE |
| 3 | Kolasib | Dist. IEC Officer | 1-BEE | 5-BEE |
| 4 | Mamit | Dist. IEC Officer | 1-BEE | 7- BEE |
| 5 | Serchhip | Dist. IEC Officer | 1-BEE | 5-BEE |
| 6 | Lunglei | Dist. IEC Officer | 2-BEE | 9-BEE |
| 7 | Champhai | Dist. IEC Officer | 3-BEE | 10-BEE |
| 8 | Saiha | Dist. IEC Officer | - | 4-BEE |
| 9 | Lawngtlai | Dist. IEC Officer | 1-BEE | 5-BEE |
| TOTAL |  | 9 | 12 | 56 |

As we have seen in the previous Table 2. there are no Media officers or IEC personnel at the district level. Few of the BEE are posted at CHC and PHC haphazardly as pointed out earlier. Table 3. is showing Manpower requirement for strengthening of BCC/IEC Bureau at State and  the district level as well as CHC & PHC.

Accordingly, Human Resources are planned in a phase wise manner.

B.10 	   STRENGETHENING OF BCC/IEC BUREAU AT DISTRICT LEVEL

| Sl.No | Designation | No.of Staff | Salary per month | Quantity | Amount (in lacs) |
| --- | --- | --- | --- | --- | --- |
| A. State level |  |  |  |  |  |
| 1 | State IEC Consultant | 2 persons | Rs. 35,000 | 12months | 8.40 |
| 2 | Editor – Audio visual | 1 person | Rs. 20,000 | 12months | 2.40 |
| 3 | Video Cameraman / Photographer | 1 person | Rs. 15,000 | 12months | 1.80 |
| 4 | Computer Operator | 1 person | Rs. 20,000 | 12months | 2.40 |
| 5 | Helper | 1 person | Rs. 6,500 | 12months | 0.78 |
| Total |  |  |  |  | 16 |

| B. District level |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | District IEC Officer | 9 person | Rs. 20,000 | 12months | 21.60 |
| 2 | Helper | 9 person | Rs.6500 | 12months | 07.02 |
|  |  |  |  | Total | 28.62 |
| Sub Total (A+B) |  |  |  |  | 44.62 |

B.10.1 		DEVELOPMENT OF STATE BCC/ IEC STRATEGY

| Sl.No | Specifications | Qty. | Rate | Amt. (in lacs) |
| --- | --- | --- | --- | --- |
|  | State Level |  |  |  |
| 1. | Xerox Copier (Toshiba-e Studio-282) | 1 | Rs. 1,50,000 | 1.5 |
| 2. | Colour Printer | 1 | Rs. 7000 | .07 |
| 3. | All in one (Laser printer, Fax machine & Scanner) | 1 | Rs. 10,000 | .1 |
| 4. | Laptop | 2nos. | Rs. 40,000 | .4 |
| 5. | LCD Projector (Hp & Infocus) | 1 | Rs. 50,000 | .5 |
| 6. | Video Camera | 1 | Rs. 30,000 | .3 |
| 7. | Spiral Binding Machine | 1 | Rs. 23000 | .23 |
| 8. | Digital Camera SLR | 1 | Rs. 35,000 | .35 |
| Sub Total |  |  |  | 3.45 |

B.10.2 		IMPLEMENTATION OF BCC /IEC STRATEGY

| B.10.2 | ACTIVITIES | Physical Target | Unit cost (Rs) | Amount (Rs) |
| --- | --- | --- | --- | --- |
| 1 | Training of IEC Personnel in the State & District | 60 | 1975 | 118500 |
| 2 | Capacity Building /Specialised Training of BCC/IEC staff in BCC in other states | 8 | 43500 | 348000 |
| 3 | Counselling at FRUs, PHC, CHC etc | 76 | 1000 | 76000 |
| 4 | Orientation Workshop on NRHM Activities for communnity in all District. | 9 | 50000 | 450000 |
| 5 | Focus Group Disccussion at Villages | 815 | 2000 | 1630000 |
| 6 | Community Meetings at PHC, CHC, SDH, DH | 76 | 10000 | 760000 |
| 7 | Review meeting of IEC personnel in the State | 4 | 50000 | 200000 |
| 8 | Inter Personnel Interaction by ASHA, ANM, AWW | 6000 | 50 | 300000 |
|  | Sub Total |  |  | 3882500 |

| B.10.2.1 | BCC/IEC Activities for Maternal Health | Physical Target | Unit cost (Rs) | Amount (Rs) |
| --- | --- | --- | --- | --- |
| 1 | JSSK Signboard with entitlements, grievance redressal Officers, name in all institutions where JSSK facilities are available | 180 institutions | 4000 | 720000 |
| 2 | Radio/TV Spots for MH ( AIR Azawl, AIR Lunglei, DDK, 5 local cables) | 150times (60 seconds each) | 2000 | 300000 |
| 3 | Wall writing | 100 nos | 4200 | 420000 |
| 4 | Renovation of wall writing | 60 nos | 2000 | 120000 |
| 5 | Promotion of voluntary blood donation through Civil Hospital Blood Bank and Association for voluntary blood donation. This activities will be linked with implementation of JSSK Scheme. ( expenditure should be incurred for collection of blood such as POL, consumables for blood donors, IEC- Awareness campaing, IEC materials, Display advertisements etc) | Lumpsum Budget |  | 200000 |
| 6 | Printing of leaflets on JSSK and other MH activities | 30000 copies | 10 | 300000 |
| 7 | Printing of posters | 20000 copies | 15 | 300000 |
| 8 | Awareness Campaign on maternal Health & Child Health to reduce MMR/IMR in 3 High Focus Districts namely Saiha, Lawngtlai and Mamit District | 9 places (3 places each) | 40000 | 360000 |
| 9 | Display advertisement through News papers | 100 times | 3000 | 300000 |
| Sub Total |  |  |  | 3020000 |
| B.10.2.2 | BCC/IEC Activities for Child Health | Physical Target | Unit cost (Rs) | Amount (Rs) |
| 1 | JSSK Signboard with entitlements, grievance redressal Officers, name in all institutions where JSSK facilities are available | Budget under MH |  |  |
| 2 | Radio/TV Spots for MH ( AIR Azawl, AIR Lunglei, DDK, 5 local cables) | 150 times ( 60 Seconds each) | 2500 | 375000 |

| 3 | Wall writing | 100 nos | 4200 | 420000 |
| --- | --- | --- | --- | --- |
| 4 | Renovation of wall writing | 60 nos | 2000 | 120000 |
| 5 | Printing of leaflets on JSSK and other CH activities such as Breast feeding, Home Based new born care etc | 20000 copies | 10 | 200000 |
| 6 | Printing of posters | 20000copies | 20 | 400000 |
| 7 | Awareness Campaign on maternal Health & Child Health to reduce MMR/IMR in 3 High Focus Districts namely Saiha, Lawngtlai and Mamit District | Budget under MH |  |  |
| 8 | Display advertisement through News papers | 100 times | 3000 | 300000 |
|  | Sub Total |  |  | 1815000 |
| B.10.2.3 | BCC/IEC Activities for Family Planning | Physical Target | Unit cost (Rs) | Amount (Rs) |
| 1 | Celebration of Worl Population Day - Banner, Meeting expenses, World Population Day Run for High School/College Students, Preparation of World Population Day T-Shirt etc | 9 Districts | 100000 | 900000 |
| 2 | Advocacy meeting with Opinion Leaders at State and District Levels Focussing use of FP method, Male participation in family planning etc | 10 times | 40000 | 400000 |
| 3 | Printing of Leaflets/ Poster/Flip Chart | 30000 copies | 10 | 300000 |
| 4 | Radio/TV Spots for MH ( AIR Azawl, AIR Lunglei, DDK, 5 local cables) | 150 times (60 seconds each) | 2500 | 375000 |
| 5 | Wall writing | 100 nos | 4200 | 420000 |
| 6 | Display advertisement through News papers | 100 times | 3000 | 300000 |
| 7 | Audio/Vedio Materials for Family Planning | Budget in lumpsum |  | 300000 |
|  | Sub Total |  |  | 2995000 |

| B.10.2.4 |  | BCC/IEC Activities for Adolescent Reproductive & Sexsual Health (Arsh) | Physical Target | Unit cost(Rs) | Amount (Rs) |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Radio/TV Spots for MH ( AIR Azawl, AIR Lunglei, DDK, 5 local cables) | 150 times (60 seconds each) | 2500 | 375000 |  |
| 2 |  | Wall writing | 100 nos | 4200 | 420000 |  |
| 3 |  | Awareness campaign at schools and Question box activities at 200 schools. While conducting awareness campaign at school, all the questions asked through the boxes will be discussed and explained. The students who ask the questions will not mention his/her name | 200 Schools | 4000 | 800000 |  |
| 4 |  | Leaflets on frequently asked question on adolescent Health | 20000 | 10 | 200000 |  |
| Sub Total |  |  |  |  | 1795000 |  |
| B.10.2.5 | OTHER ACTIVITIES (with specification) |  | Physical Target | Unit cost(Rs) | Amount (Rs) |  |
| 1 | Rallies for Celebration of NRHM day in 9 dist. |  | 9 | 100000 | 900000 |  |
| 2 | NRHM Tableau for Independence day Celebration |  | 1 | 50000 | 50000 |  |
| 3 | Folk Arts |  | 1 | 20000 | 20000 |  |
| 4 | Street Plays |  | 2 | 10000 | 20000 |  |
| 5 | Social Mobilisation Proggrame |  | 30 | 5000 | 150000 |  |
| Sub Total |  |  |  |  | 1140000 |  |
| B.10.4. | Health Melas |  | 1 | 800000 | 800000 |  |
| B.10.4. (TENTATIVE BUDGET FOR HEALTH MELA ) |  |  |  |  |  |
| Sl no. | Particulars |  |  | Amount(in Rs) |  |
| 1 | Publicity and promotion costs; |  |  | 75,000 |  |
| 2 | Preparation of Stalls & Decoration |  |  | 100,000 |  |
| 3 | Equipment and table, chair, audiovisual, etc., rentals; |  |  | 70000 |  |
| 4 | Printing & Stationery |  |  | 95000 |  |
| 5 | TA/DA for Medical Team |  |  | 95000 |  |
| 6 | Medicines for free distribution |  |  | 125000 |  |
| 7 | Mailing, including promotional and follow-up; |  |  | 5000 |  |
| 8 | Screening costs (including US, X-Ray, Lab. Facilities etc) |  |  | 75000 |  |
| 9 | Accomodation, Fooding & Lodging & Refreshments |  |  | 95000 |  |
| 10 | Contingency |  |  | 65000 |  |
|  | Budget Total |  |  | 800,000 |  |

| B.10.5 | Creating awareness on declining sex ratio issue | nil | 0 | 0 |
| --- | --- | --- | --- | --- |
| B.10.6. | OTHER ACTIVITIES |  |  |  |
| 1 | Celebration of World Health Day - Banner, Meeting expenses, Worl Health Day T-Shirt etc (9 Districts) | 9 | 100000 | 900000 |
| 2 | Display advertisement through News papers | 3000 | 1500 | 4500000 |
| 3 | Display advertisement through News papers | 2000 | 2000 | 4000000 |
| 4 | Display advertisement through News papers | 2000 | 2500 | 5000000 |
| 5 | Banners | 1000 | 1500 | 1500000 |
| 6 | Bulletin boards | 1000 | 2000 | 2000000 |
| 7 | TV / Radio spots for ASHA, VHSNC,RKS, (300 times 60 secs each) | 300 | 2500 | 750000 |
| 8 | Mizoram NRHM Documentary Film | 1 | 300000 | 300000 |
| 9 | Printing of VHSNC, RKS, ASHA etc Leaflet/pamphlets | 300000 | 10 | 3000000 |
| 10 | Mizoram State Health Society Calenders | 100000 | 13 | 1300000 |
| 11 | NRHM News letter cum bulletin | 60000 | 20 | 1200000 |
| 12 | Monitoring of BCC/IEC Activities | 9 | 20000 | 180000 |
| 13 | Evaluation of BCC/IEC Activities | 9 | 10000 | 90000 |
| Sub Total |  |  |  | 24720000 |
| Grand Total Rs. |  |  |  | 44,974,500/- |

Rupees Forty four crore ninety seven lakhs and forty five thousand only.

Qualification & Job Specification For Manpower At The State Level

| Sl/no | Category/Job Title | Essential Qualification | Preferential Qualification | Job Specification/ Responsibilities |
| --- | --- | --- | --- | --- |
| 1. | State IEC Officer (Behavioral Research) | MBBS with Post Graduate degree Diploma Health Education | 2 -3 years experience in a relevant field with MBBS / Bachelor degree in Health background. | Responsible for IEC Bureau and its division, administration and all activities for the whole state. Responsible for planning, implementation of all IEC/BCC activities for the whole state. Supervise, Monitor & Evaluation, Co-ordinate IEC activities at the State/ District Level. |
| 2. | State IEC Consultant (Training & Health Education Services Division) | Masters/Post Graduate Diploma in Mass Communication | 2 -3 years experience in a relevant field. | Responsible for planning IEC activities for the whole state. Supervise, Monitor & coordinate IEC activities at the state/ district level Arrange to develop audio-visual aids for health providers, especially on IPC with the help of professional agency. Participate in health providers training specially in IPC. Prepare an annual budget & calendar of State IEC Activities |
| 3. | State IEC Consultant (Editorial & Media Division) | Masters/Post Graduate Diploma in Mass Communication | 2 -3 years experience in a relevant field. | Responsible for Editorial & Media Division / Health Magazine activities for the whole state Arrange to develop audio-visual aids for health providers, especially on IPC with the help of professional agency. Prepare an annual budget & calendar of State IEC Activities |
| 4. | Editor – Audio visual | - Bachelors Degree with Arts or Science - At least one year diploma in computer application - Should be well conversant with Audio – Visual editing. - Should be expert in graphics designing | At least one year experience in related field. | Should responsible for editing in audio-visual media Coordinate with Journalist and media persons |
| 5. | Video Cameraman/ Photographer | - Bachelors Degree with Arts or Science - Should handle all types of Video Camera | At least one year experience in related field. | Should responsible for shooting & covering of different activities. Should responsible for taking all types of photographs |
| 6. | Computer Operator | - 10+2 with at least one year diploma in computer application - Typing speed of 20 w.p.m in English and Local language - Should be well conversant with Internet. | At least one year experience in related field. | Ensure regular entry of all relevant data in the computer Maintenance and up keep of the computer and its accessories including various defense. Should update in Internet Analyze data and compile report of the state |
| 7. | Helper | Class VIII & above | - | Upkeep and cleanliness of office |

Qualification & Job Specification For Manpower At The District Level

| Sl/no |  | Category/Job Title | Essential Qualification |  | Preferential Qualification |  | Job Specification/ responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. |  | District IEC Officer | Degree/Post Graduate Diploma in Mass Communication/Sociology |  | 2 -3 years experience in a relevant field. |  | Responsible for planning IEC activities for the district. Prepare an annual budget & calendar of district level IEC Activities Assist State IEC Consultant in planning, implementation, monitoring and supervision Coordinate with the district and internal control of weaknesses |
| 2. | Helper |  | Class VIII & above | - |  | Upkeep and cleanliness of office |  |

B.xvi PPP/NGOs

# Goal: To improve the health status of the population of underserved/ difficult area through PPP/NGO.

- MNGOs functions.

Mission Hospital namely Christian Hospital Serkawn run by Baptist Church of Mizoram in Lunglei district and Presbyterian Hospital Durtlang run by Mizoram Synod in Aizawl district were identified for Mother NGOs to cover 2 districts each. Christian Hospital Serkawn is functioning as MNGO in Lunglei and Lawngtlai districts and Presbyterian Hospital Durtlang is looking after Aizawl and Champhai districts. It has been proposed that the existing  MNGO - Presbyterian Hospital Durtlang will continue their services to promote RCH programme. However,  MNGO Christian Hospital Serkawn have been  completing 5 years  since the implementation of the programme, this MNGO may be allotted to another districts. Therefore, the remaining 4 districts in the state may be covered within another 5 years, fund requirement for the existing  2 district of Aizawl and Champhai and newly target 4 district is workout as below.

Estimation of  budget requirement for MNGO for 1 year.

| Personal Cost |  |  |
| --- | --- | --- |
| - Project Co-ordinator | @6500x1x12 | Rs. 144,000 X 6 |
| - Training Co-ordinator | @ 4500x1x12 |  |
| - Part Time Accountant | @ 1000x1x12 |  |

| Capacity Building of FNGO |  |  |  |
| --- | --- | --- | --- |
| - TA,DA, Food & Lodging materials |  |  | Rs. 30,000 X 6 |
| - Honorarium for RP | @ 500x3x4 |  |  |
| - Technical Expenditure | @ 1000x4 |  |  |
| Networking and capacity building of G.O./ANM, ASHA, MO, Block Officals |  |  |  |
| - TA, DA, Food |  | @ 5000x2 | Rs. 14,200 X 6 |
| - Materials |  | @ 70x2x30 |  |
| Develop IEC Materials |  |  |  |
| - Banner |  |  | Rs. 5,000 X 6 |
| - Poster |  |  |  |
| - Leaflets |  |  |  |
| News Bulletin |  |  |  |
| - Quarterly |  | @ 2500x4 | Rs. 10,000 X 6 |
| Networking with Stakeholders |  |  |  |
| - Refreshment |  | @4000x2 | Rs. 4,200 X 6 |
| - Training Materials batch 2 times |  | @ 70/person/30 nos.x2 |  |
| Infrastructure |  |  |  |
| - Computer & Printer |  | @ 40,000.00 | Rs. 161,300 X 6 |
| - OHP |  | @ 50,000.00 |  |
| - Laptop |  | @ 40,000.00 |  |
| - Digital Camera |  | @ 10,000.00 |  |
| - Weight Machine 4 Nos. |  | @ 2,500.00 |  |
| - Thermometer 10 Nos. |  | @ 300.00 |  |
| - BP Instrument 4 Nos. |  | @ 3,500.00 |  |
| - Furniture |  | @ 15,000.00 |  |
| Monitoring |  | @ 10,000.00 | Rs. 1,057,100 X 6 |
| Travel Cost/DA |  | @ 45,000.00 |  |
| Office Rent & Maitenance @ 2000/- |  | @ 24,000.00 |  |
| Communication : Tel/Fax/Courier/ Postage @ 500 |  | @ 6,000.00 |  |
| Audit @ 5000 per year |  | @ 5,000.00 |  |
| Contingency |  | @ 5,000.00 |  |

Total for existing 2 districts @ Rs.14,25,800/- per 1 district  X 2 =	     Rs. 28,51,600.00

Total for newly target  4 districts @ Rs.14,25,800/- per 1 district  X 4 = Rs. 57,03,200.00

Grand Total for 6 districts			 =				     Rs.85,54,800.00

(Rupees eighty five lakhs, fifty four thousand and eight hundred) only

- Marpara PHC in mamit district is operationalized as PPP mode.

Marpara PHC under Mamit district has been operationalised in collaboration with Presbyterian Hospital Durtlang (biggest Mission Hospital in the state) under PPP scheme. Marpara is located in the west of  Mizoram (Mamit dist) .It is one of the remote and hard to reach areas. Marpara PHC covers 2 S/C, 6 villages with a population of around 7600. Due to its remoteness and bad climatic condition many service providers used to refuse to work in this area. Thus, the inhabitants in this area are still lacking good health care delivery system due to its location and non availability of dedicated staff and health infrastructure. In such a situation. The Mission Hospital agreed to extend its services in this area keeping its Mission for the backward people in mind.

As approved by Government of India, MOU was signed during 2008-09 and the contract is 5 years commencing from 1st July, 2008. The State Health Society under RCH II Program provides all necessary funding for staff salaries, maintenance of health infrastructure, all equipment etc required for comprehensive health care delivery through the Mission Hospital. As implementation of  PPP has been found successful, It is planned to continue during 2012-2013. The Mission hospital is services provider, and responsible for recruitment of staff, operationalization of PHC and provide necessary services in accordance with existing norms and instruction issue by the State Health Society.

Budget for PPP (Marpara PHC):

| Sl.No | Category of Staff | No of Staff | Unit Cost/pm (Rs) | Amount P.m (Rs) |
| --- | --- | --- | --- | --- |
| 1. | Medical Officer | 1 | 42,350/- | 42,350/- |
| 2 | Staff Nurse | 4 | 12,100/- | 48,400/- |
| 3 | Health Worker/ANM | 4 | 10,800/- | 43,200/- |
| 4 | Laboratory Technician | 1 | 9,000/- | 9,000/- |
| 5 | X-Ray Technician | 1 | 9,000/- | 9,000/- |
| 6 | Ophthalmic Assistant | 1 | 9,000/- | 9,000/- |
| 7 | IV Grade | 2 | 6,500/- | 13,000/- |
|  | Sub Total |  |  | 1,73,950/- |
|  | Total for 1 year |  |  | 20,87,400/- |

Other:

- Travel and Conveyance @ Rs.6,000/-pm X 12 months = Rs.72,000/-

- Office expenses, Contingency @ Rs.7,000/-pm X 12 months = Rs.84,000/-

# Sub total = Rs.1,56,000/-

G.Total   = Rs.22,43,400/-

(Rupees twenty two  lakhs, forty three  thousand and four  hundred) only

Total fund requirement for implementation of MNGO and PPP is Rs.1,07,98,200.00

(Rupees one hundred  seven lakhs, ninety eight  thousand and two  hundred) only

# B.xvii Need Assessment and Training of Health Service Providers with special emphasis to Nursing Cadre

In order to improve the quality of service delivery at the state level, training of health service providers is proposed with special emphasis to the nursing staff at all levels. The training activities will be preceded by a quick need assessment exercise followed by training of health service providers using a ‘cascade training model’, systematic monitoring and feedback. This will be conducted by Sambodhi Research and Communications Pvt. Ltd, New Delhi.

Training Need Assessment

The training organization will engage at least two professionals with experience of conducting training needs assessment will be engaged in the process. These professionals will be supported by two field executives who will help them in conducting secondary data collection, in depth discussions, and FGDs. The scope of work for the need assessment will be a systematic gap analysis in terms of intended duties/functions and present performances. This will include both knowledge and skill gaps including: monitoring and supervision, usage of duty roasters, review and surveys, planning etc.

The cost of conducting TNA will be INR 367,000. This includes the professional cost, professional travel (to and fro from Delhi) and per diems and any other incidentals.

Training of Trainers

The gaps identified through the training need assessment will feed into the inputs for training. A detailed training manual will be prepared prior to the training. The training will be carried out using a ‘cascade training model’ to fast track training of service providers, whereby, extensive two-day training will first be imparted to the select master trainers from different districts. The knowledge gained by these master trainers will pass on progressively to the staff through one-day training at the district and sub-district levels.

The duration of the ToT will be 2 days and with a minimum of 15 participants with rate per participants per day will be INR 5000, wherein the venue will be provided by the state. Including the travel and logistics for the trainers from the training organization, per batch of training will cost approximately INR 150,000.

With an assumption of two ToTs in a state, the total cost of conducting the ToT will be INR 300,000.

Monitoring Trainings

Monitoring of training will be a comprehensive and regular activity in order to ensure and enhance the quality of the training programmes. Monitoring of the districts will be done by a team of personnel together from district officials and training organization. Two professionals from the training organization will be engaged in monitoring of the training programs at the district level conducted by the master trainers for at least 10 person days.

After the completion of the monitoring activities, a detailed report will be prepared. This will also entail engagement of the team leader for writing the findings in a report. The total cost of the engagement including monitoring activities and detailed report will be INR 220000.

With an assumption of two ToTs at the state level (more ToTs might be required in a bigger state) and 10 days’ of monitoring activities, summary of the total cost in a state will be as follows:

| Item | Cost (INR) |
| --- | --- |
| Training Need Assessment | 367000 |
| Training of Trainers (including preparation of training manuals) | 353000 |
| Monitoring of Training | 220000 |
| Miscellaneous (Communication/printing etc) | 100000 |
| Total | 10,40,000 |

The total cost of the activity in a state will be approximately INR 10.40 Lakh

|  | CONSOLIDATED BUDGET FOR MISSION FLEXI POOL (in lakhs) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SI. No. | Activity | Unit Cost | Physical Targets | Amount Proposed |
| Mission Flexible Pool |  |  |  |  |
| Bl | ASHA |  |  | 109.56 |
| Bl.l | Selection & Training of ASHA |  |  |  |
| B1.2 | Procurement of ASHA Drug Kit |  |  |  |
| B1.3 | Incentive to ASHAs under JSY |  |  |  |
| B1.4 | Incentive under Family Planning Services |  |  |  |
| B1.5 | Incentive under Child Health |  |  |  |
| B1.6 | Other Incentives to ASHAs |  |  |  |
| B1.7 | Awards to ASHA's/Link workers |  |  |  |
| B2 | Untied Funds |  |  |  |
| B2.1 | Untied Fund for CHCs | 50,000 | 9 | 4.50 |
| B2.2 | Untied Fund for PHCs | 25000 | 57 | 14.50 |
| B2.3 | Untied Fund for Sub Centers | 10000 | 370 | 37.00 |
| B2.4 | Untied fund for VHSC | 10000 | 815 | 81.50 |
| B.3 | Annual Maintenance Grants |  |  |  |
| B4.1 | CHCs | 100000 | 9 | 9.00 |
| B4.2 | PHCs | 50000 | 57 | 28.50 |
| B4.3 | Sub Centers | 10000 | 370 | 37.00 |
| B.4 | Hospital Strengthening |  |  |  |
| B.4.1 | Upgradation of CHCs, PHCs, Dist. Hospitals to IPHS) |  |  |  |
| B4.1.1 | District Hospitals |  |  |  |
| B4.1.2 | CHCs |  |  |  |
| B4.1.3 | PHCs |  |  |  |
| B4.1.4 | Sub Centers |  |  |  |
| B4.1.5 | Others |  |  |  |

| SI. No. | Activity |  | Unit Cost | Physical Targets |  | Amount Proposed |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B4.2 | Strengthening of District, Su-divisional Hospitals, CHCs, PHCs |  |  |  |  |  |  |
| B.4.3 | Sub Centre Rent and Contingencies |  |  |  |  |  |  |
| B.4.4 | Logistics management/ improvement |  |  |  |  |  |  |
| B5 | New Constructions/ Renovation and Setting up |  |  |  |  |  |  |
| B5.1 | CHCs |  |  |  |  | 1328.44 |  |
| B5.2 | PHCs |  |  |  |  |  |  |
| B5.3 | SHCs/Sub Centers |  |  |  |  |  |  |
| B5.4 | Setting up Infrastructure wing for Civil works |  |  |  |  |  |  |
| B5.5 | Govt. Dispensaries/ others renovations |  |  |  |  |  |  |
| B5.6 | Construction of BHO, Facility improvement, civil work, BemOC and CemOC centers |  |  |  |  |  |  |
| B.5.7 | Major civil works for operationalisation of FRUS |  |  |  |  |  |  |
| B.5.8 | Major civil works for operationalisation of 24 hour services at PHCs |  |  |  |  |  |  |
| B.5.9 | Civil Works for Operationalise Infection Management & Environment Plan at health facilities |  |  |  |  |  |  |
| B.6 | Corpus Grants to HMS/RKS |  |  |  |  |  |  |
| B6.1 | District Hospitals |  | 500000 | 8 |  | 40.00 |  |
| B6.2 | CHCs |  | 100000 | 9 |  | 9.00 |  |
| B6.3 | PHCs |  | 100000 | 57 |  | 57.00 |  |
| B6.4 | Other or if not bifurcated as above (SDH) |  | 100000 | 4 |  | 4.00 |  |
| B7 | State and District Action Plans (Including Block, Village) |  | 500000 | 10 |  | 50.00 |  |
| B8 | Panchayati Raj Initiative |  |  |  |  |  |  |
| B8.1 | Constitution and Orientation of Community leader & of VHSC,SHC,PHC,CHC etc |  | 2412 | 2509 |  | 60.53 |  |
| B8.2 | Orientation Workshops, Trainings and capacity building of PRI at State/Dist. Health Societies, CHQPHC |  | 30631 | 112 |  | 34.30 |  |
| B8.3 | Others |  |  |  |  |  |  |
| SI. No. |  | Activity | Unit Cost |  | Physical Targets |  | Amount Proposed |  |
| B9 |  | Mainstrearning of AYUSH |  |  |  |  | 178.03 |  |
| B9.1 |  | Activities other than HR |  |  |  |  |  |  |
| BIO |  | IEC-BCC NRHM |  |  |  |  |  |  |
| B.10 |  | Strengthening of BCC/IEC Bureaus (State and district levels) |  |  |  |  | 449.75 |  |
| B.10.1 |  | Development of State BCC/IEC strategy |  |  |  |  |  |  |
| B.10.2 |  | Implementation of BCC/IEC strategy |  |  |  |  |  |  |
| B.10.2.1 |  | BCC/IEC activities for MH |  |  |  |  |  |  |
| B.10.2.2 |  | BCC/IEC activities for CH |  |  |  |  |  |  |
| B.10.2.3 |  | BCC/IEC activities for FP |  |  |  |  |  |  |
| B.10.2.4 |  | BCC/IEC activities for ARSH |  |  |  |  |  |  |
| B.10.2.5 |  | Other activities (please specify) |  |  |  |  |  |  |
| B.10.4 |  | Health Mela |  |  |  |  |  |  |
| B.10.5 |  | Creating awareness on declining sex ratio issue |  |  |  |  |  |  |
| B.10.6 |  | Other activities |  |  |  |  |  |  |
| Bll |  | Mobile Medical Units (Including recurring expenditures) |  |  |  |  | 203.36 |  |
| B12 |  | Referral Transport |  |  |  |  | 658.88 |  |
| B12.1 |  | Ambulance/ EMRI |  |  |  |  |  |  |
| B12.2 |  | Operating Cost (POL) |  |  |  |  |  |  |
| B13 |  | School Health Programme |  |  |  |  |  |  |
| B14 |  | PPP/NGOs |  |  |  |  |  |  |
| B14.1 |  | Non governmental providers of health care RMPs/TBAs |  |  |  |  |  |  |
| B14.2 |  | PNDT and Sex Ratio |  |  |  |  |  |  |
| B14.3 |  | Public Private Partnerships | Please refer text |  |  |  | 22.43 |  |
| B14.4 |  | NGO Programme/ Grant in Aid to NGO |  |  |  |  | 85.55 |  |
| B14.5 |  | Other innovations( if any) |  |  |  |  |  |  |
| B15 |  | Planning, Implementation and Monitoring |  |  |  |  |  |  |
| B15.1 |  | Community Monitoring (Visioning workshops at State, Dist, Block level) |  |  |  |  |  |  |
| B15.1.1 |  | State level |  |  |  |  |  |  |
| B15.1.2 |  | District level |  |  |  |  |  |  |
| B15.1.3 |  | Block level |  |  |  |  |  |  |
| B15.1.4 |  | Other |  |  |  |  |  |  |

| SI. No. | Activity | Unit Cost | Physical Targets | Amount Proposed |
| --- | --- | --- | --- | --- |
| B15.2 | Quality Assurance |  |  |  |
| B15.3 | Monitoring and Evaluation |  |  |  |
| B15.3.1 | Monitoring & Evaluation / HMIS | Plse ref text |  | 197.37 |
| B15.3.2 | Computerization HMIS and e-governance, e-health |  |  |  |
| B15.3.3 | Other M & E |  |  |  |
| B.16 | PROCUREMENT |  |  |  |
| B16.1 | Procurement of Equipment |  |  |  |
| B16.1.1 | Procurement of equipment: MH | Please refer text |  | 309.15 |
| B16.1.2 | Procurement of equipment: CH | Please refer text |  | 87.60 |
| B16.1.3 | Procurement of equipment: FP | Please refer text |  | 48.60 |
| B16.1.4 | Procurement of equipment: IMEP | Please refer text |  | 18.00 |
| B16.1.5 | Procurement of Others (Solar Power Plant for all DH/CHC/PHC) | Please refer text |  | 37.80 |
| B.16.2 | Procurement of Drugs and supplies |  |  |  |
| B.16.2.1 | Drugs & supplies for MH |  |  | 300.00 |
| B.16.2.2 | Drugs & supplies for CH |  |  |  |
| B.16.2.3 | Drugs & supplies for FP |  |  |  |
| B.16.2.4 | Supplies for IMEP |  |  |  |
| B.16.2.5 | General drugs & supplies for health facilities |  |  |  |
| B.17 | PNDT Activities |  |  |  |
| B.18 | Regional drugs warehouses |  |  |  |
| B.19 | New Initiatives/ Strategic Interventions (As per State health policy)/ Innovation/ Projects (Telemedicine, Hepatitis, Mental Health, Nutition Programme for Pregnant Women, Neonatal) NRHM Helpline) as per need (Block/ District Action Plans) |  |  |  |
|  | Assessment of NRHM and assessment of various components |  |  | 50.00 |
|  | Need assessment and training of Health Service Provideers |  |  | 10.40 |
| B.20 | Health Insurance Scheme |  |  | 128.89 |
| B.21 | Research, Studies, Analysis |  |  |  |
| B.22 | State level health resources center(SHSRC) |  |  |  |
| B23 | Support Services |  |  |  |
| B23.1 | Support Strengthening NPCB |  |  |  |
| B23.2 | Support Strengthening Midwifery Services under medical services |  |  |  |
| B23.3 | Support Strengthening NVBDCP Salary of MPW | 8500/month | 75 | 76.50 |
|  | RDK (including CMAI staffs 885 voluntaries |  |  | 70.00 |
|  | ACT (including CNAI staff 885 voluntaries |  |  | 17.00 |
| B23.4 | Support Strengthening RNTCP |  |  |  |
| B23.5 | Contingency support to Govt. dispensaries |  |  |  |
| B23.6 | Other NDCP Support Programmes |  |  |  |
| B.24 | Other Expenditures (Power Backup, Convergence etc) |  |  |  |

4.C IMMUNISATION

- Mizoram currently has 8 district hospitals, 3 sub district hospitals, 9 CHCs, 57 PHCs and 370 sub centers which acts as an immunization sites. As per 2010 census there are 815 revenue villages which caters the immunization needs of the states, in these villages where the state does not have a government facility like sub-center an outreach sessions is conducted time and again depending on the number of expected beneficiaries reported by ANM/AWW/ASHAS

- The state has reported 84.75 % fully immunized as per the state HMIS, however as per SRS 2010 fully immunized children is only 37%. Therefore in the coming year the state propose to undertake coverage evaluation in order to triangulate the data. A lump  sum of RS 30  lakhs is proposed for this evaluation.

- The state plans to hire 21-25 surveyors and will cover 50 census enumeration block in both rural and urban area. Hence the coverage will be 100 census enumeration block which will be chosen using simple random sampling. In this process focus group- discussion will also be undertaken to assess the knowledge and attitude of the parents.

- This year plan also includes using maximum service of ASHAs and VHND for improving immunization coverage and the budget is reflected in the relevant portion. The necessary trainings and orientation will be taken up during the 2nd, 3rd and 4th round training of ASHA module 6 & 7 the finanancial involvement will be met from the ASHA fund.

- In order to increase the immunization coverage especially in the high focus district of the state (Mamit, Lawngtlai and Saiha) the state also propose to hire vaccinator and plan for alternative vaccine delivery so that all the required antigen is delivered at the far flung vaccination sites.

- During 2011-12 the state received 10 solar powered refrigerators which prove to be very useful in maintaining the cold chain system. However as the power supplied by the state government is very erratic it is estimated that the state will need another 20 solar powered refrigerator.

- For specific information and motivation on immunization the state plans Rs 5 lakhs especially for targeted intervention in IEC. The State plans to motivate the couple especially for more involvement of the child’s father. The IEC fund will be utilized mainly for logistic and radio jingles, banners, miking, hoarding, dramas and public functions.

- Overall objective of the immunization programme is to achieve 100% coverage for all the antigens (OPV, BCG, DPT, measles including hepatitis B and JE where applicable). The principles and planning process explained in the previous chapters are applicable to immunization as well.

- The overall supervision, monitoring and periodic review will be undertaken from NRHM  and is budgeted in part B of the state PIP. But it is strongly expressed by the district  that the state need a dedicated medical officer at the state level for planning, implementation and monitoring of immunization programme. It is therefore proposed to hires an MBBS doctor on a contractual basis from Part C ( Immunization ) at the rate of Rs 40,000/- per month in the coming year 2012-13.

- Planning for immunization would include assessment of the total number of VHND/ immunization sites needed to cater to the entire population. The sites would include sub-centres, PHC and other health facilities, Angan Wadi Centres (AWC), other sites in villages/hamlets without AWCs. The existing plan and data at PHCs would provide the number of sites under each ANM and the ANMs schedule would provide the number of sessions she holds. Developing a micro-plan would involve figuring out the difference between the number of sessions needed and number of sessions being held, reasons for shortfall in coverage and ways to bridge the gap. The States need to identify areas within the State which have low coverage and may require a more focused approach. The State and districts should use data from surveys, data collected through the State systems and HMIS for situation analysis and micro-planning. Micro-plan would also include plans to bring the children and pregnant women to the session sites primarily through ASHA. The State also needs to figure out how the vaccines/vaccinator would reach the immunization sites. Strategies may include a system of alternate vaccine delivery. Functionality of cold chain equipments and their maintenance should also be addressed in the PIP.

- Issues to be addressed in PIP: Among other issues the PIP should also include mechanisms of convergence between AWW and ANM, better utilization of services of second ANM, system of supportive supervision and periodical review and monitoring. The State also needs to ensure that key officers such as State Immunization Officer and District Immunization Officer are in place and there are systems to ensure stability of their tenure.

- Planning and budget formats: Annex 1-6 provide planning and budget formats for immunization. The budget for2012-13 should be summarized in the format given in annex.

The details of the activities given as follows:

- Situation Analysis

- Progress so far – achievement and expenditure in 2010-11 and 2011-12 (April-December)

ACHIEVEMENT OF UIP DURING 2010 – 2011

| Sl. No | District | TT P.W. | BCG | OPV-3 | DPT-3 | Measles | Fully immunized |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Aizawl West | 73.03 | 88.95 | 83.15 | 83.18 | 84.44 | 79.64 |
| 2. | Aizawl East | 62.98 | 115.67 | 112.98 | 112.98 | 108.52 | 109.49 |
| 3. | Champhai | 75.47 | 78.46 | 82.37 | 82.19 | 75.93 | 74.33 |
| 4. | Serchhip | 84.50 | 109.37 | 101.23 | 101.58 | 99.12 | 112.35 |
| 5. | Kolasib | 79.44 | 109.45 | 106.82 | 106.82 | 95.92 | 97.04 |
| 6. | Mamit | 87.53 | 105.79 | 104.08 | 104.54 | 95.92 | 94.67 |
| 7. | Lunglei | 52.76 | 76.65 | 72.82 | 74.44 | 69.24 | 63.70 |
| 8. | Lawngtlai | 70.51 | 62.58 | 63.07 | 65.37 | 54.93 | 61.02 |
| 9. | Saiha | 72.51 | 94.08 | 90.82 | 90.82 | 83.20 | 83.20 |
| 10 | State | 69.28 | 92.07 | 89.81 | 90.33 | 84.87 | 84.75 |

ACHIEVEMENT OF U.I.P. DURING April 2011-November 2011

| DISTRICT | Annual Target P W | TT (PW) | % | Annual Target Infant | BCG | % | DPT-3 | % | OPV-3 | % | MSL | % | Fully Imm. | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AIZAWL W | 4367 | 2325 | 53.2 | 3956 | 2566 | 64.9 | 2039 | 51.5 | 2039 | 51.5 | 2114 | 53.4 | 2114 | 53.4 |
| AIZAWL E | 9865 | 3171 | 32.1 | 8758 | 3799 | 43.4 | 4014 | 45.8 | 4016 | 45.9 | 3289 | 37.6 | 3286 | 37.5 |
| CHAMPHAI | 3073 | 2008 | 65.3 | 2899 | 1920 | 66.2 | 1884 | 65.0 | 1910 | 65.9 | 1843 | 63.6 | 1843 | 63.6 |
| SERCHHIP | 1306 | 767 | 58.7 | 1166 | 722 | 61.9 | 755 | 64.8 | 755 | 64.8 | 733 | 62.9 | 733 | 62.9 |
| KOLASIB | 2287 | 1418 | 62.0 | 1908 | 1246 | 65.3 | 1219 | 63.9 | 1208 | 63.3 | 1372 | 71.9 | 1357 | 71.1 |
| MAMIT | 2012 | 942 | 46.8 | 1848 | 1011 | 54.7 | 963 | 52.1 | 972 | 52.6 | 999 | 54.1 | 974 | 52.7 |
| LUNGLEI | 3238 | 1804 | 55.7 | 3077 | 2067 | 67.2 | 2138 | 69.5 | 2042 | 66.4 | 1975 | 64.2 | 1975 | 64.2 |
| LAWNGTLAI | 2867 | 1137 | 39.7 | 2471 | 1325 | 53.6 | 1260 | 51.0 | 1254 | 50.7 | 1119 | 45.3 | 858 | 34.7 |
| SAIHA | 1703 | 715 | 42.0 | 1548 | 898 | 58.0 | 884 | 57.1 | 780 | 50.4 | 856 | 55.3 | 856 | 55.3 |
| TOTAL | 30718 | 14287 | 46.5 | 27631 | 15554 | 56.3 | 15212 | 55.1 | 14803 | 53.6 | 14294 | 51.8 | 13996 | 50.7 |

- Objectives, Strategies and Activities for 2012-13

- Strategies for further improving Routine Immunization:-

The Immunization chapter of the PIP should essentially cover the aspects below (detailed guidelines provided in Annex 8c)

        - HR status (and steps to ensure tenure of at least 3 years)

- State Immunization Officer in place: Yes/No

- Number of districts without DIO (out of total no. of districts):

| RI staff at district level | Required | Sanctioned | In position | Vacant |
| --- | --- | --- | --- | --- |
| Cold chain handlers |  |  |  |  |
| Cold chain mechanics | 10 | 3 | 3 | 7 |
| Any other |  |  |  |  |

- System put in place for alternate vaccine delivery and its impact

- Systems put in place to ensure:

- Micro-planning of Immunization

- Strategy for increasing coverage, including vulnerable population –urban slums, migrants, tribal pockets

- Proper maintenance of cold chain equipments

- MIS for efficient inventory management for vaccines and other supplies

- Strategy to reduce vaccine wastage

- Integration of UIP and pulse-polio

- Co-ordination among ANM, AWW and ASHA

Situation analysis of the State Immunization Program

(The States/Uts should provide a brief write-up covering all the following issues)

1.	Current scenario of implementation of immunization program

a.	State level coverage as per District Level Household Survey-3, Coverage Evaluation Survey
2009 & Reported coverage for 2010-11, 2011-12 till Nov’ 11.

b.	District wise coverage levels of all antigens for 2010-11, 2011-12 till Nov’11 (including JE
wherever applicable).

c.	Reasons for Shortfall in coverage

d.	Reporting and incidence of VPDs for 2011-12 till Nov’ 11.

e.	Reporting and Response to Outbreaks and AEFIs for, 2011-12 till Nov’ 11.

2.	Strategies for further improving Routine Immunization

a.	Target of Immunization coverage for the year is 27631(Infant) and 30718(PW)

b.	From reports received by the State the coverage of BCG 2011-12 (Till Nov) is 56.3 and DPT-3 is 55.1 %. The districts with poor access are still Aizawl East and Lawngtlai Districts. The case of Aizawl East is complicated due to beneficiaries who were included in the target had taken Vaccines from Christian Private Hospital at Durtlang, and the case of Lawngtlai, the district population is mixed largely by Chakma Nomadic and communication is very poor.

c.	As reports shown above the achievement of DPT-3 is 55.1% whereas fully immunized achievement is 51.9% for 2011-2012.

d.	i) 	Timely(Quarterly) fund release for AVD, Mobility Support to DIOs, mobilization of ASHA, Salary of Computer Asst. To Districts

ii)	Timely submission of Micro-plan for RI by all districts

- Selected Districts are provided with ASHA mobilization.

iv)	To reduce dropouts incentive to ASHA for every immunized child.

v)	Regular monitoring done by sub-centre and PHC/CHC level headed by DIO in every district.

e.	i)  YMA biggest and most powerful NGO participation

ii)	Radio Jingle on RI

- Cold chain system- Repairable ILR/DF are collected and repaired by Fridge Mechanic where necessary tools are provided so that Cold Chain System run smoothly.

- All  9 District have Micro-plan.

- Most of the S/C have 2nd ANM, and all Male H/W are given the same training with ANM and they are expected to deliver RCH/Immunization Services.

- AWW and ASHA are fully involved in village nutritional days where immunization is also done besides Routine Immunization at S/Cs.

- As the state is situated in a Hilly Terrain Alternate Vaccine Delivery fund is very useful for timely delivery of Vaccine to Session Sites.

- As per record received by the State regular monitoring is being done by the State EPI Officer, District Immunization Officers, designated officers. In addition to this, officers of districts and State level Officers have given their services in monitoring the sessions.

- Not implemented, data is sent and received through Internet and Fax.

- Young Mizo Association (YMA) are participating actively by miking and Magazine published by Central YMA. AWW from ICDS are also participating during RI sessions and IPPI.

- Format attached.

- Status of Cold Chain Equipment-
i.)    ILRs, DF, Voltage stabilizers

| SI No | Item | Stock (functional) as on 31st Dec’11 | Requirement |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2010-11 | 2011-12 | 2012-13 |  |
| 1 | Cold Chain Equipments - |  |  |  |  |  |
| a) | WIC | 1 (non functional) |  |  |  |  |
| b) | WIF | 0 |  |  |  |  |
| c) | ILR | 0 | (S) 13. (L) 11 | (S)45, (L) 20 | (S)45, (L) 20 |  |
| d) | DF | (L) 1, (S) 1 | (S) 19, (L) 12 | (S) 45, (L) 20 | (S) 45, (L) 20 |  |
| e) | Cold Boxes | 0 |  | (S) 70, (L) 75 | (S) 70, (L) 75 |  |
| f) | Vaccine Carrier | 4 |  | 170 | 170 |  |
| g) | Ice Pack | 50 |  | 2170 | 2170 |  |
| h) | Vaccine Van | 1 (non function) |  | 4 | 4 |  |

- Not Implemented.

- Provisioned under RCH.

- Plan under NRHM/RCH.

Basic information of the State/UT related to Immunization Programme

| Position | Name & Designation | Contact No./Email |
| --- | --- | --- |
| State Immunization Officer | Dr. Lalvawna | 9436144275 (M), 03892320527 (O) 03892324697 (Fax) |
| State Cold Chain Officer | Shri. Sangliansiama | 9436154290 (M) |
| State Level Data Assistant |  |  |
| District Immunization Officers (DIO) | No. of Districts- 9 | No. of DIOs in position 2+7 |

A.

| S.No | Beneficiaries | Target |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2010-11 | 2011-12 | 2012-13 |
| 1. | Pregnant women | 29157 | 30614 | 32145 |
| 2. | 0 to 1 yr infants | 26202 | 27512 | 28888 |
|  | 1-2 yr | 21067 | 22120 | 23226 |
| 4. | 2-5 yr | 93746 | 98433 | 103354 |
| 5. | 5yr | 15800 | 10590 | 11120 |
| 6. | 10 yr | 23910 | 25105 | 26360 |
| 7. | 16 yr | 23173 | 24333 | 25550 |

The following information is to be filled based on the RI micro-plans. Please provide the details of held sessions for 2010-11 & 2011-12, while for 2012-13 the number of planned sessions is to be provided:

| S.No | Routine Immunization Sessions | 2010-11 | 2011-12 | 2012-13 |
| --- | --- | --- | --- | --- |
| 1. | Total Sessions planned | 860 | 6854 | 965/ month |
| 2. | Total Sessions Held | 860 | 10320 |  |
| 3 | No. of Outreach Sessions |  | 2901 | 2912 |
| 4. | No. of Fixed site sessions |  | 2320 | 2238 |
| 5. | No. of Sessions in Urban Areas | 541 | 891 | 567 |
| 6. | No. of Sessions in Rural Areas | 4352 | 3649 | 4503 |
| 7. | No. of sessions in hard to reach areas |  | 1184 | 1043 |
| 8. | No. of session with hired vaccinators* |  | 2 | 7 |
| 9. | No. of hired vaccinators* |  | 6 | 19 |
| 10. | No. of villages where sessions are held monthly |  | 1398 | 575 |
| 11. | No. of villages (smaller) where sessions are held on alternate months |  | 42 | 109 |
| 12. | No. of villages where sessions are held quarterly |  | 4 | 11 |

| B. | Existing Support to 1 | .he States |
| --- | --- | --- |
|  | Items | Stock (functional) as on 31st Dec'11 | 2010-11 |  | 2011-12 | 2012-13 | remarks |
| 1 | Cold Chain Equipments - |  |  |  |  |  |  |
| a) | WIC | 1 (non functional) |  |  |  |  |  |
| b) | WIF | 0 |  |  |  |  |  |
| c) | ILR | 0 | (S) 13. (L) 11 | (S)45, (L) 20 |  | (S)45, (L) 20 |  |
| d) | DF | (L) 1, (S) 1 | (S) 19, (L) 12 | (S) 45, (L) 20 |  | (S) 45, (L) 20 |  |
| e) | Cold Boxes | 0 |  | (S) 70, (L) 75 |  | (S) 70, (L) 75 |  |
| f) | Vaccine Carrier | 4 |  | 170 |  | 170 |  |
| g) | Ice Pack | 50 |  | 2170 |  | 2170 |  |
| h) | Vaccine Van | 1 (non function) |  | 4 |  | 4 |  |
| 2 | Vaccine stock and requirement (including 25% wastage and 25% buffer) |  |  |  |  |  |  |
| a) | TT |  | 146770 | 154500 |  | 162230 |  |
| b) | BCG |  | 99750 | 105000 |  | 110250 |  |
| c) | OPV |  | 361000 | 380000 |  | 399000 |  |
| d) | DPT |  | 225150 | 237000 |  | 248850 |  |
| e) | Measles |  | 45120 | 47500 |  | 100000 |  |
| f) | Hep B |  |  | 237000 |  | 248850 |  |
| g) | JE (Routine) |  |  |  |  |  |  |
| 3 | Syringes including wastage of 10% and 25 % buffer |  |  |  |  |  |  |
| a) | 0.1ml |  | 24814 | 105000 |  | 110250 |  |
| b) | 0.5 ml |  | 208533 | 676000 |  | 709800 |  |
| c) | Reconstitution Syringes |  | 6688 | 34200 |  | 36000 |  |
| 4 | Hub Cutters |  | 150 | 300 |  | 320 |  |
| 5. | Solar Refrigerator |  |  |  |  | 20 |  |

| B. | Existing Support to 1 | .he States |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SI No | Item | Stock (functional) as on 31st Dec’11 | Requirement |  |  |  |  |  | Remarks |
|  |  |  | 2010-11 |  | 2011-12 |  | 2012-13 |  |  |
| 1 | Cold Chain Equipments - |  |  |  |  |  |  |  |  |
| a) | WIC | 1 (non functional) |  |  |  |  |  |  |  |
| b) | WIF | 0 |  |  |  |  |  |  |  |
| c) | ILR | 0 | (S) 13. (L) 11 | (S)45, (L) 20 |  |  | (S)45, (L) 20 |  |  |
| d) | DF | (L) 1, (S) 1 | (S) 19, (L) 12 | (S) 45, (L) 20 |  |  | (S) 45, (L) 20 |  |  |
| e) | Cold Boxes | 0 |  | (S) 70, (L) 75 |  |  | (S) 70, (L) 75 |  |  |
| f) | Vaccine Carrier | 4 |  | 170 |  |  | 170 |  |  |
| g) | Ice Pack | 50 |  | 2170 |  |  | 2170 |  |  |
| h) | Vaccine Van | 1 (non function) |  | 4 |  |  | 4 |  |  |
| 2 | Vaccine stock and requirement (including 25% wastage and 25% buffer) |  |  |  |  |  |  |  |  |
| a) | TT |  | 146770 | 154500 |  |  | 162230 |  |  |
| b) | BCG |  | 99750 | 105000 |  |  | 110250 |  |  |
| c) | OPV |  | 361000 | 380000 |  |  | 399000 |  |  |
| d) | DPT |  | 225150 | 237000 |  |  | 248850 |  |  |
| e) | Measles |  | 45120 | 47500 |  |  | 100000 |  |  |
| f) | Hep B |  |  | 237000 |  |  | 248850 |  |  |
| g) | JE (Routine) |  |  |  |  |  |  |  |  |
| 3 | Syringes including wastage of 10% and 25 % buffer |  |  |  |  |  |  |  |  |
| a) | 0.1ml |  | 24814 | 105000 |  |  | 110250 |  |  |
| b) | 0.5 ml |  | 208533 | 676000 |  |  | 709800 |  |  |
| c) | Reconstitution Syringes |  | 6688 | 34200 |  |  | 36000 |  |  |
| 4 | Hub Cutters |  | 150 | 300 |  |  | 320 |  |  |
| 5. | Solar Refrigerator |  |  |  |  |  | 20 |  |  |

| c. | Additional Sup | port required by the State |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Service Delivery: - | Norms* | Expenditure & Achievement |  |  |  |  |  | Remarks |
|  |  | 2010-11 |  | 2011-12 (till Dec) |  | 2012-13 |  |  |
|  |  | Expenditure | Achievement | Expenditure | Achievement | Funds requireme nt | Target |  |
| Mobility support for supervision Supervisory visits by State and district level officers for monitoring and supervision of RI | @Rs.50,000 per District for district level officers (this includes POL and maintenance) per year | 550000.00 | No of sessions Supervised | 428160.00 | No of sessions Supervis ed | 450000.00 +100000.00=550000.00 | No of sessions Supervi sed |  |
|  |  |  | 80% |  | 80% |  |  |  |
|  | By State level officers @ Rs. 100,000 /year |  | No of districts visited for RI review |  | No of districts visited for RI review |  | No of districts visited for RI review |  |
|  |  |  | 80% |  | 80% |  | 9 Districts |  |
| Cold Chain maintenance | @ Rs 500 per PHC/CHC per year District Rs 10,000 per year | 123000.00 | % Funds used | 82793.00 | % Funds used | 123000.00 | % Funds used |  |
|  |  |  | 100 % |  | 67.31 % |  |  |  |
| Focus on slum & underserved areas in urban areas: | Hiring an ANM @Rs.300/sessio n for four sessions/month/ slum of 10000 population and Rs.200/- per month as contingency per slum of i.e. total expense of Rs. 1400/- per month per slum of 10000 population. | 307200.00 | No of sessions with hired vaccinators | 39200.00 | No of sessions with hired vaccinato rs | 1461600.00 | No of sessions with hired vaccina tors |  |
|  |  |  | 0.08% |  | 2.68% |  |  |  |
| Mobilization | @ Rs |  | No. of |  | No. of |  | No. of |  |

| of children through ASHA/ mobilizers | 150/session (for all States/UT.s) |  | sessions with ASHA |  | sessions with ASHA | 1350000.00 | sessions with ASHA | 990 session on hard to reach areas |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 4080 |  | 990 |  | 9000 |  |
| Incentives to ASHA for every fully immunized | @150/- per fully immunized child |  |  | 750000.00 | NA | 4333200 | 28888 children |  |
| Alternative Vaccine Delivery: | Geographically hard to reach areas (eg. Session site>30 kms from vaccine delivery point, river crossing etc.) @ Rs 100 per RI session | 718200.00 | No of sessions with AVD 860/month | 802800.00 | No of sessions with AVD 6200 sessions | 1158000.00 | No of sessions with AVD 11580 sessions |  |
|  | NE States and Hilly terrains @100 per RI session |  |  |  |  |  |  |  |
|  | For RI session in other areas @ Rs.50 per session. |  |  |  |  |  |  |  |
| Support for Computer Assistant for RI reporting (with annual increment of 10% w.e.f. from 2010-11) | State @Rs 12,000- 15,000 p.m. | 756000.00 |  | 802000.00 |  | 162000.00 |  |  |
|  | Districts @ Rs 8000- 10,000 p.m |  | No of C.A. in position |  | No of C.A. in position | 1026000.00 | No of C.A. in position |  |
|  |  |  | 9 District & State Hqtr |  | 9 District & State Hqtr |  | 9 District & State Hqtr |  |
| Hiring of MBBS Doctors @ 40,000/- (with annual increment of 10% w.e.f from 2012-13 | State @ 40,000/- |  |  |  |  | 480000.00 |  |  |
| Printing and dissemination of immunization cards, tally sheets, monitoring forms, etc. | @ Rs 5 per beneficiary | 122000.00 |  |  |  | 321450.00 |  | Rate maybe increased due to increase of printing price. |
| Review Meetings | Support for Quarterly State level Review Meetings of district officers @ Rs 1250/participant /day for 3 persons (CMO/DIO/Dist Cold Chain Officer) | 75000.00 | No of meetings held | 91900.00 | No of meetings held | 90000.00 | No of meeting s held |  |
|  |  |  | Quarterly |  | Quarterly |  | Quarterly |  |
|  | Quarterly Review & feedback meeting for exclusive for RI at district level with one Block MO.s, ICDS CDPO and other stakeholders® Rs 100/- per participant for meeting expenses (lunch, organizational expenses) |  |  | 80000.00 | Quarterly | 80000.00 | Quarterly |  |
|  | Quarterly review meeting exclusive for RI at Block level @Rs 50/-pp as honorarium for ASHAs (travel) and Rs 25 per person at the disposal of MO-I/C for meeting |  |  | 60000.00 | Quarterly | 60000.00 | Quarterly |  |

|  | Expenses(refreshments, stationery and misc. expences) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Training |  |  | No of persons trained | 79000.00 | No of persons trained |  | No of persons trained |  |
| District level orientation training for 2 days ANM, Multi Purpose Health Worker (Male), LHV, Health Assistant (Male/Female), Nurse Mid Wives, BEEs & other specialist (as per RCH norms) | As per revised norms for trainings under RCH |  |  |  |  |  |  |  |
| Three day training of Medical Officers on RI using revised MO training module | As per revised norms for trainings under RCH | 418000.00 | No. of person trained | 280000.00 |  |  | No. of person trained | Not yet conducted, but released to the district |
| One day refresher training of District RI Computer Assistants on RIMS/HMIS and | As per revised norms for trainings under RCH |  |  | 15000.00 |  |  |  | Not yet conducted, but released to the district |

| Immunization formats under NRHM |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Two day Cold Chain handlers training for block level cold chain handlers by State and District Cold Chain Officers and DIO for a batch of 15-20 trainees and three trainers | As per revised norms for trainings under RCH | 210000.00 | No of persons trained – 97 MPW/Cold Chain Handlers | 150550.00 | No of persons trained 97+38 M.O. =135 | 108000.00 | No of persons trained – 90 Nos. |  |
| One day Training of block level data handlers by DIO and District Cold chain Officer to train about the reporting formats of Immunization andNRHM | As per revised norms for trainings under RCH | 18000.00 | No of persons trained 20 Nos. | 26000.00 | No of persons trained 20 Nos. | 26000.00 | No of persons trained 20 Nos. |  |
| Microplanning |  |  |  |  |  |  |  |  |
| To develop sub-center and PHC microplans using bottom up planning with participation of ANM, ASHA, | @ Rs 100/- per sub centre (meeting at block level, logistic) |  |  | 36000.00 | 9 Districts have updated micro-pla ns this year | 37000.00 | 9 District s to updated micro-pl ans this year |  |
|  | For consolidation of microplan at PHC/CHC/UHC level @1000 |  |  | 44000.00 |  | 70000.00 |  |  |

|  | @ Rs 1000/-block & at district level @ Rs 2000/- per district |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| POL for vaccine delivery from State to District and from district to PHC/CHCs | Rsl00,000/ district/year | 900000.00 | % Funds used | 654200.00 | % Funds used | 900000.00 | % Funds used |  |
|  |  |  | 100% |  | 72.2 % |  | Timely delivery of Vaccines to all Districts |  |
| Consumables for computer including provision for internet access for RIMS | @ 400/ - month/ district | 47848.00 | 111.27 % | 33399.00 | 77.67 % | 43000.00 | Timely submission of reports |  |
| Injection Safety |  |  | % funds used | 80000.00 | % Funds used | 80000.00 | % Funds used |  |
| Red/Black Plastic bags etc | @ Rs 2/bags/session |  |  |  |  |  |  |  |
| Bleach/Hypoc hlorite solution | @ Rs 500 per PHC/CHC per year |  |  |  |  |  |  |  |
| Twin bucket | @ Rs 400 per PHC/CHC per year |  |  |  |  |  |  |  |
| IEC |  |  |  |  |  | 500000.00 |  |  |
| Hiring of surveyor for coverage evaluation survey |  |  |  |  |  | 3000000.00 |  |  |
| Any State Specific Need with | 10 % of total amount of approved PIP |  | % funds used |  | % Funds used |  | % Funds used |  |

District -wise Coverage reports (in numbers) (upto November 2011)

| s. No | Name of District | Yearly Target (2011-12) |  | BCG Coverage (in Numbers) | OPV - 1st Dose Coverage (in Numbers) | OPV - 3rd Dose Coverage (in Numbers) | DPT - 1st Dose Coverage (in Numbers) | DPT 3rd Dose Coverage (in Numbers) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Infants | Pregnant Women | 2011-12 | 2011-12 | 2011-12 | 2011-12 | 2011-12 |
|  | Azl W | 3956 | 4367 | 2566 | 1926 | 2039 | 1927 | 2039 |
|  | Azl E | 8758 | 9865 | 3799 | 3806 | 4016 | 3804 | 4016 |
|  | CPI | 2899 | 3073 | 1920 | 2015 | 1737 | 2013 | 1910 |
|  | SRP | 1166 | 1306 | 722 | 765 | 755 | 765 | 755 |
|  | KLB | 1908 | 2287 | 1246 | 1217 | 1208 | 1223 | 1208 |
|  | MMT | 1848 | 2012 | 1011 | 1050 | 972 | 1070 | 972 |
|  | LLI | 3077 | 3238 | 2067 | 1875 | 2042 | 1909 | 2042 |
|  | LTI | 2471 | 2867 | 1325 | 915 | 1254 | 1260 | 1254 |
|  | SHA | 1548 | 1703 | 898 | 762 | 780 | 849 | 780 |
|  | TOTAL | 27631 | 30718 | 15554 | 14331 | 14803 | 14820 | 114803 |

| S. No | Name of District | Measles Coverage | Measles 2nd dose Coverage | TT2+Booster Coverage | Hep B -Birth Dose Coverage | Hep B -1st Dose Coverage | Hep B - 3rd Dose Coverage | JE-routine (Wherever applicable) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Infants | Pregnant Women | 2011-12 | 2011-12 | 2011-12 | 2011-12 | 2011-12 |
|  | Azl W | 2114 |  | 2325 |  |  |  |  |
|  | Azl E | 3289 |  | 3171 |  |  |  |  |
|  | CPI | 1843 |  | 2008 |  |  |  |  |
|  | SRP | 733 |  | 767 |  |  |  |  |
|  | KLB | 1372 |  | 1418 |  |  |  |  |
|  | MMT | 999 |  | 942 |  |  |  |  |
|  | LLI | 1975 |  | 1804 |  |  |  |  |
|  | LTI | 1119 |  | 1137 |  |  |  |  |
|  | SHA | 856 |  | 715 |  |  |  |  |
|  | TOTAL | 14294 |  | 14287 |  |  |  |  |

| s. No | Name of District | DATA NOT AVAILABLE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2010-11 | 2011-12* | 2010-11 | 2011-12* | 2010-11 | 2011-12* | 2010-11 | 2011-12* | 2010-11 | 2011-12* | 2010-11 | 2011-12* |
|  | TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |

District Wise VPD reports in 2010-11 & 2011-12 (in numbers)

|  | District 1 |  | District 2 |  |
| --- | --- | --- | --- | --- |
| Disease | Cases | Deaths | Cases | Deaths |
| Diphtheria | NIL | NA | NA | NA |
| Whooping Cough | NA | NA | NA | NA |
| Neonatal Tetanus | NIL | NA | NA | NA |
| Tetanus(Other) | NIL | NA | NA | NA |
| Measles | 318 | NIL | NA | NA |
| Polio | 10 | NA | NA | NA |
| AES |  |  |  |  |

Consolidated Budget Sheet Immunization for FY 2012-13

| State | Mizoram | Budget 2012-13 (Rs. Lakhs) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| FMR Code | Activities( As proposed by the State) | Q1 | Q2 | Q3 | Q4 | ANNUAL TOTAL |
| C.I | RI Strengthening Project (Review meeting, Mobility Support, Outreach services etc |  |  |  |  |  |
| c.l.a | Mobility Support for supervision for district level officers. | 112500 | 112500 | 112500 | 112500 | 450000.00 |
| c.l.b | Mobility support for supervision at State level | 25000 | 25000 | 25000 | 25000 | 100000.00 |
| c.l.c | Printing and dissemination of Immunization cards, tally sheets, monitoring forms etc. | 321450 | 0 | 0 | 0 | 321450.00 |
| c.l.d | Support for Quarterly State level review meetings of district officer | 22500 | 22500 | 22500 | 22500 | 90000.00 |
| c.l.e | Quarterly review meetings exclusive for RI at district level with one Block Mos, CDPO, and other stake holders | 20000 | 20000 | 20000 | 20000 | 80000.00 |
| c.l.f | Quarterly review meetings exclusive for RI at block level | 15000 | 15000 | 15000 | 15000 | 60000.00 |
| c.l.g | Focus on slum & underserved areas in urban areas/alternative vaccinator for slums | 365400 | 365400 | 365400 | 365400 | 1461600.00 |
| c.l.h | Mobilization of children through ASHA or other mobilizers | 337500 | 337500 | 337500 | 337500 | 1350000.00 |
| c.l.i | Alternative vaccine delivery in hard to reach areas | 289500 | 289500 | 289500 | 289500 | 1158000.00 |

| c.l.j | Alternative Vaccine Delivery in other areas | 0 | 0 | 0 | 0 | NIL |
| --- | --- | --- | --- | --- | --- | --- |
| c.l.k | To develop microplan at sub-centre level | 0 | 0 | 0 | 36000 | 36000.00 |
| c.1.1 | For consolidation of microplans at PHC/CHC level | 0 | 0 | 0 | 44000 | 44000.00 |
| c.l.m | POL for vaccine delivery from State to district and from district to PHC/CHCs | 225000 | 225000 | 225000 | 225000 | 900000.00 |
| c.l.n | Consumables for computer including provision for internet access for RIMs | 10750 | 10750 | 10750 | 10750 | 43000.00 |
| c.l.o | Red/Black plastic bags etc. | 0 | 80000 | 0 | 0 | 80000.00 |
| c.l.p | Hub Cutter/Bleach/Hypochlorite solution/ Twin bucket | 0 | 0 | 0 | 0 | NIL |
|  |  | 0 | 0 | 0 | 0 | NIL |
| c.l.q | Safety Pits | 0 | 0 | 0 | 0 | NIL |
| c.l.r | State specific requirement | 0 | 0 | 0 | 0 | NIL |
| C.I-Sub Total |  |  |  |  |  |  |
| C.2 | Salary of Contractual Staffs -Sub Total |  |  |  |  |  |
| c.2.a c.2.b | Computer Assistants support for State level | 40500 | 40500 | 40500 | 40500 | 162000.00 |
|  | Computer Assistants support for District level | 256500 | 256500 | 256500 | 256500 | 1026000.00 |
| C.2-Sub Total |  |  |  |  |  |  |
| C.3 | Training under Immunization |  |  |  |  |  |
| c.3.a | District level Orientation training including Hep B, Measles & JE(wherever required) for 2 days ANM, Multi Purpose Health Worker (Male), LHV, Health Assistant (Male/Female), Nurse Mid Wives, BEEs & other staff ( as per RCH norms) | 0 | 0 | 0 | 0 | NIL |

| c.3.b | Three day training including Hep B, Measles & JE(wherever required) of Medical Officers of RI using revised MO training module) | 0 | 0 | 0 | 0 | NIL |
| --- | --- | --- | --- | --- | --- | --- |
| c.3.c | One day refresher training of district Computer assistants on RIMS/HIMS and immunization formats | 0 | 15000 | 0 | 0 | 15000.00 |
| c.3.d | Two days cold chain handlers training for block level cold chain handlers by State and district cold chain officers | 0 | 0 | 108000 | 0 | 108000.00 |
| c.3.e | One day training of block level data handlers by DIOs and District cold chain officer | 26000 | 0 | 0 | 0 | 26000.00 |
| C.3-Sub Total |  |  |  |  |  |  |
| C.4 | Cold chain maintenance | 30750 | 30750 | 30750 | 30750 | 123000.00 |
| C.5 | ASHA incentive for full Immunization (proposed) | 1083300 |  |  |  | 4333200.00 |
| C.6 | Pulse Polio Operational cost(Tentative) |  |  |  |  |  |
|  | IEC |  |  |  |  | 500000.00 |
|  | Hiring of surveyor for coverage evaluation survey | 750000 | 750000 | 750000 | 750000 | 3000000.00 |
|  | Hiring of MBBS Doctor for State | 120000 | 120000 | 120000 | 120000 | 480000.00 |
|  | TOTAL |  |  |  |  | 15947250 |

- NATIONAL DISEASE CONTROL PROGRAMME

D.1 National Iodine Deficiency Disorders Control Programme (NIDDCP)

WORK PLAN UNDER IODINE DEFICIENCY DISORDERS CONTROL PROGRAMME (NIDDCP) FOR MIZORAM FOR THE YEAR  2012-2013

Establishment of IDD Cell (According to 6th Pay)

| Sl.No | Designation | Amt. (Total Emolument) |
| --- | --- | --- |
| 1 | Technical Officer (1x 40000 x 12) Vacant | Rs. 480,000 |
| 2. | Statistical Assistant (1 x 35000 x 12) | Rs. 420,000 |
| 3. | L.D.C (1 x 15000x 12) Vacant | Rs. 180,000 |
|  | Total | Rs. 10,80,000 |

(Rupees Ten  lakhs eighty thousand) only

Establishment of IDD Laboratory (According to 6th Pay)

| Sl.No | Designation | Amt. (Total Emolument) |
| --- | --- | --- |
| 1 | Laboratory Technician (1x 30000x12) | Rs. 360,000 |
| 2 | Laboratory Assistant (1x25000x12) | Rs. 300,000 |
|  | Total | Rs. 660,000 |

(Rupees six lakhs sixty thousand) only

I.E.C

| Sl. No | Activities | Amt. (Rs) |
| --- | --- | --- |
| a | Printing of 20 Questions Booklet(in Mizo language) @ Rs 30 x 10,000 | 300,000.00 |
| b | Printing of Poster (IDD) (Rs.20 x 10,000) | 2,00,000.00 |
| c | Printing of Sticker @ Rs. 15 x 10,000 | 1,50,000.00 |
| d | Printing of Calendar @ Rs. 20 x 10,000 | 2,00,000.00 |
| e | Hoarding @ Rs. 7000 x 65 (57 PHC + 8 District Hospital) | 4,55,000.00 |
| F | Advertisement (Doordharshan, A.I.R, Local Cable T.V & Local Newspaper) | 5,00,000.00 |
| G | Printing of OPD Card @ Rs. 3.50 x 10000 | 35,000.00 |
|  | Total | 18,40,000.00 |

(Rupees eighteen lakhs forty thousand only)

Annexture 1

The following plans of actions are worked out for the first Quarter of 2012-2013 Plan. The assumed expenditure budget and expected outcome are tabulated below:

APRIL – JUNE (1st Quarter)

| Sl No | ACTIVITIES | EXPENDITURE BUDGET |
| --- | --- | --- |
| 1. | State level meeting on IDD and Iodated Salt with Commissioner / Ministers - Director, Health & F.W - Director, Food & Civil Supply - Director, Social Welfare Dept. - Director, Information Dept. - NGO’s No. of Participants = 40 | Resource Person 2 nos. @ Rs.500 = Rs. 1000.00 Lunch/Tea @Rs.100x 40 = Rs.4000.00 Hall Rent = Rs. 2500.00 Training material @ Rs. 40 x 80 = Rs. 3200.00 Banner = Rs. 1000.00 Total = Rs. 11,700.00 |

Annexture II

| Sl. No | ACTIVITIES | EXPENDITURE BUDGET |
| --- | --- | --- |
| 2. | Awareness Generation Meeting at 9Districts Hqrs. Meeting will be with Deputy Commissioner , Food & Civil Supply Dept., NGO’s, ICDS & Salt Traders. No. of expected Participants = 50 | Resource Person = 2 nos @ Rs 500 x 2 = Rs. 1000.00 Refreshment @ Rs. 100 x 50 = Rs. 5000.00 Banner = Rs. 1000.00 Hiring of Vehicle = Rs. 2000 Hiring of supporting staff @ 100 x 3 = Rs. 300 |
|  | Total For 9(Nine) District 9300 x 9 Districts | = Rs. 9300.00 = Rs. 83,700.00 |

# ASSUMPTION

| Sl. No | ACTIVITIES | ### EXPENDITURE BUDGET |
| --- | --- | --- |
| 3. | Training of ASHA on MBI Kits No of participants = 100 | Resource person = 2 nos @ Rs.500 x 2 = Rs. 1000.00 Refreshment @ 80 x 100 = Rs. 8000.00 Training Materials @ Rs. 80 x 100 = Rs. 8000.00 DA of trainee @ Rs. 100 x 100 = Rs. 10000.00 Banner = Rs. 1000.00 POL. For Vehicle = Rs. 2000.00 |
|  | Total For 9 Districts of Mizoram Rs. 30000 x 9 | = Rs. 30,000/- = Rs. 2,70,000/- |

JULY – SEPTEMBER (2nd QUARTER)

Annexture III

# ASSUMPTION

| Sl. No | ACTIVITIES | ### EXPENDITURE BUDGET |
| --- | --- | --- |
| 1. | Awareness training on IDD with Teachers / NGO’s and voluntary organization, Anganwadi workers. No of participants = 50 | Resource person = 2 nos @ Rs.500 x 2 = Rs. 1000.00 Refreshment @ 80 x 50 = Rs. 4000.00 Training Materials @ Rs. 80 x 50 = Rs. 4000.00 DA of trainee @ Rs. 100 x 50 = Rs 5000.00 Banner = Rs. 1000.00 Hiring of Vehicle = Rs. 2000 Hiring of Supporting Staff @ 100 x 3 = Rs. 300.00 |
|  | Total For 9 Districts of Mizoram Rs. 17,300 x 9 | = Rs. 17,300 = Rs. 1,55,700 |

OCTOBER – DECEMBER (3rd QUARTER)

Annexure IV

# ASSUMPTION

| Sl.No | ACTIVITIES | EXPENDITURE BUDGET |
| --- | --- | --- |
| 1. | Advocacy Meeting with Journalist at the State Headquarters. No of Participants expected = 50 | Resource person = 2 nos. @ Rs. 500 x 2 = Rs. 1,000.00 Refreshment @ 100 x 50 = Rs. 5000.00 Banner = Rs. 1000.00 Hiring of Vehicle = Rs. 2000 Training materials and contingencies @ Rs. 80 x 50 = Rs. 4000.00 |
|  | Total | Rs. 13,000.00 |

| Special IDD Survey for Children between 6 to 12 years of age | @ Rs. 50,000 x 3 Districts ### = Rs. 1,50,000.00 |
| --- | --- |

Annexture V

| Sl.No | ### ACTIVITIES | ### EXPENDITURE BUDGET |
| --- | --- | --- |
| 1. 2. | GLOBAL IDD DAY Awareness Campaign on IDD and its prevention at the State Headquarters. Awareness Campaign on IDD and its prevention. Awareness of Iodated salt consumption at 9 Dists. Hqrs. | = Rs. 60,000.00 = Rs. 20,000.00 for contingencies/Refreshment for 20,000 x 9 = Rs. 1,80,000.00 |
|  | Total | Rs.300,000.00 |

JANUARY – MARCH (4th QUARTER)

# ASSUMPTION

# Annexture VI

| ### Sl.No | ACTIVITIES | ### EXPENDITURE BUDGET |
| --- | --- | --- |
| 1. | State Level review meeting at State Hqrs. With Senior Officers from Health Dept. and Food & Civil Supply Dept. No. Of Participants expected = 50 nos. | Hall Rent = Rs. 2500.00 Working Lunch @ Rs. 150 x 70 = Rs. 10,500.00 Contingencies / expenditure Rs. 5000.00 TA/DA @ 150/Participants x 70 = Rs. 10,500 |
|  | Total | Rs. 28,500.00 |

SUMMARY OF THE BUDGETS

| Sl. no | Activities | Time Line |  |  |  | Amount |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Rs. |
| 1 | Establishment of IDD Cell |  |  |  |  | 10,80,000 |
| 2 | Establishment of IDD Laboratory |  |  |  |  | 6,60,000 |
| 3 | IEC |  |  |  |  | 18,40,000 |
| 4 | ## State level meeting on IDD | Rs. 11,700 (Annexture I) |  |  |  | 11,700 |
| 5 | Awareness Meeting | Rs. 83,700 (Annexture II) |  |  |  | 83,700 |
| 6 | Training of ASHA | 2,70,000 |  |  |  | 2,70,000 |
| 7 | Awareness training on IDD with Teachers, NGO’s etc |  | 1,55,700 (Annex III) |  |  | 1,55,700 |
| 9 | Advocacy meeting at state |  |  | 13,000 (Annex IV) |  | 13,000 |
| 10 | IDD Survey | 50000 | 50000 | 50000 |  | 1,50,000 |
| 11 | Global IDD Day |  |  | 3,00,000 (Annex V) |  | 3,00,000 |
| 12 | State level Review Meeting |  |  |  | 28,500 | 28,500 |
|  | Grand Total |  |  |  |  | 45,92,600 |

( Rupees Forty five lakhs ninety two thousand six hundred)only.

STATEMENT SHOWING THE ANNUAL PHYSICAL AND FINANCIAL REPORT UNDER NIDDCP FOR THE YEAR 2010-2011

|  |  |  | Quarterly Expenditure |  |  |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Items of expenditure |  | ## Pay scale | ## I | ## II | ## III | ## IV |  |
| ## IDD control cell |  |  |  |  |  |  |  |
| Tech. Officer(IDD) |  | Rs. 7500/- | 46,587 | 52,800 |  |  | ## 99387 |
| Statistical Asst. |  | Rs. 17610/- | 66728 | 67,896 | 87,252 | 82554 | ## 304430 |
| LDC/Typist |  | Rs. 5600/- | 48400 | 46,800 |  |  | ## 95200 |
| Total |  |  | ## 191928 | 1,67,496 | 87252 | 82554 | ## 529230 |
| IDD monitoring Lab. |  |  |  |  |  |  |  |
| Lab. Technician |  | Rs. 14050/- | 53663 | 54,987 | 64719 | 64719 | 238088 |
| Lab. Asst. |  | Rs. 10440/- | 43739 | 44,469 | 49014 | 49014 | 186236 |
| Total |  |  | ## 97402 | 99,456 | 113733 | 113733 | 424324 |
| Health Education Activities |  | Global IDD Day celebration on 21st Oct. in 2010 & 2011 was conducted in all the 9 districts of the state in the form of Quiz competition speeches on the importance of Iodine(Iodized salt), the ill effects of its deficiency being imparted among school children with distribution of cash prizes. Salt testing demonstration by MBI Kits being done and taught to the students |  |  | 170000 | 634648 | ## 804648 |
| Publication (IEC) |  |  |  |  |  | 1072670 | 1072670 |
| Survey/Re-Survey |  |  |  |  | 100000 |  | 100000 |
| Grand Total |  |  | 289330 | 266952 | 4,70,985 | Rs. 1903605 | 2930872 |
| Progressive Expenditure |  |  |  |  |  |  |  |
|  |  | ## Physical Achievements |  |  |  |  |  |
| ## Test Kit Method |  |  | ## I | ## II | ## III | ## IV | ## TOTAL |
| Collected |  |  | 18262 | 22282 | 20173 | 8987 | ## 69704 |
| Above 15PPM |  |  | 17468 | 21850 | 19624 | 8676 | ## 67618 |
| # Volumetric Method |  |  |  |  |  |  |  |
| # Non PFA |  |  |  |  |  |  |  |
| Collected |  |  |  |  |  |  |  |
| Conforming to Stand |  |  |  |  |  |  |  |
| # Titration |  |  |  |  |  |  |  |
| # Collected |  |  | 133 | 134 | 569 | 1483 | ## 2319 |
| # Conforming to Stand |  |  | 127 | 131 | 562 | 1477 | ## 2297 |
| # No of Urine Samples Collected |  |  | 133 | 80 | 287 | Nil | ## 500 |
| # Conforming to Stand |  |  | 133 | 80 | 287 | Nil | ## 500 |
| # Survey/Re-Survey |  |  | District | No of person | No of Goitre | Percent |  |
|  |  | 2010 April | Lunglei | 2258 | 204 | 9.0 |  |
|  |  | 2010 Dec | Aizawl E | 3562 | 196 | 5.5 |  |
|  |  | 2010 Dec | AizawlW | 3515 | 187 | 5.3 |  |

STATEMENT SHOWING THE 1ST QUARTER PHYSICAL AND FINANCIAL PROGRESS UNDER NIDDCP FOR THE YEAR 2011-2012

|  |  |  | Monthly expenditure |  |  | ## Total (Rs.) |
| --- | --- | --- | --- | --- | --- | --- |
| ## Items of expenditure | ## Pay scale |  | ## I | ## II | ## III |  |
| ## IDD control cell |  |  |  |  |  |  |
| Tech. Officer(IDD) |  |  |  |  |  |  |
| Statistical Asst. | Rs. 17610 |  | 26735 | 26735 | 26735 | 80205.00 |
| LDC/Typist |  |  |  |  |  |  |
| Total |  |  |  |  |  | ## 80205.00 |
| IDD monitoring Lab. |  |  |  |  |  |  |
| Lab. Technician | Rs. 14050 |  | 21573 | 21573 | 21573 | 64719.00 |
| Lab. Asst. | Rs. 10440 |  | 16338 | 16338 | 16338 | 49014.00 |
| Total |  |  |  |  |  | ## 113733.00 |
| Health Education Activities |  |  |  | 155500 |  | 155500.00 |
| Survey/Re-Survey |  |  | 150000 |  |  | 150000.00 |
| Grand Total |  |  | 214646 | 220146 | 64646 | 499438.00 |
| Progressive Expenditure |  |  |  |  |  |  |
| Physical Achievements for the Quarter – I |  |  |  |  |  |  |
| ## Test Kit Method |  |  |  |  |  |  |
| Collected |  |  | 4466 | 2494 | 1636 | 8596 |
| Above 15PPM |  |  | 4351 | 2457 | 1603 | 8411 |
| # Volumetric Method |  |  |  |  |  |  |
| # Non PFA |  |  |  |  |  |  |
| Collected |  |  | 490 | 493 | 495 | 1478 |
| Conforming to Stand |  |  | 487 | 491 | 494 | 1472 |
| # PFA |  |  |  |  |  |  |
| # Collected |  |  |  |  |  |  |
| # Conforming to Stand |  |  |  |  |  |  |
| # No of Urine Samples Collected |  |  | Nil | Nil | Nil | Nil |
| # Health Education # Activities |  | IDD awareness TV Spot and Scroll |  |  |  |  |
| # Survey/Re-Survey |  | District |  | No of Person | No of Goitre | Percentage |
|  |  | Serchhip |  | 1809 | 91 | 5.03 |
|  |  | Lawngtlai |  | 1501 | 109 | 7.2 |
|  |  | Saiha |  | 1392 | 114 | 8.1 |

STATEMENT SHOWING THE QUARTERLY PHYSICAL AND FINANCIAL PROGRESS UNDER NIDDCP FOR THE QUARTER ENDING SECOND FOR THE YEAR 2011-2012

| ## Items of expenditure | ## Pay scale | ## I | ## II | ## III |  |
| --- | --- | --- | --- | --- | --- |
| ## IDD control cell |  |  |  |  |  |
| Tech. Officer(IDD) |  |  |  |  |  |
| Statistical Asst. | Rs. 17610 | 29317 | 29317 | 29317 | 87951.00 |
| LDC/Typist |  |  |  |  |  |
| Total |  |  |  |  | ## 87951.00 |
| IDD monitoring Lab. |  |  |  |  |  |
| Lab. Technician | Rs. 14050 | 23644 | 23644 | 23644 | 70932.00 |
| Lab. Asst. | Rs. 10440 | 17878 | 17878 | 17878 | 53634 |
| Total |  |  |  |  | ## 124566.00 |
| Health Education Activities |  |  |  |  |  |
| Survey/Re-Survey |  |  |  |  |  |
| Grand Total |  | 70839 | 70839 | 70839 | 212517 |
| Progressive Expenditure |  |  |  |  |  |
| Physical Achievements for the Quarter – I |  |  |  |  |  |
| ## Test Kit Method |  |  |  |  |  |
| Collected |  | 2589 | 2458 | 1080 | 6127 |
| Above 15PPM |  | 2545 | 2330 | 1044 | 5919 |
| # Volumetric Method |  |  |  |  |  |
| # Non PFA |  |  |  |  |  |
| Collected |  | 497 | 490 | 492 | 1479 |
| Conforming to Stand |  | 495 | 489 | 490 | 1474 |
| # PFA |  |  |  |  |  |
| # Collected |  |  |  |  |  |
| # Conforming to Stand |  |  |  |  |  |
| # No of Urine Samples Collected |  | Nil | Nil | Nil | Nil |
| # Health Education # Activities |  |  |  |  |  |
| # Survey/Re-Survey | District |  | No of Person | No of Goitre | Percentage |

D.2 Integrated Disease Surveillance Programme (IDSP)

Introduction :  Integrated Disease Surveillance Project in Mizoram was started on 2005 and is among the 1st Phase States. Currently, there are nine Districts functioning under IDSP and there are two Priority Laboratories at  Aizawl  District and Lunglei District.  There is no Medical College in Mizoram but there are NGO hospitals and Several Private Hospitals who are reporting for IDSP.

1. Disease included in the surveillance in the State

Regular Surveillance

Vector Borne Diseases			: 1. Malaria

Water Borne Diseases				: 2. Acute Diarrhoeal Disease (Cholera)

: 3. Typhoid

Respiratory Diseases				: 4. Tuberculosis

Vaccine Preventable Diseases			: 5. Measles

Diseases Under Eradication			: 6. Polio

Other Conditions	: .Road Traffic Accidents (Linkup with Police Computers)

Other International Commitments		: 8. Plague

Unusual Clinical Syndromes			: 9. Menigoencephalitis / Respiratory Distress

(Causing death / hospitalization)		   Hemorrhagic fevers, other undiagnosed conditions

Sentinel Surveillance

Sexually Transmitted Diseases/Blood Borne	: 10. HIV/HBV, HCV

Other Conditions				: 12. Outdoor Air Quality (Large Urban Centers)

Regular Periodic Surveys

NCD Risk Factors	: 13. Anthropometry, Physical Activity, Blood Pressure, 
           Tobacco, Nutrition, Blindness and any other unusual health condition GOI may include in a public health emergency - subject to agreement at the next joint project review mission, project funds could be used for these surveillance activities.

Apart from these diseases, Mizoram had identified three other diseases – Cancer, Substance Abuse, and Acid Peptic Disease. In addition to the listed diseases under surveillance, Integrated Disease in Mizoram is also responsible on any outbreak of diseases, the control and containment measures were directly under the responsibility of IDSP.

- Administrative Setup of IDSP : Mizoram

Sentinel Surveillance Unit and Committee at State and District level had been formed in the presence of the Governor of Mizoram as under:

  - Members of State Surveillance Committee

- Commissioner & Secretary, Health & F.W.			- Chairman

- Director of Health Services					-Vice -chairman

- Director, Hospital & Medical Education			- Member

- Programme Officer, T.B.					- Member

- Programme Officer, Malaria					- Member

- Programme Officer, P.P.I.					- Member

- Programme Officer, H.I.V.					- Member

- Asst. Public Health Analyst, P.H.E.				- Member

- President, Central Y.M.A. or his Representative		- Member

- Member Secretary, Mizoram Pollution Control Board	- Member

- Programme Officer, IDSP					- Member Secretary

  - Terms of Reference of State Surveillance Committee

- The State Surveillance Committee will meet at least once a month when there is no epidemic situation and meet at more frequent intervals during times of epidemic and its large outbreaks.

- The committee is to oversee all the Surveillance activities in the State and will be administratively responsible for programme activities in Mizoram.

- The committee may co-ordinate with other Departments during large scale epidemics.

  - Responsibility of State Surveillance Unit

- Collection and analysis of all data being received from the district and transmitting the same to Central Surveillance Unit.

- Coordinating the activities of the rapid response teams and dispatching them to the field whenever the need arises.

- Monitoring and reviewing the activities of the DSUs including checks on validity of data, responsiveness of the system and functioning to the laboratories.

- Coordinating the activities of the state public health laboratories and other laboratories

- Coordinating all training activities under the project

- Coordinating meetings of the State Surveillance Committee

D. Name, Address and Contact Numbers of Officers under IDSP Mizoram:

| Sl.No | Name of Officer | Designation | Address | Phone Number |
| --- | --- | --- | --- | --- |
| 1 | Mrs.M. Zohmingthangi | Chairman & Chief Secretary i/c Health & FW etc. | Capital Complex. Mizoram: Aizawl. |  |
| 2 | Dr.C.Lalthanmawia | Vice-Chairman & Director of Health Service. | Directorate of Health Services. Dinthar, Aizawl.Mizoram. | (O)- 0389-2323452 (M)- Fax- 0389-2320169 |
| 3 | Dr.Lalvawna | State Nodal Officer & Member Secretary | Directorate of Health Services. Dinthar, Aizawl.Mizoram | (O)- 0389- 2317389 (M)- 9436144275 Fax- 0389-2319279 |
| 4 | Mr.K.Lalrammawia | Consultant (Finance & Procurement) | Directorate of Health Services. Dinthar, Aizawl.Mizoram | 0-9436388322 |
| 5. | Er.Nicky Lalremsiama | Data Manager | -do- | 0-9436194718 |

- Data Reporting

Weekly reports are prepared by reporting units on every Monday which includes data of previous week beginning from Sunday and ending of Saturday.

IDSP specific data from OPD and IPD of District Hospitals had been included besides L2 and L3 forms being collected from the hospitals. After the Govt. Hospital base reporting system is completed and on full fledge, it is also decided to include data from major Private Hospitals as well.

The information flow of weekly surveillance system is as follows :

DSU

Sub Centres

PHCs

CHCs

DHs

SSU

CSU

Pvt. Hospitals

P.H. Labs

A). Reporting Units:  525 reporting units have been established by 2011 out of which 509 are government and 16 are private reporting units. District-wise distribution of reporting units is shown below.

| Sl No | District | Form 'P' |  |  |  | Form 'S' | Form 'L' |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | PHCs/ CHCs | Public Sector Hospitals | Private | Total (Govt. + Private) | Sub Centre | Form 'L1' | Form L2/ L3 |  |  |
|  |  |  |  |  |  |  |  | Govt. | Private | Total |
|  |  | No. of Units | No. of Units | No. of Units | No. of Units | No. of Units | No. of Units | No. of Units | No. of Units | No. of Units |
| 1 | Aizawl East | 9 | 0 | 0 | 9 | 50 | 9 | 0 | 0 | 9 |
| 2 | Aizawl West | 6 | 1 | 8 | 15 | 37 | 6 | 1 | 8 | 15 |
| 3 | Champhai | 12 | 1 | 0 | 13 | 58 | 10 | 1 | 0 | 11 |
| 4 | Kolasib | 6 | 1 | 1 | 8 | 33 | 6 | 1 | 1 | 8 |
| 5 | Lawngtlai | 4 | 1 | 2 | 7 | 24 | 6 | 1 | 0 | 7 |
| 6 | Lunglei | 12 | 1 | 1 | 14 | 73 | 10 | 3 | 1 | 14 |
| 7 | Mamit | 7 | 1 | 0 | 8 | 27 | 6 | 1 | 0 | 7 |
| 8 | Saiha | 4 | 0 | 1 | 5 | 29 | 2 | 1 | 1 | 4 |
| 9 | Serchhip | 6 | 1 | 0 | 7 | 26 | 6 | 1 | 0 | 7 |
|  |  | 66 | 7 | 13 | 86 | 357 | 61 | 10 | 11 | 82 |

B). Timeliness & Completeness:

More than 84 % reporting units submitted weekly report in time for all the weeks during 20011.

| TOTAL REPORTING UNITS AND PERCENTAGE OF UNITS ACTUALLY REPORTING IN 2011 (Calculated from data upto Week no.47) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl.No. | District | P | S | L | Total (P+S+L) | Percentage |
| 1 | Aizawl East | 395 | 2184 | 403 | 2982 | 95.90% |
| 2 | Aizawl West | 682 | 1664 | 667 | 3013 | 97.76% |
| 3 | Champhai | 363 | 2082 | 343 | 2788 | 72.08% |
| 4 | Kolasib | 359 | 1402 | 308 | 2069 | 91.20% |
| 5 | Lawngtlai | 268 | 852 | 272 | 1392 | 81.62% |
| 6 | Lunglei | 474 | 2417 | 413 | 3304 | 69.90% |
| 7 | Mamit | 295 | 1042 | 268 | 1605 | 79.63% |
| 8 | Saiha | 163 | 1066 | 136 | 1365 | 73.79% |
| 9 | Serchhip | 312 | 1146 | 303 | 1761 | 96.60% |
| Over all reporting percentage during the year |  |  |  |  |  | 84.27% |

C.  Major Outbreaks

There were no major outbreaks formally reported and detected during 2011-2012.

HEAD WISE ACTION PLAN AND BUDGET ESTIMATED EXPENDITURE DURING 2012-2013

Current years’ fund proposal is prepared as per PIP guidelines of NRHM, 2012-13.

Fund requirement for IDSP Mizoram during 2012-2013

Rupees in lakhs

| Sl.No | Surveillance Units | Training | Personnel Costs | Operational Cost | IEC/BCC Activities | Laboratory Support | Financial Aids to Medical Insts. | Sero prevalence Screening of Scrub Typhus | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | State | 7.05 | 26.76 | 5.18 | 2.00 | 8.00 | 1.00 | 31.40 | 81.39 |
| B | Aizawl East | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| C | Aizawl West | - | 12.00 | 2.40 | 1.00 | - | .50 |  | 15.90 |
| D | Champhai | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| E | Mamit | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| F | Kolasib | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| G | Serchhip | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| H | Lunglei | - | 12.00 | 2.40 | 1.00 | - | .50 |  | 15.90 |
| I | Lawngtlai | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| J | Saiha | - | 9.00 | 2.40 | 1.00 | - | .50 |  | 12.90 |
| TOTAL |  |  |  |  |  |  |  |  | 203.49 |
| Say |  |  |  |  |  |  |  |  | 203.00 |

(Rupees Two hundred and three lakhs) only.

Details of proposal are given on the following pages.

FUND PROPOSED AT STATE LEVEL

INTEGRATED DISEASE SURVEILLANCE PROJECT, MIZORAM

- SUMMARY OF FUND PROPOSED AT STATE LEVEL DURING 2012-2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Personnel Costs (Salary) | 26,76,000 |
| 2 | Operational Costs | 5,18,000 |
| 3 | Training | 7,05,300 |
| 4 | IEC/ BCC Activities | 2,00,000 |
| 5 | Financial Aid to Medical Institutions | 1,00,000 |
| 6 | Laboratory support | 8,00,000 |
| 7 | Sero Prevalence Screening for Scrub typhus | 31,40,000 |
| Total |  | 81,39,300 |

(Rupees Eighty one lakhs thirty nine thousand three hundred ) only

- Personnel Costs (Salary):

| Sl.No | Title | No. | Proposed Salary p.m | Annual Cost (Rs) |
| --- | --- | --- | --- | --- |
|  | State Surveillance Unit |  |  |  |
| 1 | Epidemiologist | 1 | 40,000 | 4,80,000 |
| 2 | Microbiologist | 1 | 25,000 | 3,00,000 |
| 3 | Entomologist | 1 | 25,000 | 3,00,000 |
| 4 | Training Consultant | 1 | 28,000 | 3,36,000 |
| 5 | Veterinary Consultant | 1 | 40,000 | 4,80,000 |
| 6 | Consultant Finance | 1 | 25,000 | 3,00,000 |
| 7 | Data Manager | 1 | 25,000 | 3,00,000 |
| 8 | Data Entry Operator | 1 | 15,000 | 1,80,000 |
|  |  | 8 | 2,16,500 | 26,76,000 |

( Rupees Twenty six lakhs seventy six thousand ) only.

Salary of Consultant (Finance & Procurement) and State Data Manager is calculated so that there will be a parity of pay with other vertical health societies. It is desired by the state health society to provide same pay for same work rendered by the contractual staff. The pay of Data Managers at Districts is also proposed at Rs 20,000 p.m. and the pay of Data Entry Operators at Rs 11,000. Considering the current cost index and the fact that the state is implementing the 6th Pay, the pay of contractual staff is extremely low in comparison with their fellow contractual employee working with the state government. In order to have an effective, dedicated staff, it is important to boost their morale, to achieve this it is imperative to enhanced their pay at least up to what their counterparts received under other vertical health societies.

- Operational Costs :  The following are proposed expenditure under the as per NRHM PIP guidelines for 2012-2013.

| Sl.No | Activity | Annual Cost (Rs) |
| --- | --- | --- |
| 1 | Mobility support for visit of Districts @ Rs 2000 x 4 x 12 | 96,000 |
| 2 | Office Expenses @ Rs 5,000 x 12 | 60,000 |
| 3 | Printing of Reporting Forms | 1,80,000 |
| 4 | Broadband Expenses | 12,000 |
| 5 | TA/DA | 50,000 |
| 6 | Repairs of ICT Equipments | 70,000 |
| 7 | Collection and transportation of Samples | 50,000 |
|  | Total | 5,18,000 |

(Rupees  Five lakhs eighteen thousand ) only

- TRAINING: For the effective implementation of the project, it is a must to have a trained personnel at all levels as the trained staff is liable to be transferred anytime, also it is important to have a reorientation training as the personnel involved under IDSP have the same duty towards other health programmes . During the financial 2012-2013 it is intended to carry out one day training for;  Hospital Doctors, Hospital Pharmacists and Nurses, Data Managers and Data Entry Operators as per NRHM , PIP Guidelines for 2012-2013 as follows:

- One day Training of Hospital Doctors:

Training load: 100

No. of Batches: 5

No. of participants per batch: 20

| Particulars | Rate/day(Rs) | Days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 1 | 20 | 14,000 |
| Honorarium of Resource persons | 600 | 1 | 2 | 1,200 |
| Incidental expenditure | 250 | 1 | 20 | 5,000 |
| Working Lunch, Tea and Snacks | 200 | 1 | 20 | 4,000 |
| Hiring of Venue | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) | - | - | - | 3,700 |
| TA (Actual Maxi Cab/ Bus fare) Average | 2000 | - | 20 | 40,000 |
| TOTAL |  |  |  | 68,400 |

Total cost for 5 batches = 68,400 x 5 = Rs 3,42,000

(Rupees Three lakh forty two thousand)

- One day training of Hospital Pharmacists/Nurses:

Training load : 100

No. of Batches : 5

No. of participants per batch : 20

| Particulars | Rate/day(Rs) | Days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 1 | 20 | 8,000 |
| Honorarium of Resource persons | 600 | 1 | 2 | 1,200 |
| Incidental expenditure | 250 | 1 | 20 | 5,000 |
| Working Lunch, Tea and Snacks | 200 | 1 | 20 | 4,000 |
| Hiring of Venue | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) | - | - | - | 2,800 |
| TA (Actual Maxi Cab/ Bus fare) Average | 2000 | - | 20 | 40,000 |
| TOTAL |  |  |  | 61,500 |

Total cost for 5 batches = 61,500 x 5  = Rs 3,07,500

(Rupees Three lakhs seven thousand five hundred)

- One day training for Data Manager and Data Entry Operator

Training load : 20

No. of Batch: 1

| Particulars | Rate/day(Rs) | Days | Participants per batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 500 | 1 | 20 | 10,000 |
| Honorarium of Resource persons | 600 | 1 | 2 | 1,200 |
| Incidental expenditure | 250 | 1 | 20 | 5,000 |
| Working Lunch, Tea and Snacks | 200 | 1 | 20 | 4,000 |
| Hiring of Venue | 500 | 1 |  | 500 |
| Institutional Overhead (15% of above) | - | - | - | 3,100 |
| TA (Actual Maxi Cab/ Bus fare) Average | 2000 | - | 16 | 32,000 |
| TOTAL |  |  |  | 55,800 |

Total Cost = Rs 55,800 (Rupees Fifty five thousand eight hundred)

4.  IEC – BCC ACTIVITIES: No allocation for IEC activities is given on the approved PIP of 2010-2011 and  2011-12 as is available in the past financial years. IEC is a must for educating the personnel and public on impending /possible outbreaks. The containment measures of any particular disease is not effective with the health department intervention only but it both equally important to educate the people to checked the spread of the disease. IEC in the form of pamphlets, Radio/TV announcements, talk shows, and other innovations will be initiated during the current year and fund requirement will be as under :

State Level  								Rs   2,00,000

District Level @ Rs 1,00,000 each for 9 Districts			Rs   9,00,000

Total									Rs 11,00,000

- FINANCIAL AIDS TO MEDICAL INSTITUTIONS & COMPILER OF DATA :

There are various Private Institutions reporting under IDSP at the State and various Districts. If financial support in the form of honorariums were to be made available it is hoped that the performance of this units will be enhanced. Rs 5,00,000/- ( Rs 1,00,000 for the State and Rs 50,000 each for 9 Districts ) may be approved for this purpose. The fund will be utilized as follows :

- Procurement of Registers and Ledgers so that the Private Institutions will be able to record information as per IDSP reporting formats.

- Honorariums will be given to those personnel compiling the reports at these institutions as they are currently doing as a social service, honorarium even though minimal will motivate them.

- POL will be made available to the Private Institutions for the extra reports needed to be collected from their source.

- Mizoram is a hilly terrain and there are many Sub-Centre locations where regular transportation is not available and even road transport is absent. Currently the state is trying to collect weekly data by Mobile Phones. The ANMs were made responsible to submit the reports regularly and on time but have to resort to telephones as no viable and regular transport is available. The ANMs are currently paying the phone bills from their own pocket and if the proposal is approved, they will be re-imbursed from the funds proposed for every report they made by phone.

6. LABORATORY SUPPORT

Laboratory materials and consumables will be procured for two priority laboratories in Mizoram during 2012 – 2013 @ Rs 4,00,000 for each laboratory according to their requirements from the State and the figure is reflected under State demand.

7. 	SERO-PREVALENCE SCREENING FOR SCRUB TYPHUS IN MIZORAM

There has been an alarming increase in the number of cases of scrub typhus detected over the past few months in the state of Mizoram, which is indicated in the table below with two deaths, one each in the months of  November and December of 2011(Department of Medical Records, Civil Hospital, Aizawl). It has been postulated that several valuable lives might have been lost due to scrub typhus and even higher number of cases going undetected or misdiagnosed.

The percentage of positive findings in the general population varied from 2% in India to 40% in Malaysia [WHO (1983). Bull WHO 61:443]. Hence, the need for conducting sero-surveillance among the general population to highlight   the magnitude of scrub typhus, which has been a lesser known disease in Mizoram till the recent past, in order to increase public awareness as well as for implementation of preventive and timely curative measures.

| Fig. Scrub Typhus Cases in Mizoram, January- December, 2011 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Budget proposal of Sero-prevalence screening for Scrub typhus in Mizoram

| Sl. No. | ACTIVITY | UNIT COST (in Rupees) | PHYSICAL TARGET | AMOUNT Rs in Lakhs | REMARKS |
| --- | --- | --- | --- | --- | --- |
| 1 | HUMAN RESOURCE |  |  |  |  |
| 1.1 | Principal Investigator (PI) | - | 1 | - | Epidemiologist from the state Health Department |
| 1.2 | Field Investigators (FI) | Rs 10,000/- per month | 6 | 3.6 | for 3 (Three) FIs per district for 6months |
| 1.3 | Laboratory Technicians (LT) | Rs 10,000/- per month | 2 | 1.2 | for 2 LTs for 6 months |
| 1.4 | OPERATIONAL COST |  |  |  |  |
| 2 | Laboratory Equipments | Rs7.0Lakhs | 1 | 7.0 |  |
| 2.1 | Laboratory consumables | Rs2.4Lakhs | 1 | 2.4 |  |
| 2.2 | Training for investigators | Rs0.35lakhs | 11 | 4.2 | At National Institute identified by MoHFW, New Delhi |
| 2.3 | Mobility support for PO and Field Investigators | Rs4.0Lakhs | 3 districts | 12.0 |  |
| 2.4 | Publication of reports |  |  | 1.0 |  |
|  |  | Total |  | 31.4 |  |

(Rupees Thirty  one Lakhs and forty thousand) only

FUND PROPOSED FOR AIZAWL EAST DISTRICT

B.  AIZAWL EAST DISTRICT

Aizawl East District

SUMMARY FUND PROPOSED DURING    2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand ) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

FUND PROPOSED  FOR AIZAWL WEST DISTRICT

C.	AIZAWL WEST DISTRICT :

Annual action Plan

Year: 2012 -2013

SUMMARY FUND PROPOSED FOR    2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 12,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 15,90,000 |

(Rupees Fifteen lakhs ninety thousand) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl. | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| 4 | Microbiologist at District Laboratory | 25,000 | 1 | 3,00,000 |
| Total |  |  |  | 12,00,000 |

(Rupees Twelve lakhs ) only.

FUND PROPOSED  FOR MAMIT DISTRICT

D.	  MAMIT DISTRICT:

Annual Action Plan

SUMMARY OF ANNUAL ACTION PLAN   2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand ) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

FUND PROPOSED FOR CHAMPHAI DISTRICT

E.	CHAMPHAI DISTRICT

Annual Action Plan

Year: 2012 -2013

SUMMARY FUND PROPOSED FOR    2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

FUND PROPOSED FOR SERCHHIP DISTRICT

F.	SERCHHIP DISTRICT :			(I)

Name of the Society: IDSP: SERCHHIP

Annual action Plan

Year: 2012 -2013

SUMMARY OF ANNUAL ACTION PLAN   2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand ) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

FUND PROPOSED  FOR  KOLASIB DISTRICT

G.	KOLASIB DISTRICT:

Annual Action Plan

Year: 2012 -2013

SUMMARY FUND PROPOSED FOR    2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl. | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only

FUND PROPOSED  FOR LUNGLEI DISTRICT

H. LUNGLEI DISTRICT :

SUMMARY FUND PROPOSED FOR   2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 12,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 15,90,000 |

(Rupees Fifteen lakhs ninety thousand) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl. | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| 4 | Microbiologist at District Laboratory | 25,000 | 1 | 3,00,000 |
| Total |  |  |  | 12,00,000 |

(Rupees Twelve lakhs ) only.

I. LAWNGTLAI DISTRICT :

INTEGRATED DISESASE SURVEIILANCE PROJECT

NAME OF THE SOCIETY: LAWNGTLAI  DSU

SUMMARY OF ANNUAL ACTION PLAN   2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand ) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

FUND PROPOSED  FOR SAIHA DISTRICT

J.	 SAIHA DISTRICT:

INTEGRATED DISESASE SURVEIILANCE PROJECT

NAME OF THE SOCIETY: LAWNGTLAI  DSU

SUMMARY OF ANNUAL ACTION PLAN   2012 – 2013

| Sl. | Activity | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Operational Cost | 2,40,000 |
| 2 | Salary | 9,00,000 |
| 3 | IEC-BCC Activities | 1,00,000 |
| 4 | Financial Aid to Medical Institutions | 50,000 |
|  |  | 12,90,000 |

(Rupees Twelve lakhs ninety thousand ) only

I. OPERATIONAL COST FOR IMPLEMENTING IDSP.

District Level

| Sl.No | Activities | Unit cost (in Rs.) pm | Annual Cost (Rs) |
| --- | --- | --- | --- |
| 1 | Mobility Support | 5,000 | 60,000 |
| 2 | Office expenses | 5,000 | 60,000 |
| 3 | Broadband Expenses | 1,000 | 12,000 |
| 4 | Maintenance of equipments | 2,000 | 24,000 |
| 5 | Collection and Transportation of Samples | 5,000 | 60,000 |
| 6 | Other Incidental Charges | 2,000 | 24,000 |
| Total |  |  | 2,40,000 |

(Rupees Two lakhs forty thousand ) only

II. SALARY OF IDSP STAFF

| Sl.No | Name of post | Monthly Salary (in Rs.) | No. of post | Annual Salary (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Epidemiologist | 40,000 | 1 | 4,80,000 |
| 2 | Data Manager | 20,000 | 1 | 2,40,000 |
| 3 | Data Entry Operator | 15,000 | 1 | 1,80,000 |
| Total |  |  |  | 9,00,000 |

(Rupees Nine lakhs ) only.

D.3 National Vector Borne Disease Control Programme (NVBDCP)

SVBDCP MIZORAM PIP for inclusion in NRHM for the year 2012-13

INTRODUCTION

The SVBDCP, Mizoram is very grateful to the Central Govt. for assisting financially and materially in the implementation of SVBDCP. Though much had been accomplished through the aid given, Malaria remains a task that is still unfinished and a disease that needs to be controlled. It is therefore, felt imperative to make a new strategy in combating this dreadful disease from this financial year, 2012-2013.

Even though Malaria is a preventable and curable disease; Malaria is still a public health problem number one for Mizoram in terms of morbidity and mortality. The State economy is also greatly affected by this disease as the people have to spend a lot of their income for treatment, not to mention of deaths due to Malaria.

- The Following salient points of Malaria in Mizoram may be shown as follows (2011 - 2012):

- Annual Blood Slide Examination Rate (ABER)	-  16.61 %

- Blood Slide Positivity Rate (SPR) 			-  4.93 %

- Annual Parasite Incidence  (API)			-  8.19

- P.f  Percentage					-  94.52 %

- Death due to Malaria				-  30

It is evident from the above data that Malaria situation in Mizoram is very grave. Hence, the State needs special attention and consideration.

- Funds Situation:

  - Funds Requirement Projected to GOI during 2011-2012:   7.49 Crores.

  - Funds Allocated by GOI during 2011 – 2012 		 :   4.38 Crores.

  - Percentage of fund allocated out of fund demand projected: 58%.

From the above points, allocation of fund is found to be too meagre. Even if the allocated fund is released in full the SVBDCP would not be able to perform all its intended activities for the control of Malaria.

As already stated above, the state of Mizoram is unable to control Malaria.  It is therefore planned to take new initiatives as follows:

- Administrative failure:

The state is very thankful to the Central Government for assisting the State in terms of fund and materials.  However, it is regretted to mention that RDK and SP-ACT are not received by the State from the Central Government on demand in terms of quantity and on time. Some amount of RDK transferred from Maharashtra in 2011 immensely relieved the lack of Anti-Malarial drugs at the grass-root level.  It is therefore requested that the State requirement of RDK and SP-ACT projected that is 5,02,487 test kits and 55,186 combi-packs respectively may please be granted.

- Operational failure:

As Mizoram is fully a hilly terrain State, transportation of materials like DDT etc. is very difficult for which special consideration is necessary.  Therefore transportation of material cost stated under Procurement and Supply Chain Management may please be granted.  Also, full release of fund on time is very imperative so as to implement the Programme on time as well as the need of the Programme.

- Technical failure:

Most of the employees under this Programme are Contractual staff with no technical knowledge. Hence, induction training as well as repeated in-service trainings are needed so as to sharpen their technical skills.  In addition to this, involvement of community for successful implementation of the Programme is imperative. It is therefore aimed to involve different voluntary organizations actively from the year 2012-2013 for which at least short course training will be necessary for all categories.  Fund requirement is also projected slightly more than the previous year.

It is also planned to improve supervisory works to monitor and evaluate how the Programme is precisely implemented.  More supervisory visits/tours will be undertaken from the State, District, Sub-District, CHC/PHC levels.

By taking the aforementioned new activities, actual baseline situations would be assessed and improved automatically.

It is therefore prayed that our demand presented for the year 2012-2013 would be granted in toto so as to achieve our goals.

Hatcheries are started for the first time in Mizoram and further distribution of Larvivorous fishes will be done to all Districts. Separate budget for the same is reflected in the respective financial budget part.

EXECUTIVE SUMMARY

Epidemiological Situation for the year 2011 :

| District | Person Examined |  | Positive | P.f | No. of Death | ABER | API | P.f % | SPR | SFR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |
| Aizawl East | 16845 | 6862 | 47 | 45 | 3 | 10.04 | 0.21 | 95.74 | 0.20 | 0.20 |
| Aizawl West | 15120 | 6788 | 90 | 85 | 5 | 14.12 | 0.58 | 94.44 | 0.41 | 0.39 |
| Kolasib | 20069 | 6788 | 462 | 444 | 1 | 30.35 | 6.38 | 96.10 | 2.10 | 2.02 |
| Mamit | 17578 | 6657 | 1254 | 1224 | 2 | 30.31 | 19.37 | 97.61 | 6.39 | 6.24 |
| Serchhip | 7426 | 1600 | 61 | 52 | 3 | 14.83 | 1.01 | 85.25 | 0.68 | 0.58 |
| Lunglei | 31828 | 11995 | 3279 | 3074 | 2 | 24.14 | 22.84 | 93.75 | 9.46 | 8.87 |
| Lawngtlai | 17059 | 9793 | 2840 | 2728 | 11 | 15.27 | 22.92 | 96.06 | 15.02 | 14.42 |
| Saiha | 8791 | 4276 | 348 | 284 | 3 | 16.90 | 6.07 | 81.61 | 3.59 | 2.93 |
| Champhai | 9250 | 3796 | 68 | 50 | 0 | 10.16 | 0.54 | 73.53 | 0.53 | 0.39 |
| TOTAL | 143966 | 58555 | 8449 | 7986 | 30 | 16.61 | 8.19 | 94.52 | 4.93 | 4.66 |

Endemicity Map for the disease, Map of Vector prevalence and vector susceptibility Map,  District wise Bar chart for Malaria cases and Death:

Mizoram Map Based on API Range:

Achievement during the Year 2011 – 2012:

- Annual Parasite Incidence (API) – 8.19

- Death due to Malaria – 30

- Annual Blood Examination Rate (ABER) – 16.61%

Mizoram State Goals for the Xll Five year Plan:

| State Goals for the Xll Five year Plan | Target for 2012-2013 | Target for 2013-2014 | Target for 2014-2015 | Target for 2015-2016 | Target for 2016-2017 |
| --- | --- | --- | --- | --- | --- |
| - Reduction of Malaria Cases per 1000 population (API) | 5/1000 population | 4/1000 population | 3/1000 population | 2/1000 population | 1/1000 population |
| - Reduction of Malaria Deaths (in numbers) | 22 | 16 | 11 | 8 | 5 |
| - Increase in Annual Blood Examination Rate (ABER) | 16.5% | 18% | 19.5% | 21% | 22.5% |

Better achievement in the programme implementation is expected in subsequent years due to increase of man-power by 885 from CMAI (Community Health Volunteer) and new recruitement of staff under the State Vector Borne Disease Control Programme, Mizoram. Also, the State Government gives permission of transfer and posting of Health Workers who are grass root workers to the Districts Head (Chief Medical Officer). Accordingly, improvement is expected in number of Blood Collections, reduction of Malaria cases and deaths etc

The disease situation in the Mizoram state:

| Year | Malaria cases | Malaria Deaths | Dengue cases | Dengue deaths | Chikungunya cases | AES/JE cases | AES/JE deaths | Kala-azar cases | Kala-azar deaths | Microfilaria rate (%) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2010 | 15495 | 31 | 5(Detected in Private Hospitals, Aizawl) | Not Known | NIL | NIL | NIL | NIL | NIL | NIL |
| 2011 | 8449 | 30 | Test kit not received yet. | Not Known | NIL | NIL | NIL | NIL | NIL | NIL |

In the state of Mizoram, Malaria is still a major public health problem.

Malaria is endemic in 6 districts viz; Lawngtlai District, Saiha District, Lunglei District, Mamit District, Kolasib District and Serchhip District.

For a long time, it has been taken for granted that Mizoram is free from Dengue, Chikungunya, Acute Encephalitis Syndrome/Japanese Encephalitis, Kala Azar and Filaria cases as there are no provisions for detection of these cases in the Govt Health Institutions. These cases are not detected except few cases of Dengue by Private Hospitals. Requirement of NS1 antigen test kits and IgM capture ELISA for Dengue as well as Japanese Encephalitis test kits are included in PIP 2012-13.

Due to improvement of transport systems as well as modern lifestyles, intermixing of population in the country is such that it can no longer be taken into granted that Mizoram is free from all other Vector Borne Diseases. Hence it is planned to initiate from the year 2012 -2013 to make initial activities of implementation of these Diseases for which minimum financial budget is projected.

The requirement for programme implementation has been indicated in detail and the summary is indicated below:

( Rupees in Lakhs)

| Disease | Expected Balance from previous years as on 1.4.2012 | Committed expenditure | Cash assistance from NVBDCP | Cash assistance from NRHM flexi fund* | State resources |
| --- | --- | --- | --- | --- | --- |
| Malaria - Domestic Budget Support - World Bank fund for project states - GFATM fund for project states | NIL NIL NIL | NIL NIL NIL | 233.0 NIL 180.0 | 29.38 NIL NIL | NIL NIL NIL |
| Dengue (from Domestic Budget) | NIL | NIL | NIL | NIL | NIL |
| Chikungunya (from Domestic Budget) | NIL | NIL | NIL | NIL | NIL |
| AES including JE (from Domestic Budget) | NIL | NIL | NIL | NIL | NIL |
| Filaria (from Domestic Budget) | NIL | NIL | NIL | NIL | NIL |
| Kala-azar (from Domestic Budget) | NIL | NIL | NIL | NIL | NIL |
| Kala-azar World Bank Project assistance | NIL | NIL | NIL | NIL | NIL |
| Total | NIL | NIL | 413.0 | 29.38 | NIL NIL |

*Note: NRHM flexi fund is recommended only when the activities are required and are not supported financially under programme either by NVBDCP or by state resources.

Annual Action Plan/PIP 2012-13

1.	Demographic Profile of Mizoram State.

Population of the State: 10,32,193

| Infrastructure | Number |
| --- | --- |
| Districts | 9 |
| CHCs | 12 |
| PHCs | 57 |
| HSCs | 370 |
| Villages | 827 |
| FTDs | 1787 |
| Other Health Facilities (UHC/Health Clinic) | 5/57 |

2. District-wise status of Manpower (sanctioned & vacant)

| Regular Posts | Required | Sanctioned | In Position | Vacant |
| --- | --- | --- | --- | --- |
| District Malaria Officer/District VBD Officer | 8 | 1(Special Officer Malaria in Lunglei District) | 9(8 DMOs are designated posts only having many other charges besides Malaria) | NIL |
| District Filaria Officer | - | - | - | - |
| Assistant Malaria/ VBD Officer | 6 | 3 | 3 | NIL |
| Medical Officer |  |  |  |  |
| Senior Malaria Inspector | - | - | - | - |
| Malaria Inspector | 61 | 8 | 8 | NIL |
| Multi Purpose Health Supervisor(M&F) | 19 | 171 | 152 | 19 |
| Multi Purpose Health Assistant or Multi Purpose Worker(M&F) | 186 | 770 | 584 | 186 |
| Lab. Tech. | 5 | 67 | 62 | 5 |

Contractual Posts (applicable for the states where MPWs have been sanctioned by NVBDCP and Project staff in project districts (World Bank & GFATM Dist) :

| Post | Number | Remarks |
| --- | --- | --- |
| MPW Regular | NIL | Not applicable |
| MPW Contractual under NVBDCP | 75 | As NVBDCP will not support MPW in 12th Five Year Plan, NRHM and State Govt are requested to support the MPW from the ensuing financial year i.e 2012-2013 |
| Lab.Tech. | 10 | Financed by GFATM. |
| Consultants (District level & State level) | 14 (5 in State and 9 in Districts) | Financed by GFATM |
| Malaria Technical Supervisors/Kala-azar technical supervisors | 27 | In 12th Plan, these designations have been proposed to be changed as VBD Technical supervisors. |
| Project monitoring unit staff both at State and district level ( indicate positions ) | Statistical Asst – 1 (State). Secretarial Asst – 2 (State). Secretarial Asst – 9 (District). | Financed by GFATM |

Malaria

Target:	During XII plan period the proposed target is as below:

ABER > 10%, API<1 per thousand population (during 12th plan, the objective is to bring down annual incidence of malaria cases to less than 1 per 1000 population at national level by 2017 and its monitoring at district level).

Epidemiological Data for 2010 & 2011:

Epidemiological Data for the year 2010:

| District | Person Examined |  | Positive | P.f | No. of Death | ABER | API | P.f % | SPR | SFR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |
| Aizawl East | 23889 | 14810 | 245 | 235 | 5 | 22.02 | 1.39 | 95.92 | 0.63 | 0.61 |
| Aizawl West | 16620 | 8406 | 167 | 154 | 0 | 16.63 | 1.11 | 92.22 | 0.67 | 0.62 |
| Kolasib | 27631 | 18743 | 1381 | 1350 | 4 | 57.92 | 17.62 | 97.76 | 3.04 | 2.97 |
| Mamit | 22554 | 12720 | 2597 | 2544 | 6 | 54.49 | 40.11 | 97.96 | 7.36 | 7.21 |
| Serchhip | 12224 | 6160 | 101 | 69 | 3 | 30.42 | 1.67 | 68.32 | 0.55 | 0.38 |
| Lunglei | 18003 | 9472 | 709 | 636 | 11 | 19.14 | 4.94 | 89.70 | 2.58 | 2.31 |
| Lawngtlai | 49871 | 28576 | 5810 | 5371 | 1 | 63.36 | 46.93 | 92.44 | 7.41 | 6.85 |
| Saiha | 21268 | 15530 | 3676 | 3317 | 1 | 66.68 | 66.58 | 90.23 | 9.98 | 9.01 |
| Champhai | 15345 | 9111 | 809 | 742 | 0 | 19.43 | 6.43 | 91.72 | 3.31 | 3.03 |
| TOTAL | 207405 | 123528 | 15495 | 14418 | 31 | 33.74 | 15.85 | 93.05 | 4.70 | 4.37 |

Epidemiological Data for the year 2011:

| District | Person Examined |  | Positive | P.f | No. of Death | ABER | API | P.f % | SPR | SFR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BSE | RDT |  |  |  |  |  |  |  |  |
| Aizawl East | 16845 | 6862 | 47 | 45 | 3 | 10.04 | 0.21 | 95.74 | 0.20 | 0.20 |
| Aizawl West | 15120 | 6788 | 90 | 85 | 5 | 14.12 | 0.58 | 94.44 | 0.41 | 0.39 |
| Kolasib | 20069 | 6788 | 462 | 444 | 1 | 30.35 | 6.38 | 96.10 | 2.10 | 2.02 |
| Mamit | 17578 | 6657 | 1254 | 1224 | 2 | 30.31 | 19.37 | 97.61 | 6.39 | 6.24 |
| Serchhip | 7426 | 1600 | 61 | 52 | 3 | 14.83 | 1.01 | 85.25 | 0.68 | 0.58 |
| Lunglei | 31828 | 11995 | 3279 | 3074 | 2 | 24.14 | 22.84 | 93.75 | 9.46 | 8.87 |
| Lawngtlai | 17059 | 9793 | 2840 | 2728 | 11 | 15.27 | 22.92 | 96.06 | 15.02 | 14.42 |
| Saiha | 8791 | 4276 | 348 | 284 | 3 | 16.90 | 6.07 | 81.61 | 3.59 | 2.93 |
| Champhai | 9250 | 3796 | 68 | 50 | 0 | 10.16 | 0.54 | 73.53 | 0.53 | 0.39 |
| TOTAL | 143966 | 58555 | 8449 | 7986 | 30 | 16.61 | 8.19 | 94.52 | 4.93 | 4.66 |

Mizoram State falls into Category 3

  - Category 1: States with less than1 API including all the districts in the state with less than 1 API

  - Category 2: States with less than 1 API with few districts reporting more than 1 API

  - Category 3: States with more than 1 API with either all the districts with more than 1 API or few districts with less than 1 API and few with more than 1 API

Urban Malaria Scheme

| UMS Town | Population | Staff |  |  |  | Persons examined during 2011 | Total malaria cases | Pf Cases | Deaths |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Biologist | Field Worker | IC | Technician |  |  |  |  |
| Aizawl | 268590 | 1 | 19 | 19 | 4 | 45615 | 137 | 130 | 8 |
| Lunglei | 54880 | 1 | 4 | 4 | 1 | 43823 | 3279 | 3074 | 2 |
| NFCP Towns | Not Applicable | - | - | - | - | Persons examined during 2011 | Mf positive | Disease Positive |  |

The above figure of the format indicates the requirement as no UMS exist at present in Aizawl, Mizoram. There are 19 Wards under Aizawl Municipal Corporation, accordingly number of Field Workers  and Insect Collectors are projected for each Ward where as 4 numbers of Laboratory Technicians are projected to manned for Urban Health Centres existing in  the Aizawl, Mizoram.

UMS is also proposed for Lunglei as the urban population is more than 50,000. Malaria incidence is always high and there is always death due to Malaria in Lunglei District.

| Number | Total population | Larvicides required |  |  |  | For space spray |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | For polluted water (Qty.) | Cost | For non-polluted water (Qty.) | Cost | Pyrethrum Extt. 2% (Qty.) | Cost |
| UMS Town-2 | 323470 | 5000 litres | 7,50,000/- | 3000 litres | 4,50,000/- | - | - |
| of NFCP town | Not applicable | - | - | - | - | - | - |
| Total | 323470 | 5000 litres | Rs 7,50,000/- | 3000 litres | Rs 4,50,000/- | - | - |

As Aizawl and Lunglei city/town are on a hill top, there is practically no stagnation of water for which larvicidal requirement is out of question. However, some amount of Temephos and Bacillus Thuriengensis var Israeliensis [Bti(wp)] will be required to take care of the stagnant or stored water on the roof top, lakes, artificial ponds and ornamental ponds as well as Public Water Reservoirs. Total fund required for this purpose is Rs 12,00,000/- (Twelve Lakh rupees only).

Entomological surveillance

The entomological surveillance need to be strengthened in all the States/Uts during 12th plan period. Considering the importance of entomological activity, Govt. of India has proposed various initiatives to strengthen the entomological component, surveillance and monitoring.

| No. of Entomological Zones (1) | Cost |
| --- | --- |
| STAFF REQUIRED |  |
| 1)State Entomologist (1) | 35,000x12 = Rs 4,20,000 |
| 2) Insect Collector (2) | 5500x12x2 = Rs 1,32,000 |
| 3)Laboratory technician (1) | 8000x12 = Rs 96,000 |
| 4)Driver (1) | 5500x12 = Rs 66,000 |
| 5)Peon (1) | 5000x12 = Rs 60,000 |
| ACTIVITIES |  |
| - Mobility support | Rs 10,00,000 |
| - Equipments | Rs 5,00,000 |
| - Training | Rs 3,00,000 |
| Grand Total | Rs 25,74,000 |

Dengue and Chikungunya

Disease Situation: Data could not be shown in District/Corporate wise but only as a State. Dengue and Dengue Haemorrhagic Fever(DHF) programme will be implemented and fully functional from the Financial Year 2012-2013.

| Sl. No. | Name of district | Dengue |  |  |  | Chikungunya |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Suspected cases | Blood samples tested | Positive cases | Deaths | Suspected cases | Blood samples tested | Positive cases |  |
| 1 | Private Hospitals in Aizawl (During the year 2010) | 5 | 5 | 5 | NIL | NIL | NIL | NIL | All Dengue cases were detected in Private Hospitals as the Govt Hospitals have no test kit. |
| 2 | 2011 | Report not received from Private Hospitals | Not Known | Not Known | Not Known | NIL | NIL | NIL |  |
|  | Total | 5 | 5 | 5 | NIL | NIL | NIL | NIL | Dengue test kit proposed for the year 2012-13 is 20 kits(10 NS1 Antigen kit and 10 IgM capture ELISA) |

Dengue cases and deaths

The State has no Dengue test kit as yet although it is supposed to be received from NIV Pune during the year 2011-2012. The Dengue cases found in Mizoram were all detected from Private Hospitals during the year 2010 where Private Hospitals report were collected and these patients came from either Assam or Manipur especially Churachandpur.

During the year 2010-2011, 5 Dengue cases were detected at Private Hospitals and no death reports due to Dengue cases.

- Specific constraints, newer strategy and innovations proposed for implementation of the programme:

SPECIFIC CONSTRAINTS:

In the year 2010, 5 Dengue cases were detected and confirmed at the private hospital in Aizawl, Mizoram where serum were sent outside the State where facilities are available.

It is taken for granted that Mizoram is free from Dengue and Chikungunya as there are no provisions for detection of Dengue and Chikungunya in the State.

It is also believed that there is no indigenous case of Dengue in the state. However due to improvement of the transport system as well as modern lifestyles, intermixing of population in the country, a high chance is there that Dengue diseases can happen anytime (or already happened unknowingly) in the State as the State is bordering to Assam, Manipur (especially from Churachandpur), Bangladesh, Myanmar etc where this cases are continuously found.

STRATEGY AND INNOVATIONS PROPOSED FOR 2012 – 2013

- Procurement of Dengue test kits: 10 test kits for ELISA based NS1 Antigen test kits and 10 test kits for ELISA based IgM test kits.

- Identification of 5 more Sentinel Surveillance Hospitals for Dengue and Chikungunya:

  - Kolasib District Hospital

  - Lunglei District Hospital.

  - Lawngtlai District Hospital.

  - Mamit District Hospital

  - Lengpui Community Health Centre where frequent flyers suspected of Dengue cases or fever cases coming from Dengue endemic areas or outside the state will be tested on the Airport campus Clinic or Lengpui Community Health Centre.

- Up-gradation of already identified Dengue Sentinel Surveillance Hospital at Aizawl - Civil Hospital to make it fully functional.

- Honorarium for six voluntary workers of dengue in identified Dengue Sentinel Surveillance Hospital, Aizawl and 5 new proposed Dengue Sentinel Surveillance Hospitals.

- Six (6) numbers of ELISA readers or washers for one identified and five more proposed Dengue Sentinel Surveillance Hospitals.

- As Dengue and Dengue Haemorrhagic Fever programmes are yet to be started from the year 2012-2013, it is proposed to take up training and case management for this purpose as pilot project only. It is therefore proposed to take up case detection and management training for the Medical Specialist including Microbiologist and Pathologist, Medical Officers, Laboratory Technicians and District Vector Borne Project Officers (DVBPO) of Six Sentinel Surveillance Hospitals only.

However, as there are no experts in the State to undertake training on case detection and management, Experts/Specialists may please be deputed from NVBDCP Delhi. Minimum budget for the same is reflected in the respective financial budget part.

- Leaflet, Booklet and poster as well as infotainment (information given through entertainment), street plays etc for IEC, BCC for Social mobilization and awareness of the people.

- Partnership and involvement of NGOs, FBOs and CBOs – Intersectoral convergence for elimination of vector breeding for transmission risk reduction and prevention of occurrence of outbreak.

- Strategy and innovations proposed for implementation of Mid Term Plan strategies in urban and rural areas:

It is learnt from GOI (NVBDCP, Delhi) that Aizawl Civil Hospital is identified as Dengue Sentinel Surveillance Hospital but the state is not yet aware of it till date. Also no facility of any kind is provided to this mentioned Hospital by the state or GOI (NVBDCP, Delhi).

Therefore all the materials and funds will be required for this hospital which is the same as the new Sentinel Surveillance Hospitals proposed.

| Name of district | Name of the SSH identified | Name of SSH functional | Kits received from NIV, Pune/utilized |  | NS1 kits procured | Samples received/ tested |  |  | Found positive |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Dengue | Chik. |  | Dengue |  | Chik. | Dengue |  | Chik. |
| Aizawl W | Civil Hospital-Aizawl | NIL(Will be functional from 2012-13) | -/- | -/- |  | Igm | NS1 | -/- | Igm | NS1 |  |
| Aizawl E | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Kolasib | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Mamit | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Serchhip | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Champhai | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Lunglei | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Lawngtlai | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Saiha | - | - | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |
| Total | 1 | 1 | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |

Data could not be shown in District/Corporate wise but only as a State.

- Number of new SSHs proposed in 2012-13:

As Dengue and Chikungunya is a new disease unfamiliar to the state, the state proposed the following Heath Institutions as Sentinel Surveillance Hospitals for Dengue:

| Sl. No | District | Dengue Sentinel Surveillance Hospital Proposed |
| --- | --- | --- |
| 1 | Kolasib | Kolasib District Hospital |
| 2 | Lunglei | Lunglei District Hospital |
| 3 | Lawngtlai | Lawngtlai District Hospital |
| 4 | Mamit | Mamit District Hospital |
| 5 | Aizawl West | Lengpui CHC |

From the financial year 2012-2013, Civil Hospital, Aizawl will be made fully functional as Dengue Sentinel Surveillance Hospital. The Malaria Sentinel Doctors (Physician and Pediatrician) and Lab. Technicians in collaboration with microbiology Department will take up Dengue Sentinel Surveillance Hospital, Aizawl.

- Details of kit requirements for 2012-13:

| Districts | SSH Proposed | IgM Dengue | NS1 Dengue | ELISA Reder & Washser | Honorarium for Volunteer (1x100x20x5) |
| --- | --- | --- | --- | --- | --- |
| Kolasib | Kolasib District Hospital | 1 kit (96 test) | 1 kit (96 test) | 1 | Rs. 10,000/- |
| Lunglei | Lunglei District Hospital | 2 kits (192 tests) | 2 kits (192 tests) | 1 | Rs. 10,000/- |
| Lawngtlai | Lawngtlai District Hospital | 2 kits (192 tests) | 2 kits (192 tests) | 1 | Rs. 10,000/- |
| Mamit | Mamit District Hospital | 1 kit (96 test) | 1 kit (96 test) | 1 | Rs. 10,000/- |
| Aizawl West | Lengpui CHC | 1 kit (96 test) | 1 kit (96 test) | 1 | Rs. 10,000/- |
| Sub- Total | 5 | 7 kits (672 tests) | 7 kits (672 tests) | 5 | Rs. 50,000/- |
| Civil Hospital, Aizawl | Civil Hospital, Aizawl is already identified as SSH for Dengue | 3 kits (288 tests) | 3 kits (288 tests) | 1 | Rs. 10,000/- |
| Grand Total | 6 | 10 kits (960 tests) | 10 kits (960 tests) | 6 | Rs. 60,000 |

- Vector control teams selected and population targeted in each district should be annexed as per format below.

| Name of Towns | Population | Dengue cases reported in 2011 | Deaths due to Dengue | Chikungunya cases | No. of volunteers required for breeding source reduction & social mobilization | Funds required |
| --- | --- | --- | --- | --- | --- | --- |
| Aizawl | 382821 | Unknown | Unknown | - | 1 | Reflected in the respective Financial Budget part. |
| Lunglei | 143583 | Unknown | Unknown | - | 1 |  |
| Kolasib | 72393 | Unknown | Unknown | - | 1 |  |
| Lawngtlai | 123883 | Unknown | Unknown | - | 1 |  |
| Mamit | 64739 | Unknown | Unknown | - | 1 |  |
| Lengpui CHC | 154166 | Unknown | Unknown | - | 1 |  |
| TOTAL | 941585 | Unknown | Unknown | - | 6 |  |

Note:

- The towns should be categorized into 3:  Population more than 40 lakhs, 10-40 lakhs and 1-10 lakhs.

- Honorarium should be calculated @ Rs.100 per day per volunteer X 20 days X 5 months or transmission period whichever is less.

- Requirement for commodity as per technical norms and considering balance of stores, consumption capacity and justification

Insecticides and larvicides are decentralized items and dealt under Urban Malaria Scheme (UMS). Insecticides and larvicides requirement for Dengue and Chikungunya are included along with UMS.

Monthwise, institute wise requirement of test kits are worked out for both Dengue and Chikungunya and included in the PIP 2012-2013. For Dengue both ELISA based NS1 antigen detection kit (introduced in 2010) and IgM capture ELISA are worked out based on the epidemiological situation (both the kits 1 = 96 tests).

- Financial Requirement for Dengue and Chikungunya: The assistance required are indicated in the Annexure enclosed (Respective Financial budget part).

Acute Encephalitis Syndrome including Japanese Encephalitis

As the State is having high incidence/prevalence of Malaria, no other mosquito borne diseases are practically not taken up till date. However as already mentioned earlier that due to improvement of transport, modern lifestyle, intermixing of population, the State has a long international boundaries to Myanmar and Bangladesh including neighboring state like Assam, Tripura and Manipur where these cases are found frequently. It is therefore planned to initiate the surveillance and control programme of these diseases.

Hence, financial requirement for these diseases are proposed in their respective Financial budget part.

- Disease Situation:  The number of cases and deaths for the year 2010-2011 may be given in the following table:

| Sl.No | Name of the District | BlockwiseNo. of AES/JE cases | No. of Deaths | No. of Sera/CSF Sample tested | No. Confirmed for JE | No. of vaccinated children confirmed with JE infection |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Aizawl W | Not known | Not known | NIL | NIL | NIL |
| 2. | Aizawl E | Not known | Not known | NIL | NIL | NIL |
| 3. | Kolasib | Not known | Not known | NIL | NIL | NIL |
| 4. | Mamit | Not known | Not known | NIL | NIL | NIL |
| 5. | Serchhip | Not known | Not known | NIL | NIL | NIL |
| 6. | Champhai | Not known | Not known | NIL | NIL | NIL |
| 7. | Lunglei | Not known | Not known | NIL | NIL | NIL |
| 8. | Lawngtlai | Not known | Not known | NIL | NIL | NIL |
| 9. | Saihs | Not known | Not known | NIL | NIL | NIL |
| TOTAL |  | - | - | - | - | - |

- Specific constraints, newer strategy and innovations proposed for implementation of the programme:

Specific Constrains:

Until now there is no specific constrain to mention as the Programme is not yet implemented. From the Current Financial Year i.e. 2012-2013, it is intended to initiate the programme of Japanese Encephalitis.

STRATEGY AND INNOVATIONS PROPOSED FOR J.E 2012 - 2013:

So far in the medical history of Mizoram, it is reported that two persons: Mr. C Liansanga and Capt. Rinliana had been suffering and succumbed due to Japanese Encephalitis where their serum were sent outside the state where facilities are available and diagnosed and confirmed as a case of Japanese Encephalitis.

It is known that pigs are the amplifiers of the virus and the most numerous and most common live-stock animals in Mizoram, not to emphasize every family has at least one pig. As mentioned in earlier para., if Japanese Encephalitis entered and happened in Mizoram it will be a great burden and might affect a lot of people as the State is dynamic potential for Japanese Encephalitis virus multiplication not to mention the numerous culex mosquitoes.

The following are proposed for the implementation and initiation of the programme for the financial year 2012-2013.

- Japanese Encephalitis test kit: Civil Hospital, Aizawl and Lengpui Community Health Centre where Airport is there will be selected as testing centre for J.E. 1(one) test kit (96 test) only will be proposed for the two health Institutions.

- Training especially on the preventive side will be given to Medical Specialist, Medical Officers and District Vector Borne Project officers(DVBPO).

- Training on diagnostic procedures and case management of Japanese Encephalitis to Chief Medical Officers, Medical Specialists, Medical Officers and Districts Vector Borne Project Officers(DVBPO).

- Leaflet, booklet, pamphlet and street plays as well as essay writing competition for IEC and BCC for Social Mobilization and Awareness to the people.

- For emergency preparedness and early response of incoming J.E in the bordering areas (for example Bangladesh, Manipur, Assam, Tripura Border) 6 fogging machines are indispensable and need of the hour.

- As an initial phase for implementation of the programme for J.E, small quantity of Technical Malathion (200 ltrs. only) will be needed now.

In case an emergency condition arises it will be met from other sources.

- Monitoring of functioning of Sentinel surveillance Hospital separately for Japanese Encephalitis.

Sentinel Surveillance Hospital separately for Japanese Encephalitis (J.E) is not yet identified in the state and no functioning of such Sentinel Surveillance Hospital in the State of Mizoram.

| Sl.No | Name of the District | Total No. of Sentinel Sites identified | No. of functional | Reasons for non functional status | Suggested solutions |
| --- | --- | --- | --- | --- | --- |
| The question does not arise as there is no Sentinel Surveillance Hospital for J.E in the state at present. The programme will be implemented from the current financial year (2012-2013). |  |  |  |  |  |

- Financial Requirement for JE: The assistance required is indicated in the format as per Annexure enclosed in the respective Financial budget part.

Lymphatic Filariasis

- Goal: Lymphatic Filariasis is not a major problem in the state and almost unknown to the people in majority. However elephant legs/giant legs (Elephantiasis) and hydrocele are sometimes found in the areas of Districts like Lawngtlai, Lunglei, Mamit and Kolasib Districts where they are on the bordering area of Bangladesh, Tripura and Assam respectively.

Proposal for the financial year 2012 – 2013:

- Case Surveillance: Voluntary workers as well as Multi Purpose Workers (Male/Female) will be assigned to do Active and Passive Surveillance of Hydrocele and elephantiasis of legs in the said above districs.

- Training for Detection and Case Management of Lymphatic filariasis (Medical Management and surgical Management):

  - For Medical Specialist (Physicians, Preventive Medicines Specialist and Surgeon), Medical Officers, Districts Medical Head, Paramedical Staff and Lab. TEchnicians.

  - For Districts vector Borne Project Officers, Multipurpose Workers (Male and Female) drugs distributors and Voluntary Surveillance Workers.

- IEC/BCC Activitiess: Pamphlets, Leaflets, Advocacy meetings and awareness campaign in the bordering areas where a lot of immigrants are settled and living.

The incidence/prevalence of Lymphatic Filariasis could not be shown in District Wise (Endemic District Wise) as the Disease was not taken up seriously in the State and no record was kept in the State. However it is learnt that on immigrants from other countries like Myanmar, Bangladesh etc some cases were found and operations were done at the Civil Hospitals.

Cases were also found from manual labourers who came from Assam, Uttar Pradesh, Bihar, Madhya Pradesh etc and Army Personnel who are posted in the State. It is therefore proposed to initiate The Surveillance and Control Programme in the current Financial Year 2012-2013.

| SI. No. | Name of Districts | Population at risk | Coverage of eligible population under MDA | Microfilaria rate | No. of line listed total lymphoedema cases | No. of line listed total hydrocele cases | No. of hydrocele operations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl E | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 2 | Aizawl W | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 3 | Kolasib | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 4 | Mamit | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 5 | Serchhip | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 6 | Champhai | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 7 | Lunglei | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 8 | Lawngtlai | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |
| 9 | Saiha | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown |

- The analysis should be done for the districts:

As the Programme is not taken up before, it could not be worked out how many populations are at risk as Lymphatic Filariasis cases are not recorded. Most of the cases are labourers from other States and immigrants from other Countries like Bangladesh, Myanmar etc.

- The requirement of drugs DEC and Albendazole along with cost for the Districts  could not be shown at present situation as the Programme is yet to be implemented for the year 2012-2013, Requirement of drugs is shown in the State Wise as pilot project:

| Name of District | Population at risk | DEC 100 mg. |  | Albendazole 400 mg |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Quantity (in lakh) | Cost (Rs. in lakh) | Quantity (in lakh) | Cost (Rs. in Lakh) |
| Mizoram | Unknown at Present. Active and Passive Surveillance will be taken up during 2012-2013 | 0.05 | 2.0 | 0.05 | 1.25 |
| TOTAL |  | 0.05 | 2.0 | 0.05 | 1.25 |

- Financial requirement for Elimination of Lymphatic Filariasis (ELF): The assistance required are indicated in the Annexure enclosed (respective financial budget part).

KALA –AZAR (Endemic only in Bihar, West Bengal, Jharkhand and parts of U.P.)

Goal: Kala-azar is targeted for elimination by 2015.  The elimination is to bring down the number of kala-azar cases less than 1 per 10,000 population at block level.

- Disease Situation:  Kala-Azar is neither known nor endemic in the State. However from the medical history of Mizoram it was found that from the immigrants and Army personnel Kala-azar cases were found and treated accordingly.

| Monitoring of Diagnosis and Treatment Compliance of Kala Azar Patients |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| % age of people treated after diagnosis % age of people completed treated |  |  |  |  |  |
| Districts | Cases | Deaths | Cases treated | Cases fully treated (Treatment compliance) | % Treatment compliance |
| Aizawl E | Unknown | Unknown | NIL | NIL | - |
| Aizawl W | Unknown | Unknown | NIL | NIL | - |
| Kolasib | Unknown | Unknown | NIL | NIL | - |
| Mamit | Unknown | Unknown | NIL | NIL | - |
| Serchhip | Unknown | Unknown | NIL | NIL | - |
| Champhai | Unknown | Unknown | NIL | NIL | - |
| Lunglei | Unknown | Unknown | NIL | NIL | - |
| Lawngtlai | Unknown | Unknown | NIL | NIL | - |
| Saiha | Unknown | Unknown | NIL | NIL | - |
| TOTAL | - | - | - | - | - |

- Strategy & innovations proposed for Kala Azar 2012-2013:

  - As mentioned earlier Kala Azar is a new Programme to be initiated during 2012-2013, it is proposed to have training for Districts Officers, PHC Medical Officers and all Paramedical Staffs.

  - Pamphlets, Leaflets, Infotainments, advocacy meeting and awareness campaign in the peripheral parts and bordering areas of the State as well as among the immigrant labourers and Army Personnel.

  - Active and Passive case Surveillance will be done by the Mutipurpose Health Workers (Male/Female), Medical and Paramedical staff etc.

  - All Kala Azar cases found and treated will be strictly and correctly reported and recorded from now on.

- Financial assistance required from Centre: The Fund demand is reflected in the respective Financial budget part.

Financial Proposal of tentative plan for prevention & control of Vector Borne Diseases (2012-13)

| S. No. | Component (Sub- Component) | Financial Requirement (Rs. in Lakhs) | Remarks | Functional head as per NRHM |
| --- | --- | --- | --- | --- |
| 1 | Domestic Budget Support (DBS) |  |  |  |
| 1.1 | Malaria |  |  |  |
|  | ASHA Incentive | 15.0 | There are1787 ASHAs in the State | Honorarium & Incentives |
|  | MPW (contractual under NVBDCP will not be supported in XII Plan) | NIL | Reflected in NRHM (additional Fund) | Not applicable |
|  | Lab Technicians ( against vacancy) | NIL |  | Human Resource |
|  | VBD Technical Supervisor (one for each block) | NIL |  | Human Resource |
|  | District VBD Consultant (one per district) (Non- Project States) | NIL |  | Human Resource |
|  | State Consultant (Non – Project States) - M& E Consultant (Medical Graduate with PH qualification) - VBD Consultant (preferably entomologist) | NIL |  | Human Resource |
|  | Operational Cost |  |  |  |
|  | Spray Wages | 135.0 |  | Operating Cost |
|  | Operational cost for IRS | 192.0 |  | Operating Cost |
|  | Impregnation of Bed nets- for NE states SP – flow ( K- Othrine) | 75.0 |  | Operating Cost |
|  | Monitoring , Evaluation & Supervision & Epidemic Preparedness including mobility | 30.0 |  | Operating Cost |
|  | IEC/BCC | 79.75 |  | IEC & BCC |
|  | PPP / NGO and Intersectoral Convergence | 163.3 |  | PPP/NGO |
|  | Training / Capacity Building | 83.20 |  | Training |
|  | Zonal Entomological units | 25.74 |  |  |
|  | Biological and Environmental Management through VHSC | 16.54 |  | Operating Cost |
|  | Larvivorous Fish support | 12.0 |  | Operating Cost |
|  | Total Malaria (DBS) | 827.53 |  |  |

| 1.2 | Dengue & Chikungunya |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Strengthening surveillance (As per GOI approval) |  |  |  |  | Financial aid/grant to institutions |
|  |  Apex Referral Labs recurrent @ Rs.3.00 lakh per lab. | 3.0 Lakh |  |  | Civil Hospital,Aizawl |  |
|  |  Sentinel surveillance Hospital recurrent @ Rs. 1.00 lakhs per lab. | 6.0 Lakh |  |  |  |  |
|  | ELISA facility to Sentinel Surv Labs @ Rs.0.50 lakh | 3.0 Lakh |  |  |  | Operating Cost |
|  | Test kits (Nos.) to be supplied by GoI (kindly indicate numbers of ELISA based NS1 kit and Mac ELISA Kits required separately) | NS1 antigen test kit=10 kits ELISA Igm = 10 kits |  |  | Reflected in Decentralized commodities part. | Not applicable |
|  | Case management | 5.0 |  |  | For I.V fluids, transfusion,analgesics etc | Operating cost |
|  | Vector Control & environmental management | 30.6 |  |  | Based on 5 lakh per SSH | Operating cost |
|  | Epidemic containment | NIL |  |  |  | Operating cost |
|  | Training | 4.0 |  |  |  | Training |
|  | Operational Research | NIL |  |  |  | Operating cost |
|  | Monitoring and evaluation | 2.0 |  |  |  | Operating cost |
|  | IEC BCC for Social Mobilization | 24.60 |  |  | Highly malaria endemic districts only will be covered.600 no’s of VCPs and Secretaries plus 300 no’s of teachers. | IEC |
|  | Inter-sectoral convergence | 14.0 |  |  |  | IEC |
|  | Total Dengue/Chikungunya | 100.4 |  |  |  |  |
| 1.3 | Acute Encephalitis Syndrome (AES)/ Japanese Encephalitis (JE) |  |  |  |  |  |
|  | Diagnostics and Case Management | 5.0 |  |  |  | Procurement |
|  | IEC/BCC specific to J.E. in endemic areas | 5.0 |  |  |  | IEC |
|  | Capacity Building/Training | 3.0 |  |  |  | Training |
|  | Vector Control | NIL |  |  |  |  |
|  | Fogging Machine | NIL |  |  |  | Procurement |
|  | Technical Malathion | NIL |  |  |  | Procurement |
|  | Operational costs for malathion fogging | NIL |  |  |  | Operating cost |
|  | Operational Research | NIL |  |  |  | Operating cost |
|  | Monitoring and supervision | NIL |  |  |  | Operating cost |
|  | Rehabilitation Setup for selected endemic districts | NIL |  |  |  | Financial aid/grant to Institutions |
|  | ICU Establishment in endemic districts | NIL |  |  |  | Financial aid/grant to Institutions |
|  | ASHA Insentivization for sensitizing community | NIL |  |  |  | Honorarium/Incentive |
|  | Other Charges for Training /Workshop Meeting & payment to NIV towards JE kits at Head Quarter | 6.0 |  |  |  | Training |
|  | Total AES/JE | 19.0 |  |  |  |  |
| 1.4 | Lymphatic Filariasis |  |  |  |  |  |
|  | Meeting National, State and District level | 5.0 Lakh |  |  |  | Operating cost |
|  | BCC/Advocacy/IEC at centre, state, district/PHC, sub centre | 5.0 Lakh |  |  |  | Operating cost |
|  | Training District Officers, PHC MOs, Paramedical staff, drug distributors | 3.0 Lakh |  |  |  | Training |
|  | Lymphoedema Management | 0.075 Lakh |  |  |  | Operating cost |
|  | Hydrocelectomy | 0.63 Lakh |  |  |  | Operating cost |
|  | Monitoring by Microfilaria Survey | NIL |  |  |  | Operating cost |
|  | Honorarium for Drug Distribution |  |  |  |  |  |
|  | a) Honorarium to volunteers | NIL |  |  |  | Honorarium |
|  | b)Honorarium to supervisory staff | NIL |  |  |  | Honorarium |
|  | Contingency expenses for social mobilization & advocacy | NIL |  |  |  | Operating cost |
|  | Mobility Support (POL) | NIL |  |  |  | Operating cost |
|  | Monitoring & Evaluation (Assessment) | NIL |  |  |  | Operating cost |
|  | Verification and validation for stoppage of MDA in LF endemic districts | NIL |  |  |  | Operating cost |
|  | a) Additional MF Survey | NIL |  |  |  | Operating cost |
|  | b) ICT Survey | NIL |  |  |  | Operating cost |
|  | c) ICT Cost | NIL |  |  |  | Procurement |
|  | Verification of LF endemicity in non-endemic districts | NIL |  |  |  |  |
|  | a) LY & Hy Survey in 350 distt | NIL |  |  |  | Operating cost |
|  | b) Mf Survey in Non- endemic distt | NIL |  |  |  | Operating cost |
|  | c) ICT survey in 200 distt | NIL |  |  |  | Operating cost |
|  | Post-MDA surveillance | NIL |  |  |  | Operating cost |
|  | Total Lymphatic Filariasis | 13.70 |  |  |  |  |
| 1.5 | Kala-azar |  |  |  |  |  |
|  | Case search/ Camp Approach | NIL |  |  |  | Operating cost |
|  | Spray Pumps & accessories | NIL |  |  |  | Procurement |
|  | Operational cost for spray including spray wages | NIL |  |  |  | Operating cost |
|  | Mobility/POL/supervision | NIL |  |  |  | Operating cost |
|  | Training District Officers, PHC MOs, Paramedical staff etc | 2.0 |  |  |  | Training |
|  | IEC/ BCC/ Advocacy | 5.0 |  |  |  | IEC |
|  | Monitoring & Evaluation | NIL |  |  |  | Operating cost |
|  | Kala-azar | 7.0 |  |  |  |  |
|  | Total (DBS) | 967.63 |  |  |  |  |
| 2 | Externally aided component |  |  |  |  |  |
| 2.1 | World Bank support for Malaria (Identified state) | NIL |  |  | Not Applicable |  |
|  | Human Resource | NIL |  |  |  | Human Resource |
|  | Training /Capacity building | NIL |  |  |  | Training |
|  | Mobility support for Monitoring Supervision & Evaluation & review meetings, Reporting format (for printing formats) | NIL |  |  |  | Operating Cost |
| 2.2 | GFATM support for Malaria (NE states) |  |  |  |  |  |
|  | Project Management Unit including human resource of N.E. states | 118.16 |  |  |  | Human Resource |
|  | Training/Capacity Building | NIL |  |  | Reflected under DBS part. | Training |
|  | Planning and Administration( Office expenses recurring expenses, Office automation , printing and stationary for running of project) | 50.0 |  |  |  | Operating Cost |
|  | Monitoring Supervision & review meetings,( supervisory visits including travel expenses, etc) | 50.0 |  |  |  | Operating Cost |
|  | Infrastructure and Other Equipment (Computer Laptops, printers, Motor cycles for MTS ) | 12.60 |  |  |  | Infrastructure |
|  | IEC / BCC activities as per the project | 65.03 |  |  |  | IEC/BCC |
|  | Procurement and Supply Chain Management | 80.0 |  |  | For Renting of Storage Space, Dropping of Logistics,LLIN etc |  |
|  | Hospital base treatment and Severe and Complicated Malaria cases(Sentinel Surveillance Hospitals) | 20.0 |  |  | Civil Hospital Aizawl and Civil Hospital Lunglei are funtioning as SSH. |  |
| 2.3 | Kala-azar World Bank assisted Project | NIL |  |  | Not Applicable |  |
|  | Human resource | NIL |  |  |  | Human Resource |
|  | Capacity building | NIL |  |  |  | Training |
|  | Mobility | NIL |  |  |  | Operating cost |
|  | Total : EAC component | 395.79 |  |  |  |  |
|  | Grand total for cash assistance under NVBDCP (DBS + EAC) | 1363.42 |  |  |  |  |
| 3 | Cash grant for decentralized commodities |  |  |  |  |  |
| 3.1 | Drugs | Qty | Amt |  |  |  |
|  | Chloroquine phosphate tablets | 10.0 | 9.0 |  |  | Procurement |
|  | Primaquine tablets 2.5 mg | 9.0 | 7.20 |  |  | Procurement |
|  | Primaquine tablets 7.5 mg | 7.0 | 7.0 |  |  | Procurement |
|  | Quinine sulphate tablets | 3.5 | 12.25 |  |  | Procurement |
|  | Quinine Injections | 0.30 | 4.50 |  |  | Procurement |
|  | Sulphadoxine + Pyremethamine tablets | 0.17 | 6.80 |  |  | Procurement |
|  | ACT ( For Non Project states) | NIL | NIL |  |  | Procurement |
|  | DEC 100 mg tablets | 0.05 | 2.0 |  |  | Procurement |
|  | Albendazole 400 mg tablets | 0.05 | 1.25 |  |  | Procurement |
| 3.2 | Diagnostics |  |  |  |  |  |
|  | RDT Malaria – bi-valent (For Non Project states) | NIL | NIL |  |  | Procurement |
|  | Dengue NS1 antigen kit | 10 kits |  | 20.0 Lakh |  | Procurement |
| 3.3 | Larvicides |  |  |  |  |  |
|  | Temephos, Bti (AS) / Bti (wp) (for polluted & non polluted water) | 8000 Litres |  | 12.0 |  | Procurement |
|  | Pyrethrum extract 2% for space spray | - |  | - |  | Procurement |
|  | Total grant for decentralized commodities | 82.00 |  |  |  |  |
|  | Grand Total for grant-in-aid under NVBDCP | 1445.42 |  |  |  |  |

|  | Commodities to be supplied by NVBDCP | Source | Quantity |  |
| --- | --- | --- | --- | --- |
|  | Insecticides |  |  |  |
|  | DDT 50% wdp | Supplied by GOI | 100 MT |  |
|  | Synthetic Pyrethroid - for UT without legislation | Supplied by GOI | NIL |  |
|  | Malathion 25% wdp / Technical | By states | 200 Ltrs |  |
|  | Amphotericin-B | Supplied by GoI | NIL |  |
|  | Miltefosine | Supplied by GoI | NIL |  |
|  | RDK for Kala-azar | Supplied by GoI | NIL |  |
|  | Procurement LLIN | Supplied by GOI | 161836 |  |
|  | Microscopes | Supplied to be/Supplied by GOI | 120 nos |  |
|  | Vehicles for states and districts | Supplied to be/Supplied by GOI | 10 (Four Wheeler) |  |
|  | Commodity grant total | N.A | N.A |  |

Cash assistance required under NRHM Flexi fund

| S. No. | Component (Sub- Component) | Financial Requirement (Rs. in Lakhs) | Remarks | Functional head as per NRHM |
| --- | --- | --- | --- | --- |
| 1. | Salary for MPW | 76.50 |  | NRHM Programme |
| 2. | RDK (Including CMAI staffs 885 Volunteers) | 70.00 | 25% of State total requirement. | NRHM flexi fund |
| 3. | ACT(Including CMAI staffs 885 Volunteers) | 17.00 | 25% of State total requirement. | NRHM flexi fund |
| TOTAL |  | 163.50 |  |  |

Any other activity required as innovation and needs support may be indicated separately so that it can be considered either from programme or NRHM flexi fund

|  | Statement showing the Budget District -wise/Scheme-wise break-up 2011-12 in respect of NVBDCP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (Figures in Lakhs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl.No | Name of District | Malaria |  |  |  |  |  | Dengue & Chikungunya | AES / JE | ELF | KALA-AZAR | Decentralized Commodities | TOTAL Domestic Support ( 3-12) | World Bank |  |  | GFATM |  |  |  | TOTAL World bank + GFATM (14-20) | Total Budget from NVBDCP (13+21) | Allocation from NRHM Flexi Fund | GRAND TOTAL (22+23) | State Fund |
|  |  | Contractual MPWs | Incentives to ASHAs for identified districts | IEC | Training | M&E including Epidemic Preparedness and M & E | Mobility |  |  |  |  |  |  | Human Resource | Training | Mobility Support | Human Resource | IEC / BCC | M & E | Others |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |
| Total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Note 1 : The total should be projected in detail in PIP. This is to facilitate district wise allocation from NRHM while release the funds |
| --- | --- |
|  | Note 2 : These are not the financial head but only for activities |
|  | Note 3 : Any activity(s) which is required for the programme may be added in a separate column |

D.4 National Leprosy Eradication Programme (NLEP)

NATIONAL LEPROSY ERADICATION PROGRAMME

Guidelines for preparing of State/District Action Plan for 2012 - 2013

The year 2012-13 is to be the first year of the 12th Five Year Plan. The 12th Plan proposal is now under consideration of the Govt. and once the same is finalized, actual allocation under each category will be known. However the State/District will have to prepare the Action Plan based on proposed rates indicated in these guidelines. The emphasis here is on the planning of the Physical targets to be achieved during the year.

As in the past years, while preparing the State action plan following points may please be kept:

- The District action plans will be first drawn up.

- The State will compile the District plans and prepare the State plan for submission to the
GOI for sanction.

- While preparing the District/State plans the NRHM authorities at District/State will be duly
consulted and get approval for.

- The State action plan will also include activities to be supported by ILEP indicating clearly
the items, Quantity, time frame and budget.

The action plan should cover all important activities for achievements of the results proposed, indicating unit cost, physical targets and proposed budget required for each activity. The action plan should be realistic, comprehensive and specific, so that it is clear and performance can be measures a appropriate intervals. As mentioned earlier financial norms indicated in these guidelines be followed now, which can be subsequently modified, alongwith the NRHM financial guidelines issued from time to time.

I.	Situation analysis

Identify the strength, weakness, opportunities and threats, indicate new initiatives suggested to improve physical & financial performance of the State/UT (if any).

II.	Performance under NLEP

| S.No. | Indicators | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | No. of new cases detected (ANCDR/100,000) | 20 | 26 | 23 | 10 | 21 |
| 2 | No. of cases on record at year end (PR/10,000) | 0 | 0.009 | 0.009 | 0.02 | 0.01 |
| 3 | No. of Grade II disability among new cases (%) | 0 | 0 | 0 | 0 | 0 |
| 4 | Treatment Completion Rate | MB -100 PB -100 | MB -100 PB -100 | MB -100 PB -100 | MB -100 PB -100 | MB -100 PB -100 |
| 5 | Reconstructive Surgery conducted | 0 | 0 | 0 | 0 | 0 |
| Total |  |  |  | - |  |  |

(Cumulative number to be mentioned and Rate/Percentage to be given in brackets).

III. NLEP annual plan for the year 2012-13

The main thrust areas under NLEP for the Xllth Plan are:

- Achieving elimination of leprosy in all the districts of the country

- Reduction in Gr. II disability through prevention of disability (POD) and Reconstructive
Surgery.

To make NLEP planning compliant with NRHM guidelines, the 12th plan proposal has been made a result based plan. Following 8 results are proposed to be achieved at the end of the 12th Plan period i.e. by March 2017.

i.	Improved early case detection

ii.	Improved case management

iii.	Stigma reduced

iv.	Development of leprosy expertise sustained

v.	Research supported evidence based programme practices

vi.	Monitoring supervision and evaluation system improved

vii.	Increased participation of persons affected by leprosy in society

viii.	Programme management ensured

The State/UT may outline their annual plan for achievements of above results under the following functional heads:

1.   Improved early case detection

Under this result based initiative following two activities need to be planned district wise -1.1. Performance based incentive to ASHA and sensitisation to new ASHA.

| S.NO | No. of ASHA activity | Number | Unit person | Cost (Rs.) | per | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 10 | 10 | 100 |  |  |  |
| 2 | Incentive to ASHA | MB PB | 500 300 |  |  | X10 5,000 X10 3,000 |
| Total |  | - | - |  |  | 8,000 |

1.2. Special activities in high endemic districts where ANCDR is more than  10 per  100,000 population

| Special activities in high endemic district |  | No. of Block |  | Unit cost per Block (Rs.) |  | Amount for districts (Rupees) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Special activities* |  | Nil |  | Nil |  | Nil |  |
| In High endemic districts |  |  |  |  |  |  |  |
| Active search |  |  |  |  |  |  |  |
| Capacity building of staff |  |  |  |  |  |  |  |
| Awareness drive |  |  |  |  |  |  |
| Enhanced - monitoring and supervision - 1 person per block |  |  |  |  |  |  |
| Validation of MB and child cases |  |  |  |  |  |  |

2.   Improved case management

Activities to be planned are-2.1.DPMR services - To be calculated for each district

| S.No | Item | No. required | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 2 3 4 | MCR footwear Aids & appliance Welfare allowances for RCS patient RCS reimbursement to Institutions | Persons with insensitive feet X 2 pairs | 300 24000 5000 5000 | - - - - |
| Total |  |  |  |  |

2.2. Urban Leprosy Control

To be calculated for State/UT based on identified urban areas located.

| S.No | Category of urban area | Number | Unit cost (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 2 3 4 | Township Medium city -I Medium city - II Mega city | 1 1 | 114000 240000 472000 560000 | 1,14,000 2,40,000 - - |
| Total |  |  |  | 3,54,000 |

2.3.MPT Supply

To be supplied to the States/UTs by the centre, not to be budgeted by State/UT. 2.4. Materials and supplies

To be calculated for State/UT according to the number of districts

| S.No | Item |  |  | No. districts | of | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Supportive Drugs | & dressings |  | 4 |  | 50,000 | 20,000 |
| 2 | Laboratory equipments | reagents | and | 4 |  | 10,000 | 40,000 |
| 3 | Printing works |  |  | 9 |  | 20,000 | 1,80,000 |
|  | TOTAL |  |  |  |  | 80,000 | 4,20,000 |

2.5 NGO Services

To be calculated at State level on the basis of NGO involved through SET Schemes.

| No. of NGO under SET Scheme | Unit cost per NGO (Rupees) | Amount (Rupees) |
| --- | --- | --- |
| 2 (YMA/MHIP) | 800,000 | 16,00,000 |

3.   Stigma reduced

Objective of the communication plan will be -

- To develop effective communication vis-a-vis the target audiences and take on the task of
effectively delivering the same.

- To complement and support the detection and treatment services being provided through
the General Health Care System, making it more acceptable to the community.

- To strive to remove stigma surrounding leprosy and prevent discrimination against
leprosy affected persons.

•	To specifically cover clients, Health providers, influencers and the masses.
State/UT IEC plan will be drawn up in the Annual Plan under the following heads:

| S.No | Medium | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Mass Media (TV, Radio Press) |  | 28,000 |  |
| 2 | Outdoor Media |  | 28,000 |  |
| 3 | Rural Media |  | 39,000 |  |
| 4 | Advocacy meeting |  | 5000 |  |
| Total |  | 9 | 100000 | 9,00,000 |

*The State Leprosy Officer will be able to distribute the total funds on the basis of actual requirements of each district keeping adequate funds at State level under Mass Media and Advocacy meetings.

4.   Development of Leprosy Expertise sustained

The training plan will be prepared at the district level based on actual need per year. Need assessment will first be done so that annual plan can be developed as below-

A.  Calculated for each district -

| S.No | Type of training | No. to be trained in the District | No. of course for 30 persons | Unit cost per course (Rs.) | Amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1 | Medical Officer ( 2 days) | 30 | 1 | 74500 | 74,500 |
| 2 | Physiotherapist (2 days) | - | - | 50400 | - |
| 3 | Lab. Technician (2 days) | 10 | 1 | 50,400 | 50,400 |
| 4 | Health Supervisor/ Health Worker (2 days) | 30 | 1 | 50400 | 50,400 |
| Total |  | 70 | 3 | - | 1,75,300 |

B.  Calculation for State/UT

| S.No | Type of training | No. to be trained in the District | No. of course for 30 persons | Unit cost per course (Rs.) | Total amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1 | District level Training from Table - A | - | - | 1,75,300 | 1,75,300 |
| 2 | Management Training for District Nucleus Teams | 30 | 1 | 108000 | 1,08,000 |
| Total |  | - |  | - | 2,83,300 |

5.	Research supported evidence based programme practices

This activity will be organised from the Central Level. However, States are often involved in Operational Research as a Partner with WHO, ILEP, ICMR and other research organizations with fund support from such organizations. Such details may be included under the Additional ties proposed separately in the plan.

6.	Monitoring. Supervision and Evaluation system improved

6.1. Travel cost and Review Meetings

| S.No. | Activity | No. of unit (State/District) | Unit cost (Rupees) | Total (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Travel cost for contractual persons at State level (Tick one of these) | >50 distt. >25-49 distt. > 10-24 distt. >5-9 distt. Upto 5 distt. | 1,50,000 100,000 80,000 60,000 40,000 | 5,40,000 |
| 2 | Travel cost for contractual persons at district level | 18 | 25,000 | 4,50,000 |
| 3 | State level Review meetings (Quarterly) | 4 | 20000 to 50,000 | 2,00,000 |
| Total |  | - | - | 11,90,000 |

6.2. Office operation and maintenance

This may be calculated for State/UT according to number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 2 | Rent, Telephone, Electricity, P&T charges, Miscellaneous District State Leprosy Cell | 9 1 | 35,000 75,000 | 3,15,000 75,000 |
| 3 | Office Equipment Maintenance cost State Leprosy Cell | 1 | 50000 | 50,000 |
| Total |  | 11 | 1,60,000 | 4,40,000 |

6.3. Consumables

This may be calculated for State/UT according to number of districts

| S.No | Item | No. of districts | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- |
| 1 2 | Stationary Items District State Leprosy Cell | 9 1 | 30000 50000 | 2,70,000 50,000 |
|  | Total | 10 | 80,000 | 3,20,000 |

6.4. Vehicle Hiring and POL/Maintenance

| S.No | Item | No. of districts | No. of Vehicle | Unit cost per district (Rupees) | Total amount (Rupees) |
| --- | --- | --- | --- | --- | --- |
| 1 | District Leprosy Unit | 9 | 1 | 150000 | 13,50,000 |
| 2 | State Leprosy Cell | 0 | 2 | 200000 | 4,00,000 |
|  | Total | 9 | 3 | 3,50,000 | 17,50,000 |

7.    Increased participation of persons affected by Leprosy in Society

One member from the local leprosy Disabled Persons Organisations (DPO) may be included to encourage increased participation of persons affected by leprosy in planning as well as in programme implementation in each of the following Committees:

i)	Village Health, Sanitation & Nutrition committee

ii)	PHC Health Monitoring and Planning committee

iii)	Block Health Monitoring and Planning committee

iv)	District Health Monitoring and Planning committee

v)   State Health Monitoring and Planning committee

8.   Programme Management ensured

8.1. Contractual staff at State level - as per existing strength

| S.No | Category | No. of posts | Unit cost * per month | Cost per year (Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Surveillance Medical Officer | 1 | 40,000 | 4,80,000 |
| 2 | BFO Cum Admn. Officer | 1 | 30,000 | 3,60,000 |
| 3 | Admn. Asstt. | 1 | 16,000 | 1,92,000 |
| 4 | DEO | 1 | 15,000 | 1,80,000 |
| 5 | Driver | 2 | 11,000 | 2,64,000 |
| Total |  | - | - | 14,76,000 |

*The salaries are indicative and need to be firmed up considering respective State salaries and NRHM scale for similar categories of staff. 8.2. District Leprosy Societies

| Few contractual posts for the high endemic indicating their need for this purpose subject to 1 |  | districts proposed in 12* Plan Inal approval. |  | .. States may | )lan |
| --- | --- | --- | --- | --- | --- |
| S.No | Category of post | No. of district identified | Unit cost per month | Unit cost per year | Total cost |
| 1 | Medical Officer (high endemic district) | 0 | 40,000 | 0 | 0 |
| 2 | Physiotherapist at District Hospital (endemic district) | 0 | 25,000 | 0 | 0 |
| 3 | Driver (General) | 18 | 11,000 | 23,76,000 | 23,76,000 |
| Total |  | - | - | - | 23,76,000 |

8.3. Special Provision for selected States/UTs

As in the previous plans, the staff provided on contractual basis may be planned as below:

| S.No | State/UT | No. of NMS | Unit cost per month (Rs.) | Unit cost per year (Rs.) | Total cost (Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1 | Punjab | 20 | 20,000 | 2,40,000 | 48,00,000 |
| 2 | Haryana | 21 | 20,000 | 2,40,000 | 50,40,000 |
| 3 | Delhi | 10 | 20,000 | 2,40,000 | 24,00,000 |
| 4 | Chandigarh U.T. | 2 | 20,000 | 2,40,000 | 4,80,000 |
| 5 | Dadra & Nagar Haveli | 2 | 20,000 | 2,40,000 | 4,80,000 |
| 6 Lakshadweep |  | 1 | 20,000 | 2,40,000 | 2,40,000 |
| Total |  | 56 |  |  | 134,40,000 |

8.4.High endemic Blocks

Special provision for providing one Para Medical Worker on contractual basis for leprosy supervision, monitoring and programme implementation in high endemic blocks have been proposed and to be provided subject to approval of the Govt. The States/UT may prepare the plan as below-

| S.No | Category of post | No. of | Unit cost | Unit cost | Total |
| --- | --- | --- | --- | --- | --- |
|  |  | high | per month | per year | cost |
|  |  | endemic | (Rs.) | (Rs.) | (Rs.) |
|  |  | blocks |  |  |  |
|  |  | identified |  |  |  |
| 1 | Paramedical Worker | Nil | 16,000 | 1,92,000 | Nil |

IV. Additionally in Annual Plan

1.	NRHM

Details of activities with justification for which Additionality funds are proposed and agreed by the State NRHM may be indicated.

2.	WHO. ILEP. ICMR and Other Organizations

Project activities planned to be carried out with such other partner organizations with justification indicating budget may be shown separately for each organization.

NOTE :	A summary of the State/UT budget proposal will be indicated in the

attached Format.

| Format for submitting budget proposal under NLEP for 2012 - 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (Rs. In lakhs) |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl.No | Name of District | Functional Head wise budget |  |  |  |  |  |  |  |  |  |  |
|  |  | ASHA | Special Activities ( 209Distt.) | Improved case Management |  |  |  | Stigma reduction (IEC) | Training | Monitoring & Supervision | Programme Management (Contractual Post) | Total Budget |
|  |  |  |  | DPMR | Urban | Material & Supplies | NGO |  |  |  |  |  |
| 1 | Aizawl | 2 |  |  |  |  |  |  |  |  |  |  |
| 2 | Mamit | 2 |  |  |  |  |  |  |  |  |  |  |
| 3 | Lunglei | 3 |  |  |  |  |  |  |  |  |  |  |
| 4 | Lawngtlai | 3 |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |
| A - Total of District |  |  |  |  | 0.00 | 0.00 | 16.00 | 9.00 | 1.75 | 0.00 | 23.76 | 50.51 |
| B - State HQ Cell |  |  |  |  | 3.54 | 4.20 | 0.00 | 0.00 | 2.83 | 37.00 | 14.76 | 62.33 |
| Grand Total (A+B) |  |  |  |  | 3.54 | 4.20 | 16.00 | 9.00 | 4.58 | 37.00 | 38.52 | 112.84 |
| Additionality |  |  |  |  |  |  |  |  |  |  |  |  |
| Organization |  |  |  | Project details |  |  |  |  | Total Budget |  |  |  |
| NRHM |  |  |  |  |  |  |  |  |  |  |  |  |
| WHO |  |  |  |  |  |  |  |  |  |  |  |  |
| ILEP |  |  |  | Purchase of New Gypsy |  |  |  |  | 5.50 |  |  |  |
| Other Organization (Specify) |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  | 5.50 |  |  |  |

D.5 National Programme for Control of Blindness (NPCB)

ANNUAL  ACTION PLAN FOR NATIONAL PROGRAMME FOR CONTROL OF BLINDNESS.

State	:	Mizoram

Year	:	2012 – 2013.

Introduction :

National Programme for Control of Blindness (NPCB) was launched in the year 1976 as a 100% centrally sponsored programme with the goal of achieving a prevalence rate of 0.3% of population.

The four pronged strategy of the programme is:

strengthening service delivery,

developing human resources for eye care,

promoting outreach activities and public awareness and

developing institutional capacity.

The implementation of the programme was decentralized in 1994-95 with formation of District Health Society in each district of the country. The Government of India has been issuing guidelines from time to time to utilize the funds released to the District Health Society in an effective and efficient manner.The District Health Society is expected to enhance the coverage and improve quality of eye care services in the district

Objectives :

Main objectives are:-

To reduce the backlog of blindness through identification and treatment of blind

To develop comprehensive eye care facilities in every district

To develop human resources for providing eye care services

To improve quality of service delivery

To secure participation of voluntary organization/private practitioners in eye care

Focus areas for 11TH five year plan :

Cataract

Childhood Blindness

Refractive Error & Low Vision

Corneal Blindness

Glaucoma

Diabetic Retinopathy

Trachoma(Focal)

PREAMBLE

Mizoram is a mountainous region which became the 23rd State of the Indian Union in February, 1987. It was one of the districts of Assam till 1973 when it became a Union Territory. Sandwitched between Myanmar in the east and south and Bangladesh in the west, Mizoram occupies an area of great stategic importace in the north-eastern corner of India. It has a total of 722 Km. boundary with Myanmar and Bangladesh.

The administration of Mizoram was upgrade to Union Territory in 1972, after 15 years the Union Territory administration was changed to statehood / or the Mizoram full fledge state.

The imaginary line of Tropic of Cancer passed through the middle part of the state and having temperate climate. The temperature range is 11 – 18 C in winter and 20 – 30 C in summer.

South west monsoon, from Bay of Bengal harbinger of rainfall between April to October and the average rainfall was 2010 mm.

The topography of the state is hilly terrain rough hill range running North to South. Due to that the Road and Communication are very bad and only seasonal. Many places were cut off during rainy season due to landslide. The topography of the hill and the habit and custom of some clans like RIANG, CHAKMA create a problem to provide health care.

As per 2011 census the population was 10.91 lakhs in which male was 5.52 lakhs. Female was 5.38 lakhs, the sex ration was 975 female per 1000 male. The density of population was 52/Km Sq. Literacy rate is 91.53%. The state language is Mizo only few can speak English and Hindi. There is no discrimination either sex or caste among Mizo.

The whole state is divided into 8 administrative Districts but for the convenience of administration. The biggest District Aizawl is divided into Aizawl East & West District.

8 Districts are ;-

| Sl.no | District | Area Coverage | Population |
| --- | --- | --- | --- |
| 1. | Aizawl district (West & East) | 3576 sq km | 4,04,054 |
| 2. | Champhai district | 3185 sq km | 1,25,370 |
| 3. | Mamit district | 3025 sq km | 85,757 |
| 4. | Kolasib district | 1382 sq km | 83,054 |
| 5. | Serchhip district | 1421 sq km | 64,875 |
| 6. | Lunglei district | 4538 sq km | 1,54,094 |
| 7. | Lawngtlai district | 2557 sq km | 1,17,444 |
| 8. | Saiha district | 1399 sq km | 56,366 |

Mizoram Profile :-

1.	Doctor population		-	2623

2.	Nurse population		-	666

3.	Health Worker  “		-	1167

4.	Ophthalmic Asst.		-	41

5.	State Hospital		-	1

6.	District hospital		-	7

7.	CHC				-	9

8.	PHC				-	57

9.	SC				-	366

Each District is administrated by Chief Medical Officer under Health & Family Welfare department and  having 9 administrative Districts.

NATIONAL BLINDNESS CONTROL PROGRAMME IN MIZORAM.

Target and Achievement during 2010 – 2011:

| Sl.no | Particulars | Target | Achievement |
| --- | --- | --- | --- |
| 1. | Cataract Operation | 3000 | 66.36% |
| 2. | IOL Implantation | 2700 | 71.18% |
| 3. | Women beneficiaries | 1650 | 62.66% |
| 4. | Surgery of Bilateral Blind | 1500 | 12.13% |
| 5. | SC/ST/BPL beneficiaries | 1500 | 66.36& |

| Sl.no | Particulars | Target | Achievement |
| --- | --- | --- | --- |
| 1. | School children to be screened | 50000 | 93% |
| 2. | Estimated school children detected R.E | 3000 | 125% |
| 3. | Free spectacles provided to poor children | 1000 | 131.8% |
| 4. | Target for other eye disease (Diabetic Retinopathy, Glaucoma, Laser technique, etc) | 30 | 1440% |

| Sl.no | Particulars | Target | Achievement |
| --- | --- | --- | --- |
| 1. | Eye Donation | 30 | 93.33% |

Statement showing National Programme For Control of Blindness Grant – in – Aid to State for various Component as per Financial Norms in 2012 – 2013 :

| Head | Component | Quantity Required |  | Physical target | Funds required (Rs in lakhs) |
| --- | --- | --- | --- | --- | --- |
| A. Recurring Grant-in-Aid. (Annex. I) | 1. For Free Cataract Operation @ Rs 750/-per case | State & 9 districts |  | 4,000 nos | 30.00 |
|  | 2. Other Eye Diseases @ Rs 1,000/- per case. ( Diabetic Retinopathy, Glaucoma, Squint, Kerato plasty) | 9 districts |  | 500 nos | 5.00 |
|  | 3. School Eye Screening Programme @ Rs 250/- | 9 districts |  | 2000 nos | 5.00 |
|  | 4. Private Practitioners@ as per NGO norms | - |  | 2 | .25 |
|  | 5. Management of State Health Society | - |  | - | 14.00 |
|  | 6. Management of District Health Society | 9 districts |  | - | 9.00 |
|  | 7. Recurring GIA to Eye Donation Centres @Rs 1000/- and Eye Banks @Rs 1500/- per pair of Eye ball Collection. | State |  | 20 | 2.50 |
|  | 8. Training and IEC | State & districts |  |  | 16.00 |
|  | 9. Procurement of Ophthalmic Equipments | State & 9 districts also sub-district hospital |  |  | 40.00 |
|  | 10. Maintenance of ophthalmic Equipments |  |  |  |  |
|  | TOTAL ‘A’ |  |  |  | 121.75 |
| B.Non- recurring Grant-inAid. (Annex. II) | 1. For PHC/Vision Centres @ Rs 50,000/- | 27 | 27 |  | 13.50 |
|  | 2. For Eye Bank @ Rs 15 lakhs | 1 | 1 |  | 15.00 |
|  | 3. For Eye Donation Centres @ Rs 1 lakhs | 2 | 2 |  | 2.00 |
|  | 4. To NGOs for strengthening/expansion of Eye care units@ Rs 30 lakhs | 2 | 2 |  | 60.00 |
|  | 5. For Eye Wards & Eye OTS @ Rs 75 lakhs | 1 | 1 |  | 75.00 |
|  | 6. For Mobile Ophthalmic units with telenetwork @ Rs 60 lakhs | 2 | 2 |  | 120.00 |
|  | Management information system, Education, monitoring and Evaluation | 1 | 12 months |  | 3.00 |
|  | TOTAL ‘B’ |  |  |  | 288.50 |
| C. Contractual Manpower. (Annex III) | 1. Ophthalmic Surgeon(Salary of Rs 45,000/-) | 1 | 12months |  | 5.40 |
|  | 4. Eye Donation Counsellor(Salary of Rs 23,000/) | 1 | 12months |  | 2.76 |
|  | 5. Ophthalmic assistant (Salary of Rs 18,000/-) | 26 | 12months |  | 56.16 |
|  | TOTAL ‘C’ |  |  |  | 64.32 |
|  | Total Grant- in – Aid (A + B + C) |  |  |  | 474.57 |
|  | Say |  |  |  | 474.60 |

(Rupees Four hundred and seventy Four lakhs and Sixty thousand) only

Strategies of PIP 2012 - 2013 in order to achieve the objectives are :-

ANNEXTURE – I.

A.	RECURRING GRANT – IN – AID :

1.	 Free Cataract Operation :-

Cataract is the dominant cause of blidnness as it accounts for nearly two third of blind population. The purpose of cataract surgery is to restore vision of the affected person through provision of package of services that can enable the person to gain sight and return to his normal working as before. The focus of NPCB is specifically targeted towards providing services in rural/tribal and other difficult areas. Physical target for the state of Mizoram during 2011 - 12:

Cataract Operation			-	4000

IOL Implantation			-	3800 (90%)

Women Beneficiaries		-	2200 (55%)

Surgery or Bilateral Blind		-	2000 (50%)

Sc/ ST/ BPL beneficiaries		-	2000 (50%).

Cataract Operations are performed at the State and District Hospitals, Sub-District Hospitals/CHCs, PHCs and at the Presbyterian Hospital, Durtlang, Aizawl run by the Presbyterian Church. It may be mentioned that the Presbyterian Hospital is identified as one of the base hospital for Cataract Operation. Surgical (Cataract) Eye Camps were organized by District Blindness Control programme in which Eye Surgeons working under Mizoram Govt. and Presbyterian Hospital.

2.	Other Eye Diseases :-

Grant – in – aid for management of other eye diseases like Diabetic Retinopathy, Glaucoma Management, Laser Techniques, Corneal Tranplantation, Vitreoretinal surgery, Treatment of Childhood Blindness etc is Rs 1000 per case. During 2010 – 2011. 432nos was detected..

3.	School Eye Screening Programme :-

These activities included organization of screening camps at school or visits for school eye screening programme, monitoring and supervisory visits and other eye care activities. These programme is very important while it is estimated that nearly 50% of blind childred should be suffering form preventable or curable blindness due to cataract, corneal opacity and retinal disorders. Efforts should be made to identify underlying cause of blindness, assess chances of sight restoration and provide best possible treatment to the affected population. It is urgent to take up this activity and manege curable blindness in children as a priority intervention.

During 2011 – 2012, achievement was made @ more than 90%. For the year of 2012 – 2013, 2000 nos of children is expected to screen in this programme.

Requirement of fund towards provision of spectacles is given below at Table 3.

Table

4.	Private Practitioners as per NGO norms :-

Various activities and initiatives are being undertaken to improve community awareness on eye care however one of the era that is being strengthened with greater vigor and strategic approach is voluntary eye donation and eye banking in the country. In addition, institutional & health personnel responsiveness is also being addressed. But, there is backlog shown in the result outcome. One of the deficiency noticed was inadequate availability of human resource in health facilities providing eye care services in a satisfactory and competent manner. For this reason, Private practitioners plays very important and provision has been made as per NGO norms.

5.	Management of State Health Society :-

Recurring grant-in –aid of Rs 14.00 lakhs per annum to meet the cost on salaries of the staffs(State Ophthalmic staffs.). TA/DA, organizing review meetings, hiring of vehicle, operating and maintenance of office equipments and contingencies:

Recurring Assistance for State Health Societies :

| S/n | Post | Remuneration P.M | Cost P.A |
| --- | --- | --- | --- |
| 1 | Honorarium of SPO | Rs 5,000/- | Rs 60,000/- |
| 2 | Accounts Officer | Rs 30,000/- | Rs 3,60,000/- |
| 3 | Data Entry Operator | Rs 15,000/- | Rs 1,80,000/- |
| 4 | IV Grade | Rs 10,000/- | Rs 1,20,000/- |
|  | TA/DA to Staff/ POL and vehicle maintenance/stationery & Consumables/ Quarterly Review meetings, contingency, hiring of vehicles etc. |  | Rs 6,80,000/- |
|  | Total |  | Rs 14,00,000/- |

6.	Management of District Health Society :-

Recurring assistance in installment of Rs 5.lakh or more will be released to District Health Societies through State Health Societies. GIA will be utilized towards cost of consumables, minor equipments/instruments as per approved list, spectacles, POL and maintenance of vehicles and equipments, hiring of vehicle, IEC activities, village blind registry, remuneration to DPm and support staff, grant in aid to NGOs for performing free cataract operations, support for other eye diseases, assistance to Panchayats for screening, motivation and transportation of cataract patients recurring GIA to Eye Banks and Eye Donation Centres, SES, eye donation activities, training within the districts and other contingent ecpenditure as per guidelines. GIA can also be utilized for treatment of poor patients suffering from other eye problems like Galucoma, Corneal Blindness, Diabetic Retinopathy etc.

In each DBCS/DHS (Blindness) one officer at the office of Chief Medical Officer is designated as District Programme Manager (DPM) who is also the Member Secretary of the District society. Remuneration of Rs. 2,000/- (maximum) per month is paid to each DPM amounting to a total of Rs. 24,000/- per annum. Account Assistant @ 1,500/- p.m. amounting to a total of Rs. 18,000/- p.m. Eye Camps were organized by District Blindness Control Societies So. Table  shows names of all the DBCS with their budget required for Remuneration and other requirement for the District Health Society as well.

Table  :-	 Budget Requirement for District Health Society For the year of 2012 – 2013.

| Sl no. | District / DBCS |  | Honorarium to DPM/Acc. Asst. | TA/DA and Other Contingencies | POL & Maintenance. | AndOther Contingencies | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl West |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 2 | Aizawl East |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 3 | Lunglei |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 4 | Saiha |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 5 | Lawngtlai |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 6 | Serchhip |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 7 | Champhai |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 8 | Kolasib |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
| 9 | Mamit |  | 42,000/- | 40,000 | 10,000 | 8,000 | 1,00,000 |
|  |  | TOTAL |  |  |  |  | 9,00,000 |

7.	Recurring GIA to Eye Donation Centre  :-

Target made for Mizoram State Blindness Control Society by ministry for Eye Donation during 2011 – 2012 was 30 nos. For collection of Eye ball @ Rs 1000/- for Eye Donation Centres and the @Rs 1500/- for Eye Banks will be borne as per existing norms. During this current year (2011 – 2012), Four(24) eye balls have been collected then all have been received successfully

8.	IEC:-

The importance of IEC in eye care activities stems from the fact that most eye ailments are preventable or cureable. IEC activities have to be carried on continuously so that there will be behavioural change with increase utilization of available services amongst the public. Message to the community are broadcasted through AIR and Local newspaper, telecasted through Doordarshan Kendra and local cable TV network in local language. Hoardings and colour leaflets/folders on various topics will be displayed and distributed. Prevention of Blindness Week, Eye Donation Fortnight and World Sight Day (12th October) will be observed in accordance with instructions and themes given by Govt. of India. Budget requirement for undertaking IEC activities is given below at Table .

Table 5.		 Budget Requirement for IEC at State level 2012-2013

| IEC |  |  |
| --- | --- | --- |
| 1 | Publicity NEC – Poster, banners, light/Folder, Health talk etc | 360,000.00 |
| 2 | Radio rate Rs. 225 per broadcast X 50 | 11,250.00 |
| 3 | Newspaper @ Rs. 2500/- per display X 50 display | 125,000.00 |
| 4 | Doordarshan Kendra @ Rs. 500 per display X 90 | 45,000.00 |
| 5 | Cable TV rate Rs. 500 per display X 50 | 25,000.00 |
| 6 | Banner @ Rs. 1500 X 50 | 75,000.00 |
| 7 | Leaflet @ Rs. 25 X 2000 | 50,000.00 |
| 8 | Prescription chart / card @ Rs.10 X 100 | 10,000.00 |
| 9 | Eye Donors Card & Pledge @ Rs 5 x 750 | 3,750.00 |
|  | Total | 705,000.00 |

Training :

Training and retraining of health personnel from grass root level upto Eye Surgeon is of utmost importance in order to update technical knowledge and to achieve the target under the programme. As per norm,

Training of Eye Surgeons and other eye care personnel :

Training of Eye Surgeons in identified institutes in following areas –

ECCE/IOL implantation surgery, small incision cataract surgery, phaco – emulsification, Low vision services, Glaucoma, Pediatric Ophthalmology, indirect Ophthalmology & Laser Techniques, Vitreoretinal surgery, Eye Banking & Corneal Transplantation surgery etc.

Training in Ophthalmic Nursing, training of PMOAs, refresher training of Mos PHC/CHC/DH and PMOs will be organized at state level. Basic training of Ophthalmic Assistants will be revamped and initiated.

Training of State and District Programme Managers, ASHA & ICDS etc will be organized at state level.

At the State level -

(a)Refresher Training of PHC/CHC Medical Officers.

(b)Training in Ophthalmic Nursing for Nursing personnel

(c)Training of Paramedical Ophthalmic Assistants (PMOA).

(d)Refresher training For Eye Donation Counsellor (For effective & efficient of eye Donation performed)

(e) Review Meeting (Quarterly & Half Yearly) for District Programme Manager & Eye Surgeons.

Financial Assistance for Training of Eye Surgoens and other Eye Care personnel like PMOAs and other will be carried out like Rs 8,95,000/-annually cause the following included on these trainning expenditure:

| Consumables, Instruments, Drugs / Medicines etc | Rs 80,000 |
| --- | --- |
| Support to training institutions for organizing training towards training material remuneration to faculty, use of equipments organizing changes etc | Rs 4,93,100 |
| Travel cost – AC II Tier/ By Road | Rs 55,000 |
| DA @ Rs 1000 X 90 daysX 60days X 7days | Rs 1,57,000 |
| Accomodation Rentals @ Rs700 X 90 days X 60days X 7days | Rs 1,09,900 |
| Total | Rs 8,95,000 |

.

9. Ophthalmic Equipments :

Ophthalmic Equipments will be procured for use in the State, District and Sub-District Hospitals within the norms and procedures of the state.

Rs 15 lakhs had been released by National Programme for Control of Blindness as per existing norms for Mizoram Eye Bank. Furnishing and maintenace of equipments for this Eye Bank,amounting Rs 5,00,000/- is prepared required Fund for this year.

An Ophthalmic Equipments to be procured will be selected as per requirements from the list given at Table .

Table  :-	List of Ophthalmic Equipments for procurement to be procured by State Health Society

| S.No. | Name of Equipments |
| --- | --- |
| 1 | (a) Minor Equipment & Instruments |
| 2 | Binomags (Binocular loupe) |
| 3 | Cataract Set including ECCE/Intra Ocular Lens implantation and Blades for |
| 4 | Small Incision Cataract Surgery. |
| 5 | Disposable blades for SICS - MVR- Crescent, 3-2/5-2 etc. |
| 6 | Distant vision Charts |
| 7 | Foreign Body Spud & Needle |
| 8 | Lacrimal Cannula & Probes (various sizes) |
| 9 | Lid retractors (Desmarres) |
| 10 | Near Vision Charts |
| 11 | Punctum Dialator |
| 12 | Retinoscopic Mirror |
| 13 | Rotating Visual Acuity Drum |
| 14 | Torch |
| 15 | Trial Frame Adult/Children |
| 16 | Trial Lens Set |
| 17 | Auto refractormeter |
| 18 | Phacoemulsifier |
| 19 | Refraction units, Slit lamp |
| 20 | Indirect ophthalmoscope with 20D lens |
| 21 | UPS |
| 22 | Lacrimal Cannula & Probes (various sizes) |
| 23 | Generator |
| 24 | Surgical sets of all sub specialties of Ophthalmology as per demand/need |
| 25 | Consumable required for ophthalmic surgeries |
| 26 | Consumables for Phaco Machine (Phaco tips, cassettes) & SICS surgery (Blades) |
| 27 | . Drugs |
| 28 | IOL |
| 29 | Sutures (Vicryl, Prolene, Nylone, Silk) |
| 30 | Generator |
| 31 | Eye Ointments |
| 32 | Atropine (1%) |
| 33 | Local antibiotic: Framycetin/Gentamicin /Tetracycline etc. |
| 34 | Local antibiotic steroid ointment |
| 35 | Ophthalmic Drops |
| 36 | Xylocaine 4% (30ml) / Paracaine Eye Drops |
| 37 | Local antibiotic: Framycetin/Gentamicin/Sulphacetamide etc. |
| 38 | Local antibiotic steroid drops |
| 39 | Pilocarpine Nitrate 2% |
| 40 | Timolol 0.5% / Latano prost Eye Drops/Alphagan Eye Drops |
| 41 | Homatropine 2% |
| 42 | Tropicamide 1% |
| 43 | Cyclomide 1% |
| 44 | Sulphactamide Eye Drops 10% , 20% |
| 45 | Betadine Solution/Betadine Eye Drops/Betadine scrub |
| 46 | Tablet Azithromycin 10mg, 20mg, 50mg. |
| 47 | Injections |
| 48 | Inj.Xylocaine 2% (30 ml) |
| 49 | nj Hyalase (Hyaluronidase) |
| 50 | Inj. Gentamycin |
| 51 | Inj.Betamethasone/Dexamethasone |
| 52 | Inj. Maracaine (0.5%) (For regoinal anesthesia) |
| 53 | Inj. Adrenaline |
| 54 | Inj.Ringer Lacate (540 ml) from reputed firm |
| 55 | Inj. Trypan Blue |
| 56 | Eye Ointments |
| 57 | Atropine (1%) |
| 58 | Surgical Accessories |
| 59 | Gauze |
| 60 | Green Shades |
| 61 | Blades (Carbon Steel) |
| 62 | Opsite surgical gauze (10x14 c.m.) |
| 63 | 8-0 & 10-0 double needle Suture |
| 64 | Visco-elastics from reputed firms |
| 65 | Spectacles |
| 66 | For Operated Cataract Cases (after refraction) (Rs.125/-) |
| 67 | For poor school-age children with refractive errors (@Rs.200/-) |

ANNEXTURE – II.

B.	NON RECURRING GRANT – IN – AID :

1. For Vision Centres :-

For providing basic services to  rural population Vision Centres may be set up in atleast 10 PHC/CHC during 2007-08 in addition to the existing 5 Vision centers. During 2008 – 2010; 12 numbers of CHC/PHC were set up at Vision Centres, currently there are 27 numbers Vision Centres services within mizoram. List of existing 27 Vision Centres is given at Table 1. Non recurring assistance upto Rs 50,000/- for basic equipments, furniture and fixtures etc.

Table 1 :-		 Existing Vision Centres (CHC/PHC)

| Sl. No. | Vision Centres (PHC/CHC) | District |
| --- | --- | --- |
| 1. | Hnahthial CHC | Lunglei |
| 2. | Chawngte CHC | Lawngtlai |
| 3. | Thenzawl PHC | Serchhip |
| 4. | Ngopa CHC | Champhai |
| 5. | Kawrthah | Mamit |
| 6. | Sialsuk | Aizawl West |
| 7. | Kanghmun | Aizawl West |
| 8. | Sakawrdai | Aizawl East |
| 9. | Chhipphir | Lunglei |
| 10. | Tuipang | Saiha |
| 11. | Bungtlang South | Lawngtlai |
| 12. | N. Vanlaiphai | Serchhip |
| 13. | Khawbung | Champhai |
| 14. | Vairengte | Kolasib |
| 15. | West Phaileng | Mamit |
| 16. | Lengpui | Aizawl ‘W’ |
| 17. | Sairang | ‘Aizawl ‘W’ |
| 18. | Thingsulthliah | Aizawl ‘E’ |
| 19. | Suangpuilawn | Aizawl ‘E’ |
| 20. | Buarpui | Lunglei |
| 21. | Sangau | Saiha |
| 22. | Borapansury | Lawngtlai |
| 23. | Chhingchhip | Serchhip |
| 24. | Khawzawl | Champhai |
| 25. | Kawnpui | Kolasib |
| 26. | Zawlnuam | Mamit |
| 27. | Kristian Hospital, Serkawn | Lunglei. |

Requirement of assistance for development of vision centres at PHCs & CHCs :-

| S/n | Equipments / Furnishing |
| --- | --- |
| 1 | Tonometers (Schiotz) |
| 2 | Direct Ophthalmoscope |
| 3 | Illuminated Vision Testing Drum |
| 4 | Trial Lens Sets with trial Frames |
| 5 | Snellen & Near Vision Charts |
| 6 | Battery Operated Torch (2) |
| 7 | Furnishing & Fixtures |
| 8 | Slit Lamp |
| 9 | Epilation forceps Xylocaine Eye drops 4 % |

2..	Non Recurring GIA to Eye Bank :-

An Eye Bank will mean an organization that is :

1)	Registered under “The transplantation of Human Organs, Act 1994”

2)	Provide a round the clock public response system for eye donation;

3)	Coordinate with donor families and hospitals to motivate eye donation;

4)	Harvest corneal tissue not less than 50 eyes in a year.

5)	Collect/process and evaluate the collected tissue and blood for serology;

6) Distribute tissue in an equitable manner to organizations having capacity for corneal transplantation;

7)	Ensure safe tranportation of tissue.

8) conduct health personnel and public awareness programs on eye donation.

Mizoram Eye bank based in Civil Hospital, Aizawl, Mizoram, India has been inaugurated on the 31 July 2008. In collaboration with Sri Sankaradeva Netralaya Eye Institute, Guwahati and Eye Department Civil Hospital, Aizawl the first Corneal Transplant in the Mizoram state history was performed in Civil Hospital Aizawl, on 25/Sept/2009.
Mizoram Eye Bank is a member of Eye Bank Association of India (EBAI) . It is a non profit organization, purely funded by NPCB. Mizoram Eye Bank attends to a spectrum of Eye Banking activities such as cornea retrieval from deceased, storage and distribution. Complete evaluation is not yet possible as the Eye bank is not equipped with Specular microscope . Mizoram Eye bank is hospital based with one trained grief counselor and one trained technician, both undergo training in LV Prasad Eye Institute, Hyderabad. The eye bank retrieve corneas from the hospital itself and few from deceased home, it accepts pledges from individuals who wish to donate their eyes in the future. In the Hospital Cornea Retrieval Programme the counselor move to other hospital within the nearby area and have lately identified Presbyterian Hospital Durtlang as collection centre..

| S/n | Equipments/Furnishing |
| --- | --- |
| 1 | Slit Lamp Microscope |
| 2 | Operating Microscope with Camera attachment |
| 3 | Specular Microscope |
| 4 | Laminar Flow |
| 5 | Serology Equipment |
| 6 | Instruments for corneal excision and enucleation includung containers |
| 7 | Autoclave |
| 8 | Keratoplasty instruments |
| 9 | Transport Facility(one 4 wheeler & one 2 wheeler) |
| 10 | Refrigerator |
| 11 | Computer & Accessories |
| 12 | Telephone Line |
| 13 | Air – Conditioner |
| 14 | Renovation, Repair, Furniture & Fixtures. |

3. For Eye Donation Centres :-

A per financial norms, Non – recurring assistance upto Rs 1,00,000/- (One lakh) for strengthening / developing eye donation Centres and Recurring assistance upto Rs 1,000/- (One thousand) per pair of eyes collected towards honorarium of eye bank staff, consumables including preservation material & media, transportation/travel cost/ POL and contingencies.

In Mizoram, there are two(2) Eye Donation Centres, such as :

1)	Civil Hospital, Aizawl &

2)	Presbyterian Hospital, Durtlang.

4. For NGOs :-

Recurring Grant –in-aid for NGOs for performing free cataract operation and other intra-ocular surgeries and also for management of other Eye diseases like Diabetic Retinopathy, Glaucoma management, Laser techniques, corneal transplantation, vitreoretinal surgery, treatment of childhooh blindness etc @ Rs 1000 per case.

For identifying blind persons (blind registry), organizing & motivating identified persons and transporting them to Government/ VO fixed facilities, primary health centre, panchayats, ASHA etc. will be involved in this treatment. Reimbursement will be made as per norms :-

|  |  | ECCE/IOL | SICS/PHACO |
| --- | --- | --- | --- |
| a. | Drugs and consumables | 200 | 200 |
| b. | Sutures | 50 | 0 |
| c. | Spectacles | 125 | 125 |
| d. | Transport/ POL | 100 | 100 |
| e. | Organization & Publicity | 75 | 75 |
| f. | IOL, Viscoelastic & additional Consumables | 200 | 250 |
|  | Total | 750 | 750 |

Bring together all eye care units whether in the Government, NGO or Private Sectors is one of the main function of Blindness control Society. Mizoram State Blindness Control Society have good co-operation with NGO and Private Practitioner for delivering eye care services to difficult and underserved areas. NGO named Presbyterian Hospital, Durtlang and Serkawn Christian Hospital brings out good achievement. They are very active and contribute a lot in outreach services. Since, 2011 – 2012, Mara Christian Hospital is also involved in these activities.

Non –Recurring GIA to NGOs for strengthening / Expanding Eye Care Facility :

| S/n | Component |
| --- | --- |
| A | Ophthalmic Equipments : |
| 1 | Operating Microscope with Assistantscope & Camera attachments |
| 2 | A – Scan Biometer |
| 3 | Keratometer |
| 4 | Slit Lamp |
| 5 | Yag Laser |
| 6 | Applanation Tonometer |
| 7 | Auto Refractometer |
| 8 | Vitrectomy Unit |
| 9 | Flash Autoclave |
| 10 | Automated Perimeter with field analyzer |
| 11 | Phacoemulsifier |
| 12 | Double Frequency Yag Laser/ Argon Green Laser with delivery systems |
| 13 | Fundus Fluorescein Angiography Camera |
| 14 | B- Scan |
| 15 | Surgical instruments for various eye specialists |
| 16 | IOLs |
| 17 | Sutures 4-0, 8-0, 10-0 |
| B | Surgical instruments for various eye specialties |
| C | Furniture & Fixtures of operation theatres & Ward |
| D | Mobile Ophthalmic unit with diagnostic equipments and minor surgical instruments. |

5. For Eye wards & Eye OTs :

Non recurring assistance upto Rs 75 lakhs is required where dedicated operation theatres are not available as per demand to develop eye care infractructure. Details of infrastructure are as below :-

Completed building :

1.	Civil Hospital, Aizawl

2.	Serchhip District Hospital

On – Going construction :

1.	Lunglei Civil Hospital

2.	Champhai District Hospital

3.	Saiha District Hospital

4.	Mamit District Hospital

5.	Kolasib District Hospital.

New Location proposed :

1.	Lawngtlai District Hospital.

6. For Mobile Ophthalmic units with telenetwork :-

Non recurring assistance upto Rs 60 lakhs towards development of mobile ophthalmic units with tele – ophthalmic network and few fixed tele- model.

For organizing Eye Camp at interior and remote areas Mobile Ophthalmic unit plays very important. During the current year (2009 – 2010) 2(two) Mobile Ophthalmic Van are purchased and continuously active in eye care Services. Since that day mobile ophthalmic units are purchased as per PIP approval and allocated in districts hospital: At present, mobile  ophthalmic vehicles are running smoothly and effectively for conducting and organizing eye camp from :

1) Aizawl Civil Hospital

2) Kolasib District Hospital

3) Lunglei District Hospital

4) Serchhip District Hospital

also one vehicle was alloted at SPO office.

In collaboration with S.A.T.H.I, New Delhi, mobile ophthalmic telenetwork with Vision Centres are installed and inaugurated at 8 districts. The main centre is runnning from Civil Hospital, Aizawl. Annual maintenance and operation would be done by S.A.T.H.I funded by NPCB.

7.	Management information system, Education, Monitoring and Evaluation:

Development of software

Training of MIS staff

Conduct of beneficiary assessment and evaluation surveys

Data entry and analysis of performance and expenditure on various components

Studying profile of beneficiaries and

Undertaking Rapid survey and other related activities

ANNEXTURE – III.

C.	CONTRACTUAL MANPOWER:

Health personnel play a key role in the implementation of NPCB health programme. Under Mizoram State Blindness Control Society, there are 18 contractual staff presently employed i/e  Accounts Officer, Eye Donation Counsellor, 21(Fifteen) Ophthalmic Assistants and Data Entry Operator and also IV Grade are engaged on contractual basis. Due to insuffiency of Ophthalmic Surgeon within Mizoram, Ministry of Health & Family Welfare gives us permitted order to recruit the qualified  for filling up this post then advertisement for recruitment of Ophthalmic Surgeon is floated for this current year. However, no application is yet received for the said post. It is observed that no applicants received due to less pay and including high pay of their counterparts of regular services. Also 6th pay Commission was implemented in the previous year. Hence, it is proposed to increase to a reasonable amount for each staff of contractual staff under this Society. These contractual Staff plays an important key point at the management level and grass root level work. Proposed Salaries shown as below.

| Sl. No. | Category | Proposed Salary Per Month |
| --- | --- | --- |
| 1. | Ophthalmic Surgeon | Rs 45,000/- |
| 2. | Eye Donation Counsellor | Rs 23,000/- |
| 3. | Ophthalmic Assistants | Rs 18,000/- |

D.6 Revised National Tuberculosis Control Programme (RNTCP)

Section-A — General Information about the State

| 1 | State Population (in lakh) please give projected population for next year | 10.05 |  |
| --- | --- | --- | --- |
| 2 | Number of districts in the State | 8 |  |
| 3 | Urban population | 49% |  |
| 4 | Tribal population | 100% |  |
| 5 | Hilly population | 100% |  |
| 6 | Any other known groups of special population for specific interventions (e.g. nomadic, migrant, industrial workers, urban slums, etc.) |  |  |

(These population statistics may be obtained from Census data /State Statistical Dept/Districtplans)

No. of districts without DTC: Nil

No. of districts that submitted annual action plans, which have been consolidated in this State plan:8 District :

Organization of services in the State:

| s. No. | Name of the District | Projected Population (in Lakhs) | Please indicate number of TUs of each type |  | Please indicate no. of DMCs of each type in the district |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Govt | NGO | Public Sector* | NGO | Pri vat e Se cto rA |
| 1 | Aizawl | 3.78 | 2 | - | 9 | 1 | - |
| 2 | Champhai | 1.13 | 1 | - | 4 | - | - |
| 3 | Kolasib | 0.68 | 1 | - | 2 | - | - |
| 4 | Lawngtlai | 0.81 | 1 | - | 2 | - | - |
| 5 | Lunglei | 1.53 | 1 | - | 3 | 1 | - |
| 6 | Mamit | 0.69 | 1 | - | 3 | - | - |
| 7 | Saiha | 0.68 | 1 | - | 2 | - | - |
| 8 | Serchhip | 0.62 | 1 | - | 3 | - | - |
|  | Total | 10.05 | 9 | - | 28 | 2 | - |

*Public Sector includes Medical Colleges, Govt. health department, other Govt. department and SUs i. e. as defined in PMR report

A Similarly, Private Sector includes Private Medical College, Private Practitioners, Private Clinics/Nursing Homes and Corporate sector

RNTCP performance indicators:

Important: Please give the performance for the last 4 quarters i.e. Oct2010	to September 2011

| Name of the | Total | Annualised | No of new | Annualised | Success | Plan for the | next | Proport | No. of | No. of |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District (also | number of | total case | smear | New smear | rate for | year |  | ion of | MDR | MDR |
| indicate if it is | patients | detection rate | positive | positive case | cases |  |  | TB | TB | TB |
| notified hilly or | put on |  | cases put | detection rate | detected | Annualized | Succe | patient | suspects | cases |
| tribal district) | treatment* | (per lakh | on | (per lakh | in the last | NSP case | ss | s tested | identifie | diagnose |
|  |  | pop.) | treatment * | pop) | 4 | detection | rate | for | d and | d&put |
|  |  |  |  |  | correspon | rate |  | HIV | subjects | on |
|  |  |  |  |  | ding |  |  |  | to | treatmen |
|  |  |  |  |  | quarters |  |  |  | C/DST | t |
|  |  |  |  |  |  |  |  |  | of |  |
|  |  |  |  |  |  |  |  |  | sputum |  |
| Aizawl (Tribal) | 1180 | 328 | 177 | 72 | 86 | 70 | 85 | 71% | 37 | 0 |
| Champhai (Tribal) | 128 | 126 | 35 | 51 | 82 | 70 | 85 | 87% | 0 | 0 |
| Kolasib (Tribal) | 162 | 238 | 36 | 32 | 86 | 70 | 85 | 61% | 0 | 0 |
| Lawngtlai (Tribal) | 136 | 184 | 22 | 51 | 87 | 70 | 85 | 37% | 0 | 0 |
| Lunglei (Tribal) | 264 | 200 | 105 | 78 | 95 | 70 | 85 | 80% | 0 | 0 |
| Mamit (Tribal) | 70 | 113 | 25 | 49 | 72 | 70 | 85 | 76% | 3 | 0 |
| Saiha (Tribal) | 202 | 297 | 37 | 75 | 100 | 70 | 85 | 30% | 0 | 0 |
| Serchhip (Tribal) | 63 | 102 | 22 | 39 | 88 | 70 | 85 | 100% | 0 | 0 |
| Total | 2350 | 235 | 459 | 65 | 87 | 70 | 85 | 74% | 40 | 0 |

Patients put on treatment under DOTS regimens only are to be included.

#### Section B – List Priority areas at the State level for achieving the objectives planned:

| S.No. | Priority areas | Activity planned under each priority area |
| --- | --- | --- |
| 1 | To increase case detection | a) Training of untrained M.O.s & LTs |
|  |  | b) Awareness Campaign for general population at district & PHI level. c) Recruitment of additional RNTCP contractual LTs |
| 2 | To improve cure rate | a) Intensify Supervision at all levels |
|  |  | b) Re-training of Health Workers |
|  |  | c) More patients home visit & proper counselling before starting treatment. d) Prompt retrieval of default patients. |
| 3 | To improve quality of sputum smear microscopy | a) Timely repair and replacement of damage binocular microscope b) Demonstration of correct sputum collection technique by the LTs |
| 4 | To increase detection and cure rate regarding MDR TB | a) Increased IEC activities in MDRTB b) Setting up of new DTC, SDS and DOTS Plus Site |
| 5 | Involvement of political and administrative leaders, private practitioners & NGOs | a) Sensitisation of political and administrative leaders |
|  |  | b) Sensitisation of private practitioners |
| 6 | To establish more sputum collection centres | a) Establish sputum collection centres in all non DMC PHIs and hard to reach villages |
| 7 | Involvement of school children’s | 5 a) Sensitisation of Teachers |
|  |  | 5 b) Awareness Campaign in all Govt and private schools |

Priority Districts for Supervision and Monitoring by State during the next year

| S.No | District | Reason for inclusion in priority list |
| --- | --- | --- |
| 1 | ##### Serchhip | ##### Low NSP case detection and cure rate |
| 2 | ##### Lawngtlai | ##### Low NSP case detection and cure rate, less contribution from Chawngte MC |
| 3 | ##### Mamit | ##### Low NSP case detection and cure rate, less contribution from W.Phaileng ##### & Kawrthah DMC |
| 4 | ##### Champhai | ##### Low NSP case detection and cure rate, less contribution from Ngopa MC |
| 5 | ##### Kolasib | ##### Low NSP case detection and cure rate |

Section C - Consolidated Plan for Performance and Expenditure under each head, including estimates submitted by all districts, and the requirements at the State Level

1.	Civil Works

| Activity | No. required as per the norms in the State | No. already upgraded/ present in the State | No. planned to be upgraded during next financial year | PI provide justification if an increase is planned in excess of norms (use separate sheet ifrequired) | Estimated Expenditure on the activity | Quarter in which the planned activity expected to be completed |
| --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) | CO |
| ##### SDS, State TB Office | ##### 1 | ##### - | ##### 1 | ##### Allowed as per norms (maintenance) | ##### Rs. 75,000 x 1.3 = 97,500 | ##### 1st Quarter |
| ##### DOTS Plus site | ##### 1 | ##### - | ##### 1 | ##### Allowed as per norms | ##### Rs. 10,00000 x 1.3 = 13,00,000 | ##### 1st Quarter |
| ##### DTCs | ##### 8 | ##### - | ##### 8 | ##### Allowed as per norms (maintenance) | ##### Rs. 36,000 x 8x1.3 = 374400 | ##### 1st Quarter |
| ##### TUs | ##### 9 | ##### - | ##### 9 | ##### -Allowed as per norms (maintenance) | ##### Rs. 1300 x 9 x 1.3 = 15210 | ##### 1st Quarter |
| ##### DMCs | ##### 30 + 7 new additional DMCs | ##### - | ##### 37 | ##### - Allowed as per norms (maintenance) | ##### Rs 1000 x 37 x 1.3 = 48,100 | ##### 2nd Quarter |
| ##### District Drug store | ##### 8 | ##### - | ##### - | ##### District drug store for second line drugs | ##### Rs 30000 x8x1.3=3,12,000 | ##### - |
| ##### TOTAL |  |  |  |  | Rs.21,47,210 |  |

2.         Laboratory Materials

| Activity | Amount permissible as per the norms in the State | Amount actually spent in the last 4 quarters | Procurement planned during the current financial year (in Rupees) | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/Remarks for(d) |
| --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) |
| ##### Purchase of Lab Materials by Districts | ##### - | ##### 1,50,000 | ##### 3,00,000 | ##### 5,50,000 | ##### Total case detection is more than 135/lakh population in Aizawl, Lunglei and Kolasib District |
| ##### Lab materials for EQA activity at STDC (eg. Lab consumables for trainings, preparation of Panel slides etc) | ##### - | ##### 47,000 | ##### 85,000 | ##### 4,50,000 | ##### Planned by District Level |
| ##### Lab materials & consumables for Culture/DST activity at IRL and other Accredited Culture & DST labs in Govt. sector including Medical Colleges | ##### - | ##### 40,440 | ##### 75,000 | ##### 2,95,000 | ##### Planned by District Level |
| ##### TOTAL |  | ##### 237440 | ##### 460000 | ##### 1295000 |  |

3. Honorarium

| Activity | Amount permissible as per the norms in the State | Amount actually spent in the last 4 quarters | E?q)enditure (inRs) planned for current financial year | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/ Remarks for (d) |
| --- | --- | --- | --- | --- | --- |
| ##### Honorarium for DOT providers. | ##### - | ##### 200000 | ##### 4,93,000 | ##### 535925 | ##### (1649 x Rs.250 x 1.3) |
| ##### Honorarium for DOT Plus providers (Cat IV patients). | ##### - | ##### - | ##### 4,93,000 | ##### 487500 | ##### (150 x Rs.2500 x 1.3) |
| ##### Honorarium for DOT Patients. | ##### - | ##### 233000 | ##### - | ##### 535925 | ##### (1649 x Rs.250 x 1.3) |
| ##### Honorarium for Cat IV Patients. | ##### - | ##### - | ##### - | ##### 48750 | ##### (150 x Rs.250 x 1.3) |
| ##### Sputum Transportation from Districts to DOTS Plus Site. | ##### - | ##### 33000 | ##### - | ##### 122918 | ##### 11819 (for all 8 districts) x 8 x 1.3 |
| ##### Sputum Transportation from DOTS Plus Site. To LRS Delhi | ##### - | ##### - | ##### - | ##### 62400 | ##### Rs 4000 x 12 months x1.3 |
| ##### Travelling Cost for DOTS Plus patients & attendants to DPS & DTC | ##### - | ##### - | ##### - | ##### 28,02,240 | ##### This was planned under miscellanous head In the plan submitted to CTD |
| ##### Pre Treatment Evaluation (thyroid function test) for DOTS Plus Pateints. | ##### - | ##### - | ##### - | ##### 1,02,960 | ##### 99 patients x Rs.800 x 1.3 (this was planned under miscellanous head in the plan submitted to CTD) |
| ##### Travel support for TB/HIV patient |  |  |  | ##### 162600 | ##### This planned was under different head in the plan submitted to CTD |
| ##### Total | ##### - | ##### 466000 | ##### 9,86,000 | ##### 4861218 |  |

|  | No. presently involved in RNTCP | Additional enrolment proposed for the next fin. year | Remarks |
| --- | --- | --- | --- |
| Community volunteers in all the districts* | 308 | 107 | This was not included in the plan submitted to CTD |

* These community volunteers are other than salaried employees of Central/State government and are involved in provision of DOT e.g. Anganwadi workers, trained dais, village health guides, ASHA, other volunteers, etc.

4. Annual Action Plan Format Advocacy, Communication and Social Mobilization (ACSM) for RNTCP

1)	Information on previous year's Annual Action Plan (Communication Facilitators )

- Budget proposed in last Annual Action Plan: Rs.2962360

- Amount released by the State : Rs.4,04,100

- Amount spent by the District: Rs.3,94,494

- Permissible budget as per norm :  Rs.575000

- Budget for next financial year for the district as per action plan detailed below:Rs.2424616

| Program Challenges to be tackled by ACSM during the Year 2012 -2013 | WHY ACSM Objective | For WHOM Target Audience |  | WHAT ACSM Activities |  |  | When Time Frame |  |  |  |  | By WHOM | Monitoring and Evaluation |  | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Based on existing TB indicators and analysis of communication challenges (Maximum 3 Challenges ) | Desired behavior or action (make SMART: specific, measurable, achievable, realistic & time bound objectives) |  |  | Activities | Media/ Material Required |  | Q1 | Q2 | Q3 | Q4 |  | Key implementer and RNTCP officer responsible for supervision | Outputs; Evidence that the activities have been done | Outcomes: Evidence that it has been effective | Total expenditure for the activity during the financial year |
| Challenge 1. Low Case Detection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low Case Detection | Gaining Administrative support from Policy makers, Journalist | MLA’s Ministers District Magistrate/ DHS |  | 1.Sensitization meeting 2. Briefing meetings 3. Programme information 4. Factsheets | Publications -Posters-booklets/ brochure -poster in local language -Factsheets -success stories |  |  | X |  |  |  | 1. STO 2. APO (with support from WHO Consultant) 3. IECO 4. MO-DOTS Plus 5. DOTS Plus Site Committee | 1.Meeting Minutes 2.Photographs 3. Reports 4. Review meeting by the authorities | 1. Increase referral of chest symptomatic 2. Continuous Political commitment | Rs. 50,000 at state level Rs. 5000x7 districts = Rs. 35,000 |
| Communication Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low Case Detection | To inform communities and care providers about the DOT services for early detection Develop | 1General Public 2. Schools 3. Religious bodies 4. Care provider |  | Use of regional / cable channels | Booklet, Flip Book, Posters, Stickers, Banners, Pamphlet, Patient information booklet |  | X | X | X | X |  | - DTO 1. CMO 2. DTO 3. MO-TC | 1.Developed IPC Material 2. Flip books for STS and CFs 3. Wall writings 4. Stock Register | 1.Increase self reporting/ referral 2. Increase awareness level of general public. 3. Increase OPD Attendance and suspect cases | Cable@400 per day x 2cables x60days =Rs.48,000 DDK@3312x6 timesx3spot = Rs. 59,616 AIR@5000x 6monthsx 2 =60,000 School Quiz Competition@Rs. 25,000x7 = 1,75,000 For Aizawl =Rs. 50000 |
|  | Awareness Generation in general public | General Public, schools, |  | Hoarding on TB |  |  | X |  |  |  |  | CMO, DTO, MO-TC, IEC Officer | Visible Hoarding at DTC/MC and DOTS Plus Site Small Hoarding at Road site |  | 5nos. x @Rs.10000 Size – 8ftx6ft for state = Rs. 50,000 30nos@Rs.3000 for DTCs & MCs = Rs. 90,000 100nos@Rs.250 =Rs. 25,000 |
|  |  |  |  | News Paper Advertisement | Advertisement for news paper, Letter to NEWs Paper Editor. |  |  | X |  | X |  | DTO, Communication Facilitator, STS, IEC Officer, NGO Partners | NEWS paper Clippings |  | @Rs.1000x30 newspaper at state level = Rs. 30,000 @Rs.1000x10x7district newspaper at district level = Rs. 70,000 |
| Social Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low Case Detection | 1.Generate Awareness in general public 2. Encourage early self reporting 3. Community Groups. PRI | Community General Public, Patients, DOTs Providers |  | Community Meeting | Flip Chart and Posters, Talks |  | X | X | X | X |  | MO-TC, IEC Officer, Communication Facilitator | Minutes of Meetings Display of Posters Flip Chart | Increase OPD attendance and suspect cases | Meeting – 20nos.@Rs. 3000 at state level Total – 60,000 10nos x 7dist.@Rs. 3000 Total – 70,000 |
|  |  |  |  | Celebration of World TB day | Display Material for World TB Day |  |  |  |  |  |  | STO, MO-TC, MO, Communication Facilitator, IEC Officer | Documentation of l world TB Day activities | Pre- post evaluation of WTB Day activities with specific objectives | Rs.3,00,000 at state level @Rs.10000 each at 7 district = 70,000 @Rs. 5000x22DMC =Rs. 1,10,000 |
| Challenge 2: Lack of Awareness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lack of Awareness | 1. Sensitizing district authorities about the symptoms and diagnosis. | 1. District Magistrate, Village health Sanitation committee - STS |  | 1.Interaction Meetings 2. Use of Information Booklet | Audio Visual Adds -Posters-booklets/brochure -poster in local language -Factsheets -success stories |  |  | X |  |  |  | CMO, DTO MO, Communication Facilitator, IEC Officer | 1.Meeting Minutes 2.Photographs 3. Reports 4. Record of meetings | Increase sputum examination Increase OPD attendance and suspect cases | Rs. 2000x30nos. meeting. =Rs. 60,000 at the district level |
| Communication Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lack of Awareness | To increase awareness at the community level | Patients, Their Family Members, DOTs Providers |  | Sharing of experience of cured patients / Patients during Treatment. | Patient Provider interaction meetings & involvement of cured persons |  | X | X | X | X |  | MO, Communication Facilitator, IEC Officer | Records of meeting Evidence of material development – pre testing | Increase in diagnosis Increase in no. community based NGOs involvement Adherence of treatment | @Rs.1500x10x8dist. =Rs.1,20,000 |
|  |  | Community TB Groups / NGOs |  |  |  |  | X | X | X | X |  | MO-TC, STS, ANMs |  |  |  |
|  |  | One to one meeting with the patient |  | Interpersonal communication with patients | Patient information booklet |  | X | X | X | X |  | MO, STS, DOT Provider | Evidence of such meeting Patient information booklet | Complete treatment | Patient information booklet @10x5000 = Rs. 50,000 |
| Social Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lack of awareness | To increase awareness at the community level | Community TB Groups / NGOs |  | Sensitization meeting for different church members | programme fact sheet, Presentation |  | X | X | X | X |  | DTO, MO TC, CF, STS | Documentation, Records , Photographs | Increase in diagnosis | @Rs.2000x80 =Rs.1,60,000 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,42,616 |
| Communication Facilitator honorarium |  |  | 2nos. |  |  | Rs. 10,000x12monthsx2 |  |  |  |  | Total |  |  |  | 2,40,000 |
|  |  |  |  |  |  |  |  |  |  |  | Grand Total |  |  |  | 19,82,616 |

5. .Equipment Maintenance:

| Item | No. actually present in the State | Amount actually spent in the last 4 quarters | Amount Proposed for Maintenance during current financial yr. | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | lustification/ Remarks for (d) |
| --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) |
| ##### Computer ##### (Maintenance includes AMC, software and hardware upgrades, Printer Cartridges and Internet expenses) | ##### 9 | ##### 47516 | ##### 60000 | ##### 30,000 x 9 x 1.3 = 351000 | ##### Including maintenance for 8 districts and state |
| ##### Photocopier (includes AMC, toner etc) | ##### 9 | ##### - | ##### - | ##### 30,000 x 9 x 1.3 = 351000 | ##### For all 8 districts and state |
| ##### Fax | ##### 9 | ##### - | ##### - | ##### 30,000 x 9 x 1.3 = 351000 | ##### For all 8 districts and state |
| ##### OHP |  | ##### - | ##### - |  |  |
| ##### Binocular Microscopes (RNTCP) | ##### 40 | ##### - | ##### - | ##### 1500 x 40microscopes x 1.3 = 78000 | ##### For all binocular microscopes |
| ##### STDC/ IRL Equipment | ##### - | ##### - | ##### - |  |  |
| ##### Any other ( Please specify) Printer repairing | ##### 9 |  |  | ##### 2000 x 9 x 1.3 = 23400 | ##### For all 8 districts and state |
| ##### TOTAL |  | ##### 113475 | ##### 100000 | ##### Rs. 1154400 |  |

6. Training:

| Activity | No. in the State | No. already trained in RNTCP | No. planned to be trained in RNTCP during each quarter of next FY (c) |  |  |  | Expenditur e (in Rs) planned for current financial year | Estim ated Expen diture for the next financ ial year (Rs.) | Justifi cation / remar ks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | Qi | Q2 | Q3 | Q 4 | (d) | (e) | (f) |
| ##### Training of DTOs (at National level) | ##### 8 | ##### 8 | ##### 1 | ##### 1 | ##### 1 | ##### 1 |  | ##### 500000 | ##### TA/DA |
| ##### Training of Pharmacist | ##### 1 (New) | ##### - | ##### - | ##### 1 | ##### - | ##### - | ##### - | ##### 30000 | ##### TA/DA |
| ##### Training of MO-TCs (newly identified) (modular and DOT Plus) | ##### 8 | ##### 1 |  | ##### 1 |  |  |  | ##### 400000 | TA/DA including lunch, refreshment ,course organisation, honorarium for resource person, course material, and venue cost |
| ##### Training of MOs (Govt + Non-Govt) (Modular and DOTS Plus) | ##### 67 | ##### 27 (40 initial, 27 retraining) |  |  | ##### 1 |  | ##### 120000 | ##### 11,41600 | TA/DA including lunch, refreshment, course organisation, honorarium for resource person, course material and venue cost |
| Training of LTs of DMCs- Govt + Non Govt For DOTS PLUS. | ##### 79 |  | ##### 1 |  | ##### 1 |  | ##### 90000 | ##### 3,91200 | TA/DA including lunch, refreshment , course organisation, honorarium for resource person, course material and venue cost |
| ##### Training of MPWs |  |  |  |  |  |  | ##### 50000 |  | TA/DA inc TA/DA including lunch, refreshment and venue cost |
| ##### Training of MPHS, pharmacists, nursing staff, BEO etc |  |  |  |  |  |  |  |  | TA/DA including lunch, refreshment and venue cost |
| ##### STS/STLS DOTS Plus Training | ##### 18 | ##### 4 |  | ##### 1 |  |  |  | ##### 101500 | TA/DA including lunch, refreshment course organisation, honorarium for resource person, course material, and venue cost |
| ##### Training of Data Entry Operator | ##### 9 | ##### 9 |  | ##### 1 |  |  |  | ##### 90800 | TA/DA including lunch, refreshment course organisation, honorarium for resource person, course material, and venue cost |
| ##### TB/HIV Training of MO-TCs and MOs (newly recruit) | ##### 67 | ##### 0 |  | 1 | ##### Q3 | ##### Q4 |  | ##### 274500 | TA/DA including lunch, refreshment course organisation, honorarium for resource person, course material, and venue cost |
| ##### TB/HIV Training of DOTS Plus Supervisor | ##### 8 | ##### 0 | ##### Q1 | ##### Q2 1 | ##### Q3 | ##### Q4 |  | ##### 154600 | TA/DA including lunch, refreshment course organisation, honorarium for resource person, course material, and venue cost |
| ##### Provision for Update Training at Various Levels: ##### # STO Meeting ##### # DTOs/APOs/AO/IECO/DEO Review Meetings at State Level |  |  | 1 | 1 | 1 | 1 | 100000 1,00,000 Rs. 12,40,000/- | 3,00,000 2,00,000 1,00,000 Rs. 15,03,200 | TA/DA including lunch, refreshment course organisation, honorarium for resource person, course material, and venue cost |
| ##### Any Other Training Activity TOTAL |  |  |  |  |  |  |  |  |  |

Total of A	: Rs. 35,84,200/-

# Please specify	: Meeting/Training of STO, Asst. Programme Officer, Accounts Officer, IEC Officer, All Technical Staff for DOTS Plus etc.. At Central level.

  - Training : Distreict Lev el Training Plan

| ##### Activity | ##### No. in the state | ##### No. already trained in RNTCP | ##### No. planned to be trained in RNTCP during each quarter of next FY (c) |  |  |  | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### Q1 | ##### Q2 | ##### Q3 | ##### Q4 | ##### (d) | ##### (e) | ##### (f) |
| ##### Training of DTOs (at National level) |  |  |  |  |  |  |  |  |  |
| ##### Training of MO-TCs |  |  |  |  |  |  |  |  |  |
| ##### Training of MOs (Govt + Non-Govt) |  |  |  |  |  |  |  |  |  |
| ##### Training of LTs of DMCs- Govt + Non Govt |  |  |  |  |  |  |  |  |  |
| ##### Training of MPWs | ##### 1025 | ##### 760 | ##### 2 | ##### 2 | ##### 2 | ##### 2 | ##### - | ##### 2,43,120 | ##### 8 batches at district level for Rs.30390 per batch. |
| ##### Training of MPHS, pharmacists, nursing staff, BEO etc | ##### 500 | ##### 250 | ##### - | ##### 1 | ##### 1 | ##### - |  | ##### 60,000 | ##### 2 batches at district level for Rs.30,000 per batch for MPHS, Pharmacist. |
| ##### Training of Community Volunteers |  |  |  |  |  |  |  |  |  |
| ##### Training of Pvt Practitioners |  |  |  |  |  |  |  |  |  |
| ##### Other trainings # |  |  |  |  |  |  |  |  |  |
| ##### Re- training of MOs |  |  |  |  |  |  |  |  |  |
| ##### Re- Training of LTs of DMCs |  |  |  |  |  |  |  |  |  |
| ##### Re- Training of MPWs | ##### 1025 | ##### 760 | ##### 2 | ##### 2 | ##### 2 | ##### 2 |  | ##### 3,66,400 | ##### 8 batches at district level for Rs.45,800 per batch. |
| ##### Re- Training of MPHS, pharmacists, nursing staff, BEO |  |  |  |  |  |  |  |  |  |
| ##### Re- Training of CVs |  |  |  |  |  |  |  |  |  |
| ##### Re-training of Pvt Practitioners |  |  |  |  |  |  |  |  |  |

| ##### Activity | ##### No. in the state | ##### No. already trained in RNTCP | ##### No. planned to be trained in RNTCP during each quarter of next FY (c) |  |  |  | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | ##### Q1 | ##### Q2 | ##### Q3 | ##### Q4 |  |  |  |
| ##### TB/HIV Training of MO-TCs and MOs |  |  |  |  |  |  |  |  |  |
| ##### TB/HIV Training of STLS, LTs , MPWs, MPHS, Nursing Staff, Community Volunteers etc | ##### 2000 | ##### 60 | ##### 2 | ##### 2 | ##### 2 | ##### 2 | ##### - | ##### 1,73,400 | ##### 8 batches at district level for Rs.21,675 per batch. |
| ##### TB/HIV Training of STS |  |  |  |  |  |  |  |  |  |
| ##### Provision for Update Training at Various Levels # Review Meetings at State Level |  |  |  |  |  |  | Total of B | 8,42,920 | For state level For state level |
| ##### Any Other Training Activity TOTAL |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | ##### Grand Total of Training | ##### 44,27,120 |  |

7. Vehicle Maintenance

| Type of Vehicle | Number permissible as per the norms in the State | Number actually present | Amount spent on POL and Maintenance in the previous 4 quarters | Expenditure (inRs) planned for current financial year | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) | CO |
| ##### Four Wheelers | ##### 1 | ##### 1 | ##### 57053 | ##### 260000 | ##### 125000 x 9 x 1.3 = 1462500 | ##### Including 8 districts and state as per Norms. |
| ##### Two Wheelers | ##### 1 | ##### 1 | ##### - | ##### 32500 | ##### 30,000 x 9 x 1.3 = 507000 |  |
| ##### For DOT Plus Site Ambulance | ##### 1 | ##### 1 | ##### - | ##### - | ##### 125000X1.3= ##### 162500 |  |
| ##### TOTAL |  |  |  |  | ##### 21,32,000 |  |

8.         Vehicle Hiring*:

| Hiring of Four Wheeler | Number permissible as per the norms in the State | Number actually requiring hired vehicles | Amount spent in theprev 4qtrs | Expenditure (in Rs) planned for current financial year | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) | CO |
| ##### For STC/STDC |  |  | ##### Nil | ##### 1,50,000 | ##### 950 x7days x 12monthsx 1.3 x 1MO STC = 79800 | ##### Supervisory visits by MO-STCS |
| ##### For DTO |  |  |  | ##### - | ##### - |  |
| ##### For MO-TC | ##### 9 | ##### 9 | ##### Nil | ##### 150000 | ##### 950 x7days x 12monthsx 1.3 x 8 MOTCs = 829920 | ##### Supervisory visits of DTC by MO-TC. |
| ##### TOTAL |  |  |  |  | ##### 909720 |  |

Vehicle Hiring permissible only where RNTCP vehicles have not been provided

9.         NGO/PP Support:

NGO/PP Support: (New schemes w.e.f. 01-10-2008)

| Activity | No. of currently involved in RNTCP | Additional enrolment planned for this year | Amount spent in the previous 4 quarters | Expenditure (inRs) planned for current financial year | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) | (f) |
| ACSMScheme: TB advocacy, communication, and social mobilization | ##### - | ##### 8 | ##### - | ##### - | ##### 4,00,000 | ##### @Rs.50,000 is estimated for 8 districts. 1 NGOs each will be engage for ACSM in 8 districts. |
| SC Scheme: Sputum Collection Centre/s |  |  |  |  |  |  |
| Transport Scheme: Sputum Pick-Up and Transport Service | ##### - | ##### 8 | ##### - | ##### - | ##### 1,60,000 | ##### @Rs. 20,000 is estimated for 8 districts. Sumo/Pick up will be engage for sputum transportation in 8 districts. |
| DMC Scheme: Designated Microscopy Cum Treatment Centre (A&B) | ##### 2 |  | ##### 3,00,000 | ##### 3,00,000 | ##### 3 ,00,000 | ##### Presbyterian Hospital, Durtlang & ##### Serkawn Christian Hospital, Lunglei ##### (This was put under NGO involvement Scheme IV in the plan submitted to CTD)) |
| LT Scheme: Strengthening RNTCP diagnostic services |  |  |  |  |  |  |
| Culture and DST Scheme: Providing Quality Assured Culture and Drug Susceptibility Testing Services |  |  |  |  |  |  |
| Adherence scheme: Promoting treatment adherence |  |  |  |  |  |  |
| Slum Scheme: Improving TB control in Urban Slums |  |  |  |  |  |  |
| Tuberculosis Unit Model |  |  |  |  |  |  |
| TB-HIVScheme: Delivering TB-HIV interventions to high HIV Risk groups (HRGs) |  |  |  |  |  |  |
| ##### TOTAL |  |  |  |  | ##### 8,60,000 |  |

10.	Miscellaneous:

| ##### Activity* e.g. TA/DA, Stationary, etc | ##### Amount permissible as per the norms in the state | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
| ##### TA/DA | ##### - | ##### 4,00,657 | ##### 600000 | ##### 11,85,400 | ##### All Contractual Staff |
| ##### Phones Bills/internet etc.. | ##### - | ##### 2,60,000 | ##### 200000 | ##### 3,00,000 | ##### Phones Bills/internet etc..including DOTS Plus site |
| ##### Stationeries | ##### - | ##### 2,50,000 | ##### 50000 | ##### 2,52,600 | ##### Stationeries |
| ##### Audit Fees | ##### - | ##### 39,000 | ##### 50000 | ##### 45,000 | ##### Audit Fees |
| ##### Total |  | ##### 949657 | ##### 10,00,000 | ##### 178,30,00 |  |

* Please mention the main activities proposed to be met out through this head

* Please mention the main activities proposed to be met out through this head

11.       Contractual Services: (A)

| Category of Staff | No. permissible as per the norms in the State | No. actually present in the State | No. planned to be additionally hired during this year | Amount spent in the previous 4 quarters | Expenditure (inRs) planned for current Gn. year | Estimated Expenditure for the next financial year (Rs.) | Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) |  | (d) | (e) |  |
| ##### Asst.Programme Officer | ##### 1 | ##### 1 | ##### - | ##### NA | ##### 480000 | ##### 528000 | ##### 42000@12months plus 5%increment |
| ##### MO for DOTS Plus | ##### 1 | ##### 1 | ##### - | ##### NA | ##### 360000 | ##### 378000 | ##### 30000@12months plus 5%increment |
| ##### MO-STCS | ##### 1 | ##### 1 | ##### - | ##### NA | ##### 360000 | ##### 378000 | ##### 30000@12months plus 5%increment |
| ##### TB/HIV Coordinator | ##### 1 | ##### 0 | ##### 1 | ##### NA | ##### 420000 | ##### 441000 | ##### 35000@12months plus 5% increment |
| ##### State Accounts Officer | ##### 1 | ##### 1 | ##### - | ##### 216000 | ##### 226800 | ##### 237600 | ##### 18000@12 months plus 5%increment |
| ##### State IEC Officer | ##### 1 | ##### 1 | ##### - | ##### 216000 | ##### 226800 | ##### 237600 | ##### 18000@12 months plus 5%increment |
| ##### Pharmacist | ##### 1 | ##### 1 | ##### - | ##### 144000 | ##### 151200 | ##### 158400 | ##### 12000@12 months plus 5%increment |
| ##### Statistical Assistant for DOTS Plus | ##### 1 | ##### 1 |  | ##### - | ##### 180000 | ##### 189000 | ##### 15000@12 months plus 5%increment |
| ##### Secretarial Asst | ##### 1 | ##### 1 | ##### - | ##### 102000 | ##### 107100 | ##### 112200 | ##### 8500@12 months plus 5%increment |
| ##### Supervisor for DOTS Plus | ##### 1 | ##### 1 | ##### - | ##### - | ##### 180000 | ##### 189000 | ##### 15000@12 months plus 5%increment |
| ##### DEO | ##### 1 | ##### 1 | ##### - | ##### 120000 | ##### 126000 | ##### 132000 | ##### 10000@12 months plus 5%increment |
| ##### Store Assistant SDS | ##### 1 | ##### 1 |  | ##### 96000 | ##### 100800 | ##### 105600 | ##### 8000@12 months plus 5%increment |
| ##### Driver | ##### 1 | ##### 1 |  | ##### 84000 | ##### 88200 | ##### 92400 | ##### 7000@12 months plus 5%increment |
| ##### TOTAL |  |  |  |  |  | ##### Rs 3178800 |  |

- Districts Contractual Remuneration: Rs. 6426600

| Activity | No.required as per the norms in the district | Number actually present in the district | No.planned to be additionally hired during this year | Amount spent in the previous 4 quarters | Expenditure (In Rs.) planned for current financial year | Estimated expenditure for the next financial year for which plan is bing submitted (Rs.) | Justification /Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Medical Officer-Dot Plus | 1 | 1 | - | - | - | 3,60,000 | * One more TBHV to be required as per norm |
| STS | 9 | 9 | - | 15,33,600 | 15,33,600 | 15,98,400 |  |
| Stls | 9 | 9 | - | 15,33,600 | 15,33,600 | 15,98,400 |  |
| Tbhv | 2 | 1 | - | 1,03,200 | 1,03,200 | 1,10,400 |  |
| Dei | 8 | 8 | - | 8,97,600 | 8,97,600 | 9,38,400 |  |
| Accountant-Part Time | 8 | 8 | - | 3,16,800 | 3,16,800 | 3,31,200 |  |
| Contractual LT | 6 | 6 | - | 6,73,200 | 6,73,200 | 7,03,800 |  |
| Statistical Assistant-DOT Plus | 1 | 1 | - | - | - | 1,80,000 |  |
| Supervisor-DOT Plus | 8 | 8 | - | - | - | 14,40,000 |  |
| CF | 2 | 2 | - | - | - | - | CF salary from ACSM |
| Driver | 6 | 6 | - | 5,54,400 | 5,54,400 | 5,79,600 |  |
| MO-TC | 1 | 1 | - | 3,69,600 | 3,69,600 | 3,86,400 |  |
| TOTAL | 61 | 60 | - | 59,82,000 | 59,82,000 | 8226600 |  |

Grant Total of a+b (For Contractual remuneration)- 3178800+ 8226600

- Rs. 114,05,400 ( Total amount is increased from Rs.9392400 to Rs. 114,05,400  due to mis calculation in the plan already submitted to CTD

12. Printing

| Activity | Amount permissible as per the norms in the State | Amount spent in the previous 4 quarters | Expenditure (inRs) planned for current financial year | Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/ remarks |
| --- | --- | --- | --- | --- | --- |
|  | (a) | (b) | (c) | (d) | (e) |
| ##### Printing-State level:* Printed Items like Identity cards for DOTS, Non-DOTS,DOTS_plus,Training Modules, Mannual, Treatment Cards, Forms, Calendars etc.. |  | ##### 437000 | ##### 3,00,000 | ##### 6,00,000 | Printed Items like Identity cards for DOTS, Non-DOTS, DOTS Plus Training Modules, Mannual, Treatment Cards, Forms, Calendars etc.. |
| ##### Printing- Dist. Level:* | ##### - | ##### - | ##### - | ##### - | ##### - |
|  | ##### Total |  |  | ##### 600000 |  |

13. Research and studies (excluding OR in Medical Colleges)

Any Operational Research Projects planned (Yes/No) : Yes

Estimated Total Budget = Rs.8,00,000

14. Medical Colleges

| Activity | Amount permissible as per norms | Estimated Expenditure for the next financial year (Rs.) | Justification/Remarks |
| --- | --- | --- | --- |
|  | (a) | (b) | (c) |
| Contractual Staff : - MO-Medical College (Total approved in____ State ) - STLS in Medical Colleges (Total no in __ State) - LT for Medical College (Total no in State__) |  |  |  |
| Research and Studies : - Thesis of PG Students - Operations Research * |  |  |  |
| Travel Expenses for attending STF/ZTF/NTF meetings |  |  |  |
| IEC : Meetings and CME Planned |  |  |  |
| Equipment Maintenance at Nodal centres |  |  |  |

15. Procurement of Vehicles :

| Equipment | No. actually present in the state | No.planned for procurement this year (only if permissible as per norms) | Estimated expenditure for the next financial year for which plan is being submitted (Rs.) | Justification/Remarks |
| --- | --- | --- | --- | --- |
|  | (a) | (b) | © | (d) |
| 4-wheeler ** | 9 | - | - | - |
| 2-wheeler | 10 | - | - | - |

** Only if authorized in writing by Central TB Division

16.	Procurement of Equipment

| ##### Equipment | ##### No. actually present in the state | ##### No. planned for this year (only as per norms) | ##### Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) |
| ##### Office Equipment (Computer, modem, scanner, printer, UPS etc.) | ##### - | ##### 2 computer sets for Dots plus Site & SDS 1 computer set with internet connection for State TB Cell 1 printer 3 office tables 2 steel almirah 1 UPS 1 AC & installation 3 office chair 1 dozen plastic chair Racks Falcon tubes Procurement of packaging materials Procurement of Thermocol Boxes | ##### 60,000 45000 7,000 24,000 30,000 7,000 45,000 21,000 12,000 50,000 20,000 26,73,000 15,000 | ##### 2 computers x 30,000 I computer Rs 30000x15,000internet connection 1 printers x 7000 3 tables x 8000 2 almirah x 15,000 1 ups x 7,000 1 AC x 45,000 3 chair x 7,000 12 nos x 1000 For DOTS Plus Site at state level. Drugs store at DOTS-Plus Site |

| ##### Any Other – Air Conditioner, Hydrothermometer | ##### 0 | ##### 9 | ##### 376000 | ##### Planned by districts level For purchasing Air conditioner for each drugs store. |
| --- | --- | --- | --- | --- |
| ##### Mask (N95) |  |  | ##### 90000 | ##### For DOTS-Plus Site |
| ##### Dressing Materials Syringes (different sizes) Sterile gloves (different sizes) Glove powder |  |  | Rs. 50,000 Rs.45000 Rs 40000 Rs.50 x 10 kgs = Rs.500 |  |
| ##### Hospital Furniture’s & Appliances Waste Management |  | ##### Bedside locker 16”x14”x32” Instrument table 30”x2”x32” Removable stretcher or Trolley 213Lx56Wx81H cms Instrument Cabinet 58”x24”x12” Footstep Double Revolving stool 18”x27”(Adjustible) Oxygen cylinder Trolley Instrument Sterilizers(Electrically operated0 17”x8”x6” Chart holder113Wx4” l Portable autoclave Single Drum(Electric) 300mm Dx300mmH Dressing Drum Stainless Steel 8”x5” 13”x10”+ Sterilant Disposable sputum mug for DOTS Plus patients Spit Toon Bed Pan etc Dustbin with garbage bags | ##### 2000x10=20000 7000x2=14000 6500x3=19500 12000x2=24000 1500x10=15000 1000x3=3000 900x2=1800 5500x1=5500 500x10=5000 5500x1=5500 500x2=1000 2500x2=5000 60000 Rs10x500=5000 Rs100x20=2000 50000 Rs 60,000 |  |
| Fire Extinguisher (CO2) |  | ##### Fire Extinguisher (CO2) 9 nos. | ##### 9 Nos x Rs.9000 = Rs.81,000 ##### (For Purchase) 9 Nos x Rs.4500 = Rs. 40,500 (for Maintanence) 12.5% VAT = Rs.15,188 | ##### 9 Nos of Fire Extinguishers is required for each districts drugs store including Dots Plus Site. |
| Electric Generator(Diesel engine) |  |  | ##### Rs 2,00,000 | ##### For State Drug Store and DOTS Plus Site |
| ##### Xerox machine |  |  | ##### Rs 75,000 | ##### For State TB Cell,The existing Xerox machine is 8yrs and needs replacement. |
| ##### Laptop computer |  |  | ##### Rs 25,000x9=225000 | ##### For State TB Cell & 8 Districts for Review Meeting & Community Meeting |
| ##### Water Storage |  |  | ##### Rs 50,000 | ##### For DOTS-Plus Site |
| ##### Disinfectants & Sterillants |  |  | ##### Rs 30,000 | ##### For DOTS Plus Site |
| ##### Projector |  |  | ##### Rs 70000x9x1.3=819000 | ##### For State TB Cell & 8 Districts,for awareness campaign , training & review meeting. |
|  |  | ##### Total | ##### 6969988 |  |

Section D: Summary of proposed budget for the State -

| Category of Expenditure | Budget estimate for the coming FY 2012 - 2013 (To be based on the planned activities and expenditure in Section C) |
| --- | --- |
| - Civil works | 21,47,210 |
| 2. Laboratory materials | 12,95,000 |
| 3. Honorarium | 48,61,218 |
| 4. IEC/ Publicity | 19,82,616 |
| 5. Equipment maintenance | 11,54,400 |
| 6. Training | 44,27,120 |
| 7. Vehicle maintenance | 21,32,000 |
| 8. Vehicle hiring | 9,09,720 |
| 9. NGO/PP support | 8,60,000 |
| 10. Miscellaneous | 17,83,000 |
| 11. Contractual services | 11405400 |
| 12. Printing | 6,00,000 |
| 13. Research and studies | 8,00,000 |
| 14. Medical Colleges | - |
| 15. Procurement -vehicles | - |
| 16. Procurement - equipment | 69,69,988 |
| TOTAL | 413,27,672 |

Additionality Funds from NRHM-Details of the activities with justification for which Additionality Funds are proposed to be sought.

D. 7 NATIONAL PROGRAMME FOR PREVENTION AND CONTROL OF FLUOROSIS (NPPCF)

There is no information on the prevalence of fluorosis in Mizoram even after extensive search for literature. The lone river sample analysed by the state Public Health Laboratory of Public Health Engineering Department, Mizoram,  indicated that the level is within acceptable limit (assessed by Cell Test using Spectroquant –Nova 60, 2011).With the increasing consumption of carbonated drinks, fluoridated tooth pastes and several other commercial products containing fluoride,  and the increasing dependence on ground water  during non-monsoon seasons, the state Health & Family Welfare  Department welcomes the initiative of the Government of India by launching NPPCF. Implementation of the programme in Mizoram is expected to highlight the need for undertaking the programme further or otherwise in the state.

The NPPCF Programme shall be implemented in the state of Mizoram for the first time as Pilot Projects in Aizawl West District which has urban, semi-urban and rural population. The component-wise break-up for implementation of this Pilot Project is given in the table below.

BUDGET PROPOSAL FOR HUMAN RESOURCE FOR PILOT PROJECT UNDER NPPCF,MIZORAM: 2012-2013

| Sl. No. | HUMAN RESOURCE |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Activity | Unit Cost (in Rupees) | Physical Target | Amount proposed for the District Rs in Lakhs | Remarks |
| 1.2 | Consultant* | Rs35,000/- per month | 1 (One) | 4.2 | For 12 months *MBBS with PG in public health background desirable |
| 1.3 | Field Investigator (FI) | Rs 12,000/- per month | 1 (Three) | 2.16 | For 6 (Six) months |
| 1.4 | Laboratory Technician (LT) | Rs 10,000/-per month | 1(One) | 1.8 | For 6 (Six)months |
| 1.5 | Data Entry Operator (DEO) | Rs 8,000/- per month for6 (six) months | 1(One) | 0.48 | 2 (Two) months for each district |
| 2 | OPERATIONAL COST |  |  |  |  |
| 2.1 | District Laboratory Equipments (Non-recurring) | Rs7.0Lakhs per district | 1 (One District) | 7.0 |  |
| 2.2 | Laboratory consumables (Recurring) | Rs2.4Lakhs per district | For 1 District | 2.4 |  |
| 2.3 | Training for- i) Programme Officer (1) ii) Consultant (1) iii) Field Investigators (3) iv) Laboratory Technician (1) |  | For 6 (Six) Programme staff | 4.5 | Training at reputed National Institute recommended by MoHFW, New Delhi |
| 2.4 | District Level Training of medical and Para-medical staff | Rs3.0Lakhs per district | 1 (One) | 3.0 |  |
| 2.4 | One Co-ordination Meeting at district level* | Rs1.0Lakh | 1 (One) | 1.0 | *Professor/Scientist from reputed institute (AIIH&PH/GMC/RIMS,etc.) to preside over the meeting |
| 2.5 | Mobility support for Consultant and Field Investigators | Rs4.0Lakhs per district |  | 4.0 |  |
| 2.6 | Medical management of Fluorosis cases including treatment, surgery, rehabilitation | Rs 5.0Lakhs | 1 (One) District | 5.0 |  |
| 2.7 | Health Education and Publicity | Rs3.5Lakh per district | 3(Three) | 3.5 |  |
| 2.8 | Format Printing and Report Publication | Rs 1.0Lakh |  | 1.0 |  |
|  |  |  | Total | 40.04 |  |

(Rupees Forty Lakhs and Four Thousand Only)

D.8 Oral Health

- INTRODUCTION :

‘Oral Health’ is an integral part of general health. With increasing life expectancy, Oral Health is bound to play a major role in improving the quality of life. The prevalence of oral diseases, such as Dental caries, Periodontitis (diseases of the gum), Mal-occlusion and Oral cancer, are very high in Mizoram. Mal-occlusion of teeth is common among 50% of school children. Oral Cancer accounts for almost 40% of the total diagnosed cancer cases and the wide usage of tobacco in various forms attributes to 90% of all oral cancers.

‘Oral Health’  means being free of Chronic mouth and facial pain,  oral and throat cancer, oral sores, birth defects such as cleft lip and cleft palate, periodontal (gum) diseases, tooth decay and tooth loss and other diseases and disorders that effect the mouth and oral cavity.

Incidence of oral cancer ranges from 1 to 10 cases per 1,00,000 population in most countries; 40 to 50% of people who are HIV Positive have oral fungal, oral bacterial or oral viral infections which often occur early in the course of HIV infection; 5 – 10 % of public health expenditure relates to oral health in developed countries and by using preventive strategies, the high cost of dental treatment can be avoided.

The activities of the World Health Organization (WHO) span advocacy, prevention and treatment of oral diseases and WHO gives technical support for countries that are integrating ‘Oral Health’ into their public health system.

Oral Health Programme has never been implemented in the state. It used to be the most neglected part of all Health & Family Welfare Department activities. It is estimated that nearly 90% of the state’s population is suffering from one or the other dental disease. And it is noticed that this alarming rise in dental diseases is mainly due to the lack of awareness among the indigenous people and the almost non – existence infrastructure of the Oral Health Care Services in the State.

The reality is that in the society of the Mizo’s, uses of tobacco were not associated with taboos, as such there used to be high usage of Tobacco in the State. With the passing of time and the societies coming to know more about the harmful effects from the substances used in tobacco, people have come to know the felt need for Oral Health more than ever. Therefore, it is envisaged that the State Government in convergence with the National Rural Health Mission (NRHM) will intervene in full scale at all levels by strengthening the systems of the state. And it is advised that the State will take up activities and programmes relating to Oral Health in at least 2(two) Districts of the State, as a part of the Programme Implementation Plan under National Rural Health Mission.

- PRESENT STATUS : At present there are 47(forty seven) Government Dental Surgeons in Mizoram, among which 5(five) have been promoted to Senior Dental Surgeons

- The District Hospitals where Dental Surgeons have been posted are :-

- Aizawl Civil Hospital – Aizawl being the State Capital, it has 2 (two) hospitals attached to it, namely Kulikawn Hospital and Referral Hospital, Falkawn where dental Surgeons are also posted.

- Lunglei Civil Hospital – It is the second biggest District Hospital.

- Saiha Civil Hospital

- Lawngtlai Hospital

- Champhai Hospital

- Serchhip Hospital

- Kolasib Hospital

- Mamit Hospital

- The Community Health Centres (CHCs) where Dental Surgeons have been posted are :-

- Kawrthah		vii)	Ngopa		xiii)	Chawngte Sub-Dist. Hospital

- Chawngte		viii)	Thingsulthliah

- Sakawrdai		ix)	Thenzawl

- Khawzawl		x)	Hnahthial Sub-Dist. Hospital

- Biate			xi)	Saitual Sub-District Hospital

- Lengpui			xii)	Vairengte

[NB : Total number of CHCs in the State is 12.]

- Sub – Divisional Hospital where Dental Surgeon had been posted is :

- Tlabung

- The Primary Health Centres (PHCs) where Dental Surgeons have been posted are :

- Tuipang			vi)	Reiek

- North Vanlaiphai	vii)	Aibawk

- West Phaileng		viii)	Sairang

- Darlawn

- Haulawng

[NB : Total number of PHCs in the State is 57.]

Among the Dental Surgeons, some were posted where any Dental Surgeon had never been posted before. In some of the Dental Surgeon posting places, the Dental Chair and its unit or any other Dental Equipments had never been supplied before and even if supplied they were in-completely given and are by now non-functioning and getting rusted and all of them need replenishment or replacement.

In order to propagate and implement Oral Health in the State, one Senior Dental Surgeons (who is the senior most in the Dental Surgeons sub-cadre of the Mizoram Health Services Rules, 2009) has been posted as Programme Officer (Oral Health) in the Directorate of Hospital & Medical Education, Health & Family Welfare Department, Government of Mizoram under NRHM by way of attachment; which will be re-designated to Deputy Director (Oral Health) who will monitor all Oral Health activities and programmes in the State. In order to provide quality Oral Health Care, it is essential that the Central Government provide recurring grant as the State Government’s resources are limited. Information, Education and Communication (IEC) is very much essential to impart awareness to the public. As such sufficient funds may kindly be provided so as to create Oral Health awareness among the rural people as well as the urban people. IEC Activities will include Posters, banners and handout displayed at Hospitals, CHCs, PHCs and Strategic public places. Traditional ways of creating public awareness and training manuals made available for Dental Surgeons, Nurses and Health Workers & ASHA and providing need-based & short term training for awareness, disease identification, pain relief & referrel to Nurses/Health Workers & ASHA.

- Budgetary Requirement : Initially, 2(two) districts are selected to implement the programme on pilot basis within the financial year and extend it to other districts in the subsequent years after gaining experience from the implementing districts. Aizawl and Lunglei are selected as the initial districts to implement the Oral Health Programme in the State. To monitor and implement the programme in the districts, it is proposed to create a post of District Oral Health Programme Officer in each of the 2(two) districts under the supervision of the State Oral Health Programme Officer.

| COMPONENTS | BUDGET (INR in lakhs) |
| --- | --- |
| - Renumeration of Regular Staff & Contractual Staff | 22.38 lakhs/year |
| - Strengthening of Dental Department in Civil Hospital, Aizawl | 73.00 lakhs |
| - Strengthening of District Hospitals | 242.00 lakhs |
| - Training of Health Work-Force in Oral Health Programme | 36.00 lakhs/year |
| - IEC, School Oral Health Promotion & Community Outreach Programme | 34.00 lakhs/year |
| - State Oral Health Programme Set-Up [Office Equipments and Transportation (conveyance)] | 31.38 lakhs |
| TOTAL | Rs. 438.76 lakhs/year |

- Renumeration of Regular Staff & Contractual Staff :-

- Regular Staff	–

| Sl. No. | Name of Post | No. of Post | Scale of Pay (in Rupees) | Amount (in Rupees) |
| --- | --- | --- | --- | --- |
| 1 | State Oral Health Programme Officer [NB : Now, a Programme Officer (Oral Health) to be re-designated as Deputy Director (Oral Health) | 1 No. | Will continue with present pay |  |
| 2 | District Oral Health Programme Officer [NB : Aizawl and Lunglei are selected as the initial districts to implement the programme. The District Programme Officers are to be appointed on the basis of seniority from the Dental Surgeon sub-cadre of Mizoram Health Service Rules, 2009 in each District] | 2 Nos. | Will continue with present pay |  |

- Contractual Staff		–

| Sl. No. | Name of Post | No. of Post | Scale of Pay (in Rupees) | Amount (in Rupees) |
| --- | --- | --- | --- | --- |
| 1 | Dental Surgeon (One each in Aizawl District and Lunglei District) | 2 Nos. | 25,000/- (fixed0 p.m. | 6,00,000/- p.a. |
| 2 | Dental Nurse | 2 Nos. | 6500 + 50% RM = 9750/- p.m. | 2,34,000/- p.a. |
| 3 | Dental Technician | 2 Nos. | 6500 + 50% RM = 9750/- p.m. | 2,34,000/- p.a. |
| 4 | UDC (Accountant) | 1 No. | 6500 + 50% RM = 9750/- p.m. | 1,17,000/- p.a. |
| 5 | LDC (Cashier) | 1No. | 6500 + 50% RM = 9750/- p.m. | 1,17,000/- p.a. |
| 6 | LDC (one each in Aizawl District & Lunglei District) | 2 Nos. | 5500 + 50% RM = 8250/- | 1,98,000/- p.a. |
| 7 | Data Entry Operator (one each in Aizawl District & Lunglei District) | 2 Nos. | 5500 + 50% RM = 8250/- p.m. | 1,98,000/- p.a. |
| 8 | Driver | 2 Nos. | 5000 + 50% RM = 7500/- p.m. | 1,80,000/- p.a. |
| 9 | Peon | 4 Nos. | 4000 + 50% RM = 6000/- p.m. | 2,88,000/- p.a. |
| 10 | DAK Runner | 1 No. | 4000 + 50% RM = 6000/- p.m. | 72,000/- p.a. |
|  | TOTAL | 19 Nos. |  | 22,38,000/- p.a. |

- Strengthening of Dental Department in Civil Hospital, Aizawl in Mizoram.

(Operation Theatre (OT) & Dental Ward in the Civil Hospital, Aizawl):-

The Dental – out – patient (outdoor) Department started functioning since 1975 with the then two working Doctors – Dr. Sharma & Dr. Sinha. In 1979 the first Bachelor of Dental surgery (BDS) among the Mizos, Dr. Lalzarliana Ralte (L) had replaced them.

At present, the average daily dental patients attendance is 100 at the Dental – OPD in the Civil Hospital, Aizawl which is the largest and most advanced hospital in the State. Referred dental patients are coming from all corners of the State and the serious ones need prompt and utmost care that can be done only under general Anaesthesia (GA) in Operation theatre (OT).  Along with the usual routine of the OPD the patients who need treatments in the OT are looked after simultaneously by sharing ENT dept. OT & Ortho – dept. OT which causes untold miseries to the poor patients. The working Sr. Dental Surgeons and Dental Surgeons here comprise of 2 (two) Oral – Maxillo – Facial Surgeons, 1 (one) orthodontist, 1 (one) Periodontist  and 1 (one) Endodontist and 3 (three) general Dental Surgeons, for all these working as a team, a separate & distinct operation theatre (OT) is a must and badly needed. The proposed Dental operation theatre (OT) must be having an attached Dental ward having at least 4 (four) beds and it is anticipated that the re-arrangement of the existing OTs here will give just enough space for the Dental operation theatre (OT) & Dental ward to squeeze in, for the betterment and complete treatment of all kinds of Dental surgeries.

OPERATION THEATRE (OT) FOR DENTAL DEPARTMENT

CIVIL HOSPITAL, AIZAWL

EQUIPMENTS REQUIRED :-

| Sl. No. | Name of the equipment with specification | Approx cost |
| --- | --- | --- |
| 1. | Air Conditioner (AC) | `. 50,000/- |
| 2. | OT Table (for patient) | `. 2,50,000/- |
| 3. | OT Trolley – 3 Nos. (for patient) | `. 60,000/- @ x 3 i.e `. 180,000/- |
| 4. | OT Drums (different sizes) | `. 50,000/- |
| 5. | OT Lightning System | `. 3,00,000/- |
| 6. | Diathermy Machine | `. 6,00,000/- |
| 7. | Anaesthesia Machine & Accessories | `. 5,00,000/- |
| 8. | Patient Trolley | `. 10,000/- |
| 9. | Laryngoscopes Set i) Adult – 2 Nos. ii) Paediatric – 2 Nos. | `. 10,000/- @ x 4 `. 40,000/- |
| 10. | OT Trays (different sizes) | `. 20,000/- |
| 11. | Suction Machine – 2 Nos. | `. 60,000/- @ x 2 i.e `. 1,20,000/- |
| 12. | Forceps & Light Surgical Instruments | `. 1,00,000/- |
| 13. | Chair & Table (for Doctros) | `. 20,000/- |
| 14. | Steel Almirah – 2 Nos. | `. 20,000/- @ x 2 i.e `. 40,000/- |
| 15. | Miscellaneous : OT Linen, etc. | ` 20,000/- |
| 16. | Dental Ward construction, Electric fitting, water & air fitting & furniture etc. | ` 50,00,000/- |
|  | TOTAL | ` 73,00,000/- |

- Strengthening of District Hospitals :-

The 8(eight) District Hospitals are Saiha, Lawngtlai, Lunglei, Serchhip, Champhai, Mamit, Kolasib, Aizawl including Kulikawn Hospital and Referral Hospital, Falkawn in Aizawl District.

| Upgradation, Equipment and Consumables : |  |  |
| --- | --- | --- |
| Items | Rates | Expenditure in lakhs |
| Room Renovation, Electric refitting, Water & Air refitting & Furniture | @ 10 x 10.0 | ` 100.00 |
| Dental chair with adequate accessories | @ 10 x 3.5 | ` 35.00 |
| Autoclave | @ 10 x 1.0 | ` 10.00 |
| Ultrasonic scaler | @ 10 x 1.5 | ` 15.00 |
| Dental X-Ray Unit with Developer | @ 10 x 1.7 | ` 17.00 |
| Light cure gun | @ 10 x 1.0 | ` 10.00 |
| Extraction Forceps | @ 10 x 1.0 | ` 10.00 |
| Restorative (filling) Instruments | @ 10 x 1.5 | ` 15.00 |
| Root Canal Instrument Set | @ 10 x 1.5 | ` 15.00 |
| Consumable Dental Material, Instruments, Repair, contingencies | @ 10 x 1.5 | ` 15.00 |
| TOTAL |  | ` 242.00 |

- Training of Health Work-Force in Oral Health Programme :-

| Training of Oral Health Manpower | Rates (in lakhs) | Rupees (in lakhs) | REMARKS |
| --- | --- | --- | --- |
| Training of Health Workers at PHC/CHC (Rs. 10,000 per training x 10 training sessions/year) | 18 PHC/CHC/ Sub. Div. Hqrs. x @ 1.0 | 18.0 | Training to happen at the 12 CHCs, 1 Sub-Divisional Hqrs. & 5 PHCs |
| Training and Continuing Dental Education of Dental Surgeons in Civil Hospital, Aizawl/year (Travel/Stay/Other logistics) | 18 PHC/CHC/ Sub. Div. Hqrs. x @ 1.0 | 18.0 | 12 CHCs 1 Sub. Div. Hqrs. 5 PHCs 18 Dental Surgeons are to be trained yearly |
| TOTAL |  | 36.00 lakhs |  |

- IEC, School Oral Health Promotion and Community Out Reach Programme :-

These are 497 Schools in Aizawl district and 164 Schools in Lunglei District. It is ideal to reach out all the schools and conduct health programmes but considering the strength of the manpower, 200 schools will be targeted for awareness in the initial year.

| School Oral Health Promotion and Community Out Reach Program |  | Rs. (in lakhs) | Remarks |
| --- | --- | --- | --- |
| Awareness program in Schools | Rates |  |  |
| Screening of school children for oro-dental problems | Rs. 1000 per school x 200 | 2.0 |  |
| No. of schools in which awareness could be promoted and screening performed | Rough estimates; 200 schools x 1000 = 2.0 lakhs | 2.0 |  |
| Involvement of NGO’s/CBO’s |  |  |  |
| Organizing camps for awareness and screening or Oral Dental Diseases | Rs. 5000 per camp |  | 100 camps will be the target for the initial two districts as people have difficulties accessing places because of the terrain and sparse nature of population. |
| Hiring Dental Surgeons for support in camps |  |  |  |
| - Dental Surgeon x Rs. 500 per day |  |  |  |
| - Nurse x Rs. 300 per day |  |  |  |
| - Assistant x Rs. 200 per day |  |  |  |
| Consumables for providing dental treatment of basic dental problems like extraction, restoration and hand scaling | Rs. 4000 per camps |  |  |
| No. of camps to be organized and awareness at schools can be decided on the actual population in that district | 100 camps x 10,000 = 2.0 lakhs | 10.00 |  |
| Community awareness – IEC Activities – Hoardings, Banners, Posters, Booklets, Leaflets, Radio & Local TV Cable Networks, Press, Short songs etc. | Rs. 20.00 lakhs/year | 20.00 |  |
| Total |  | 34.00 lakhs |  |

- State Oral Health Programme Set – Up [Office Equipments & Transportation (conveyance)] :-

| A | OFFICE EQUIPMENTS |  |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | Name of Equipment | No. of Post | Rate ( in Rupees ) | Amount ( in Rupees ) |
| 1 | Executive Table (T-104) | 3 nos. | 14,556/- | 43,668/- |
| 2 | Executive Chair (PCH 500IT) | 3 nos. | 6,258/- | 18,774/- |
| 3 | Visitor’s Chairs (CH 1018) | 11 nos. | 2,184/- | 24,024/- |
| 4 | T-8 Table | 8 nos. | 7,206/- | 57,648/- |
| 5 | Almirah (Small) Locker | 9 nos. | 10,546/- | 94,914/- |
| 6 | Bookcase (4 door) | 3 nos. | 15,759/- | 47,277/- |
| 7 | Officer chair (CH 7B) | 4 nos. | 2,287/- | 9,148/- |
| 8 | Revolving Chair (PCH 41031) | 3 nos. | 3,583/- | 10,749/- |
| 9 | Computer Complete Set | 3 nos. | 30,000/- | 90,000/- |
| 10 | Laptop Computer | 3 nos. | 33,400/- | 1,00,200/- |
| 11 | Top Glass | 11 nos. | 700/- | 7,700/- |
| 12 | Internet facilities | 1 no. | As per company rate |  |
| 13 | Telephone connection | 2 nos. | As per company rate |  |
| 14 | Wall Clock | 4 nos. | 300/- | 1,200/- |
| 15 | Water Filter | 4 nos. | 1,500/- | 6,000/- |
| 16 | Refrigerator/Medicine Storage (220 ltr.) | 2 nos. | 14,250/- | 28,500/- |
| 17 | Photo Copier | 2 nos. | 80,000/- | 1,60,000/- |
| 18 | Air Conditioner | 1 no. | 50,000/- | 50,000/- |
| 19 | Office Stationery |  |  | 5,00,000/- pa |
| 20 | Office Contingencies (Tour etc. Seminar etc.) |  |  | 5,00,000/- pa |
|  | TOTAL |  |  | 16,79,796/- pa |
| B | TRANSPORTATION |  |  |  |
| 1 | BOLERO CAR ( LX 4WD 7STR PS BS – 11 ) | 1 no. | 6,41,752/- | 6,41,752/- |
| 2 | Bike for Despatch of DAK | 1 no. | 50,000/- | 50,000/- |
| 3 | TATA WINGER (13 + 1 STD ) | 1 no. | 5,50,881/- | 5,50,881/- |
| 4 | POL (for vehicles) | Sufficient | 1,50,000/- | 1,50,000/- pa |
| 5 | Annual Maintenance cost of vehicles | 3 vehicles | 1,25,000/- | 1,25,000/- |
|  | TOTAL |  |  | 15,17,633/- |
|  | Sub TOTAL |  |  | 31,37,429/- |

D9. Mizoram State Health Care Scheme

PROGRAMME IMPLEMENTATION PLAN FOR STATE INNOVATION UNDER NRHM-HEALTH INSURANCE SCHEMES IN MIZORAM :- 2012-2013

- INTRODUCTION:

Various activities and programmes under NRHM have been generating quite a welcome change and improvements in Health Care delivery in Mizoram. Conditions of hospitals, CHC, PHC have improved through RKS; working condition of Health Care Staffs have seen commendable changes and community participation have reached an all time high and general health-related awareness have also risen. But in spite of all these, optimum Health Care delivery and access still  eluded large number of the population due to the endemic poverty among certain sections of the Society as the costs of treatment continue to soar resulting in rising out-of-pocket expenditure on the part of the patients. And this resulted in low level of quality treatment that can be accessed by these populace. The vulnerability of the poor informal workers increases when they have to pay fully for their medical care with no subsidy or support. On the one hand, such a worker does not have the financial resources to bear the cost of medical treatment and at the same time the health infrastructure too, leaves a lot to be desired. Large proportions of people, especially below poverty line still, borrow money or sell assets to pay for the treatment in private hospitals.

Thus, Health Insurance can be the best way of removing the financial barriers and improving access to quality medical care; of providing financial protection against high medical expenses; and negotiating with the Providers for better quality care and to incentivize creation of health related infrastructures, both in the public and private domain.

The Government of Mizoram has, accordingly formulated a Health Insurance Scheme called the Mizoram State Health Care Scheme (MSHCS) for implementation in all districts of the State in 2008. This need had also a reason as a result of feedback from district health functionaries. A State Nodal Agency - Mizoram State Health Care Society was thus formed. The Scheme covers hospitalization expenses and selected Day Care procedures.

In order to operate the Scheme professionally in a cost effective manner, public private partnership was envisaged between the Insurance Company, the Private Sector Hospitals and the State Agencies. State Government/Nodal Agency will assist the Insurance Company in  establishing  network of  hospitals, fixing of  treatment protocol  and  costs,  treatment authorization, claims scrutiny and  any other related work, such  that  the cost of administering  the Scheme  is kept at the lowest, while  making full use of the  resources available  in the  Government/Private Health System. Private hospitals fulfilling minimum qualifications in terms of availability of inpatient medical beds, laboratory, equipments, operation theatres, etc. and a track record in the treatment of the specified diseases can be enlisted for providing treatment to the families under the Scheme.

The first year of implementation of the Scheme was initiated from April, 2008. The whole population of Mizoram, excluding Government Servants and their dependants were included and the Scheme had a sum insured of Rs. 1 lakh and an additional amount of Rs. 2 lakhs for identified critical illness (Annexure-I), making the total cover at Rs. 3 lakhs.

Also, apart from the State Health Care Scheme, the Society has been implementing Rashtriya Swasthya Bima Yojana (RSBY), a Union Ministry of Labour & Employment Programme since September, 2010.

- MIZORAM STATE HEALTH CARE SCHEME & RSBY: As mentioned above, since 2010-2011, the Society has been actively implementing both MSHCS & RSBY, with the Government of Mizoram dove-tailing both the Schemes. As of now, RSBY covers only Below Poverty Line (BPL) families, where they are entitled to use upto Rs. 30,000/- for their hospitalization after contributing Rs. 30/- only as Registration Fee and Smart Card cost.

MSHCS, on the other hand, covers Above Poverty Line (APL) families who are not otherwise eligible for Medical Attendance Rules of Government of Mizoram. Under this Scheme the beneficiaries can claim their medical expenses for a set of Critical Illnesses defined by the Society (Annexure-I) The Premium payable and the respective Sum-insured is as follows:

| APL (Sum Insured) | Premium upto 5 members | >5 members additional premium |
| --- | --- | --- |
| Rs. 1 lakh | Rs. 500/- | Rs. 100 per person |
| Rs. 2 lakh | Rs. 750/- | Rs. 200 per person |
| Rs. 3 lakh | Rs. 1,000/- | Rs. 300 per person |

The State Government has also decided to include RSBY beneficiaries under MSHCS without having to pay any additional premium with insurance cover upto Rs. 70,000/- for their ongoing illness and Rs. 2.7 lakhs for critical illness, over and above the sum insured of Rs. 30,000/- under RSBY, thus making the total sum-insured upto Rs. 3 lakhs.

The period of insurance is for one year.

- MODES OF DELIVERY: RSBY, a centrally sponsored programme is implemented along the lines of definite guidelines and directives given by Union Ministry of Labour & Employment. Where the Society selected a reputed Insurance Company as ‘Insurer’. And the Insurer, in turn hires Third Party Administrator (TPA) and Smart Card Vendors. The Scheme follows totally cashless transactions and the respective hospitalization bills are directly settled by the Insurer. The State Government contributes 10% of the premium as a State share, per annum.

Till, last year, MSHCS too, was delivered through Insurance Company where delay of payments from them was the main stumbling block in the smooth implementation of the Scheme. But, from September, 2011 the Government of Mizoram has decided to implement the Scheme through Self-financing basis where the Society shall directly receive, scrutinize, process and make the necessary payments.

- STAFFS UNDER MIZORAM STATE HEALTH CARE SOCIETY: The following are the Current Staff position of the Society:

| Sl. No. | Designation | Number | Status | Pay Source |
| --- | --- | --- | --- | --- |
| 1. | CEO | 1 | Contract | MSHCS |
| 2. | Dy CEO (Medical) | 1 | Regular | DHS |
| 3. | OSD/SMO | 1 | Regular (Deputation) | Civil Hospital |
| 4. | Medical Officer | 1 | Contract | NRHM |
| 5. | Assistant | 1 | Regular | DHME |
| 6. | LDC | 1 | Regular | DHME |
| 7. | Sub Inspector of Statistics | 1 | Contract | DHME |
| 8. | Accounts Clerk | 1 | Contract | NRHM |
| 9. | Computer Operator | 1 | Contract | DHME |
| 10. | IVth Grade | 1 | Regular | DHME |
| 11. | IVth Grade | 1 | Contract | DHME |
| 12. | Claim Supervisor | 1 | Contract | MSHCS |
| 13. | Data Manager | 1 | Contract | MSHCS |
| 14. | Accounts Clerk | 1 | Contract | MSHCS |
| 15. | Claim Processor | 5 | Contract | MSHCS |
| 16. | Data Entry Operator(District) | 9 | Contract | MSHCS |
| 17. | Medical Officer | 1 | Contract | MSHCS |
| 18. | IVth Grade | 1 | Contract | MSHCS |
| Total |  | 30 |  |  |

- BENEFICIARIES AND ENROLMENT STATUS : MSHCS and RSBY now cover the entire Districts of Mizoram. The Enrolment/Beneficiaries status are as follows:

2008-2009 = 125732 Families.

2009-2010 = Suspended temporarily.

2010-2011 = BPL- 28245, APL- 11940, RSBY- 18129.

2011-2012 = Ongoing, to be completed by end of January, 2012.

- FUND SOURCES: At the time of inception of the Society (2008), Government of Mizoram had earmarked Rs. 50 crore only for the establishment, administrative costs, claim settlement (premium given to Insurance Company) and implementation of the Mizoram State Health Care Scheme. Since that time (three fiscals), the Society has been running with that amount without any additional funds till now. Though RSBY is a centrally-initiated Scheme, no funds whatsoever are received from the concerned Ministry (MoLE) for administrative costs or any other expenses incurred in its implementation. In fact, the Society has been bearing the State share (10% of total premium) to be given to the Insurance Company. And also the Society has been bearing substantial sum in helping out the Insurance Company in IEC, Capacity Building measures and Enrolment processes.

Now, for the implementation of Mizoram State Health Care Scheme from the year 2011-2012, a Corpus Fund of Rs. 117.8 crore has been received from Asian Development Bank (ADB) with a catch, where the Society can utilize only the interest accrued from the Corpus Fund investments. And this Fund is solely for settlement of Insurance Claims and not for other purposes. The entire corpus and interests are controlled by Finance Department, Government of Mizoram.

Another source is the Premium collected from the beneficiaries which as may be apparent in Sl. No. II, does not even cover half of the Claims received.

In nutshell the funds that are available to the Society is grossly inadequate to run the Scheme smoothly.

- REQUIREMENTS:

  - STAFF REMUNERATION:

As mentioned above, the fund that is available is grossly inadequate for the smooth operation of the Scheme. The Staffs under contract of the Society are being given remuneration equivalent to other NRHM Staffs and they are:

| Sl. No. | Designation | No. of Posts | Remuneration per month (Rs) | Remuneration per year (Rs) |
| --- | --- | --- | --- | --- |
| 1. | Chief Executive Officer | 1 | 45,000/- | 5,40,000/- |
| 2. | Medical Officer | 2 | 40,000/- | 9,60,000/- |
| 3. | Claim Supervisor | 1 | 25,000/- | 3,00,000/- |
| 4. | Data Manager | 1 | 25,000/- | 3,00,000/- |
| 5. | Accounts Clerk | 1 | 16,000/- | 1,92,000/- |
| 4. | Claim Processor | 5 | 12,000/- | 7,20,000/- |
| 5. | Data Entry Operator | 9 | 12,000/- | 12,96,000/- |
| 6. | IVth Grade | 1 | 8,000/- | 96,000/- |
| Total per annum |  |  |  | Rs. 44,04,000/- |
| (Rupees fourty four lakhs four thousand only). |  |  |  |  |

  - IEC/CAPACITY BUILDING/WORKSHOPS etc., :

As with all Programmes, these Health Insurance Schemes also need to be extensively publicised and mass awareness campaigns need to be undertaken. So far, several actions have already been carried out and many more are being planned for the coming fiscal too. These would include village campaigns to be undertaken in all revenue villages at least twice a year for 2012-13. Further, Public Notice through audio, visual and print media; radio and television jingles, short play, street play, live TV and telephone interview, hoardings, display, banner, dialogue, advertisements through Electronic and Print Media and distribution of Information leaflets/booklets, etc.

Various Staffs at District and Village level are also needed to be apprised of the Scheme in general and for that extensive and thorough Capacity Building workshops and Trainings are required. So, District Workshops involving the Deputy Commissioners, Block Development Officers, Medical Officers, Health Workers, ANMs, Village Panchayat, NGOs and Grass-root Workers have been conducted and more are being planned for the coming years as well.

And one of our main focuses is to spread awareness extensively throughout each village in Mizoram. This will be undertaken in consultation with each Village Council Court and the sensitization and awareness camps/visits shall be done twice i.e., March and September, 2012.

The tentative requirements for above is as under:

| Sl. No. | Particulars | Amount | Total |
| --- | --- | --- | --- |
| I | TRAINING |  |  |
| a) | Trainer’s training for CMO’s and SMO’s at Headquarter |  |  |
|  | Hall rent | Rs. 1,500.00 | Rs. 60,000.00 |
|  | Banner | Rs. 1,500.00 |  |
|  | Training materials | Rs. 12,000.00 |  |
|  | Resource persons@1,200/- x 5 persons | Rs. 6,000.00 |  |
|  | D.A for 30 persons @ 1,000/- | Rs. 30,000.00 |  |
|  | Refreshment for 30 persons @100/- | Rs. 3,000.00 |  |
|  | Miscellaneous | Rs. 6,000.00 |  |
| b) | Trainer’s training for MO’s/MPW’s for each district i.e 9 District |  |  |
|  | Hall rent | Rs. 1,500.00 | 9 x 1,30,000.00 Rs. 11,70,000.00 |
|  | Banner | Rs. 1,500.00 |  |
|  | Training materials | Rs. 10,000.00 |  |
|  | Resource persons for 5 persons @1,000/- | Rs. 5,000.00 |  |
|  | D.A for MO’s @ 500/- x 50 | Rs. 25,000.00 |  |
|  | D.A for MPW’s @ 200/- x 50 | Rs. 10,000.00 |  |
|  | Refreshment for 100 persons | Rs. 10,000.00 |  |
|  | Hiring charge of Vehicle | Rs. 12,000.00 |  |
|  | TA for MO’s/MPW | Rs. 50,000.00 |  |
|  | Miscellaneous | Rs. 5,000.00 |  |
|  |  | Rs. 1,30,000.00 |  |
| c) | Training on Health Care Scheme & RSBY for NGO’s and Prominent Citizens for 9 Dist. |  |  |
|  | Hall rent | Rs. 1,500.00 | 9 x 67,000.00 Rs. 6,03,000.00 |
|  | Banner | Rs. 1,500.00 |  |
|  | Training materials | Rs. 12,000.00 |  |
|  | Resource persons for 5 persons @1,000/- | Rs. 5,000.00 |  |
|  | D.A @ 200/- x 100 | Rs. 20,000.00 |  |
|  | Refreshment for 100 persons | Rs. 10,000.00 |  |
|  | Hiring charge of Vehicle | Rs. 12,000.00 |  |
|  | Miscellaneous | Rs. 5,000.00 |  |
|  |  | Rs. 67,000.00 |  |
| II | Hoarding 4’x5’ Flex Steel/Aluminum frame RSBY & MSHCS @ 6,000/- x 100 nos. |  |  |
| 1 | Aizawl-Lunglei(WB Rd.)=20 | Rs. 6,000.00 | 6,000 x 100 Rs. 6,00,000.00 |
| 2 | Aizawl-Champhai-Zokhawthar-10 |  |  |
| 3 | Aizawl-Mamit-Kanhmun-10 |  |  |
| 4 | Aizawl-Vairengte=10 |  |  |
| 5 | Aizawl-Lungdai-Kawnpui=5 |  |  |
| 6 | Aizawl-Serchhip-Lunglei=10 |  |  |
| 7 | Aizawl-Seling-Sakawrdai=5 |  |  |
| 8 | Aizawl-Kawlkulh-Ngopa=10 |  |  |
| 9 | Lunglei-Saiha=10 |  |  |
| 10 | Lunglei -Chawngte-Tlabung=10 |  |  |
| III | POSTER | Rs. 250.00 | 250 x 500 Rs. 1,25,000.00 |
|  | 2’x4’ Flexboard @ Rs. 250/- x 500 nos. |  |  |
|  | Health Sub-Center - 370 |  |  |
|  | Health Clinic - 51 |  |  |
|  | Hospital - 10 |  |  |
|  | CHC - 12 |  |  |
|  | PHC - 57 |  |  |
| IV | Booklet @ 5/- x 1,00,000 |  | Rs. 5,00,000.00 |
| V | Press Advertisement 10 (ten) newspaper Full page display @ Rs.2,500/- |  | Rs. 25,000.00 |
| VI | TV/RADIO Spots |  |  |
|  | DDK @ 551.5 per 10 secs = 60secs | Rs. 3309.00 | Rs. 3,00,000.00 |
|  | AIR @ 340 per 10 secs = 60secs | Rs. 1350.00 |  |
|  | LPS @ 400 per spot | Rs. 400.00 |  |
|  | Zonet @ 300 per spot | Rs. 300.00 |  |
| VII | Awareness visit to each Village Council twice in a year. Rs. 3,000/- for each visit for 817 villages | Rs. 49,02,000.00 | Rs. 49,02,000.00 |
| G.TOTAL |  |  | Rs. 82,85,000.00 |
| (Rupees eighty two lakhs and eighty five thousand only). |  |  |  |

Grand Total of Requirements: Rs. 1,26,89,000/- (Rupees one crore twenty six lakhs eighty nine thousand) only.

- CONCLUSION: As apparent from above, NRHM Innovation programme regarding Health Insurance, though it is in its nascent Stage in Mizoram, efforts are laboriously being undertaken by the State Health Care Society and the response from the general public is also quite welcoming. And with the clubbing of State Health Care Scheme and RSBY we believe Health Insurance as it is, will soon be one of the most productive innovations under NRHM in Mizoram. As shown in Annexure I, the set of Critical Illness has also been increased year after year implying more and more disease covered and more benefits to the beneficiaries.

As the beneficiaries of the Schemes are mainly treated in the existing State Goverments’ hospitals set-up, fund flow to the District Hospital, CHC, PHC from the Society and Insurance Company is quite substantial. This directly or indirectly benefits these Hospitals and in-turn RKS; and that really helps in infrastructural developments of these Health Institutions. And also as members of the public who were otherwise ineligible for Medical Claims can now avail full medical benefit by insuring in the above Schemes which in-turn considerably help improve the Public Health in general.

Mizoram State Health Care Scheme, as it is (sum insured upto Rs. 3 lakhs), we believe, is probably the first of its kind in the country and if the requirements highlighted above are met with Health Care Delivery and benefits in Mizoram shall be greatly enhanced.

D10.  District Mental Health Programme

District Mental Health Programme

Introduction

Mental health is as important as any other aspect of life, realizing this WHO has not forgotten to mention this while defining health, which is as follows “Health is a state of complete Physical, MENTAL and social wellbeing and not merely the absence of disease or infirmity,” here we realize that the mental aspect is a totally separate entity and as important as physical and social wellbeing. However it is with a heavy heart that we bring forward the fact that in a very literate state like Mizoram, mental health has not received the same importance as the other dimensions even in the field of health, leave alone other aspects of life. Hence it is due to this reason that our society is paying a heavy price.

The younger generation who is considered the future of a society is under the grip of many a mental and behavioural problem, like alcoholism, drug addiction, truancy, sexual perversions/ promiscuity and due to this, an increase is seen in the recent past in many related diseases like HIV/AIDS, HCV HbsAg, STDs, other social problems like divorces/separations, school dropouts, etc have also sprung up due to the same reason.

A family is the basic unit of any society, however our younger generation doesn’t seems to think so... they do not seem to mind a trial and error even in their own individual lives, marriages/ eloping followed by separation/ divorces are a common place in almost every corner which again lead to feeling of guilt and depression. Even extreme behaviour like suicide is on the rise. Sadly even though many of us are aware of this, hardly anything is being done to rid of the problems and improve the situation.

In order to meet the needs and requirement for the stated problems, the central government implemented National Mental Health Programme (NMHP) to cover all the states. Programme in the state is run district wise (DMHP). And in Mizoram the programme has been running in Aizawl district since 1999 and in Lunglei district since 2006.

KOLASIB DISTRICT:

BACKGROUND

In the State of Mizoram, there used to be only three administrative districts after the Mizoram attained statehood in 1986 – Aizawl, Lunglei, Chhimtuipui.

During the later part of the 1990s, the Government of Mizoram decided to have eight administrative districts for the State instead of three. Hence new districts are established from the existing three districts. The new districts carved out of Aizawl District are Kolasib, Mamit, and Champhai Districts. At present we have nine Districts under Health Department which are: - Aizawl ‘E’. Aizawl ‘W’,  Lunglei, Lawngtlai. Serchhip, Saiha, Mamit, Kolasib and Champhai.

Kolasib is situated on the northern end part of the state with a geographical area of 1383.15 sq. Kms contributing 7% total area in the state. The District sharing its boundary with Cachar District of Assam in the Northern and Western Side, Aizawl District and Mamit District in the Eastern, Western And Southern side. The distance from State Capital (Aizawl) is 90 kms towards North and it is 3 hours drive from the State Capital. The District has a population of 77,208  (as on 1st April 2009 District population survey) with a decadal growth rate of 36 spreading over a population density of 44 per sq.kms and the literacy rate of the District is 90.01%. Christianity is the major Religion of the District and Mizo is the languages spoken by the major population.

# A  Geography and Climate

The District is mainly hilly, but it is not high altitude. Because of this we have hot and humid climate which basically leads to diseases like Malaria, Diarrhoea and Typhoid etc. The District has 4 important rivers – Tuirial, Chemlui, Tuichhuahen, Tlawng & Serlui. There are two important Hydel Projects, Tuirial Hydel Project & Serlui Hydel Project under construction. The only Railway Station of the State is situated within the District communicating Assam at Bairabi.

The District is the most potential area for agriculture and bamboo processing Industries. National Highway No 54 is running through the District communicating neighbouring State Assam and the Capital of the District. Because of the heavy rainfall, hilly region and National Highway a natural calamities and disaster like land slide, traffic accident always happened for which Accident Trauma Centre construction has been finished at Kolasib District on Dec.2007, with Central Funding.

Thermal Power Project also established at Bairabi where the Rail Head is located and it is functioning and operating which the insufficiency of power supply for the State is much supported. There are regular Bus and Sumo service to the State Capital and neighbouring State, Assam. In medical emergencies, people have to rely on air services to Guwahati and Kolkata.

B. Map of Kolasib district

# C. Demographic profile

The Demographic Profile of the District is mentioned below:

# Demographic profile

# Source: NRHM Monthly Report & District population survey 2009

| Indicators | District | State |
| --- | --- | --- |
| Population | 77,208 | 8,88,573 |
| Males | 39,556 | 459109 |
| Female | 37,652 | 429464 |
| Total | 77,208 | 8,88,573 |
| Population Density | 44 | 42 |
| Urban | Nil | 49.6 |
| Rural | 77,208 | 50.4 |
| Scheduled Castes | 6177 (8%) | 272 |
| Scheduled Tribes | 71031(92%) | 831390 |
| Languages | Mizo | Mizo |
| Religions | Christian | Christian |
| Children (0-5 years) | 9137 (11.8%) | 143734 |
| Adolescents (12-19 years) | 16675 (21.6%) | 195486 |
| Women (14-45 years) | 6581 (8.6%) | 159943 |
| Population Below Poverty Line (BPL) | 10809 (14%) | 22% |
| Population growth rate (1991-2001) | 35.2% | 28.8% |
| Vital statistics |  |  |
| Crude Birth Rate | 24 | 26% |
| Crude Death Rate | 4 | 4.97 |
| Sex Ratio |  |  |
| Overall | 36.57/37.65 | 935/1000 |
| Literacy | - | - |
| Literacy among Males | 90% | 90.97% |
| Literacy among Females | 90% | 86.67% |
| Total | 97.4% | 88.82% |

The male-female ratio in the district is almost 50-50 and the literacy rate among males is also almost similar to females. The literacy rate of females in the district is lower than the male. Adolescents constitute 7.5 % of the population whereas around 8 % of the population are women in the reproductive age group. On the other hand, both birth rate and death rate is higher in the district as compared to the state. All the population in the district is rural, which means, as per the standard norms of health institutions, there is a requirement of 22 Sub Centres and around 4 PHCs but the Government permitted the District to have 29 Sub-Centres with 4 S/C clinics, 5 PHC, one CHC and one District Hospital due to difficult area and hilly terrain to make accessible to the Health Centres by the public from the interior villages.

The population of Kolasib District is the mixture of Mizo, Bru, and Hmar and Gorkhas communities. The common people used jhum cultivation as the source of living and 14% of the people are living under poverty line.

# D. Administrative profile

The District Headquarter Kolasib which is 90 kms from the State Capital, Aizawl. Details of the Administrative Profile are discussed in the table below.

# Administrative Profile

| Administrative levels | Number |
| --- | --- |
| Assembly constituencies (no.) | 3 |
| Number of Blocks (RD Blocks) | 2 |
| Number of Village Council | 48 |
| Number of villages | 53 |
| Number of villages with population below 500 | 13 |
| Number of villages with population 501 – 2000 | 27 |
| Number of villages with population 2001 – 5000 | 11 |
| Number of villages with 5000+ population | 2 |

Source : District population survey 2009-10

There are 3 MLAs in the District which means there are three sources of MLA LADs Fund which can be used for procuring Ambulances, renovation of Hospitals, donation to RKS.etc. The District Hospital Kolasib has Hospital Biological waste management i.e. “INCINERATOR”, completed construction at 2007 under central funding.

SITUATION ANALYSIS

Public Health Infrastructure

Facility:

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No of Beds | Occupancy Rates | OPD Attendance |  |
| District Hospital | 58 | 60% | 107/day | OPD, Indoor, STD Clinic, PP Unit (MCH), X-Ray, all Lab. Test: Sputum test, (except Culture, Thyroid etc). Blood storage facilities, HIV/AIDS/ VCCTC & PPTCT Surgery, Gynae, Dental. |
| CHC | 30 | 65% | 38/day | OPD, Indoor, X-Ray, Lab Test, (Sputum test, Blood RE, Stool RE) |
| PHC | 10 | 55% | 33-48/day | OPD, Indoor, X-Ray(2 out of 5 PHC), Lab. Services (blood MP & RE, Stool RE, and Urine RE.) |
| Sub-Centres | - | - | 9/day | Immunization, RCH (ANC Clinic), DDT spray, Blood MP, home visit, Health Education, Post natal Care etc. |

The District Hospital is upgraded from a CHC and therefore has less than 100 beds. It is also seen that the bed occupancy is similar across the facilities, with even the PHCs providing in-patient care.

The above table also shows that there is no facility of diagnostic tests. On the other hand some of the PHCs have X-ray facilities. The OPD load also seems to be very low in different institution due to lack of infrastructure facilities.

Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric social worker and psychiatric nurse.

# Health Workforce

# A description of the staff sanctioned in place in the district is given in the table below.

| S.No. | Staff Position | In-Position |  | Vacant |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
|  | Chief Medical Officer | 1 | - |  |
|  | Medical Superintendent – DH | 0 | - |  |
|  | Senior Medical Officer including Specialists | 5 | - |  |
|  | Gynaecologist | 1 | - |  |
|  | Paediatrician | 0 | - |  |
|  | Anaesthetist | 1 | - |  |
|  | Surgeon | 0 | - |  |
|  | Medical Officer - General Grade (from AYUSH also) | 10 | 2 |  |
|  | Medical Officer - General Grade - Female | 4 |  |  |
|  | District TB Officer | 1 | - |  |
|  | X-ray Technician | 3 | 3 |  |
|  | Staff Nurse | 30 | 19 |  |
|  | Chief Pharmacist/Pharmacist | 7 | 1 |  |
|  | Lab Technician/Senior LT | 4 | 9 |  |
|  | BCG team Leader | - | - |  |
|  | BCG Technician | - | - |  |
|  | Eye Assistant | 2 | 1 |  |
|  | Occupational Therapist | 1 | - |  |
|  | Physiotherapist | - | - |  |
|  | Health Educator | 1 | 1 |  |
|  | Dental Hygienist/ Dental Surgeon | 3 | - |  |
|  | Chief Clerk | - | - |  |
|  | Statistical Assistant/ | - | 1 |  |
|  | Senior Assistant | - | - |  |
|  | Senior Clerk | - | - |  |
|  | Computer Operator | - | 3 |  |
|  | Stenographer | - | - |  |
|  | Public Health Nurse | - | - |  |
|  | Drug Inspector | 1 | - |  |
|  | Store keeper cum Clerk | - | - |  |
|  | Malaria Inspector/ Sr. Maleria Inspector | - | - |  |
|  | Health Education Officer | - | - |  |
|  | Health Supervisor | 12 | - |  |
|  | LHV | - | - |  |
|  | ANM/FHW | 19 | 22 |  |
|  | MPW/HW(M) | 18 | 11 |  |
|  | Refrigerator Mechanic | - | - |  |
|  | Electrician | - | - |  |
|  | Refrigerator Assistant | - | - |  |
|  | ECG Technician | - | - |  |
|  | O.T Technician | - | - |  |
|  | Projectionist | - | - |  |
|  | Driver | 8 | 7 |  |
|  | Class IV staff | 54 | 1 |  |
|  | Sweeper | 6 | - |  |

As per the above table, the number of positions sanctioned for each staff categories not known; hence, the number of vacancies cannot be determined. On the other hand, it can be seen that there is one Gynaecologist, Medicine, Anaesthetist and 2 two Dental Surgeon. In addition, there are 50 FHWs (20 contract) and 34 HW (M) (13 contract) for 29 Sub Centres and 4 Sub – Centre clinics; six X-ray technicians for 2 PHCs and 1 CHC and DH each where there are X-ray facilities. It is important to note that refrigerator technician was absence of which the maintenance of cold chain equipment might be a problem. Also, the district has no doctor for general surgeon.

The table also shows that all the institution are lack in manpower and infrastructure facilities, the doctors, specialist and general medical practitioner, Here we can see that, there are no mental health professionals (i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse) and other health staff are not pointed much at the different institution as compare to the needs and population of the District as well as to achieve the IPHS norms/standard.

DMHP plan for 2012 -2013; Kolasib District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary as per Annexure II | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Kolasib district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme: Mamit

Map of Mamit District

BACKGROUND

The District is located in the North-Western part of the State of Mizoram with the District headquarter Mamit situated at a height of 901 metres above sea level. Mamit, one of the new districts was established during the 1990s from the then Aizawl West District. It ranks the fourth largest district in the state and is the sixth most populated (62725) district in the state.

The district of Mamit is bordered by Cachar district of Assam on the north, Lunglei, Aizawl West & Kolasib districts on the southern front and by the state of Tripura and the country of Bangladesh on the West.

The district of Mamit is 104Km from the capital Aizawl, and it is about 3.5 hours away from the capital by road. The means of communication are cars & buses. The population is a mix of Christians (84.3%) who constitute the majority followed by the Buddist (4%) and the Muslims (1.8%). The language by majority of the population is Mizo.

Administrative profile

| Administrative levels | Description/Number |
| --- | --- |
| District headquarter | Mamit |
| Parliamentary constituencies (no.) | - |
| Assembly constituencies (no.) | 3 |
| Number of Blocks (CD Blocks) | 3 |
| Number of Village Council (Panchayat) | 58 |
| Number of villages : | 72 |
| Number of villages with population below 300 | 19 |
| Number of villages with population 301 - 500 | 16 |
| Number of villages with population 501 - 1000 | 21 |
| Number of villages with population 1001 - 2000 | 9 |
| Number of villages with population 2001 - 5000 | 6 |
| Number of villages with more than 5000 | 1 |

As it is indicated in the table above, there are 72 villages. Majority of the villages    (i.e. 55) are having Village council and the remaining villages (i.e. 17) does not have Village Council. The number of villages having population less than 300 is 19 which is 26.38% of the District. No. of villages with population ranging between 501 – 1000 is 21 (i.e. 29%) which is the highest in the district and there is only one village having population more than 5000.

Geography and Climate

- Topography: the district remains spread across mountains as well as plains.

- River: Tut is the only major river that flows through the district and is a major source of sand used in constructions. The river water however, is not used as a source of drinking water as it is very dirty.

- Rainfall: the usual rainy season ranges between May to September while the rest of the year is practically dry leading to acute scarcity of drinking water. This is one of the reasons behind rain water harvesting during the rainy seasons to ensure supply of drinking water for extended periods of time.

- Crops: Rice, Maize, papaya, pumpkin, oranges etc.

- Disaster / natural calamities: frequent landslides are the biggest problem, forest fires and the occasional storms which at times destroy entire villages.

- Road connectivity and accessibility (both overall and seasonal): during the rainy season, the accessibility of Sub Centres becomes difficult and a few of them become totally inaccessible.

- public transport system available: Road transport

Demographic profile

| Indicators | District | State |
| --- | --- | --- |
| Population |  |  |
| Male | 31038 | 459109 |
| Female | 28720 | 429464 |
| Total | 59758 | 888573 |
| Population Density | 21/sq km | 42/sq km |
| Urban | - | 441006 |
| Rural | All rural | 447567 |
| Scheduled Castes | 0.04% |  |
| Scheduled Tribes | 99.96% |  |
| Languages | Mizo | Mizo |
| Religions |  |  |
| Christianity | 84.3 % |  |
| Muslim | 1.8 % |  |
| Hindu | 4 % |  |
| Children 0 -1 yr | 1788 |  |
| Children (0-5 years) | 11024 | 143734 |
| Adolescents (12-19 years) | 6474 |  |
| No. of Below Poverty Line (BPL) families | 2547 |  |
| No. of houses | 11945 |  |
| Vital statistics |  |  |
| Crude Birth Rate | 24.2% | 21.47% |
| Crude Death Rate | 5.1 % | 4.97% |
| Sex Ratio |  |  |
| Overall | 896 | 935 |
| Child | 937 |  |
| Literacy(2001 Census) |  |  |
| Literacy among Males | 85% | 52.93 |
| Literacy among Females | 72% | 47.07% |
| Total | 79% | 88.8% |

The district of Mamit accounts for 7.05% of the population of Mizoram with a population density of just half (21/sq km) that for the state (42/sq km). Contrary to that for the state, where almost half of the population is urban, the district of Mamit has a totally rural population. The overall sex ratio for the district is lower at 896 compared to that for the state. On the literacy front, though the male literacy rate is better than the state average, the female literacy rates as far lower at just 21%. An increase

| DISTRIBUTION OF POPULATION UNDER HEALTH INSTITUTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Block: Zawlnuam Block |  |  |  |  |  |
| Main Centre | Sub-Centre | Village Covered | Population |  |  |
|  |  |  | Male | Female | TOTAL |
| MAMIT M/C | Mamit S/C | Mamit | 3146 | 3055 | 6201 |
|  |  | Phaizau | 175 | 180 | 355 |
|  | Darlak S/C | Darlak | 462 | 435 | 897 |
|  |  | Bawngva | 280 | 321 | 601 |
|  | Nalzawl S/C | Nalzawl | 206 | 221 | 427 |
|  | Sabual S/C | Sabual | 118 | 101 | 219 |
|  |  | Tlangkhang | 74 | 71 | 145 |
|  |  | Pathiantlang | 85 | 78 | 163 |
|  |  | Chilui | 48 | 47 | 95 |
|  | Damdiai S/C | Damdiai | 86 | 97 | 183 |
|  | Dampui S/C | Dampui | 350 | 321 | 671 |
| TOTAL | 6 | 11 | 5030 | 4927 | 9957 |
| ZAWLNUAM M/C | Zawlnuam S/C | Zawlnuam | 578 | 619 | 1197 |
|  |  | Thuampui | 481 | 484 | 965 |
|  |  | Zawlpui | 175 | 185 | 360 |
|  | Bawrai S/C | Bawrai | 424 | 417 | 841 |
|  | Bungthuam S/C | Bungthuam | 382 | 366 | 748 |
| TOTAL | 3 | 5 | 2040 | 2071 | 4111 |
| KANHMUN M/C | Kanhmun S/C | Kanhmun | 890 | 948 | 1838 |
|  |  | Luimawi | 220 | 198 | 418 |
|  | Thinghlun S/C | Thinghlun | 335 | 336 | 671 |
| TOTAL | 2 | 3 | 1445 | 1482 | 2927 |
| KAWRTETHAW VENG M/C | Kawrtethawveng S/C | Kawrtethawveng | 769 | 808 | 1577 |
|  |  | Mualthuam | 228 | 215 | 443 |
|  | Tuidam S/C | Tuidam | 906 | 832 | 1738 |
|  |  | Tumpanglui | 98 | 89 | 187 |
|  | New Eden S/C | New Eden | 69 | 74 | 143 |
|  | Bunghmun S/C | Bunghmun | 301 | 285 | 586 |
|  |  | Serhmun | 287 | 252 | 539 |
|  |  | Thaidawr | 248 | 213 | 461 |
| TOTAL | 4 | 8 | 2906 | 2768 | 5674 |
| KAWRTHAH M/C | Kawrthah S/C | Kawrthah | 1410 | 1540 | 2950 |
|  |  | Sarali | 136 | 76 | 212 |
|  | Rengdil S/C | Rengdil | 967 | 935 | 1902 |
|  |  | Sihthiang | 138 | 91 | 229 |
|  | Zamuang S/C | Zamuang | 531 | 514 | 1045 |
|  | Hriphaw S/C | Hriphaw | 378 | 391 | 769 |
| TOTAL | 4 | 6 | 3560 | 3547 | 7107 |

| NAME OF BLOCK : W.PHAILENG |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Main Centre |  | Sub-Centre |  | Village Covered | Population |  |  |
|  |  |  |  |  | Male | Female | TOTAL |
| W.PHAILENG M/C |  | W.Phaileng S/C |  | W.Phaileng | 2174 | 2136 | 4310 |
|  |  |  |  | Phaileng Dinthar | 984 | 837 | 1821 |
|  |  |  |  | Teirei Forest | 168 | 158 | 326 |
|  |  |  |  | Salem Boarding | 57 | 53 | 110 |
|  |  | Lallen S/C |  | Lallen | 427 | 422 | 849 |
|  |  |  |  | Saithah | 192 | 182 | 374 |
|  |  |  |  | Chhippui | 122 | 99 | 221 |
|  |  |  |  | Kawnmawi | 309 | 292 | 601 |
|  |  | Tuipuibari S/C |  | Tuipuibari | 765 | 823 | 1588 |
|  |  |  |  | Tuipuibari I | 88 | 64 | 152 |
|  |  |  |  | Tuipuibari II | 1418 | 1395 | 2813 |
|  |  |  |  | Andermanik | 461 | 481 | 942 |
|  |  |  |  | Belkhai | 206 | 196 | 402 |
|  |  |  |  | Zomuantlang | 140 | 173 | 313 |
|  |  |  |  | Khantlang | 253 | 237 | 490 |
|  |  | Damparengpui S/C |  | Damparengpui | 1084 | 1003 | 2087 |
|  |  |  |  | Tuirum | 288 | 234 | 522 |
|  |  |  |  | Khawhnai | 182 | 159 | 341 |
| TOTAL |  | 4 |  | 18 | 9318 | 8944 | 18262 |
| PHULDUNGSEI M/C |  | Phuldungsei S/C |  | Phuldungsei | 275 | 267 | 542 |
|  |  |  |  | Phulbial | 222 | 206 | 428 |
|  |  |  |  | Chaltui | 90 | 80 | 170 |
|  |  |  |  | Vengthar | 243 | 234 | 477 |
|  |  |  |  | Ramrikawn | 44 | 53 | 97 |
|  |  | Pukzing S/C |  | Pukzing | 205 | 239 | 444 |
|  |  |  |  | Phulpui | 311 | 245 | 556 |
|  |  |  |  | Vengthar | 153 | 129 | 282 |
|  |  | Parvatui S/C |  | Parvatui | 199 | 162 | 361 |
| TOTAL |  | 3 |  | 9 | 1742 | 1615 | 3357 |
| MARPARA M/C |  | Marpara S/C |  | Marpara S | 1378 | 1232 | 2610 |
|  |  |  |  | Marpara N | 1039 | 964 | 2003 |
|  |  |  |  | Marpara Mizoveng | 203 | 165 | 368 |
|  |  |  |  | Hruiduk | 410 | 400 | 810 |
|  |  |  |  | Eringsuri | 80 | 75 | 155 |
|  |  | Silsuri S/C |  | Silsuri | 1517 | 1345 | 2862 |
|  |  |  |  | Hnahva | 525 | 465 | 990 |
|  |  |  |  | Indroramsora | 152 | 150 | 302 |
| TOTAL |  | 2 |  | 8 | 5304 | 4796 | 10100 |
| NAME OF BLOCK : REIEK |  |  |  |  |  |  |  |
| Main Centre | Sub-Centre |  | Village Covered |  | Population |  |  |
|  |  |  |  |  | Male | Female | TOTAL |
| RAWPUICHHIP PHC / M/C | Rawpuichhip S/C |  | Tuahzawl |  | 255 | 232 | 487 |
|  |  |  | Dapchhuah |  | 455 | 421 | 876 |
|  |  |  | Rawpuichhip |  | 808 | 724 | 1532 |
|  | Rulpuihlim S/C |  | Rulpuihlim |  | 203 | 190 | 393 |
|  |  |  | Chungtlang |  | 203 | 201 | 404 |
| TOTAL | 2 |  | 5 |  | 1924 | 1768 | 3692 |

SITUATION ANALYSIS

Human Resources

| STAFF | INPOSITION |  | VACANT |
| --- | --- | --- | --- |
|  | Regular | Contractual |  |
| Chief Medical Officer | 1 | 0 | 0 |
| Senior Medical Officer | 1 | 0 | 0 |
| Medical Superintendent DT/Sub District/Hospital | 0 | 0 | 1 |
| Specialists | 2 | 0 | 5 |
| Medical Officers | 1 | 2 | 12 |
| Gynaecologist | 1 | 0 | 0 |
| Paediatrician | 0 | 0 | 1 |
| Anaesthetist | 0 | 0 | 1 |
| Lady Medical Officers (only if there is any separate cadre in the State) | 0 | 0 | 0 |
| Lab. Technician | 3 | 4 | NA |
| X – ray Technician | 2 | 2 | 2 |
| Staff Nurse | 15 | 14 | 0 |
| Community Health Officer | 1 | 0 | 0 |
| ANMs | 12 | 16 | 0 |
| Male MPWs | 20 | 15 | 0 |
| Other; Support Staff at PHCs (Compounder/Pharmacist/Dressor/Others | 13 | 12 | NA |

Status of Logistics

| LOGISTIC ELEMENTS | DESCRIPTION |
| --- | --- |
| Availability of a dedicated District warehouse for Health Department stores room organisation: adequacy at District/CHC/PHC level | One store room at District Hospital |
| At time of inspection – at District, Block, PHC and Sub-Centre level Essential Drugs not in stock Drug not in essential list but in stock | Drug not in essential but in stock |
| Stock out of any vital supplies in last year - At District Hospital, At CHC, At PHC, At Sub-Centre |  |
| Indenting systems (from peripheral facilities to District) |  |
| Existence of a functional system - For assessing quality of vaccines - For quality of drugs |  |

Health Infrastructure

Health Facilities

| Public Health Facility | Number |
| --- | --- |
| District Hospital |  |
| Number | 1 |
| Average population per DH | 63430 |
| Community Health Centres (CHC) |  |
| Number | 1 |
| Average population per CHC | 6513 |
| Primary Health Centres (PHC) |  |
| Number | 7 |
| Average population per PHC | 5452 |
| Sub-Centres |  |
| Number | 27 |
| Average population per SC | 2213 |
| Average number of villages covered per SC | 2.6 |
| Government Ayurvedic Hospitals | - |
| Government Ayurvedic Dispensaries/Posts | - |
| Government Homeopathic Hospitals | - |
| Government Homeopathic Dispensaries/Posts | 1 |
| Others | - |

Current Service Norms

The services currently provided by each of the facility levels are as follows:

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No of Beds | Occupancy Rates | OPD Attendance |  |
| District Hospital | 30 | 90 | 70 - 80 (approx) | OPD, eye, Dental clinic, OT services, IUD, MTP, deliveries, ENT, Emergency Service |
| CHC | 30 (20 functional beds) | 92 | 70 -80 (approx) | OPD, Dental clinic, Minor OT services, IUD, MTP, delivery cases, Emergency Services |
| PHC | 10 | 95 | 30-40 (approx) | MTP, OPD, IUD, normal Delivery, I & D, dental clinic, Emergency Service |
| Sub-Centres | - | - | 20-25 (approx) | ANC, Immunisation, Dressing, Injection, I&D, Emergency Service |
| Others | - | - | - | - |

As is evident from the information available, the entire health infrastructure is overburdened and more so during the rainy seasons due to the high incidences of infectious diseases especially malaria & diarrhoea.

A closer look at the services offered by the district hospital and community health centre indicates that barring general OPD services which include medicine and dental clinic along with maternal care, no other services are available through specialists. The onus of offering healthcare to the people therefore lies solely upon the medical officers present at the hospitals who are in reality general practitioners. Even cases like fractures (something very common due to the primarily hilly terrain) and other critical injuries are required to be taken care of by these MOs in the absence of specialists.

The people are deprived of the specialist facilities like Obstetrics & Gynaecology, General surgery, Paediatric medicine, Anaesthesiology amongst others. This compels not only the patients themselves but also the district health officials to refer the patients to higher healthcare facilities within the state especially to Aizawl civil hospital. This observation calls for a closer look at the private healthcare facilities available within the district.

Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

The district to Mamit does not have a single private healthcare facility. Neither are any private practitioners available. This translates into total dependence on the district health infrastructure to enable provisions of healthcare. This fact coupled with the lack of specialist manpower at the level of district health infrastructure especially the district hospital and the community health centres is further increasing the burden on the existing medical officers.

Health Workforce

Health Workforce in the district

| Staff Position | Sanctioned as per IPHS guidelines | In-Position |  | Vacant(shortage as per IPHS guidelines) |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
| Chief Medical Officer | 1 | 1 | 0 | 0 |
| Senior Medical Officer/Additional CMHO/Additional DHO, RCH Officer/AYUSH Officer | 1 | 1 | 0 | 0 |
| District Medical Superintendent – DH | 1 | 0 | 0 | 1 |
| Senior Medical Officer including Specialists – SDH (include MOs from AYUSH also) |  | 0 | 0 |  |
| Gynaecologist | 1 | 1 | 0 | 1 |
| Paediatrician | 1 | 0 | 0 | 1 |
| Anaesthetist | 1 | 0 | 0 | 1 |
| Surgeon | 1 | 0 | 0 | 1 |
| Medical Officer - General Grade (from AYUSH also) | - | 6 | 3 | - |
| Medical Officer - General Grade - Female | - | 1 | 2 | - |
| District TB Officer | 1 | 0 | 0 | 1 |
| X-ray Technician | - | 1 | 2 | - |
| Staff Nurse | - | 15 | 14 | - |
| Chief Pharmacist/Pharmacist | 1 | 1 | 0 | 1 |
| Lab Technician/Senior LT | - | 0 | 10 | - |
| ECG team Leader | 1 | 0 | 0 | 1 |
| ECG Technician | 1 | 0 | 0 | 1 |
| Eye Assistant | - | 1 | 0 | 2 |
| Occupational Therapist | 1 | 0 | 0 | 1 |
| Physiotherapist | 1 | 0 | 0 | 1 |
| Health Educator | 1 | 0 | 0 | 1 |
| Dental Hygienist | 1 | 0 | 0 | 1 |
| Chief Clerk / UDC |  | 2 | 0 | 1 |
| Statistical Assistant/ Senior SA |  | 1 | 0 | 0 |
| Senior Assistant |  | 0 | 0 |  |
| Senior Clerk |  | 0 | 0 |  |
| Computer Clerk / Junior Clerk |  | 0 | 4 |  |
| Stenographer |  | 0 | 0 |  |
| Public Health Nurse |  | 7 | 0 |  |
| Food Inspector |  | 0 | 0 |  |
| Store keeper cum Clerk |  | 0 | 0 |  |
| Maleria Inspector/ Sr. Maleria Inspector | 1 | 0 | 0 |  |
| Health Education Officer | 1 | 0 | 0 |  |
| Health Supervisor | - | 14 | 0 |  |
| LHV |  | 0 | 0 |  |
| ANM |  | 12 | 19 |  |
| MPW |  | 20 | 15 |  |
| Refrigerator Mechanic |  |  |  |  |
| Electrician |  |  |  |  |
| Refrigerator Assistant |  |  |  |  |
| X-ray Technician |  | 2 | 2 |  |
| ECG Technician |  |  |  |  |
| O.T Technician |  |  |  |  |
| Projectionist |  |  |  |  |
| Driver |  | 1 | 5 |  |
| Class IV staff / Sweeper |  | 42 | 12 |  |
| Sweeper |  |  |  |  |

Additional Details

| No. of Sub Centres without ANMs | 1 |
| --- | --- |
| No. of SC taken up for renovations | 4 |
| No. of new SC being constructed | 6 |
| No. of PHC without BEmOC facility | 4 |
| No. of PHC taken up for renovations | 0 |
| No. of new PHC being constructed | 1 |
| No. of FRU without Gynae/Obstetricians | 0 |
| No. of FRU without OT facilities | 1 |
| No. of FRU without Surgeons | 1 |
| No. of FRU without Aneasthetists | 1 |
| No. of FRU taken up for renovations | 0 |
| No. of new CHC being constructed | 0 |

DMHP plan for 2012 -2013; Mamit District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Mamit district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme

Serchhip

Map of Serchhip

Background:

Serchhip District is located in the heart of the State of Mizoram. It was created in latter part of 1990s from Aizawl District as Mizoram Govt decided to have 8 administrative District in the State instead of 3 District previously; by 2008 it is proposed to form 11 District in Mizoram. The total area is 1421 sq.km with the population of 53861 (2001 census). The distance of the district from the State capital is 110 kms by road. It is bounded in the North by Aizawl District, in the East by Champhai District and Myanmar, in the west by Aizawl District and Lunglei District. Being situated in the centre of the State it is accessible to most part of the District though there are some areas which are difficult to reach due to lack of proper road and transportation system. The majority of the population are homogenous community and Christian by faith in religion. There are also some other religion like Hindu, Muslim, Sikh, Buddhist and Jains (2001 census). The main language spoken is Lushai.

Administrative profile

The Administrative set up of the District is administered by the Dy.Commissioner. The District consists of two rural development blocks and further down the District is further divided into 40 Village Council. The District does not have the three- tier Panchayati Raj system; it follows Village Council System where the Village Council President is the overall in charge of his area under the supervision of the BDO and the District Local Administrative Officer.

The administrative profile of the District is given in the table below

Administrative Profile

| Administrative levels | Description/Number |
| --- | --- |
| Assembly constituencies (no.) | 3 |
| Number of Blocks (CD Blocks) | 2 |
| Number of Village Council | 40 |
| Number of villages | 33 |
| Number of villages with population below 500 | 9 |
| Number of villages with population 501 - 2000 | 19 |
| Number of villages with population 2001 – 5000 | 5 |
| Number of villages with 5000+ population | 3 |

Geography and Climate:

Almost the entire entire District is hilly with only one valley by the bank of Mat River which is used for cultivation of paddy during monsoon and cabbage during winter season. The highest waterfall in Mizoram (Vantawng Khawhthla) is located inside Serchhip District near village of Thenzawl. The climate is pleasant throughout the year with a maximum of 27.8 Celsius Degree 11.2 Celsius Degree during winter. Relative maximum humidity is 98 with a minimum of 17%. The monthly average rainfall is 2180 mm. The crops grown in the District are mainly rice and maize. The natural calamity faced by the District is landslide. The National Highway 54 runs through the District from North to South connecting 3 southern District. All the PHC are connected by all weather roads except Ngentiang PHC area, which covers 3 Sub-Centres. Most of the Sub-Centres are connected by motorable roads except one Sub-Centre, which is connected by foot only (Thinglian S/C). There is a Bus/Sumo service in the four PHC except Ngentiang PHC area.

Demographic profile

| Indicators | District | State |
| --- | --- | --- |
| Population | 56459 | 888573 (Census-2001) |
| Males | 27981 | 459109 |
| Female | 28478 | 429464 |
| Total | 56459 | 888573 |
| Population Density ( Per sq.km ) | 39 | 42 |
| Urban ( % ) | - | 49.6 % |
| Rural (%) | 100 | 50.4 % |
| Scheduled Castes | 5 | 272 |
| Scheduled Tribes | 56454 | 831390 |
| Languages | Mizo | Mizo |
| Religions | Christian | Christian |
| Children (0-5 years) | 6775 | 143734 |
| Adolescents (10-19 years) | NA | 195486 |
| Women (14-45 years) | NA | 159943 |
| Population Below Poverty Line (BPL) | 30.6 % | 22% |
| Population growth rate (1991-2001) | 15.6 % | 28.8 % |
| Vital statistics |  |  |
| Crude Birth Rate | 21.4 | 21.9 |
| Crude Death Rate | 2.85 | 5.10 |
| Sex Ratio |  |  |
| Overall | 925/1000 | 935/1000 |
| Child | * | 964/1000 |
| Literacy Rate | 95.1 | 90.7 |

Serchhip District has a population of 6.35 % of the state’s total population and this small population is scattered throughout the district and the population density is only 39 per square kilometre. The population is rural in nature and as per the state decision there is no designated urban area. The majority of the population is Scheduled tribe and this homogenous population is mainly Christian by faith having a very high literacy rate of 99.9 % which is even higher than the state literacy rate. This high literacy provides a good scope for developing successful IEC campaign through print media. The district has a high BPL population of 30.6% which is higher than the state figure. The district sex ratio is 9:3 which is lower than the state figure.

SITUATION ANALYSIS

Health Infrastructure

| Public Health Facility | Number |
| --- | --- |
| No. of District Hospital | 1 |
| No. of Community Health Centres (CHC) | 1 |
| Average population per CHC | 6646 |
| No. of Primary Health Centres (PHC) | 5 |
| Average population per PHC | 6000 |
| No. of Sub-Centres | 26 |
| Average population per SC | 2000 |
| Average number of villages covered per SC | 1 |
| Government Ayurvedic Hospitals | NIL |
| Government Ayurvedic Dispensaries/Posts | 1 |
| Government Homeopathic Hospitals | NIL |
| Government Homeopathic Dispensaries/Posts | 1 |
| Others | NIL |
| Private Health Facility | Number |
| For Profit | NIL |
| Not-for Profit | NIL |
| Private Practitioners (GP) | NIL |
| Surgeons | NIL |
| Paediatricians | NIL |
| Gynaecologists | NIL |
| Anaesthetists | NIL |
| Homeopaths | NIL |
| Ayurvedic Practitioners | NIL |

The above table clearly brings out the fact that the entire population in the District is dependent on the government public health infrastructure which is a great load on the existing resources of the government. With no private health facility in place in the entire district it is now the responsibility of the government to provide greater resources to cater to the health of all. Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

Current Service Norms

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No. of Beds | Occupancy Rates | Average OPD Attendance |  |
| District Hospital | 50 | 80 % | 120 | Gynaecology, General Medicine and Paediatric services with X-ray & Routine Lab investigation. |
| CHC | 30 | 70 % | 60 | General Medicine, Family Planning, normal delivery. |
| PHC | 10 | 90 % | 40 | General Medicine, Family Planning, normal delivery. |
| Sub-Centres | NIL | NIL | 25 | Public Health, minor ailment and normal delivery in some centre |

The service provided at the district level and utilisation of the services is good but more manpower and greater facilities like blood bio-chemistry and Serology, USG, laparoscopic, and Endoscopy services are required. More facility for greater diagnostic services is an urgent need for proper diagnosis and treatment. Greater services particularly diagnostic services and specialised services need to be provided at the CHC level. It would also be very appreciable if a surgeon and an Anaesthetist could be posted at the District Hospital and a GA Machine supplied to the District Hospital.

Health Workforce

| Staff Position | Sanctioned | In-Position |  | Vacant |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
| CMO | 1 | 1 | 0 | 0 |
| Medical Superintendent / Senior MS | 0 | 0 | 0 | 1 |
| Senior Medical Officer | 0 | 0 | 0 | 1 |
| Medical Officer - General Grade – Male | 11 | 3 | 8 | 0 |
| Medical Officer - General Grade – Female | 4 | 4 | 0 | 0 |
| Dental Surgeon | 0 | 0 | 0 | 1 |
| District Programme Manager | 1 | 0 | 1 | 0 |
| District Immunization Officer (Designated) | 1 | 1 | 0 | 0 |
| Asst. Matron | 1 | 1 | 0 | 0 |
| Sister / ward Suprintendent | 4 | 4 | 0 | 0 |
| Staff Nurse | 43 | 31 | 12 | 0 |
| Lab Technician | 14 | 4 | 10 | 0 |
| Eye Assistant (ophthalmic assistant) | 1 | 1 | 0 | 0 |
| Health Educator / BEE | 2 | 1 | 1 | 0 |
| Accountant / Accounts Clerk | 7 | 0 | 6 | 0 |
| Statistician / CHO | 1 | 1 | 0 | 0 |
| Head Assistant / UDC | 0 | 0 | 0 | 1 |
| Computer Operator / Data entry operator | 5 | 0 | 5 | 0 |
| District Health Education Information Officer | 1 | 1 | 0 | 0 |
| Store keeper cum Clerk | 0 | 0 | 0 | 0 |
| SLT /STLS – TB (RNTCP) | 1 | 0 | 1 | 0 |
| Malaria Treatment Supervisor | 1 | 0 | 1 | 0 |
| Pharmacist | 10 | 6 | 4 | 0 |
| Health Supervisor | 13 | 13 | 0 | 0 |
| Health Supervisor (F) | 6 | 6 | 0 | 0 |
| Health Workers (Male & female ) / MPW | 63 | 40 | 23 | 0 |
| X-ray Technician | 6 | 3 | 3 | 0 |
| Lab Asst. | 1 | 1 | 0 | 0 |
| Driver | 13 | 7 | 6 | 0 |
| Class IV staff (cook,sweeper,peon etc) | 77 | 76 | 1 | 0 |

The District Office is run by CMO along with the coordination of District Programme Manager. This shows great improvement in Health delivery system. All the PHC are functioning with HS (M&F) resulting in better performance of the health programme. At present there are 3 (24 x 7) PHC. Moreover, Ngentiang PHC is now functioning with Medical Officer.

The Block still faces some shortage of category in manpower right from the specialist doctors to Class IV employees. Many of the post lay vacant resulting in extra burden to whatever little staff is present. This seriously affects the quality of work in all respect.

DMHP plan for 2012 -2013; Serchhip District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary as per Annexure II | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Serchhip district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme

Champhai

Map of Champhai

Block map- Champhai

BACKGROUND

The Champhai District is one of the new Districts in Mizoram with basically a very minimal functional Primary Health Care Delivery system even today. Champhai District is located in the North-Eastern part of the state of Mizoram.  The District is bounded by Aizawl East and Serchhip Districts and in the north by Manipur State.  The total area of the District is 3185 Sq km. Champhai town is the Headquarter of the District and is elevated at an by Myanmar in the east and south, in the west altitude of 1678 meters from the sea level.The total population is 124128 (as on April ‘09),comprising 12.19 percent of the State population.

Champhai District is located 194 km. distance from the State Capital. Christianity is the major religion.  But there are some Hindus and Muslims, though they are minimal in number. Major languages spoken are Mizo and English as official languages.  Paihte is also spoken by a few belonging to the Paihte community.

The Public Health Administration lies under the responsibility of the District CMO (Chief Medical Officer), who is In-Charge of overall administration and management of public health service delivery of the Department of Health & Family Welfare. However, the District hospital is under a separate directorate – the Directorate of Hospitals & Medical Education. The Medical Superintendent of the District Hospital reports directly to the DHME and not to the CMO.

Administrative Profile

The District administration is looked after by the Deputy Commissioner, He is responsible of maintaining Law & Order, revenue, civil supplies etc. Under the DC’s direction the District is divided into four (4) rural development blocks:

- Ngopa block

- Khawzawl block

- Khawbung block

- Hnahlan block

Each Block is headed by a Block Development Officer (BDO). Further down, the blocks are again sub-divided into 102 Village Councils. As in the State, this District also does not have the 3-tier Panchayati Raj System. It follows this Village Council System where the Village Council President is the Overall in-charge of his area under the supervision of the Block Development Officer, the District DC and the Executive Community, Chairman of the respective District Councils. The Village Council consists of members elected by the people of a village.

| Administrative levels | Description/Number |
| --- | --- |
| District headquarter | Champhai |
| Assembly constituencies (no.) | 5 |
| Number of Blocks (CD Blocks) | 4 |
| Number of Village Councils | 102 |
| Number of villages | 103 |
| Number of villages with population below 500 | 49 |
| Number of villages with population 501 – 2000 | 41 |
| Number of villages with population 2001 – 5000 | 12 |
| Number of villages with 5000+ population | 1 |

Geography and Climate

Champhai town is situated at an altitude of 1678 metres above sea level. The District has an annual rainfall of 1814 mm. The temperature varies between a minimum temperature of 8 degrees Celcius during winter season and a maximum temperature of 30 degrees Celcius during summer season. The Geo-coordinates in degrees (decimal) is 23.48 degrees North and 93.38 degrees east.

Champhai is a bustling commercial town at the Indo-Myanmar border, is a beautiful place that has five big rivers and small tributaries.  The well known rivers are Tiau (159.38 kms.) at the Myanmar border, Tuipui (86.94 kms.), Tuichang (120.75 kms.), Tuiphal (79.31 kms.) and Tuivawl (72.45 kms.) river which is situated between Aizawl and Champhai Districts.  The 3 main rivers Tuipui, Tuichang and Tuiphal make it geographically inaccessible for villagers who live near these rivers to access to any form of Health care.

The villagers are industrious and the livelihood is mostly agrarian.  The main crops cultivated are rice, grapes and passion fruits.  Champhai is fast emerging as the fruit bowl of Mizoram.

Fortunately, there has been no catastrophic disasters in recent years but the District often suffer from natural calamities such as landslides resulting in road blockade during rainy season and bush fires during dry and hot season.

It is well connected by road and can be reached from Aizawl by traversing a distance of 194 kms.  By Government and private buses or sumo services which ply day and night on all days except Sundays.  Taxis can be hired on all days from any part of the State.

Demographic Profile

The population of Champhai District is 124128 (as on April ‘09) with a population density of 34.03 per sqkm.  The Demographic profile of the District is given below:

Demographic profile

(Source: District data as on April ’09 & State data 2001, Census)

| Indicators | District | State |
| --- | --- | --- |
| Population(2001) |  |  |
| Males | 63305(50.99%) | 459109 (51.6%) |
| Female | 60823(49.01%) | 429464 (48.4%) |
| Total | 124128 | 888573 |
| Population Density (per square km) | 34.03 | 42 |
| Urban (%) | 0.25 | 49.6 |
| Rural (%) | 96.8 | 50.4 |
| Scheduled Castes | Nil | 272 (0.03%) |
| Scheduled Tribes | 121309 | 831390 (94.5%) |
| Languages | Mizo, Paihte | Mizo, English |
| Religions (%) | Christian -96.90 Muslim – 0.39 Hindus – 2.07 | Christian – 86.90 Muslims – 1.13 Hindus – 3.55 Buddhist – 7.9 |
| Children (0-5 years) | 15324 | 143734 |
| Adolescents (10-19 years) | 23703 | 195486.06 |
| Women (20-45 years) | 20936 | 159943 |
| Population Below Poverty Line (BPL) (%) | 34 | 22.50 |
| Population growth rate (1991-2001) (%) | 30.10 | 22.80 |
| Vital statistics |  |  |
| Crude Birth Rate (%) | 25.17 | 21.47 |
| Crude Death Rate (%) | 2 | 4.97 |
| Sex Ratio |  |  |
| Overall | 944 | 935 |
| Child | Not available | 964 |
| Literacy |  |  |
| Literacy among Males (%) | 97.05 | 90.97 |
| Literacy among Females (%) | 95.33 | 86.67 |
| Total (%) | 96.19 | 88.8 |

As the above table reflects, Champhai is a District with the population density lower than that of the State. The population is primarily rural, with a statistically negligible portion living in urban areas. Christianity is the major religion (96.9%), with some Hindus (2.07%) and an even smaller Muslim population (0.39%). Poverty level is high in this District with 35% of the population belonging to BPL category, as against 22.5% BPL population at the state level. The CBR of the District is higher than the State, but the CDR is lower. The overall Sex Ratio is better than the State, but information on the Sex Ratio among children is not available. Despite the poverty, the literacy rate in the District is very high at 96.19%, which is significantly better than the literacy rate of the State.

SITUATION ANALYSIS

Health Infrastructure

| Public Health Facility | Number |
| --- | --- |
| Community Health Centres (CHC) |  |
| Number | 2 |
| Average population per CHC | 6425 |
| Primary Health Centres (PHC) |  |
| Number | 11 |
| Average population per PHC | 6165 |
| Sub-Centres |  |
| Number | 59 |
| Average population per SC | 2103 |
| Average number of villages covered per SC | 1.71 |
| Government Ayurvedic Hospitals | Ayurvedic Hospital/ Dispensary not available at present in the District |
| Government Ayurvedic Dispensaries/Posts |  |
| Government Homeopathic Hospitals |  |
| Government Homeopathic Dispensaries/Posts |  |
| Others |  |
| Private Health Facility | Number |
| For Profit | Private Health Facility not available at present in the District |
| Not-for Profit |  |
| Private Practitioners (GP) |  |
| Surgeons |  |
| Paediatricians |  |
| Gynaecologists |  |
| Anasthaetists |  |
| Homeopaths |  |
| Ayurvedic Practitioners |  |
| Others |  |

As given in the above table, the healthcare infrastructure consists of 1 District Hospital, 2 Community Health Centres, and 11 PHCs out of which only 10 PHCs are functioning and 59 Sub-Centres. In the District there is AYUSH dispensary or practitioners at present.

Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric social worker and psychiatric nurse.

There are no private health facilities in the District, no individual private practitioners of any branch of medicine. This implies that the burden of healthcare service delivery is entirely on the public healthcare system. Given this situation, 1 PHC being non-functional implies that around 3,000 people are left without a PHC to cater to them. This is critical, because the population per PHC may be far less than the institutional guidelines set by Government of India for hilly states, but the geographical area each PHC covers is quite large. This difference happens because the residential pattern in the District is scattered, as the low population density reflects.

Current Service Norms

The services currently provided by each facility level is as follows

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No of Beds | Occupancy Rates | Average OPD Attendance per day |  |
| District Hospital | 60 | 50 | 95 | OPD, IP, Outreach, Maternal Health, Child Health. |
| CHC | 30 | 10 | 64 | OPD, IP, Maternal Health, Child Health. |
| PHC | 10 | 8 | 80 | OPD, IP, Maternal Health, Child Health. |
| Sub-Centres |  |  | 5 | OPD, Maternal Health, Child Health. |
| Others | - | - | - | - |

The above table reflects that the utilization of the IP services is quite high, though not 100%. However, it is important to remember that these are annual averages that do not reflect seasonal variations. During the rainy seasons, for example, which is also the Malaria season, bed occupancy at all 3 levels of PHC, CHC and DH become more than 100%, needing extra beds and the utilization of corridors.

It is also important to note that the high rate of OPD attendance at the PHC level implies overload for one single MO placed at this level, given the fact that s/he also has to manage IP – especially normal deliveries - and the Sub-Centres. Given that each Sub-Centre has to be visited at least once a month and such a visit implies 3 to 4 hours spent in journey.

DMHP plan for 2012 -2013; Champhai District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Champhai district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme

Saiha

BACKGROUND

Saiha district was carved out of Chhimtuipui district and got the status of a district when Mizoram attained statehood in 1990. Chhimtuipui district was one of the original 3 districts of Union Territory Mizoram since 1972.The district has an area of 1320 Sq. Kms and is at the southernmost tip of Mizoram bordering Myanmar in the eastern and southern part. The international boundary runs 159 Kms. The district population is 55400 (Saiha block and Tuipang block) with 9457households. Road communication is the only available means of connectivity and takes 13 hours journey. The district capital, Saiha  is 350 Kms away from the State capital. As in other part of the State, Saiha is a Christian dominated district with only few Hindu and Muslim population. Mizo language is commonly spoken though Mara is the local dialect. English and Mizo are the official language.

Administrative profile :

The district has a special feature of being Mara Autonomous District Council (MADC), which runs all departments except Health and Police Departments. School education up to middle level is also undertaken by them. MADC is governed by the Chief Executive Member (CEM) and 7 Executive Members (EM) holding different portfolios elected from the 22 Members of District Council (MDCs). However, Civil Administration is headed by the District Commissioner as in other districts.

| Administrative levels | Description/Number |
| --- | --- |
| District headquarter | Saiha |
| Assembly constituencies (no.) | 2 |
| Number of Blocks (CD Blocks) | 2 |
| Number of villages | 49 |
| Number of village council | 74 |
| Number of villages with population below 500 | 17 |
| Number of villages with population 501 – 1000 | 21 |
| Number of villages with population 1001 – 2000 | 9 |
| Number of villages with 2000+ population | 2 |

Geography and Climate:

The district comprises of difficult hilly terrains and natural forest areas and sparsely populated. The district capital is situated at an altitude of 1225 metres above sea level. The temperature ranges from 11.2 to 28.57 degree Celsius in 2005 and relative humidity, 17 to 97.2%. The river Kolodyne flows along the inter border district with Lawngtlai district into Myanmar. Many areas of the district as well as the connecting highway are landslide prone. In rainy seasons, 3 out of 4 PHCs and their Sub Centres along with their satellite villages (2/3rd of the district) totally are cut off. Public transport (bus) system is limited in all seasons. Sumo services have a slightly wider coverage but only during dry seasons.

Demographic profile:

| Indicators | District | State |
| --- | --- | --- |
| Population (CMO Office, Saiha 2006 - 2007) | 55400 | 888573 |
| Males | 26998 | 459109 |
| Female | 28402 | 429464 |
| Population Density | 49.7 | 42 |
| Urban |  | 441006 |
| Rural | 55400 | 447567 |
| Scheduled Castes | 0.16 | 210 |
| Scheduled Tribes | 99.84 | 839310 |
| Languages | Mizo | Mizo |
| Religions | Christianity | Christianity |
| Children (0-2 year) | 1496 | - |
| Children (0-5 years) | 6095 | 143734 |
| Adolescents (14-19 years) | 5685 | 195486 |
| Women (14-45 years) | 7605 | - |
| Population Below Poverty Line (BPL) (in percentage) | 72.12% | 24 % |
| Crude Birth Rate | 25.36 | - |
| Crude Death Rate | 2.36 | - |
| Sex Ratio | 512:671 | - |
| Overall | 5782 | 935 |
| Child | 85% | 964 |
| Literacy | 82.2 | 88.8 |
| Literacy among Males | 82.8 | 90.7 |
| Literacy among Females | 81.9 | 86.7 |

From the above table this has become evident that the district comprises only 6.23% of the total population of the state. The district is predominantly rural as there is no urban area in the district. This is revealed from the above data that the population of the district mainly comprises the scheduled tribes as there is a very low proportion of the scheduled castes in the district. The literacy is marginally low as compared with the state average. Again the literacy among the male and the females are more or less same throughout the district.  A high percentage of the population, i.e,72.12% of the population falls under the BPL category which is quite high comparing with the state percentage, i.e., 24%.

SITUATIONAL ANALYSIS :

HEALTH  INFRASTRUCTURE :

| Public Health Facility | Number |
| --- | --- |
| District Hospital | 1 |
| Number of PHC | 4 (2functional) |
| Area covered by each PHC | 280.7 sq km |
| Sub-Centres |  |
| Number | 24 |
| Area covered per SC | 40.2 |
| Average number of villages covered by SC | 70 |
| Government Ayurvedic Hospitals | 0 |
| Government Ayurvedic Dispensaries/Posts | 0 |
| Government Homeopathic Hospitals | 0 |
| Government Homeopathic Dispensaries/Posts | 0 |
| Others | 0 |

| Private Health Facility | Number |
| --- | --- |
| For Profit | 1 |
| Not-for Profit | 0 |
| Private Practitioners (GP) | 1 |
| Surgeons | 0 |
| Paediatricians | 0 |
| Gynaecologist | 0 |
| Anaesthetists | 0 |
| Homeopaths (AYUSH) | 0 |
| Ayurvedic Practitioners | 0 |

The district hospital serves as the only FRU for 1320 Sq.Km of the entire district. Similarly, each PHC and SC serves difficult hilly terrain with poor public transport system and poor seasonal roads. Private health facilities are negligible and the people of this district have to depend solely on Public Health System. This indicates the need to strengthen every level of Public Health institution in the district in terms of infrastructure, manpower and other facilities.

HEALTH   WORK FORCE    IN   THE   DISTRICT :

| Staff Position | Sanctioned | In-Position |  | Vacant |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
| Chief Medical Officer | 1 | 1 | 0 | 0 |
| Medical Superintendent – District Hospital | 1 | 1 | 0 | 0 |
| Paediatrician | 0 | 1 | 0 | 0 |
| Anaesthetist |  | 1 | 0 | 0 |
| Surgeon |  | 1 | 0 | 0 |
| Dental Surgeon |  | 0 | 2 | 0 |
| ENT |  | 0 | 1 | 0 |
| Medical Officer - General Grade (from AYUSH also) |  | 5 | 1 | 3 |
| Medical Officer - General Grade – Female |  | 2 | 0 | 1 |
| District TB Officer i/c |  | 1 | 0 | 0 |
| X-ray Technician |  | 1 | 0 | 3 |
| Staff Nurse |  | 18 | 17 | 23 |
| Pharmacist |  | 1 | 1(MMU) | 4 |
| Lab Technician |  | 1 | 3 |  |
| Senior LT |  | 1 |  |  |
| Ophthalmic Assistant |  | 1 | 2 |  |
| Health Educator |  | 1 | - |  |
| Head Assistant |  | 1 | - | 1 |
| Statistical Assistant/ Inspector SA |  | 4 |  |  |
| Senior Assistant (UDC) |  | 2 |  | 2 |
| LDC |  | 6 |  | 4 |
| Computer Clerk / Junior Clerk |  | -- | 6 |  |
| Malaria Supervisor |  | Nil | 1 | 1 |
| Health Supervisor |  | 6 |  | 4 |
| ANM( Female H/W ) |  | 23 | 8 | 4 |
| MPW (Male H/W) |  | 19 | 4 | 4 |
| Cold Chain Mechanic |  | 1 |  | 5 |
| Electrician |  | 1 |  | 1 |
| Driver |  | 9 | 4 |  |
| Class IV staff including sweeper |  | 106 | 1 |  |
| Accounts clerk NRHM,RCH,IDSP,RNTCP |  |  | 7 |  |

22 categories of the above staff listed are not there in the district. CMO has no support of Senior Medical Officers or Deputy CMOs. Doctor or nurse trained in Public health to assist him in programme management and epidemiology services are absent. Cold chain staffs are non-existent. IEC/BCC staffs are inadequate to undertake effective activity. Material and other logistics management staff are in shortage. Health staffs to ensure food and water safety are lacking. There are no specialists’ posts even at district level. Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

FUNCTIONALITIES OF DH, PHCs AND SUB_CENTRE (INTERMS OF AVAILABILITY OF CRITICAL STAFF POSITION):						The services currently provided by each facility level are as follows:

| CRITICAL STAFFs | No. OF FACILITIES | GIVE NAMES OF FACILITIES | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No of Beds | Occupancy Rates | OPD Attendance |  |
| DH | 1 |  | 60 | 72% | 59 | OPD, IPD, OT, Emergency services. |
| PHCs with Medical Officer Available | 2 | Tuipang PHC, Phura PHC | 10 10 | 35% 10% | 49 23 | OPD, deliveries (in 1 PHC), regular checkups, female sterilisation. |
| Sub-Centre with ANM available | 24 SC+7 Clinic | 54 ANMs at 24SC+7Clinic | 0 |  |  | OPD, ANC,PNC. |

Due to lack of infrastructure and manpower, the health institutions are far from fulfilling IPHS standard of providing expected services. District Hospital cannot function as FRU. Out of the 4 PHCs in the district 2 PHC  is  functional in 24X7  but without having MOs the PHCs has almost become non functional. Naturally the service utilization of the functional PHC is not satisfactory.

DMHP plan for 2012 -2013; Saiha District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary as per Annexure II | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilization activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Saiha district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme

Lawngtlai District

Background.

The District Lawngtlai is located in the southern end of the State of Mizoram. The District headquarters Lawngtlai situated at a height of 849 metres from the sea level. The District shares its border with Bangladesh on the western side, Lunglei district of Mizoram on the northern side, Saiha district of Mizoram on the eastern side and Myanmar on the southern side.

Lawngtlai is one of the New district established during the 1990s from the then Chhimtuipui District. It has four blocks such as Lawngtlai Block, Bungtlang Block, Sangau Block and Chawngte Block. In terms of the geographical area coverage, Lawngtlai district ranks the fifth largest district in the state, covering 2519 Sq.Kms. However, it is only the fourth most populated district in Mizoram. The density of population in Lawngtlai District is 39.43 per sq.km.

The Lawngtlai District of Mizoram is situated in the South -Western part of the State of Mizoram. The District is surrounded by

North:			Lunglei District of Mizoram

West:			Bangladesh

South:			Myanmar

East:			Saiha District of Mizoram

A large community of Brus and other minority resides in the District. Apart from these the district is inhabited both the two sub-tribes of the Lai and the Chakma which have an Autonomous District Council on their own. The Official language in the Chakma ADC is English and Chakmas, because of this there is some communication problem now and then – All the IEC/BCC materials have to be prepared in Mizo, English and the language of the local tribes.

The Statistical Handbook 2005 (Lawngtlai Dis’t) indicates a population of 99342 in 2005. But in 2008, a population was 112788 (Nov, 2008). Lawngtlai is connected to Aizawl  by road which is 300 Km. In Communication 23 out of 38 Sub Centre are connected by all weather road and 15 Sub Centres are connected by seasonal road and only 31 villages out of 160 are connected by all weather road. One river called Chawngte lui which flows from Parva to Chawngte Autonomous District Council Hqrs Is being used for communication with a maximum utilisation in rainy season. To have full utilisation throughout the year sufficient provision of fund for hiring Steam Boat / Boat is necessary. The bad communication connecting villages to sub centres, sub centres to PHCs cause poor health care delivery and low utilisation of health services available in the health centre. Whereas the adjacent Lunglei district has 98% sub centre connected by all weather road resulting into high performance in various health programmes and more utilisation of health services.

The major religions include Buddhism (52.2 %) & Christianity (44.7 %) and the major languages spoken by the population are Mizo and Chakma.

## Administrative Profile

Source: 		Statistical Handbook 2005 (Lawngtlai District)

| Administrative levels | Description/Number |
| --- | --- |
| District headquarter | Lawngtlai |
| Parliamentary constituencies (no.) | Nil |
| Assembly constituencies (no.) | 3 |
| Number of Blocks (CD Blocks) | 4 |
| Number of Gram Panchayats | 160 |
| Number of villages | 165 |
| Number of villages with population below 500 | 95 |
| Number of villages with population 501 – 2000 | 64 |
| Number of villages with population 2001 – 5000 | 6 |
| Number of villages with 5000+ population |  |

In Lawngtlai District there are two autonomous District Councils namely (i) Lai Autonomous District Council which have it’s headquarter at Lawngtlai and (ii) Chakma Autonomous District Council which have its headquarter at Chawngte (Kamalanagar). These Autonomous District Councils are elected for a fixed tenure. The council receive development funds and administrative etc. from central government (GOI) through state government. The autonomous councils have different department as in state government except Health services and Police department. As other departments are going hand in hand in the autonomous district, the health services has to function alone all the health care delivery systems have to be managed by state.

## Geography and Climate

Topography - Lawngtlai District is situated in the Southern part of Mizoram.  Geographically it covered 2519 Sq Kms.  It lies between longitude 92.15’ E to 93.29’ E and the Latitude 21.58’ N to 24.35’ N.

A total of three rivers that traverse the district from the north to south are Chhimtuipui, Ngengpui Lui, Chawngte Lui. The district experiences an annual rainfall of around 2461 mm. The major crops include Paddy, Maize, Ginger, Pulses, Sugarcane, Cotton, Potato, Orange, Banana, Chillies etc.

The hilly terrain is one of the major contributing factors to occurrence of natural disasters and approximately 25% of the district is affected by landslides and occasional tornados.

The road connectivity and accessibility varies (both overall and seasonal) –

1). National Highway passes through Lawngtlai Town, Kawlchaw Sc and  Thingkah SC. (Overall)

2). Road (Black Topping) from Lawngtlai Town to Damdep SC is passing through Mampui SC, Khawmawi SC, Diltlang SC, Bungtlang PHC/SC, M. Kawnpui SC, Vaseikai Village. (Overall)

3). Road from Lawngtlai to Paithar SC (Overall)

4). Road from Bungtlang PHC to Tuithumhnar SC (Seasonal)

5). Road from M. Kawnpui SC to Chamdur P SC, Vathuampui SC and Mautlang SC (Seasonal)

6). Road from Damdep to Devasora SC and Parva (Seasonal)

7). Road from Lunglei to Lungrang SC, Rualalung SC, Chawngte (Overall)

8). Road from Chawngte to Hmunlai SC, Saizawh W SC, Ajasora SC (Seasonal)

9). Road from Chawngte to Borapansury PHC/SC (Seasonal)

10). Path from Chawngte to Sumsilui SC, Jarulsury (Seasonal)

Public transport system available includes State Transport Aizawl to Lawngtlai, Kawlchaw SC, State Transport Lawngtlai to Vaseikai (twice a week) and Private Transportation also available in the form of bus, taxi.

## Demographic Profile

The demographic profile of the district may be summarized as follows:

| Indicators | 2007 – ‘08 | 2008– ‘09(Oct ’09) |
| --- | --- | --- |
| Population | 99342(2001, Census) | 112788 (2008, Record) |
| Males | 50857 | 12116 |
| Female | 48485 | 11023 |
| Total | 99342 | 112788 |
| Population Density | 39.43 | 41 |
| Urban (%) |  |  |
| Rural (%) | 100% | 100% |
| Scheduled Castes |  |  |
| Scheduled Tribes | 99342 | 100% |
| Major Languages | Mizo and Chakma | Mizo and Chakma |
| Religions | Buddhism and Christianity | Buddhism and Christianity |
| Children (0-5 years) | 11923 | 15790 |
| Adolescents (10-19 years) | 7948 | 8907 |
| Women (15-49 years) | 21086 | 25122 |
| Population Below Poverty Line (BPL) | 80411 | 84591(75%) |
| Population growth rate (1991-2001) | 35.8% | NA |
| Crude Birth Rate | 26.73 % (District Report,2006 | 25% (District Report,2008) |
| Crude Death Rate | 3.7 % (District Report,2006) | 3.9% (District Report,2008) |
| Sex Ratio |  | Male- 52% Female 48% |
| Literacy among Males | 68% | 69% |
| Literacy among Females | 64% | 65% |

Lawngtlai District is the most economically backward district in the state. The District has 75 % of total population below poverty line whereas the State figure is 22 %. This shows that the District needs special consideration in terms of infrastructure and manpower assistance. The population density for the district is below that for the state. However, one should note that the entire population of the district is rural. The birth rate recorded for the district is 25% whereas the death rates stand at 3.9%. On the other hand the population growth rate for the district (35.80%) is far higher than that for the state (28.82%). This necessitates more attention so far as providing provisions of healthcare are concerned especially in light of the fact that Lawngtlai is one of the poorest districts in the state of Mizoram.

The overall sex ratio for the district is close to that of the state at 899 per 1000 males. The literacy rates for the district are low (64.5%) in comparison to that for the state which stands at 88.80%. Moreover, unlike the state, where both the male and female literacy rates are close, for Lawngtlai, the female literacy rates are far below that of the males. Lawngtlai district is one of the lowest literacy rates in the state having 64% where as the state is 88.8% and the highest achiever is Aizawl District 96.5%.

Lawngtlai District has to major language viz. Chakma and Mizo this result into problem in communication and deep understanding. The District needs much more emphasis on the IEC to break down the barrier.

## Health Infrastructure

The health infrastructure of the district is primarily government with only two private nursing homes operating in the district. The public and private health infrastructure in the district may be summarized a follows:

| Public Health Facility | Number |
| --- | --- |
| District Hospital | 1 |
| Community Health Centres (CHC) | 1 |
| Average population per CHC | 50110 |
| Primary Health Centres (PHC) | 5 |
| Average population per PHC | 22558 |
| Sub-Centres | 37 |
| Average population per SC | 3048 |
| Average number of villages covered per SC | 5 |
| Government Ayurvedic Hospitals | - |
| Government Ayurvedic Dispensaries/Posts | 2 |
| Government Homeopathic Hospitals | - |
| Government Homeopathic Dispensaries/Posts | - |
| Others | - |

A look at the health infrastructure available within the district indicates that with only one CHC the population coverage per CHC stands high at 50110. The average population covered per PHC is close to the norms of 30000 per PHC. However, considering the mountainous terrain of the district and the communication available, which makes a sizeable portion of the district inaccessible during the rainy season, providing healthcare to the people in the district becomes a major challenge. This is true in-spite of the fact that the population coverage per Sub centre is 3048 which is already exceeds the norms of IPHS (Rural Areas) and the average number of villages covered per SC is just 5. One of the major hindrances faced towards creation of provisions towards healthcare is the fact that the villages are scattered across the mountains and do not necessarily form pockets as would be ideal for the operations of the SCs.

When one takes look at the private healthcare facilities available within the district the situation that prevails becomes even clearer. There are only two nursing homes existing within the district and not a single specialist is present in the form of surgeon, paediatrician, gynaecologist or anaesthetist. The entire population therefore, depends exclusively on the public healthcare system thus creating a huge pressure on the CHC and the district hospital in particular. Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

Current Service Norms

The services currently provided by each facility level is as follows

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No of Beds | Occupancy Rates | OPD Attendance |  |
| District Hospital | 30 | 85 % | 55 per Day | Medicine, Delivery Services, Sterilization (Mini Lab.) , Minor Operation, Satellite Blood Bank, Laboratory Investigation (Routine and HIV Testing), TB-Sputum Examination, X-Ray, Malaria – Blood MP etc. |
| CHC | 10 | 71 % | 30 per Day | Delivery, Minor Surgery, Sterilization (Mini Lab.), Laboratory Investigation (Routine and HIV Testing), TB-Sputum Examination, Malaria – Blood MP etc. |
| PHC | 10 | 60 % | 20 per day | Delivery, Minor Surgery, Sterilization (Mini Lab.), Malaria – Blood MP, etc. |
| Sub-Centres | - | - | 10 per day | ANC, Immunization (BCG, DPT, OPV, Measles, TT Pregnant and 10,16 yrs of Age., IFA, Vitamin A), FP and Minor Ailments, IEC etc. |
| Others (Anganwadi Centres) | - | - | - | Health, Nutrition, Education, VHND etc. |

When one looks into the details of the services offered by the district hospital, CHC and the PHCs, it becomes clear that the services offered are not up to the mark by IPHS norms and standards. One of the major weaknesses lies in the fact that none of these facilities especially the district hospital and the CHC do not have the specialists required to effect complete healthcare. The public healthcare facilities therefore end up providing just delivery services, general medicine support, and minor operations and conducting minor operations. The medical officers working in these healthcare facilities are left with no other option but to refer the patients requiring specialist care to the Aizawl civil hospital.

DMHP plan for 2012 -2013; Lawngtlai District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary as per Annexure II | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Lawngtlai district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

istrict Mental Health Programme

Lunglei

Map of Lunglei district

Background

Lunglei district is the largest district in the state of Mizoram covering an area of 4536 sq km with the population of 140573 (Source : DOS, Government of Mizoram, 2008-2009). It is located in the southern part of the state, touching Myanmar are in the eastern international and Bangladesh in the western international border and is bounded in the North by Serchhip District and in the South by Lawngtlai District. It is 235 kms from the State Capital Aizawl and is connected by National Highway No 54. Being situated in the southern part of the state, it is mostly an accessible district, though there are some areas/villages which are difficult to reach due to lack of proper roads, transportation and communication systems. Inaccessibility of healthcare services to the people of these difficult-to-reach pockets remains cause for concern.

Majority of the people are Christians and minority of the population formed by Hinduism, Muslim, Buddhism, Sikhism, Jainism and other tribal religions common amongst the people living near the international borders. Majority of the people speaks Mizo and few people speak Chakma, Lakher, Mara etc.

During the last 20 years, the health situation of the district has not been very encouraging, with high IMR, MMR and deaths due to malaria due to inadequacy of health infrastructure, transportation facilities and a well-organized and easily accessible referral system.

- Situation Analysis

The profile of this district can be summarized under the following heads:

Administrative profile

The District Headquarter of Lunglei District is Lunglei. Lunglei District is divided into 4 CD Blocks covering 161 villages. There are 123 Village Councils (Gram Panchayats). The District is divided into 7 assembly constituencies.   81% of the villages are categorised as villages with a population below 500 and 16% of the villages are categorised as villages with a population 501-2000 and only 1% of the villages are categorised as villages with a population 2001-5000.

Administrative Profile

| Administrative levels | Description/Number |
| --- | --- |
| District Headquarter | Lunglei |
| Assembly Constituencies (no.) | 7 |
| Number of Blocks (CD Blocks) | 4 |
| Number of Village Councils (Gram Panchayats) | 132 |
| Number of Villages | 161 |
| Number of Villages with population below 500 | 131 |
| Number of Villages with population 501 – 2000 | 27 |
| Number of Villages with population 2001 – 5000 | 2 |
| Number of villages with 5000+ population | 1 |

(Source : Statistical Handbook, Mizoram 2006)

Geography and Climate

Lunglei is situated in the southern part of Mizoram and is a hilly district covered by forest throughout the year. There are no plain areas. The climate of the region is tropical, with the following the seasons; summer season starting from last week of May up to September followed by winter season lasting up to February. Apart from this, the monsoon season starts from June, lasting up to October every year. There are many important rivers in the district making communication difficult, especially during the rainy season. Those are: the Tlawng river, Mat river, Khawchhak Tuipui river, Tuichawng river, Kau river and Khawthlang Tuipui (Karnaphuli). The main occupation of the people living in this district is jhum cultivation. The most common crops in the region are rice, maize, pulses, oil-seeds, cotton, tobacco, sugarcane and potatoes. Apart from these, orange, banana, passion fruit, areca nut, ginger and turmeric are also cultivated.

The district receives adequate rainfall every year. The average rainfall in the district headquarter is recorded as 4076 ml (2004). The district usually faces elemental problems like landslides and storms every year. The total length of road in the district is 633.7 Kms and the road density is 7.15. Most of the places are accessible by road except areas near the district borders. But, during the rainy season, many of the places are difficult to access due to landslides etc. The district is connected with the state capital and other districts by road. Daily buses and sumo services are available for communication and goods are transported by lorries and trucks.

Demographic Profile

The following table reflects the demographic profile of the district

Source: Target Census 2009

| Indicators | District | State |
| --- | --- | --- |
| Population |  |  |
| Males | 71163 | 459109 |
| Female | 70563 | 429464 |
| Total | 141726 | 888573 |
| Population Density | 31.26 | 42 |
| Urban | 58560 | 306794 |
| Rural | 83166 | 581779 |
| Scheduled Castes | 41 | 272 |
| Scheduled Tribes | 141685 | 839310 |
| Others |  | 48991 |
| Languages | Mizo, Chakma, Mara | Mizo |
| Religions | Christian, Hindu, Sikh, Muslim, Buddhist, Jain and other tribal religions | Christian |
| Children (0-5 years) | 14785 | 143743 |
| Adolescents (10-19 years) | 19285 | 195486 |
| Women (14-45 years) | 17153 | 159943 |
| Population Below Poverty Line (BPL) | 13406 |  |
| Population growth rate (1991-2001) | 23.1 | 28.8 |
| Vital Statistics |  |  |
| Crude Birth Rate | 19 | 21.9 |
| Crude Death Rate | NA | 5.10 |
| Sex Ratio |  |  |
| Overall | 989 | 935 |
| Child | 754 | 964 |
| Literacy |  |  |
| Total | 84.20 | 88.8 |
| Literacy among Males | 85 | 90.7 |
| Literacy among Females | 83.8 | 86.7 |
| Total | 84.20 | 88.8 |

From the above table it is being observed that the district covers around 15.9% of the total population of the state. The population density of the district is 31.26, which is far less than the state average of 42. Though there is only one urban area in the district, a large section of the population (41.3%) live in that area. Analysis from the above table reveals that the percentage of children, adolescent, and women of reproductive age are 10.4%, 13.6% and 12.1% respectively.

The literacy rate of the district is lower than that of the state, both for males and females. The sex ratio is worse than the last year, but a reversal of the sharp decline in the sex ratio of children has been achieved.

Health Infrastructure

Health Facilities

| Public Health Facility | Number |
| --- | --- |
| District Hospital | 1 |
| Sub-Divisional Hospital | 1 |
| Community Health Centres (CHC) | 1 |
| Average population per CHC | 11253 |
| Primary Health Centres (PHC) | 9 |
| Average population per PHC | 5869 |
| Sub-Centres (SC) | 72 |
| Average population per SC | 1933 |
| Average number of villages covered per SC | 2.27 |
| Urban Health Centres (UHC) | 1 |
| Average population per UHC | 5000 |
| Government Ayurvedic Hospitals | 1 No under construction |
| Government Ayurvedic Dispensaries/Posts | 0 |
| Government Homeopathic Hospitals | 0 |
| Government Homeopathic Dispensaries/Posts | 0 |
| Others | 0 |

As far as the health facilities are concerned, there is only one DH, 1 SDH, 1 CHC and 9 PHCs in the district. There are no Homeopathic or Ayurvedic hospitals functioning in the district. Through the 72 Sub-Centres under the 9 PHCs, the district looks after its population and provides the basic healthcare facilities.

| Private Health Facility | Number |
| --- | --- |
| For Profit | 1 |
| Not-for Profit | 0 |
| Private Practitioners (GP) | 0 |
| Surgeons | 1 |
| Paediatricians | 0 |
| Gynaecologists | 1 |
| Anaesthetists | 0 |
| Homeopaths | 0 |
| Ayurvedic Practitioners | 0 |
| Others | 0 |

From the above table, it is being found that the scope to access to the private facilities is very limited in the district as there is only one private facility that has been functioning on profit basis. No private specialist doctors are available in the district to provide service for the people, apart from one surgeon and one gynaecologist in private Hospital. This implies that the healthcare system is entirely dependent on the public healthcare facilities.  This is why; more Sub-Centres are needed, along with the up gradation of the existing ones for improving the quality and access of healthcare service delivery.

Health Workforce

Health Workforce in the District

| Staff Position | Sanctioned | In-Position |  | Vacant |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
| Chief Medical Officer |  | 1 | 0 | 0 |
| Deputy Chief Medical Officer / Additional CMO / Additional DHO / RCH Officer / AYUSH Officer |  | 0 | 0 | 1 |
| Medical Superintendent – DH |  | 1 | 0 | 0 |
| Senior Medical Officer including Specialists – SDH (including MOs from AYUSH) |  | 3 | 0 | 0 |
| Gynaecologist |  | 1 | 0 | 3 |
| Paediatrician |  | 1 | 0 | 3 |
| Anaesthetist |  | 1 | 0 | 3 |
| Surgeon |  | 1 | 0 | 3 |
| Medical Officer - General Grade (from AYUSH also) |  | 7 | 4 | 6 |
| Medical Officer - General Grade – Female |  | 5 | 4 | 5 |
| District TB Officer |  | 1 | 0 | 0 |
| X-ray Technician |  | 3 | 1 | 3 |
| Staff Nurse |  | 72 | 59 | 15 |
| Chief Pharmacist/Pharmacist |  | 8 | 0 | 5 |
| Lab Technician/Senior LT |  | 13 | 7 | 8 |
| BCG team Leader |  | 0 | 0 | 1 |
| BCG Technician |  | 0 | 0 | 4 |
| Eye Assistant/Ophthalmic Assistant |  | 4 | 0 | 6 |
| Occupational Therapist |  | 0 | 0 | 1 |
| Physiotherapist |  | 0 | 0 | 2 |
| Health Educator |  | 0 | 3 | 2 |
| Dental Hygienist/Dental surgeon |  | 3 | 0 | 9 |
| Chief Clerk/Head Assistant |  | 1 | 0 | 1 |
| Statistical Assistant/ Senior SA |  | 5 | 0 | 9 |
| Senior Assistant |  | 0 | 0 | 2 |
| Senior Clerk/UDC |  | 7 | 0 | 3 |
| Computer Clerk / Junior Clerk / LDC |  | 8 | 0 | 9 |
| Stenographer |  | 0 | 0 | 2 |
| Public Health Nurse(District Nursing Superintendent) |  | 1 | 0 | 1 |
| Food Inspector |  | 0 | 0 | 2 |
| Drugs Inspector |  | 2 | 0 | 1 |
| Store keeper cum Clerk |  | 0 | 0 | 1 |
| Malaria Inspector/ Special Officer(Malaria) |  | 1 | 0 | 1 |
| Health Education Officer |  | 1 | 0 | 0 |
| Health Supervisor(Male) |  | 11 | 0 | 1 |
| LHV |  | 11 | 0 | 0 |
| HFW(ANM) |  | 61 | 28 | 10 |
| MPW |  | 71 | 14 | 19 |
| Refrigerator Mechanic |  | 0 | 0 | 1 |
| Electrician |  | 0 | 0 | 4 |
| Refrigerator Assistant |  | 0 | 0 | 4 |
| X-ray Technician |  | 2 | 0 | 3 |
| ECG Technician |  | 1 | 0 | 2 |
| OT Technician |  | 0 | 0 | 3 |
| Projectionist |  | 0 | 0 | 1 |
| Driver |  | 17 | 3 | 5 |
| Class IV staff |  | 127 | 10 | 10 |
| Sweeper |  | 5 | 0 | 6 |

Some additions to this existing workforce, as reflected below:

| Sl No | Staff Position | Number | Status |
| --- | --- | --- | --- |
| 1 | SM Consultant / MO (RCH II) | 5 | Contractual |
| 2 | Staff Nurse / PHN (RCH II) | 39 | Contractual |
| 3 | HFW(ANM) / Health Worker (RCH II) | 12 | Contractual |
| 4 | Lab Technician (RCH II) | 7 | Contractual |
| 5 | Grade IV Staff (RCH II) | 8 | Contractual |
| 6 | Project Assistant (RCH II) | 1 | Contractual |
| 7 | Data Entry Operator (RI) | 1 | Contractual |
| 8 | Accounts Clerk | 1 | Contractual |

Though workforce is treated as one of the most important aspects to carry out any planned activities, from the above table it is evident that that there are some critical positions that remain vacant in this district – leading to a dismal situation in delivering the basic as well as emergency healthcare services. Apart from the above demonstrated positions, there are other posts such as Eye Assistant, Dental Surgeon, Health Educators, MPW etc that need to be filled up immediately to strengthen the existing healthcare delivery system in the district. Most interestingly, a great deal of confusion prevails in defining the sanctioned posts, implying that there is a structured system of appointment, transfers, promotions etc. is non-existent in the district.

Current Service Norms

The services currently provided by each facility level are as follows:

source: District Health Office, Lunglei District

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
|  | No of Beds | Occupancy Rates | OPD Attendance Average Per day |  |
| District Hospital | 110 | 65% | 200 | OPD, First Aid, Treatment of Minor Ailment, Major Surgery, Minor Surgery, Safe Delivery, Normal and complicated delivery, Caesarean section, MTP, C-Section, IUD, Tubectomy |
| Sub-Divisional Hospital | 50 | 52% | 80 | OPD, Leprosy treatment including indoor treatment, Normal and Complicated Delivery, Minor Surgery, MTP, Tubectomy, IUD |
| CHC | 30 | 46% | 150 | OPD, Minor Surgery, Safe Delivery, MTP & Tubectomy |
| PHC | 10 | 36.52% | 80 | OPD, Minor Surgery, Safe Delivery, MTP & Tubectomy |
| Sub-Centres | 0 | 0 | 10 | First Aid, H.E., Treatment of minor ailment, IUD Insertion & Immunization |
| UHC | 4 | 20% | 20 | OPD, Normal Delivery, Tubectomy, IUD, minor ailments |
| Others (Private Hospital) | 100 | 60% | 100 | Emergency, OPD, Major Surgery, Normal and Complicated Delivery, CS, FP services |

The District hospital in this district takes care of a large number of people, with an average OPD attendance rate of 200 per day. The bed occupancy rate of this facility is remarkably high with more than 65% occupancy rate justifying the fact that the District needs another such facility within its own area that may be possible by upgrading the existing CHC.  At the SDH also, while the average bed occupancy rate is 52% and the average OPD attendance is about 80, there are major seasonal variations. During the monsoons, malaria is a big problem and both OPD and IPD become stretched beyond their capacity.

DMHP plan for 2012 -2013; Lunglei District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary as per Annexure II | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Lunglei district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

District Mental Health Programme

Aizawl

Map of Aizawl E

Map of Aizawl E

BACKGROUND

In the state of Mizoram, there used to be three administrative districts after the Mizoram attained Statehood in 1986. During this period, Aizawl District which was large in population and area, the Mizoram government decided to split Aizawl District into two, namely – Aizawl East District and Aizawl West District for Health Department. Again, Mizoram is divided into eight administrative districts. Aizawl District remains divided into two and so Aizawl District is under two Chief Medical Officers. Aizawl East District is situated at central and northern part of Mizoram bounded by Kolasib District, Cachar District (Assam) and Manipur in the north; in the west Kolasib District and Aizawl West District, in the south Serchhip District and in the east Champhai District. It has a total area of 2693 sq. Km with a total population of 212965, of which 1, 34, 493 (63.15 %) live in Aizawl City. The remaining 78, 472 (36.85 %) live in rural area. Most of the PHC/CHC and Sub-Centres are connected by fair weather road. But in a center like Phuaibuang PHC, there is difficulty in transport and communication throughout the year. The religion of the district is mainly Christianity and language spoken is Mizo language. There are some areas in the north which spoke Hmar and Paite dialect.

The District is divided into four Blocks such as Thingsulthliah Block, Darlawn Block, Phullen Block and Tlangnuam Block. There are 2 CHC, 2 UHC, 5 PHC, 50 Sub Centres and  20 Clinics. To meet the healthcare needs of all areas, a strategy for infrastructure development has been formulated to strengthen or upgrade the existing facilities. Recently Thingsulthliah PHC is upgraded to CHC .

Administrative profile

The District headquarter is situated in Aizawl headed by Deputy Commissioner. He is responsible of maintaining Law & Order, revenue, civil supplies etc. Under the Deputy Commissioner direction the District is divided into four (4) rural development blocks:

Thingsulthliah Bock

Darlawn Block

Phullen Block

Tlangnuam Block

The details of the administrative profile is given below

| Administrative levels | Description/Number |
| --- | --- |
| Assembly constituencies (no.) | 8 |
| Number of Blocks (CD Blocks) | 4 |
| Number of Village Councils | 110 |
| Number of villages | 115 |
| Number of villages with population below 500 | 24 |
| Number of villages with population 501 - 2000 | 39 |
| Number of villages with population 2001 – 5000 | 15 |
| Number of villages with 5000+ population | 37 |

As it is indicated in the table above, there are 115 villages. Majority of the villages (110) are having Village council and the remaining villages (5) do not have Village Council administration. The number of villages having population less than 500 is 24 which are 20.86% of the District. No. of villages with population ranging between 501 – 2000 is 39 (34%) which is the highest in the district and the villages mentioned above especially population 5000+, are not necessary a rural villages but Urban areas in Aizawl. Like rural areas, these urban villages also have sub centres for basic health services. Because in the sub centres with the population of 5000 + areas the work load is heavy and is divided into sub centre clinic areas which are under sub centres concerned and functioned just like Sub Centre in all respect.

Geography and Climate:

Aizawl East District is situated at the North and Central part of Mizoram; it also covers about 50 % of the State capital, viz Aizawl.  It is hill ranges with no plain area. There are three (3) major rivers running in north-south direction viz. Tlawng, Tuirial and Tuirini. The annual rainfall is rather heavy during the Monsoons ie. April to  October. Aizawl District is situated at an altitude of 1678 metres above sea level. The district has an annual rainfall of 1714 mm. The temperature varies between a minimum temperature of 13 degrees Celsius during winter season and a maximum temperature of 30 degrees Celsius during summer season. Major crops grown are mainly rice, corn, ginger, chilli, mustard, etc. Every year landslides occurs with road blocks hampering health services in certain areas. Vehicular accident and cyclone also often brings disaster. Road connectivity is available to all the villages, although, some are not of all weather roads. Regarding public transport system, there are bus and Maxi cab (Sumo etc.) services in most of the areas, road connectivity and accessibility (both overall and seasonal): during the rainy season, the accessibility of Sub Centres becomes difficult and a few of them become totally inaccessible. Remarkably, the people of the areas are hard working and somehow self-sufficient for managing their livelihood. Some places like Sesawng, Baktawng, Seling, Chhingchhip etc are well-known for their high product of vegetables and fruits like banana, pineapple, passion fruits etc and they are the major suppliers of fruits and vegetables in Aizawl city.

Demographic profile:

Aizawl East District is the most populated district in Mizoram. More detail of the demographic profile is given in the table below:

Source: Census 2009   Statistics Cell of CMO, Aizawl East District.

| Indicators | District | State |
| --- | --- | --- |
| Population : |  |  |
| Males (Statistics Cell of CMO) | 1,09,856 | 459109 |
| Female (Statistics Cell of CMO) | 1,10,635 | 429464 |
| Total | 2,20,491 | 8,88,573 |
| Population Density (Statistics Cell of CMO) {per Sq.Km} | 133. | 42 |
| Urban (Statistics Cell of CMO) | 141071 | 441006 |
| Rural (Statistics Cell of CMO) | 79348 | 447567 |
| Scheduled Castes | 0.1 % | 210 |
| Scheduled Tribes | 93.2 % | 839310 |
| Languages | Mizo | Mizo |
| Religions | Christianity | Christianity |
| Children (0-5 years) | 24073 | 143734 |
| Adolescents (5-15 years) | 48342 | 195846 |
| Women (16-45 years) | 95523 | 159943 |
| Population Below Poverty Line (BPL) (own source) | 27.5 % | 20% |
| Number of Houses | 39959 | NA |
| Population growth rate (1991-2001) | --- | 28.8% |
| Vital statistics : |  | 52152 |
| Crude Birth Rate | 13.98 | 21.47% |
| Crude Death Rate | 1.6 | 4.97 |
| Literacy : |  |  |
| Literacy among Males | 96.7 | 90.97% |
| Literacy among Females | 96.3 | 86.67% |
| Total | 96.5 | 88.8% |

The male-female ratio in the district is almost 50-50 and the literacy rate among males is also similar to females. It is one of the two urban districts in the state, with 64% of the population living in urban Aizawl. Population density in the district is higher than the state while the death rate is lower. As per the standard norms of health institutions, there is a requirement of 80 Sub Centres and around 11 PHC/UHC.

SITUATION ANALYSIS OF AIZAWL EAST DISTRICT

Health Infrastructure

(a) Public Health facilities

The government health infrastructure in the district is described in the table below.

| Public Health Facility | Number |
| --- | --- |
| District Hospital | 0 |
| Community Health Centres (CHC) | 2 |
| Average population per CHC | 13805 |
| Primary/Urban Health Centres (PHC/UHC) | 8 (6+2) |
| Average population per PHC | 24111 |
| Sub-Centres/SC clinic | 70 (50+20) |
| Average population per SC | 3150 |
| Average number of villages covered per SC | 2 |
| Government Ayurvedic Hospitals | 0 |
| Government Ayurvedic Dispensaries/Posts | 1 |
| Government Homeopathic Hospitals | 0 |
| Government Homeopathic Dispensaries/Posts | 0 |
| Others | 0 |

As can be seen from the table above, the coverage by public health institutions in the district is less than adequate. Going by the population norms, there are 70(50+20) Sub Centres for a requirement of 80 and there are 8 PHC/UHC against a requirement of 11. This is mainly because of the high population density in urban areas, and so the Sub Centres in Aizawl City are having Clinics for better serving of the population and better implementation of all health programmes. There is no District Hospital in the district as there is one Civil Hospital at the state level in Aizawl under the Department of Hospital and Medical Education.

(b) Private Health Facilities

| Private Health Facility | Number |
| --- | --- |
| For Profit | 7 |
| Not-for Profit | 0 |
| Surgeons | 7 |
| Paediatricians | 5 |
| Gynaecologists | 6 |
| Anaesthetists | 4 |
| Homeopaths | 3 |
| Ayurvedic Practitioners | 5 |

As seen in the above table, there are some private Hospital and clinics and specialists like surgeons, gynaecologists and paediatricians are available, though not in big numbers, and concentrated only in Aizawl.

Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

Health Workforce in the district

| Staff Position | Sanctioned | In-Position |  | Vacant |
| --- | --- | --- | --- | --- |
|  |  | Regular Staff | Contractual Staff |  |
| Chief Medical Officer | 1 | 1 | 0 | 0 |
| Senior Medical Officer | 2 | 2 | 0 | 0 |
| Gynaecologist | 2 | 0 | 0 | 2 |
| Paediatrician | 2 | 0 | 0 | 2 |
| Anaesthetist | 2 | 1 | 0 | 1 |
| Surgeon | 0 | 0 | 0 | 1 |
| Pathologist | 0 | 0 | 0 | 1 |
| Radiologist | 0 | 0 | 0 | 1 |
| Medical Officer - General Grade - Male | 5 | 2 | 3 | 0 |
| Medical Officer - General Grade - Female | 7 | 2 | 5 | 0 |
| Dental Surgeon | 2 | 2 | 1 | 5 |
| Matron | 0 | 0 | 0 | 1 |
| District Administrative Officer | 0 | 0 | 0 | 0 |
| Bio-Chemist | 0 | 0 | 0 | 0 |
| District Malaria Officer | 2 | 2 | 0 | 0 |
| Assistant Accounts Officer | 0 | 1 | 0 | 0 |
| Chief Food Inspector | 0 | 0 | 0 | 0 |
| Asst Matron | 0 | 0 | 0 | 0 |
| Sister Tutor | 0 | 0 | 0 | 0 |
| P.H.N. Tutor | 0 | 0 | 0 | 8 |
| Chief Tutor | 0 | 0 | 0 | 0 |
| Sister | 3 | 3 | 0 | 0 |
| Staff Nurse | 39 | 15 | 24 | 0 |
| Chief Pharmacist | 0 | 0 | 0 | 0 |
| Lab Technician | 10 | 6 | 4 | 0 |
| Dark Room assistant | 0 | 0 | 0 | 0 |
| BCG team Leader | 0 | 0 | 0 | 0 |
| BCG Technician | 0 | 0 | 0 | 0 |
| Eye Assistant | 1 | 1 | 0 | 0 |
| Occupational Therapist | 0 | 0 | 0 | 0 |
| Physiotherapist | 0 | 0 | 0 | 0 |
| Health Educator | 2 | 1 | 1 | 0 |
| Dental Hygienist | 0 | 0 | 0 | 0 |
| Health Visitor or Health Supervisor (TB) | 2 | 0 | 2 | 0 |
| Asst. Superintendent (Hospital - Office) | 0 | 0 | 0 | 0 |
| Chief Clerk/Account Clerk | 0 | 0 | 0 | 0 |
| Statistical Assistant/ Senior SA | 2 | 2 | 0 | 0 |
| Senior Assistant | 1 | 1 | 0 | 0 |
| Senior Clerk | 1 | 1 | 0 | 0 |
| Computer Clerk / Junior Clerk/DEO | 4 | 0 | 4 | 0 |
| Stenographer | 0 | 0 | 0 | 0 |
| Tutor ANMTC (Training Centre) | 0 | 0 | 0 | 0 |
| Public Health Nurse | 0 | 0 | 0 | 1 |
| District Public Health Nurse | 0 | 0 | 0 | 1 |
| Food Inspector | 1 | 1 | 0 | 0 |
| District Health Education Information Officer | 0 | 0 | 0 | 1 |
| Store keeper cum Clerk | 0 | 0 | 0 | 1 |
| SLT - Senior Lab Technician | 2 | 2 | 0 | 0 |
| Maleria Inspector/ Sr. Malaria Inspector | 2 | 2 | 0 | 0 |
| Health Education Officer | 0 | 0 | 0 | 1 |
| Pharmacist | 5 | 5 | 0 | 3 |
| Health Supervisor (M) | 10 | 10 | 0 | 0 |
| LHV/ Health Supervisor (M) | 11 | 11 | 0 | 0 |
| ANM/HFW Health Worker (F) | 79 | 56 | 68 | 1 |
| MPW/Health Worker (M) | 80 | 56 | 24 | 3 |
| Refrigerator Mechanic | 0 | 0 | 0 | 1 |
| Electrician | 0 | 0 | 0 | 1 |
| Refrigerator Assistant | 0 | 0 | 0 | 1 |
| X-ray Technician | 4 | 3 | 1 | 0 |
| ECG Technician | 0 | 0 | 0 | 0 |
| O.T Technician | 0 | 0 | 0 | 2 |
| Projectionist | 0 | 0 | 0 | 0 |
| Lab Asst. | 4 | 4 | 0 | 2 |
| Driver | 9 | 6 | 3 | 0 |
| Class IV staff | 112 | 99 | 13 | 0 |
| Cook(IV Grd. staff work as cook) |  |  |  |  |
| Sweeper | 6 | 6 | 0 | 0 |
| Mali (IV Grd. staff Mali) | 2 | 2 | 0 | 0 |
| Dhobi (IV Grd. staff Dhobi) | 3 | 3 | 0 | 0 |

There is no specialist in any discipline in all the health institution due to lack of manpower. The people especially in rural areas are deprived of the specialist facilities like Obstetrics & Gynaecology, General surgery, Paediatric medicine, Anaesthesiology amongst others.  There is no Health supervisors female at Khawruhlian and Phuaibuang PHC. There are two (2) H/S (F) and (M) each at Aizawl North and Aizawl East Main Centre while there is no H/S (F) at Suangpuilawn and H/S (M) at Phuaibuang Main Centre. Dental Surgeon is posted only at two CHC and one PHC within the whole District

Current Service Norms The services currently provided by each facility level are as follows:

| CRITICAL STAFFs | No. OF FACILITIES | GIVE NAMES OF FACILITIES | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No of Beds | Occupancy Rates | OPD Attendance |  |
| CHCs with Obstetric, Gynae, Paediatrician and Anaesthetist (either qualified or trained) available | 2 | Saitual CHC Sakawrdai CHC | 30 | 40% | 70 | OPD, Indoor, X-Ray, Lab Test, (Sputum test, Blood RE, Stool RE), MCH services, VCTC |
| PHCs with Medical Officer Available | 2 | Thingsulthliah PHC Darlawn PHC Khawruhlian PHC Suangpuilawn PHC Phuaibuang PHC Phullen PHC | 10 | 35% 25 % | 49 23 | OPD, Indoor, X-Ray Lab. Services (blood MP & RE, Stool RE, Urine RE.), MCH services . |
| UHC | 2 | Ramhlun UHC ITI UHC | 10 | 30% |  | OPD, Indoor, Delivery, MCH Service |
| Sub-Centre with ANM available | 50 SC+20Clinic | 79 ANMs at 50SC+20Clinic | 0 |  |  | OPD, ANC,PNC. |

The CHC and PHC have standard number of beds and the utilisation varies seasonally. Cases in the OPD are not very high in the PHC and CHCs. This may be because of the easy access to the Civil Hospital, which does not necessitate going to PHC/CHC. Due to lack of infrastructure and manpower, the health institutions are far from fulfilling IPHS standard of providing expected services.

AIZAWL WEST

- BACKGROUND

A)	History of Creation of the District

In the State of Mizoram, there used to be only three administrative districts after Mizoram attained statehood in 1986:

Aizawl District

Lunglei District

Chhimtuipui District

However, as the population of Aizawl district is almost half of the entire population of the State. Aizawl district has  two Chief Medical Officers’ jurisdictions: the Aizawl East District and the Aizawl West District. Aizawl itself was also divided among these two CMOs, though administratively it continues to remain one district.

During the later part of the 1990s, the Government of Mizoram decided to have eight administrative districts for the State instead of three. Hence new districts are established from the existing three districts. The new districts are:

New districts created from Aizawl district

- Aizawl District

- Kolasib District

- Champhai District

- Serchhip District

- Mamit District

New districts created from Chhimtuipui District

- Saiha District

- Lawngtlai District

Lunglei District remains unchanged.

In the new Aizawl District as even the city of Aizawl was under two Chief Medical Officers, the department of Health & Family Welfare and the Government of Mizoram decided that the district may still be under two CMOs for better implementation and monitoring of healthcare service deliveries.

The Aizawl West District Headquarters is located in the southern site of the Aizawl City, and the Aizawl West District is bounded by :

North	:	Aizawl East and Kolasib District of Mizoram

West 	:	Mamit District of Mizoram

South	:	Serchhip District of Mizoram

East	:	Aizawl East District of Mizoram

In the city of Aizawl the Western part and the Southern part of the city is under the jurisdiction of the Aizawl West Chief Medical Officer.

The district consists of 1986.9 Sq.Km, and the total population is 138,540 (Source: Economic and Statistic survey report,2007). Two-third of the population is in the Aizawl Area and the State Capital is in this district. The Major Religion is Christianity, but there are 7240 Hindu, and 2408 Muslims. There are also few practitioners of other religions like Sikh, Buddhism and Jainism, though negligible in number (Economic & Statistics survey report, 2007 ). Languages spoken are Mizo and English, with some Hindi and some Nepalese also being spoken.

There has been major change in the population size and the healthcare service delivery system of the District as 50% of the urban population attached to Aizawl West during 2005-06 has been shifted to the healthcare delivery system of Aizawl East district in 2006-07.

B)  Administrative Profile:

The District administration is looked after by The Deputy Commisioner, He is responsible for maintaining Law & Order, revenue, civil supplies etc. Under the DCs direction the District is divided into three rural development blocks:

- Tlangnuam block

- Reiek block and

- Aibawk block.

These Blocks are headed by the Block Development Officers (BDOs). Further down the District is again divided into 86 Village Councils, which are the Mizo counterpart of the Panchayati Raj system in some other states of the country. Village Councils consist of representatives elected directly by the people of particular villages, where the Village Council President is the Overall in-charge of his area under the supervision of the Block Development Officer.

The table below captures the administrative profile of the district in further details:

Administrative Profile

| Administrative levels | Description/Number |
| --- | --- |
| Assembly constituencies (no.) | 5 |
| Number of Blocks (RD Blocks) | 3 |
| Number of Village Council | 86 |
| Number of villages | 96 |
| Number of villages with population below 500 | 18 |
| Number of villages with population 501 – 2000 | 59 |
| Number of villages with population 2001 – 5000 | 28 |
| Number of villages with 5000+ population | 1 |

C) Geography and Climate :

Aizawl West District is situated 1132 mtrs. above sea level and is a hilly terrain with long duration of rainy season starting from March to September. There are two big rivers, namely, Tlawng River in the west and Tuirial River in the east. The main crops of the district are fruits like banana, pineapple and passion fruit. The district is also rich in flowers like a variety of roses and orchids, as well as anthuriums. Though the rainy season is long, the district enjoys temperate climate throughout the year with average temperature remaining at 26 degrees Celsius.

One of the major problems of Aizawl West district is that it lies in the earthquake prone area and also suffers from other natural disasters like hailstorm, cyclone and landslide.

Though road connectivity is good, but during rainy season it is more or less inaccessible. The Public Transport system in the area as a whole is very poor, except in two PHC areas i.e Sairang PHC and Lengpui PHC.

D)	Demographic profile

The table below captures the demographic profile of the District, along with some of the important Human Development indicators:

| Indicators | District | State |
| --- | --- | --- |
| Population |  |  |
| Males | 76367 | 459109 |
| Female | 72974 | 429464 |
| Total | 149341 | 888573 |
| Population Density | 69/sq.Km | 42 |
| Urban | 78 % | 49.6 % |
| Rural | 22.3 % | 50.4 % |
| Scheduled Castes | 1385(1%) | 272 |

| Indicators | District | State |
| --- | --- | --- |
| Scheduled Tribes | 137155 | 831390 |
| Languages | Mizo, English, Nepalese, Hindi | Mizo |
| Religions | Christianity, Hinduism, Islam, Sikhism, Jainism, Buddhism | Christian |
| Children (0-5 years) | 17459 | NA |
| Children (1-3 years) | 11065 | NA |
| Total no. of eligible couple (15-45 years) eligible couple | 32675 | NA |
| Population Below Poverty Line (BPL) | 10661 | 22% |
| Population growth rate | 1.94% | 28.8 % |
| Vital Statistics |  |  |
| Crude Birth Rate | 26.1% | 21.9% |
| Crude Death Rate | 1.37% | 5.10% |
| Sex Ratio |  |  |
| Overall | 956 | 935/1000 |
| Child | 972 | 964/1000 |
| Literacy |  |  |
| Literacy among Males | 97.2% | 90.7% |
| Literacy among Females | 96.06% | 86.7% |
| Total | 96.6% | 88.8% |

SITUATION ANALYSIS

Health Infrastructure

- Health Facilities

As described in the demographic profile, this District has a high urban population, which is the reason behind the health infrastructure in the District being organized differently, as reflected in the table below:

Health Infrastructure

| Public Health Facility | Number |
| --- | --- |
| District Hospital | 1 |
| 40 bedded Kulikawn Hospital | 1 |
| 10 bedded PPU (attached to the above Hospital) | - |
| T.B Hospital (50 bedded) | 1 |
| Urban Health Centre | 2 |
| Average population per UHC | 73,000 (approx) |
| Supervisory Main-Centre (Aizawl City Area) | 2 |
| Sub-Centres Supervised | 13 |
| Primary Health Centres (PHC) | 6 |
| Average population per PHC | 12858 |
| Sub-Centres | 37 |
| Average population per SC | 4057 |
| Average number of villages covered per SC | 3 |
| Government Ayurvedic Hospitals | - |
| Government Ayurvedic Dispensaries/Posts | - |
| Government Homeopathic Hospitals | - |
| Government Homeopathic Dispensaries/Posts | - |
| Others | - |
| Private Health Facility | Number |
| For Profit | 2 |
| Not-for Profit | 0 |
| Private Practitioners (GP) | 2 |
| Surgeons | 2 |
| Paediatricians | 3 |
| Gynaecologists | 1 |
| Anaesthetists | 1 |
| Homeopaths | - |
| Ayurvedic Practitioners | - |
| Others | - |

Source: District Profile 2009-10, Statistical Department, District of Aizawl

The above table clearly brings out the load on existing government health facility in the district. Despite the large segment of urban population, private sector presence is minimal. This causes great stress on the public health system and calls for greater allocation of manpower and resources to cater to the healthcare needs of the population. This is clearly reflected in the average population catered to by the PHCs, which is above the national average for hilly states. The PHCs do not just run OPDs, but also provide normal delivery services and have to supervise the Sub-Centres, which have to be visited at least once every month. All of these activities have to be catered to by one MO. There are  6 PHCs and 4PHC are 24 X 7 facilities.

Aizawl West District being predominantly an urban district, in the place of CHCs, there are two Urban Health Centres, as reflected above. The situation in these UHCs is even more serious, with just one MO providing services to an average population of 73,000 – including daily OPD services and normal delivery services. These are also 24 X 7 centres and the load on the MO can be easily inferred.

The 2 Supervisory Main Centres in Aizawl City area have the responsibility of collecting all the data from the 32SCs and SCs Clinic, along with distributing all the necessary clinical (medicines, vaccines, medical supplies) and non-clinical (information brochures / calendars / posters) items.

Here we can see that both in private and public sector, there are no mental health professionals i.e. Psychiatrist, Clinical Psychologist, Psychiatric Social Worker and Psychiatric Nurse.

Current Service Norms

The services currently provided by each facility level are as follows:

| Level of Facility | Size |  |  | Services Provided |
| --- | --- | --- | --- | --- |
| OPD Attendance |  | Occupancy Rates |  |  |
| TB Hospital | 50 | 92% | 58/day | Complicated cases of Tuberculosis |
| 40 Bedded Kulikawn Hospital & 10 Bedded Post-Partum Unit | 50 | 88% | 396/day | Function as PPU and 40 Bedded Hospital |
| PHC | 8 | 50.2% | 82/day | Primary Health Services |
| Sub-Centres | - |  |  | Preventive Health Care |
| Others | 20+20 | 50% | 110/day | Tertiary Health Care (Private) |

DMHP plan for 2012 -2013; Aizawl District

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for Aizawl district in the 1st year is Rs. 46.37 lakhs.

Fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year.

Hence, total funds required is Rs. 46.37 lakhs + Rs. 3.5 lakhs = Rs. 49. 87 lakhs.

|  | Operationalization of the first phase of DMHP as reflected below: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.No. | Designation | No. of Staff | Status | Salary (P.M.) | 1st year | 2nd year (including annual increment of 5%) |
| 1 | Psychiatrist/Medical Officer | 1 | Deputation/ contract | 50000/ 30000 | 528000 | 554400 |
| 2 | Cl Psychologist/ Psychologist | 1 | contract | 30000/ 18000 | 252000 | 264600 |
| 3 | Psychiatric social worker/Social worker | 1 | contract | 30000/ 18000 | 252000 | 264600 |
| 4 | Psychiatric Nurse/Trained General Nurse | 1 | contract | 25000/ 15000 | 210000 | 220500 |
| 5 | Record keeper | 1 | contract | 10000 | 120000 | 126000 |
| 6 | Community Nurse/Case Manager | 1 | contract | 25000 | 300000 | 315000 |
| 7 | Case Registry Assistant | 1 | contract | 8000 | 96000 | 100800 |
|  | Total |  |  |  | Rs 1758000/- | Rs 1845900/- |
|  | GRAND TOTAL |  |  |  | Rs 17.58 Lakhs | Rs 18.459 Lakhs |

DMHP plan for 2012 -2012

| Activity |  | Allocation per district |  |
| --- | --- | --- | --- |
|  |  | 1st year | 2nd year |
| 1. | (Non Recurring) - Infrastructure for District DMHP Centre - Recruitment of DMHP staff and development of district plan | 2.00 | 0 |
| 2. | Staff Salary | 13.62 | 18.459 |
| 3. | Training - Training of PHC Medical officers, nurses, for each paramedical workers & other health staff - IEC and community mobilisation activities | 3.25 6 | 3.25 6 |
| 4. | Targeted interventions at community level | 12 | 12 |
| 5. | Drugs | 4 | 4.5 |
| 6. | Operational expenses of the district centre | 1 | 1 |
| 7. | Miscellaneous (e.g. ASHA/Caretaker) /Travel/ Contingency | 4.5 | 4.5 |
|  | Total in lakhs | 46.37 | 49.709 |

Allocation for each district in the 1st year is Rs. 46.37 lakhs

The proposal is for the following districts:

| Sl. No. | Name of the District | Allocation for each district (in lakhs) |
| --- | --- | --- |
| 1. | Kolasib | 46.37 |
| 2. | Mamit | 46.37 |
| 3. | Champhai | 46.37 |
| 4. | Serchhip | 46.37 |
| 5. | Lunglei | 46.37 |
| 6. | Saiha | 46.37 |
| Total |  | 278.22 |

The above mentioned districts are areas where DMHP has not yet been implemented.

In Aizawl District the DMHP had been implemented since 1999 and in Lunglei District since 2006. The programme in these 2 districts is currently functioning however additional activities are introduced by the DMHP for the Eleventh Plan Period such as:

- Life Skills Education and Counselling in schools

- College Counselling Services

- Work Place Stress Management

- Training of Health and Community Workers for all years

- Dedicated Monitoring team

- Essential participation of Community based organisations

- More effective integration of DMHP in the district health system

- Revised to seven member team for implementing DMHP.

Hence proposed funds for Aizawl and Lunglei is Rs 46.37 lakhs each, and  fund allocated for Research is Rs. 3.5 lakhs, which may be added to the total allocation for the 1st year. Therefore the consolidated total for eight districts of Mizoram is Rs 370.96 Lakhs. plus 3.5 lakhs i.e. Rs 374.46 Lakhs.

CHAPTER-5

MONITORING AND EVALUATION

It is a known fact that Monitoring and Evaluation through HMIS is the key for assessing  Physical and Financial progress of NRHM. The State therefore put up all out efforts for full operationalization.

1 (i).	For HMIS Portal :

Mizoram is using HMIS Portal for Monthly and Quarterly reporting System. On the other hand, due to poor connectivity of Internet facility in the State, HMIS Portal is used from District Headquarters onwards only. S/C, PHC, CHC,SDH, Accredited Private Hospital and DH monthly reports are entered  in HMIS Portal at the District Headquarters and the same is sent to the State.

Regarding Private Sector, Accredited Private Hospital monthly reports are captured and entered in HMIS Portal at the District Headquarters.

No HMIS Portal System is possible for reporting from S/C, PHC, CHC,SDH, Accredited Private Hospital and DH level. Hence reporting from these level to the District Headquarters is done by Hard copy for which printing of form etc. is suggested.

Since April,2011 the State is trying to capture all the  monthly physical performance by facility based in the ministry Web Portal having State level training in collaboration with RRC,Guwahati and Ministry Statistical Cell. Though there are some facilities which  cannot be access in the Portal, about 95% of facility based  monthly physical performance are already uploaded and forwarded from each district Headquarters to the State Headquarters and  State Headquarters to the Ministry.

(ii).	For MCH Tracking System.

Beside the problems faced in the internet connectivity in the State, about 181 facilities names cannot enter in the software due to Census Code do not compromise the Health Department administrative division in the State, so mapping of facility based for  online and Offline Version software for MCH Tracking System is not yet possible in the State. MCH tracking is implemented by Manual System in the State by using Tracking  Cards, Registers and Monthly Reporting Formats.

MCH Tracking Register, Card and Monthly reporting formats for both Mother and child are printed and already in used at all level of Sub-Centre and Main Centre/PHC/CHC. About 88% of Mother and 85% of  Children  are already register in the MCTS Registers. Pregnant  Mother register in the Sub-Centre since April,2010 and for New born child since April,2009  are tracked by Health Worker. Pregnant Mother and Children who have received services from Private clinics and Hospital are also track by ASHA with MCTS  Tracking Cards. In this regards, ASHA  are given incentives @ Rs. 50/- for tracking of Pregnant (Non JSY beneficiaries) completing 42 days of delivery. Besides, incentives @ Rs. 50/- for tracking of Children  who have received services from Private clinics and Hospital is also given to ASHA after having full Immunization.

2.	The monitoring team is set up at State and District Headquarters to monitor the physical and financial performance at all level of  facilities  periodically throughout the year. Monthly Review meeting at PHC/CHC level, district level and State level quarterly reviewed meeting are regularly organized throughout the year.

State has already implemented Death Auditing and Review for Maternal and Infant for which State and District level Death Review is formed in each District Headquarters. Facility Based Death Review Committee is also will be  formed at all the District Hospitals and at 2 NGO Hospital namely Presbyterian Hospital, Durtlang and Christian Hospital Serkawn with accordance of Notification issued by the  Government of Mizoram as per GOI guidelines for MDR.

a.	Integration of Monitoring & Evaluation activities across programmes :

The main component of Monitoring and Evaluation is done through State HMIS, Review Meeting at State and District on Quarterly basis and at PHC & CHC level on monthly basis. Besides, field visit by Nodal Officer and Programme Officer from the State Hqtrs. and District Programme Officer, DPM (NRHM) etc. as well as GOI and RRC monitoring team on various health programmes do the monitoring & evaluation visit.

The flow of chart for Monthly State HMIS is scaled up following the existing system of the Health Facility Protocol as under.

- SC (HW by Hard Copy)                                                                   Main Centre

- MC (HS by Hard Copy)                                                                    Dist. Hqtrs.

- PHC/CHC (Acct. Clerk/HS by Hard Copy)                                       Dist. Hqtrs.

- DH/SDH/Private Hosp. (Acct. Clerk/Stats. Personal by Hard Copy)   Dist. Hqtrs.

- Dist Hqtrs. (DEO-NRHM/RCH by using DHIS2 software)                  State Hqtrs.

- State Hqtrs. (DEO, Consultant (HMIS) by HMIS Portal)                  Govt. of India

For the smooth flow of HMIS, Statistical personal are given training relating to the indicators integrated in the format and Computer Software at District level.

MCH Tracking as already mentioned is   implemented in the State  by Manual system  using Tracking Cards, Registers and Monthly reporting formats. The flow of  Tracking is line up from Sub-Centre to PHCs/CHCs for Monitoring of Pregnant Mother and Children immunisation and consolidated report is sent to their respective District Headquarters.

Regarding Death Review, Infant death Review is included in the lines of Maternal Death Review of GOI guidelines of MDR   for which all  infant death should be Audited for review by   District and State  Death Review Committee. The same is assigned to the Facility Committee at District Hospital and 2 NGO Hospital.

b.	Monitoring and Evaluation Action Plan

M&E Action Plan may be made to strengthen the existing system of M&E system as under.

- To have accurate, timely submission of reports on Physical and Financial Management, Training of Statistical Personal/Acct. Clerks/Other Staff who deals in HMIS and Financial Reports will be   conducted.

- Regular monitoring and evaluation of monitoring team will be conducted  from State to District on quarter basis and District level to CHC/PHC and  CHC/PHC level to Sub-Centre level  on monthly basis and such cost of mobility for hiring Vehicles / TA/DA and fund requirement is  budget.

- Quarterly Review meeting is conducted at State and District level and Monthly Review meeting at CHC/PHC/MC. Also the   District level and Facility level Death review committee will be held on monthly basis and fund requirement for such meeting  is also budget.

iv.	Monitoring Formats, NRHM Reporting Formats, registers, MCH tracking Materials and Death Review Materials will print at the local Printing Press and fund requirement is  budget.

c. 	Ensuring Nodal Monitoring and Evaluation Officer :

Notification of Nodal M&E Officer for HMIS and MCH Tracking

| Level | Nos. Required | Nos. Present | Remarks |
| --- | --- | --- | --- |
| State | 1 | 1 |  |
| Districts | 9 | 9 | DIO/SMO at District Headquarters are acting as Nodal M&E Officer for HMIS and MCH Tracking. |
| CHC/PHC | 69 | 0 | Notification is under process for appointing MO incharged. |

d. 	Integration to facilitate capturing Physical Performance is operational whereas Financial Performance is not yet included in the HMIS Portal.

e.	There	is no SIHFW and RHFWTC etc. existing in the State of Mizoram. But training courses of different level of staff are undertaken. Training Plan, Load, Timeline along with Budget in general including Monitoring and Evaluation is Plan under RCH.

f.	MCTS has already being started in the State. But the implementation  by Online and Offline version Software prepared by NIC is  not possible in the State. However, MCH Tracking Card, Reporting Format and Register have been printed for used at different level.

| BUDGET ESTIMATE FOR MIONITORING & EVALUATION |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl.No | Major Head | Minor Head |  | Budget in Rs in lakh | Details (including cost per Unit) | Remarks | Amount approved in 2011-12 | Actual Exp. In 2011-12 |
| 1 | Strengthening of M&E / HMIS/ MCH tracking/Death review | Salaries of HMIS Consultant and Data Entry Consultant | 1.1 | 7.2 | Salaries of HMIS Consultant @ 35,000/- and Data Entry Consultant @ 18,000/- per month |  | 3.6 |  |
|  |  | Mobility for M & E Officers and other designated officers and Staffs | 1.2 | 6 | Monthly Field visit and Supervison on HMIS & MCTS by Nodal Officer and Designated Staff @50000/- per months |  | 1.5 |  |
|  |  |  | 1.2.1 | 18 | Quarterly Field visit and Supervison on HMIS & MCTS District Monitoring Team Leader/DPM & Statistical Personal @50000x4qtrsx9 |  |  |  |
|  |  |  | 1.2.2 | 14.22 | Monthly Field visit and Supervison by MO/CHO/HS at PHC/CHC/MC @1500x12qtrsx79= 1422000 |  |  |  |
|  |  | Workshops/Training on M&E | 1.3 | 1.5 | Workshop / Training on M&E at State Hqtrs. representing not more than 3 official from the District ie, District Monitoring team leader and DPM / other official designated by CMO will be conducted. DA will be given @ 400/- head for 5 days |  |  |  |
|  |  |  | 1.3.1 | 2.5 | Workshop / Training on M&E at 9 District Hqtrs. representing MO of PHCs/CHCs / other official designated by MO will be conducted. DA will be given @ 400/- head for 5 days |  |  |  |
|  |  |  | 1.3.2 | 1.5 | Training for MO and other official designated by MO will be conducted. TA will be given on actual expenses and DA will be given @ 300/- per head for 5 days |  |  |  |
|  |  |  | 1.3.3 | 5 | Training for CHO/HS/HW from Main Centre and SC will be conducted. TA will be given on actual expenses and DA will be given @ 200/- per head for 5 days |  |  |  |
|  |  | M&E Studies | 1.4 | 25 | End line Survey of 1st phrase NRHM will be conducted in the State. |  |  |  |
|  |  | Others - 1. Maternal and Infant Death Audit and Review committee | 1.5 | 0.36 | Maternal and Infant Death reporting incentive to ASHA @ Rs 50 per case X 20 nos.and 700 nos of maternal and infant death respectively. |  | 1.5 is budget under RCH 2011-12 PIP |  |
|  |  |  | 1.5.1 | 1.46 | Honorarium for conducting Audit @ 200/-per case of infant death for 2 person (incase Facility Auditing is needed) if not 100 for HW and @300/-per case of Maternal death for max. of 3 person (incase Facility Auditing is needed) |  |  |  |
|  |  |  | 1.5.2 | 2.59 | Monthly District Maternal and Infant Death Review committee expense - DA @ 400/- per head for 6 person approx. X 9 district X 12 months |  |  |  |
|  |  |  | 1.5.3 | 3.16 | Monthly Facility Maternal and Infant Death Review committee expense - DA @ 400/- per head for 6 person approx. X 11(ie 9 district hospital and 2 NGO Hospital) X 12 months |  |  |  |
|  |  |  | 1.5.4 | 3.6 | TA / DA @ 500/- per decease relatives attending District Maternal and Infant Death Review committee for 720 persons |  |  |  |
|  |  |  | 1.5.5 | 0.12 | State level Maternal and Infant Death Review committee expense - DA @ 400/- per head for 15 person approx. X half yearly |  |  |  |
|  |  | Sub Total |  | 92.21 |  |  |  |  |
| 2 | Procurement of HW/SW and other equipement | Hardware /Software procurement | 2.1 | 1.8 | 4 nos of Laptop Computer for Training on HMIS/MCH/MCP @ 45000/- |  | 16.83 |  |
|  |  |  | 2.2 | 0.48 | Internet Conection for 6nos of District @ 8000x6 (including cost of installation & Modem) |  | 0.84 |  |
|  |  |  | 2.3 | 3.95 | Others :1. Annual Maintenance of Computer (Hardware/Software) PHC/CHC/MC in District Capital@5000x79 |  | 4.1 |  |
|  |  |  | 2.4 | 1.44 | Operational Cost @4000x9x4 |  | 2.05 |  |
|  |  |  | 2.5.1 | 7.9 | 2. UPS 1KV @ 10000x79 |  | 0 |  |
|  |  | Sub Total |  | 15.57 |  |  |  |  |
| 3 | Operationalising HMIS at Sub District Lvel | Review of existing registers - to make them compatible with National HMIS | 3.1 | 0.15 | Field Visit to Study the existing Register. |  |  |  |
|  |  | Printing of New Registers/Forms | 3.2 | 3.5 | Printing of New form NRHM monthly report Forms for 600 nos. PHC/CHC/MC/SC/SC clinics |  |  |  |
|  |  | Training of Staff | 3.3 | 1.5 | State level training for District Statistical Personal official TA will be given on actual expenses and DA will be given @ 200/- per head for 5 days |  |  |  |
|  |  |  | 3.4 | 10 | Training on NRHM monthly reporting formats for CHO/HS/HW from Main Centre and SC at 9 district @ DA 200/- per head for 3 days and TA will be given on actual expenses |  |  |  |
|  |  | Sub Total |  | 15.15 |  |  |  |  |
| 4 | Operationalising MCH Tracking | Printing and reproducing Registers/Forms | 4.1 | 7.2 | 1. Printing of New Register for ANC/Immunisation/MCTS @ 600X600(for PHC/CHC/MC/SC/SC clinics)X2 |  |  |  |
|  |  |  | 4.1.2 | 5 | Printing of MCTS cards and monthly reporting Formats for 600 nos. PHC/CHC/MC/SC/SC clinics |  |  |  |
|  |  | Capacity building of teams | 4.2 | 3.5 | Ditrict level Training on Computer Software HMIS for 70 PHC/CHC/UHC Account's Clerk |  |  |  |
|  |  | Ongoning review of MCH tracking activities | 4.3 | 4 | Quarterly State level Review meeting @ 100,000X4 |  |  |  |
|  |  |  | 4.3.1 | 10 | Quarterly District level Review meeting @ 250,000X4 |  |  |  |
|  |  |  | 4.3.2 | 34.74 | Monthly PHC/CHC/MC level Review meeting @ 289526X12 |  |  |  |
|  |  | Monitoring data collection and data quality | 4.4 | 10 | Training on service indicators included in NRHM monthly reporting formats/ MCTS Cards,Registers/Monthly reporting formats / MCP cards for CHO/HS/HW from Main Centre and SC at 9 district @ DA 200/- per head for 3 days and TA will be given on actual expenses |  |  |  |
|  |  | Sub Total |  | 74.44 |  |  |  |  |
|  |  | Grand Total |  | 197.37 |  |  |  |  |
| (Rupees one hundred ninety seven thirty seven thousand ) only |  |  |  |  |  |  |  |  |

CHAPTER – 6:

FINANCIAL MANAGEMENT:

The state of Mizoram is following the guideline and frame work for delegation of administrative and financial powers under NRHM. The financial management system under NRHM in short is as follows:

- Budgeting for Various Activities: The budgeting for various activities under NRHM is prepared in accordance with FMR format. The pro. Management cost is kept well within the ceiling amount of 6% and for civil works is also within the ceiling amount of 33% as the state is a high focus state.

- Financial Management Staff: at the state level JD (Acct) who is a member of Mizoram Finance and Accounts Service cadre is appointed as SFM and one State Account Manager having M.Com degree at the state, also one A/C having B.Com degree and one DEO with a Cashier who is well versed in account system from state permanent service. In the District level one Dist. Acct Manager and one each A/C in all CHC and PHC with B.Com degrees are in station. Remuneration of the PMU staff including NDCP has been revised within the allocated/approved amount giving 10% increase over & above normal /soft posting for diff areas and another 10% increase for very/most difficult areas. Remuneration of the PMU staff including NDCP has been revised within the allocated/approved amount giving 10% increase over & above normal /soft posting for diff areas and another 10% increase for very/most difficult areas.

- Statutory Audit: Statutory Audit report and UCs for 2010-11 have been submitted for NRHM, RCH and all other NDCPs. No deficiency yet intimated by FMG till date

- Concurrent Audit: one chartered firm has been already appointed for performing for concurring audit in 2011-12 but reports are yet to be submitted.

- Implementation of Tally: Tally has been procured, formal training for 2 days conducted but operationalisation at state & district level. It is further felt imperative to conduct another proper training for state & district level so as to make tally function.

- Mode of funds transfer: funds are being release electronically from state to District, whereas district transfer funds down the line by electronic wherever possible and by cheque where electronic transfer facility is not available.

- Up loading of FMRs on HMIS portal: the system is functional at the state with GOI but, the same is not possible at the district level due to non availability of internet connection.

- Financial reporting under NRHM: FMRs for NRHM additionalties and RCH are sent in time but consolidated FMR for all NDCP is yet to catch up, however, the specific NDCP are submitting their FMR in time to their specific division at the central. FMR for NRHM additionalities and RCH are already submitted.

- MIS: is implemented and reports is submitted regularly and also enter on the Web portal.

- Statutory Audit: consolidate statutory audit report for 2010-11 for NRHM & all NDCP have been submitted already in the month of October, 2011. These reports includes right from District level while the district audit includes PHC& CHC of the concerned Districts.

Rogi Kalyan Samiti:

The Rogi Kalyan Samiti as the pivot of facility based planning and community involvement. RKSs have contributed to local level leadership and need based decision making. So far 678 district hospitals, 4875 CHCs, and 27596 other facilities have a registered RKS in place. The issues which now need to find a reflection in planning would interalia relate to:

- Constitution of RKS in 100% facilities

- Functional RKS against constituted facilities

- Performance of RKS and pace of utilization of funds

- Major heads under which RKS funds are being utilized

- Facilities utilized less than 50 % of RKS fund in 2010-11 & 11 -12- RKS funds are released to the District Health Society through electronic transfer and the DHS also transfer funds to District Hospital/SDH/CHC/PHC by electronic wherever possible and by cheque where electronic transfer facility is not available. There is no fund utilised less 50% of RKS .

- Activities being under taken by RKS

- Capacity building of RKS members (including number of training/workshop conducted for

- RKS members to revitalize the expectations of RKS in 2011-12)

- Status of RKS meetings- RKS meeting is conducted regularly under the chairmanship of SDO/BDO/VCP.

- Sharing of success stories and best practices.- Civil Hospital Aizawl is awarded ISO certificate  because of RKS.

- Monitoring and Review of functioning of RKS- Monitoring is developed and distribute to the District Health Society. Monitoring is done from the District Health Society due to insufficiency of staff in the state.

CHAPTER – 7:

INFRASTRUCTURE MAINTENANCE (TREASURY ROUTE)

CHAPTER - 8  :  INFRASTRUCTURE MAINTENANCE

- DIRECTION & ADMINISTRATION (Family Welfare Bureaus at State & District Level) :

- Direction :

| S/n | Name of Post | No. of Post | Pay Scale | Financial Implication for 1 month (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | JDHS | 1 | PB.3-15600-39100+GP 7600 | 88,300.00 |
| 2 | DDHS | 1 | PB.3-15600-39100+GP 6600 | 92,164.00 |
| 3 | SMEMO | 1 | PB.3-15600-39100+GP 5400 | 41,924.00 |
| 4 | R.O. | 1 | PB.3-15600-39100+GP 5400 | 45,706.00 |
| 5 | Officer i/c Cold Chain | 1 | PB.2- 9300-34800+GP 4400 | 34,416.00 |
| 6 | Assistant | 1 | PB.2- 9300-34800+GP 4400 | 35,619.00 |
| 7 | Technical Assistant | 1 | PB.2- 9300-34800+GP 4400 | 36,921.00 |
| 8 | UDC | 3 | PB.2- 9300-34800+GP 4200 | 1,00,743.00 |
| 9 | Asst. Editor | 1 | PB.1- 5200-20200+GP 2400 | 20,171.00 |
| 10 | Projectionist | 1 | PB.1- 5200-20200+GP 2400 | 23,478.00 |
| 11 | LDC | 2 | PB.1- 5200-20200+GP 2400 | 46,884.00 |
| 12 | Steno Typist | 1 | PB.1- 5200-20200+GP 2400 | 23,287.00 |
| 13 | Driver | 3 | PB.2- 5200-20200+GP 1900 | 59,259.00 |
| 14 | Peon | 3 | IS. 4440-7440+ GP 1650 | 47,619.00 |
| Total |  | 21 |  | 6,96,491.00 |
| Approximate requirement for one (1) year |  |  |  | 83,57,892.00 |

- Administration :

| 1 | DIO | 3 | PB. 3-15600-39100+ GP 6600 | 2,24,856.00 |
| --- | --- | --- | --- | --- |
| 2 | DFWMO | 1 | PB. 3-15600-39100+ GP 6600 | 74,952.00 |
| 3 | Dist.PH Supervisor (PHNO) | 1 | PB. 2-9300-34800+ GP 4600 | 35,619.00 |
| 4 | H/S (M&F) 1 each | 2 | PB. 2-9300-34800+ GP 4200 | 67,054.00 |
| 5 | DEMO | 1 | PB. 2-9300-34800+ GP 4600 | 35,619.00 |
| 6 | Dy. DEMO | 2 | PB. 2-9300-34800+ GP 4600 | 71,238.00 |
| 7 | Stat. Investigator | 3 | PB. 1-5200-20200+ GP 2800 | 33,527.00 |
| 8 | Health Worker (F) | 1 | PB. 1-5200-20200+ GP 2800 | 33,527.00 |
| 9 | Projectionist | 1 | PB. 2-5200-20200+ GP 2400 | 23,478.00 |
| 10 | I.S. | 1 | PB. 3-9300-34800+ GP 4200 | 40,161.00 |
| 11 | UDC | 3 | PB. 3-9300-34800+ GP 4200 | 1,00,743.00 |
| 12 | LDC | 4 | PB. 1-5200-20200+ GP 2400 | 93,768.00 |
| 13 | Steno Typist | 1 | PB. 1-5200-20200+ GP 2400 | 23,287.00 |
| 14 | Fridge Mechanic | 3 | PB. 1-5200-20200+ GP 2400 | 56,304.00 |
| 15 | Driver | 9 | PB. 1-5200-20200+ GP 1900 | 2,53,926.00 |
| 16 | Attendant (M&F) 1 each | 2 | IS – 4440-7440 + 1650 | 25,746.00 |
| 17 | F.A. | 2 | IS – 4440-7440 + 1650 | 25,746.00 |
| 18 | Peon | 3 | IS – 4440-7440 + 1650 | 38,619.00 |
| 19 | IV Grade | 2 | IS – 4440-7440 + 1650 | 25,746.00 |
| Total |  | 45 |  | 12,83,916.00 |
| Approximate requirement for one (1) year |  |  |  | 1,54,06,992.00 |

- MAINTENANCE OF SUB CENTRE :

| Sl.No | Category | Existing as on 1.4.2002 | Added after 1.4.2002 | Estimated in Total |
| --- | --- | --- | --- | --- |
| 1 | ANM | 388 | Nil | 388 |
| 2 | LHV | 85 | Nil | 85 |
| 3 | Male Multi Purpose Health Worker | 382 | Nil | 382 |

Basic requirements of Drugs & Equipments have been supplied to all the Sub Centres as per norms subject to the availability of Funds released from the Government of India. During 2010-11, a total sum of Rs.116.03 lakhs had been utilized for purchased of certain drugs and equipments. The minimal requirement of funds for the purpose to cover all the Sub Centres would be approximately Rs. 200.00 lakhs per anumn.

- URBAN FAMILY WELFARE CENTRES (UFWCs) :

| Sl.No | Type of facility | No. of Facility | Rent proposed | Contingencies proposed | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | II | 2 | Nil | 14,000/- | 14,000/- |

HR Involved

| Sl.No | Type of Post | No. of Posts | No. of staff in position | Estimated expenditure in 2012-13 |
| --- | --- | --- | --- | --- |
| 1 | IV Grade | 2 | 2 | Rs. 4.20 lakhs |

- HEALTH POSTS (Urban Revamping Scheme) :

| Sl.No | Type of facility | No. of facility | Rent proposed | Contingencies proposed | Total |
| --- | --- | --- | --- | --- | --- |

HR Involved

| Sl.No | Type of Post | No. of Posts | No. of staff in position | Estimated expenditure in 2011-12 |
| --- | --- | --- | --- | --- |

- BASIC TRAINING OF ANM/LHV TRAINING SCHOOL :

(Rupees in lakhs)

| Financial Year | No. of Training School | Total no. of Trainees trained in the year | Total no. of Staff in place | Total Funds allocated | Total expenditure incurred |
| --- | --- | --- | --- | --- | --- |
| 2007-08 | 1 | 40 (F-22,M-18) | 15 | 31.92 | 27.88 |
| 2008-09 | 1 | 42 (F) | 15 | 33.08 | 28.50 |
| 2009-10 | 1 | 60 (F-39,M-21) | 15 | 34.63 | 41.51 |
| 2010-11 | 1 | 60 (F-30,M-30) | 15 | 48.40 | 212.45 |
| 2011-12 | 1 | 60 (F-30,M-30) | 16 | 44.00 (upto 3rd Qtr) | 23.84 (Upto 2nd Qtr) |
| Total |  |  |  |  |  |

Information for the year 2012-13

| S/n | Name of Trg School | Total no. trainees to be trained in the year | Total no. of staff in place | Total Amt. proposed for salaries | Amount required for Stipend | Amount required for contingencies | Amount required for rent | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | H/W Trg. School | 60 | 16 (T-12, Nt-4) | 50.00 lakhs | 5.40 lakhs | 30.00 lakhs | Nil | 85.40 lakhs |
| 2 |  |  |  |  |  |  |  |  |

BASIC TRAINING FOR MULTI-PURPOSE HEALTH WORKER (Male)

(Rupees in lakhs)

| Financial Year | No. of Training Schools | Total no. of trainess trained in the year | Total no. of staff in place | Total Fund allocated | Total expenditure incurred |
| --- | --- | --- | --- | --- | --- |
| 2007-08 | 1 | 40 | 15 | 18.38 | 14.42 |
| 2008-09 | 1 | 42 | 15 | 19.24 | 21.08 |
| 2009-10 | 1 | 60 | 15 | 61.65 | 42.94 |
| 2010-11 | 1 | 60 | 15 | 47.64 | 73.48 |
| 2011-12 | 1 | 60 | 15 | 43.00 (Upto 3rd Qtr) | 22.24 (upto 2nd Qtr) |
| TOTAL |  |  |  |  |  |

Information for the year 2012-13

(Rupees in lakhs)

| S/n | Name of Trg School | Total no. trainees to be trained in the year | Total no. of staff in place | Total Amt. proposed for salaries | Amount required for Stipend | Amount required for contingencies | Amount required for rent | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | H/W Trg. School | 60 | 16 | 35.00 | 5.40 | 30.00 | Nil | 70.40 |
| 2 |  |  |  |  |  |  |  |  |

MAINTENANCE OF HEALTH & FAMILY WELFARE TRAINING CENTRES (HFWTC)

| Financial Year | No. of Training Schools | Total no. of trainess trained in the year | Total no. of staff in place | Total Fund allocated | Total expenditure incurred |
| --- | --- | --- | --- | --- | --- |
| 2007-08 |  |  |  |  |  |
| 2008-09 |  |  |  |  |  |
| 2009-10 |  |  |  |  |  |
| 2010-11 |  |  |  |  |  |
| 2011-12 |  |  |  |  |  |
| TOTAL |  |  |  |  |  |

Information for the year 2012-13

(Rupees in lakhs)

| S/n | Name of Trg School | Total no. trainees to be trained in the year | Total no. of staff in place | Total Amt. proposed for salaries | Amount required for Stipend | Amount required for contingencies | Amount required for rent | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |

| Functional Head Wise Classification of the Budget |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl.No. | Activity | Unit Cost | Physical Target | Required fund under NRHM |
| Human Resources |  |  |  |  |
| A | RCH |  |  |  |
| 1 | Contractual Staff & Services |  |  |  |
| 1 | Contractual Staff & Services(Excluding |  |  |  |
|  | AYUSH) |  |  |  |
| A.9.1 | ANMs,Supervisory Nurses, LHVs, |  |  | 972.15 |
| A.9.1.1 | Laboratory Technicians,MPWs |  |  | 61.63 |
| A.9.1.2 | Specialists (Anesthetists, Pediatricians, Ob/Gyn, Surgeons, Physicians, Dental Surgeons, Radiologist, Sonologist, Pathologist,Specialist for CHC ) |  |  | 50.00 |
| A.9.1.3 | PHNs at CHC, PHC level |  |  |  |
| A.9.1.4 | Medical Officers at CHCs / PHCs |  |  | 229.35 |
| A.9.1.5 | Additional Allowances/ Incentives to M.O.s of PHCs and CHCs |  |  |  |
| A.9.1.6 | Others - Computer Assistants/ BCC Co-ordinator, Dental Surgeon/Pharmacist/X-Ray Technician/BEE/FP Counselllor etc |  |  | 235.04 |
| A.9.1.7 | Incentive/ Awards etc. to SN, ANMs etc. |  |  |  |
| A.9.1.8 | Human Resources Development (Other than above) |  |  |  |
| A.9.1.9 | Other Incentives Schemes (Pl.Specify) |  |  |  |
| A.11 | PROGRAMME / NRHM MANAGEMENT COSTS |  |  |  |
| A.11.1 | Strengthening of SHS /SPMU (Including HR, Management Cost, Mobility Support, Field Visits ) |  |  | 100.93 |
| A.11.2 | Strengthening of DHS/DPMU (Including HR, Management Cost, Mobilty Support, Field Visits ) |  |  | 111.55 |
| A.11.3 | Strengthening of Block PMU (Including HR,Management Cost, Mobilty Support, Field Visits) ) |  |  | 103.70 |
| A.11.4 | Strengthening (Others) |  |  | 8.00 |
| A.11.5 | Audit Fees |  |  | 8.00 |
| A.11.6 | Concurrent Audit |  |  | 10.00 |
| A.11.7 | Mobility Support , Field Visits to BMO/MO/Others |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B.9 | Contractual Staff & Services(Only |  |  |  |
|  | AYUSH) |  |  |  |
| B.9.1 | Staff/ Supervisory Nurses /Other Staffs for PHCs,CHCs |  |  |  |
| B9.2 | Medical Officers at CHCs/ PHCs |  |  |  |
| C | Routine Immunisation |  |  |  |
| C.2 A) | Computer Assistants Salary |  |  | 11.88 |
| C.2 B) | Other HR Personnels(Technicians, Cold Chain Mechanic) |  |  |  |
| D | Other National Disease Control Programme |  |  |  |
|  | NVBDCP |  |  |  |
| a) | Remuneration to Contractual MPWs |  |  | 118.16 |
| b) | Contractual LTs |  |  |  |
| E | NLEP |  |  |  |
| a) | Contractual Services (State SMO, BFO cum AO, Admn. Assistant, DEO) |  |  | 38.52 |
| b) | State Driver |  |  |  |
| c) | District Drivers |  |  |  |
| F | NBCP |  |  |  |
| a) | Ophthalmic Surgeon |  |  | 64.32 |
| b) | Ophthalmic Assistant |  |  |  |
| c) | Eye Donation Counsellor |  |  |  |
| G) | RNTCP |  |  |  |
| a) | Honarium to DOT Providers |  |  | 162.67 |
| b) | Contractual Staff Payments |  |  |  |
| H) | IDSP |  |  |  |
| a) | Remuneration of Epidemiologists |  |  | 48.00 |
| b) | Remuneration of Microbiologists |  |  | 9.00 |
| c) | Remuneration of Entomologists |  |  | 3.00 |
| d) | Consultant-Finance |  |  | 3.00 |
| e) | Consultant-Training |  |  | 3.36 |
| f) | Data Managers |  |  | 24.60 |
| g) | Data Entry Operators |  |  | 18.00 |
|  | Vetenary consultant |  |  | 4.80 |
| I) | NIDDCP |  |  |  |
|  | IDD Control Cell- |  |  |  |
| (i) | Technical Officer |  |  | 10.80 |
| (ii) | Statistical Assistant |  |  |  |
| (iii) | LDC Typist |  |  |  |
|  | IDD Monitoring Lab- |  |  |  |
| (i) | Lab Technician |  |  |  |
| (ii) | Lab. Assistant |  |  |  |
|  | Training |  |  |  |
| I | RCH Flexible Pool |  |  |  |
| A.10 | TRAINING |  |  |  |
| A.10.1 | Strengthening of Training Institutions |  |  |  |
| A.10.2 | Development of training packages |  |  | 25.00 |
| A.10.3 | Maternal Health Training |  |  |  |
| A.10.3.1 | Skilled Birth Attendance / SBA |  |  | 28.76 |
| A.10.3.2 | EmOC Training / BEmOC |  |  | 5.92 |
| A.10.3.3 | Life saving Anesthesia skills training |  |  | 2.70 |
| A.10.3.4 | MTP training |  |  | 2.30 |
| A.10.3.5 | RTI / STI Training |  |  | 4.42 |
| A.10.3.6 | Dai Training |  |  |  |
| A.10.3.7 | Other MH Training (ISD Refresher ) |  |  |  |
| A.10.4 | IMEP Training |  |  | 4.86 |
| A.10.5 | Child Health Training |  |  |  |
| A.10.5.1 | IMNCI / F-IMNCI |  |  | 23.51 |
| A.10.5.2 | Facility Based Newborn Care |  |  |  |
| A.10.5.3 | Home Based Newborn Care |  |  |  |
| A.10.5.4 | Care of Sick Children and severe malnutrition |  |  |  |
| A.10.5.5 | Other CH Training (pl. specify)/NSSK |  |  | 9.15 |
| A.10.6 | Family Planning Training |  |  |  |
| A.10.6.1 | Laparoscopic Sterilisation Training |  |  | 0.44 |
| A.10.6.2 | Minilap Training |  |  | 2.30 |
| A.10.6.3 | NSV Training |  |  |  |
| A.10.6.4 | IUD Insertion Training |  |  | 1.88 |
| A.10.6.5 | Contraceptive Update/ISD Training |  |  |  |
| A.10.6.6 | Other FP Training (pl. specify) |  |  |  |
| A.10.7 | ARSH Training |  |  |  |
| A.10.8 | Programme Management Training |  |  |  |
| A.10.8.1 | SPMU Training |  |  | 0.64 |
| A.10.8.2 | DPMU Training |  |  | 5.99 |
| A.10.9 | Other training (pl. specify) |  |  |  |
| A.10.10 | Training (Nurshing) |  |  |  |
| A.10.10.1 | Strengthening of Existing Training Institutions/Nursing School |  |  |  |
| A.10.10.2 | New Training Institutions/School |  |  |  |
| A.10.11 | Training (Other Health Pesonnels) |  |  |  |
| A.10.11.1 | Promotional Trg of health workers females to lady health visitor etc. |  |  |  |
| A.10.11.2 | Training of AMNs,Staff nurses,AWW,AWS |  |  |  |
| A.10.11.3 | Other training and capacity building programmes |  |  |  |
| 2 | Routine Immunisation |  |  |  |
|  | Training for Cold Chain |  |  | 1.49 |
| 2.1 | Handlers/refrigerator mechanics |  |  |  |
| 2.2 | Training of M.O.s /Other Staffs on R.I. |  |  |  |
| 2.3 | Training for Computer Assistants |  |  |  |
|  | Other National Disease Control Programme |  |  |  |
| 3 | NVBDCP |  |  |  |
| 3.1 | Training for MPWs |  |  | 98.20 |
| 3.2 | Training for ASHAs |  |  |  |
| 3.3 | Training for M.O.s |  |  |  |
| 3.4 | Training for para-medicals for MDA |  |  |  |
| 3.5 | Other Training & Capacity building programmes |  |  |  |
| 4 | NLEP |  |  |  |
| 4.1 | Training for Newly appointed medical and para medical staffs |  |  | 4.58 |
| 4.2 | Training for existing medical and para medical staffs |  |  |  |
| 4.3 | Other Training & Capacity building programmes |  |  |  |
| 5 | NBCP |  |  |  |
| 5.1 | Training /Capacity Building for Health personnels |  |  | 10.00 |
| 5.2 | Training of Teachers & Others |  |  |  |
| 6 | RNTCP |  |  |  |
| 6.1 | Induction Training |  |  | 44.27 |
| 7 | IDSP |  |  |  |
| 7.1 | Training for M.O.s,Nurses, Data Managers and DEO |  |  | 7.05 |
| 8 | NIDDCP |  |  |  |
| Note: FMR Codes of NDCP' has not been given |  |  |  |  |
| Civil Work |  |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B.4 | Hospital Strengthening |  |  |  |
| B.4.1 | Upgradation of CHCs, PHCs, Dist. Hospitals to IPHS) |  |  |  |
| B4.1.1 | District Hospitals |  |  | 1328.44 |
| B4.1.2 | CHCs |  |  |  |
| B4.1.3 | PHCs |  |  |  |
| B4.1.4 | Sub Centers |  |  |  |
| B4.1.5 | Others |  |  |  |
| B 4.2 | Strengthening of District,Su-divisional CHC,PHC |  |  |  |
| B.4.3 | Sub Centre Rent and Contingencies |  |  |  |
| B.4.4 | Construction (Others) |  |  |  |
| B5 | New construction/rennovtions and Settingup |  |  |  |
| B5.1 | CHCs |  |  |  |
| B5.2 | PHCs |  |  |  |
| B5.3 | SHCs/Sub Centers |  |  |  |
| B5.4 | Setting up Infrastructure wing for Civil works |  |  |  |
| B5.6 | Construction of BHO, Facility improvement, civil work, BemOC and CemOC centers |  |  |  |
| B.5.7 | Major civil works for operationalisation of FRUS |  |  |  |
| B.5.8 | Major civil works for operationalisation of 24 hour services at PHCs |  |  |  |
| B.5.9 | Civil Works for Operationalise Infection Management & Environment Plan at health facilities |  |  |  |
| B6 | Minor Civil Works |  |  |  |
| B6.1 | Minor civil works for operationalisation of FRUs |  |  |  |
| B6.2 | Minor civil works for operationalisation of 24 hour services at PHCs |  |  |  |
| E | RNTCP |  |  |  |
| a) | Civil Works |  |  | 21.47 |
| F | IDSP |  |  |  |
| a) | Civil Works |  |  |  |
| Note: FMR Codes of NDCP' has not been given |  |  |  |  |
| Procurements-Drugs & Supplies |  |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B.16.2 | Procurement of Drugs and supplies |  |  |  |
| B.16.2.1 | Drugs & supplies for MH |  |  | 300 |
| B.16.2.2 | Drugs & supplies for CH |  |  |  |
| B.16.2.3 | Drugs & supplies for FP |  |  |  |
| B.16.2.4 | Supplies for IMEP |  |  |  |
| B.16.2.5 | General drugs & supplies for health facilities |  |  |  |
| C | Routine Immunisation |  |  | 3.64 |
|  | Other National Disease Control Programme |  |  |  |
| D | NVBDCP |  |  |  |
| a) | Procurement of Drugs |  |  | 162.00 |
| E | NLEP |  |  |  |
| a) | Procurement of Supportive Drugs, Reagents, MCR Footware, Aids Appliances |  |  |  |
| F | NBCP |  |  |  |
| a) | Procurement of Drugs & Supplies |  |  |  |
| G | RNTCP |  |  |  |
| a) | Note-Below |  |  |  |
| H | IDSP |  |  | 8.00 |
| I | NIDDCP |  |  | 6.60 |
| Note: | In RNTCP, commodity grant for anti TB Drugs has been approved from Central Level procurements and specific Laboratory Equipments |  |  |  |
| Procurements-Equipment |  |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B.16.1 | Procurement of Equipments |  |  |  |
| B16.1.1 | Procurement under Maternal Health |  |  | 309.15 |
| B16.1.2 | Procurement under Child Health |  |  | 87.6 |
| B16.1.3 | Procurement under Family Planning Services |  |  | 48.6 |
| B16.1.4 | Procurement under IMEP |  |  | 18 |
| B16.1.5 | Procurement Others |  |  | 37.8 |
| C | Routine Immunisation |  |  |  |
|  | Procurement -Equipments (e.g.ADS,Bags, Buckets ) |  |  |  |
|  | Other National Disease Control Programme |  |  |  |
| D | NVBDCP |  |  |  |
| a) | Procurement -Kits (e.g. Elisa Kit,Chikengunia Kits ) |  |  | 32.00 |
| E | NLEP |  |  |  |
| a) | Procurement of Equipments (Equipments related to RCS). Printing forms |  |  | 4.20 |
| b) | Other Procurements |  |  |  |
| F | NBCP |  |  |  |
| a) | Procurement of Equipments-Opthalmic Microscopes, Flash Auto claves etc. |  |  | 40.00 |
| G | RNTCP |  |  |  |
| a) | Procurement of Equipments |  |  | 82.65 |
| b) | Procurement of Two wheelers |  |  |  |
| H | IDSP |  |  |  |
| a) | Procurement of Equipements for Strengthening of Survillance Unit. |  |  |  |
| b) | Other Procurements |  |  |  |
| I | NIDDCP |  |  |  |
|  | Procurement of Kits (Salt Testing Kits) |  |  |  |
| IEC/BCC Works |  |  |  |  |
| B | NRHM Additionlities |  |  |  |
| B10 | IEC-BCC NRHM |  |  |  |
| B.10 | Strengthening of BCC/IEC Bureaus (State and district levels) |  |  |  |
| B.10.1 | Development of State BCC/IEC strategy |  |  |  |
| B.10.2 | Implementation of BCC/IEC strategy |  |  |  |
| B.10.2.1 | BCC/IEC activities for MH |  |  | 449.75 |
| B.10.2.2 | BCC/IEC activities for CH |  |  |  |
| B.10.2.3 | BCC/IEC activities for FP |  |  |  |
| B.10.2.4 | BCC/IEC activities for ARSH |  |  |  |
| B.10.2.5 | Other activities (please specify) |  |  |  |
| B.10.4 | Health Mela |  |  |  |
| B.10.5 | Creating awareness on declining sex ratio issue |  |  |  |
| B.10.6 | Other activities |  |  |  |
|  | Other NDCPs |  |  |  |
| c) | Routine Immunisation |  |  |  |
|  | IEC-BCC Activities |  |  | 5.00 |
| D | NVBDCP |  |  |  |
|  | IEC-BCC Activities |  |  | 198.05 |
| E | NLEP |  |  |  |
|  | IEC-BCC Activities |  |  | 9.00 |
| F | NBCP |  |  |  |
|  | IEC-BCC Activities |  |  | 6.00 |
| a) | Cataract Operations |  |  |  |
| b) | Eye Donation Camps |  |  |  |
| c) | Other Activities |  |  |  |
| G | RNTCP |  |  |  |
|  | IEC/Publicity |  |  | 19.83 |
| H | IDSP |  |  |  |
|  | IEC-BCC Activites |  |  | 11.00 |
| I | NIDDCP |  |  | 25.06 |
|  | Untied Funds |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B.2 | Untied Funds |  |  |  |
| B2.1 | Untied Fund for CHCs |  |  | 4.50 |
| B2.2 | Untied Fund for PHCs |  |  | 14.50 |
| B2.3 | Untied Fund for Sub Centers |  |  | 37.00 |
| B2.4 | Untied fund for VHSC |  |  | 81.50 |
| B.3 | Annual Maintenance Grants |  |  |  |
| B4.1 | CHCs |  |  | 9.00 |
| B4.2 | PHCs |  |  | 28.50 |
| B4.3 | Sub Centres |  |  | 37.00 |
| B8 | Panchayti Raj Initiative |  |  |  |
| B8.1 | Constitution and Orientation of Community leader & of VHSC,SHC,PHC,CHC etc |  |  | 60.53 |
| B8.2 | Orientation Workshops, Trainings and capacity building of PRI at State/Dist. Health Societies, CHC,PHC |  |  |  |
| B8.3 | Others |  |  |  |
| ASHAs |  |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B1 | ASHA |  |  |  |
| B1.1 | Selection & Training of ASHA |  |  | 109.50 |
| B1.2 | Procurement of ASHA Drug Kit |  |  |  |
| B1.3 | Incentive to ASHAs under JSY Budget under RCH |  |  | 62.21 |
| B1.4 | Incentive under Family Planning Services |  |  |  |
| B1.5 | Incentive under Child Health |  |  |  |
| B1.6 | Incentive to ASHA's for motivating families for Sanitary Toilets/Other Incentives |  |  |  |
| B1.7 | Awards to ASHA's/Link workers |  |  |  |
| C | Routine Immunisation |  |  |  |
| a) | Special ASHA Incentive under Immunisation |  |  | 43.33 |
| b) | Social Mobilization by ASHA / Link Workers |  |  |  |
| c) | ASHA Incentive on PPI Day (may be considered with the cost of PPI) |  |  |  |
| D | NVBDCP |  |  |  |
| a) | Incentive to ASHAs |  |  | 15.00 |
| E | NLEP |  |  |  |
| a) | Services through ASHAs |  |  |  |
| b) | Honorium to ASHAs, Sensitization through ASHAs |  |  | 3.54 |
| F | NBCP |  |  |  |
| a) | ASHA Incentive |  |  |  |
| G | RNTCP |  |  |  |
|  | ASHA Incentive for DOTs |  |  |  |
| RKS/HMS |  |  |  |  |
| 1.1 | RCH |  |  |  |
| 1.2 | NRHM Additionalities |  |  |  |
| (i) | Corpus Grants to HMS/RKS |  |  |  |
| B6.1 | District Hospitals |  |  | 40.00 |
| B6.2 | CHCs |  |  | 9.00 |
| B6.3 | PHCs |  |  | 57.00 |
| B6.4 | Other or if not bifurcated as above |  |  | 4.00 |
| JSY |  |  |  |  |
| 1.1 | RCH |  |  |  |
|  | Maternal Health |  |  |  |
|  | Janani Suraksha Yojana / JSY |  |  |  |
| a) | Home Deliveries |  |  | 12.88 |
| b) | Institutional Deliveries |  |  | 98.19 |
| c) | 24 Hours Deliveries/ Others Operational Expenses |  |  |  |
| d) | Payment to Other Link Workers/AWW/AWS (Other than ASHA's) |  |  |  |
| Incentive for Sterilization |  |  |  |  |
| 1 | RCH |  |  |  |
| A.3 | FAMILY PLANNING |  |  |  |
| A.3.1 | Terminal/Limiting Methods |  |  |  |
| A.3.1.1 | Dissemination of manuals on sterilisation standards & quality assurance of sterilisation services |  |  |  |
| A.3.1.2 | Female Sterilisation camps |  |  | 2.25 |
| A.3.1.3 | NSV camps |  |  |  |
| A.3.1.4 | Compensation for female sterilisation |  |  | 36.70 |
| A.3.1.5 | Compensation for male sterilisation |  |  | 0.15 |
| A.3.1.6 | Accreditation of private providers for |  |  |  |
|  | sterilisation services |  |  |  |
| A.3.2.1 | IUD camps |  |  |  |
| A.3.2.2 | IUD services at health facilities |  |  | 2.50 |
| A.3.2.3 | Accreditation of private providers for IUD insertion services |  |  |  |
| A.3.2.4 | Social Marketing of contraceptives |  |  |  |
| A.3.2.5 | Contraceptive Update seminars |  |  |  |
| A.3.3 | POL for Family Planning |  |  | 2.00 |
| A.3.4 | Repairs of Laparoscopes |  |  |  |
| A.3.5 | Other FP Services |  |  | 34.82 |
| Referral Transport |  |  |  |  |
| 1.1 | RCH |  |  |  |
|  | Referral Transport |  |  |  |
| a) | Maternal Health |  |  |  |
| b) | Other Programmes |  |  |  |
| 1.2 | NRHM Additionalities |  |  |  |
|  | Referral Transport |  |  |  |
| a) | Ambulance /EMRI |  |  | 658.88 |
| b) | Operating Cost (POL) /EMRI |  |  |  |
| 1.3 | Routine Immunisation |  |  |  |
| 1.4 | NVBDCP |  |  |  |
|  | Referral Services |  |  |  |
| 1.5 | NLEP |  |  |  |
| 1.6 | NBCP |  |  | 120.00 |
| 1.7 | RNTCP |  |  |  |
| 1.8 | IDSP |  |  |  |
| 1.9 | NIDDCP |  |  |  |
| Other RCH Activities |  |  |  |  |
| 1 | RCH |  |  |  |
| 1.1 | Maternal Health |  |  |  |
| 1.1.2 | Operationalise facilities (only dissemination, monitoring, and quality) |  |  |  |
| (i) | Operationalise FRUs |  |  | 3.00 |
| (ii) | Operationalise 24x7 PHCs |  |  | 2.50 |
| (ii) | MTP services at health facilities |  |  |  |
| (iv) | RTI/STI services at health facilities |  |  |  |
| (v) | Operationalise Sub-centres |  |  | 1.00 |
| 1.1.3 | Integrated outreach RCH services |  |  |  |
| (i) | RCH Outreach Camps |  |  | 2.40 |
| (ii) | Monthly Village Health and Nutrition Days |  |  |  |
|  | Other Maternal Health - JSSK, Death Audit etc |  |  | 506.93 |
| 1.1.4 | CHILD HEALTH |  |  |  |
| (i) | IMNCI |  |  |  |
| (ii) | Facility Based Newborn Care/FBNC |  |  | 10.00 |
| (ii) | Home Based Newborn Care/HBNC |  |  |  |
| (iv) | School Health Programme |  |  |  |
| (v) | Infant and Young Child Feeding/IYCF Care of Sick Children and Severe |  |  |  |
| (vi) | Malnutrition |  |  |  |
|  | Management of Diarrohea, ARI and |  |  |  |
| (vii) | Micronutrient Malnutrition |  |  |  |
| (viii) | Other strategies/activities - JSSK, Incentive to ASHA etc |  |  | 53.05 |
| 1.1.5 | URBAN RCH |  |  |  |
| a) | Establishment of New Urban Centres |  |  |  |
| b) | Urban RCH Services |  |  | 31.38 |
| 1.1.6 | ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH / ARSH |  |  |  |
| a) | Adolescent services at health facilities. |  |  | 70.00 |
| b) | Other strategies/activities |  |  |  |
|  | Vulnerable Groups |  |  |  |
| A | RCH |  |  |  |
| A.6 | TRIBAL RCH |  |  |  |
| a) | Organise Tribal Camps |  |  |  |
| b) | Other Tribal Activities |  |  |  |
| A.7 | VULNERABLE GROUPS |  |  |  |
| B | NRHM Additionalities |  |  |  |
|  | Other MFP activities |  |  |  |
|  | District Health Action Plans (Including |  |  |  |
| B7 | Block, Village) |  |  |  |
| B9 | Mainstreaming of AYUSH |  |  | 178.03 |
| B10 | Mobile Medical Units (Including recurring expenditures) |  |  | 203.36 |
| B13 | School Health Programme |  |  | 92.33 |
| B15 | Planning, Implementation and Monitoring |  |  |  |
| B15.1 | Community Monitoring (Visioning workshops at State, Dist, Block level) |  |  |  |
| B15.1.1 | State level |  |  |  |
| B15.1.2 | District level |  |  |  |
| B15.1.3 | Block level |  |  |  |
| B15.1.4 | Other |  |  |  |
| B15.2 | Quality Assurance |  |  |  |
| B15.3 | Monitoring and Evaluation |  |  |  |
| B15.3.1 | Monitoring & Evaluation / HMIS |  |  | 197.37 |
| B15.3.2 | Computerization HMIS and e-governance, e-health |  |  |  |
| B15.3.3 | Other M & E |  |  |  |
| B.20 | Health Insurance Scheme |  |  | 128.89 |
| B21 | Research, Studies, Analysis |  |  |  |
| B.22 | State level health resources center(SHSRC) |  |  |  |
| B23 | Support Services |  |  |  |
| B23.1 | Support Strengthening NPCB |  |  |  |
| B23.2 | Support Strengthening Midwifery Services under medical services |  |  |  |
| B23.3 | Support Strengthening NVBDCP |  |  | 76.50 |
|  | RDK (including CMAI staffs 885 voluntaries |  |  | 70.00 |
|  | ACT (including CNAI staff 885 voluntaries |  |  | 17.00 |
| B23.4 | Support Strengthening RNTCP |  |  |  |
| B23.5 | Contingency support to Govt. dispensaries |  |  |  |
| B23.6 | Other NDCP Support Programmes |  |  |  |
| B.24 | Other Expenditures (Power Backup, Convergence etc) |  |  |  |
| INNOVATIONS/ PPP/ NGO |  |  |  |  |
| B | NRHM Additionalities |  |  |  |
| B14 | PPP/ NGOs |  |  |  |
| B14.1 | Non governmental providers of health care RMPs/TBAs |  |  |  |
| B14.2 | PNDT and Sex Ratio |  |  | 4.00 |
| B14.3 | Public Private Partnerships |  |  | 22.43 |
| B14.4 | NGO Programme/ Grant in Aid to NGO |  |  | 85.50 |
| B14.5 | Other innovations( if any) |  |  | 34.30 |
| C | Routine Immunization |  |  | 94.13 |
| 1.4 | NVBDCP |  |  | 163.30 |
| D | NLEP |  |  |  |
|  | NGO Services |  |  | 16.00 |
| a) | NGOs |  |  |  |
| b) | Pvt. Sector |  |  |  |
| E | NBCP |  |  |  |
|  | Cataract Performance |  |  | 37.75 |
| a) | NGOs |  |  |  |
| b) | Pvt. Sector |  |  |  |
| F | RNTCP |  |  | 8.60 |
|  | NGO/PPP Support |  |  |  |
| G | IDSP |  |  | 31.40 |
| H | NIDDCP |  |  |  |
| Operational Cost |  |  |  |  |
|  | Other NDCPs |  |  |  |
| E | NVBDCP |  |  |  |
|  | Mobility Support |  |  | 658.71 |
|  | Lab Consumables/ Materials |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Formats and Reports |  |  |  |
|  | Communication facility to Staffs |  |  |  |
|  | Repair of Laparoscopes |  |  |  |
| F | NLEP |  |  |  |
|  | Mobility Support |  |  | 37.00 |
|  | Lab Consumables |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Office Expenditures, Formats and Reports |  |  |  |
| G | NBCP |  |  |  |
|  | Mobility Support |  |  | 136.53 |
|  | Lab Consumables |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Formats and Reports |  |  |  |
| H | RNTCP |  |  |  |
|  | Mobility Support |  |  | 73.79 |
|  | Lab Consumables |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Formats and Reports |  |  |  |
| I | IDSP |  |  |  |
|  | Mobility Support |  |  | 26.78 |
|  | Lab Consumables |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Formats and Reports |  |  |  |
| I | NIDDCP |  |  |  |
|  | Mobility Support |  |  | 3.46 |
|  | Lab Consumables |  |  |  |
|  | Review Meetings |  |  |  |
|  | Field Visits |  |  |  |
|  | Formats and Reports |  |  |  |
| Financial Aid /Grant to Institutions |  |  |  |  |
|  | For all NDCP's---- |  |  |  |
| i) | Financial Aid /Grant to Medical Collages |  |  |  |
| ii) | Financial Aid /Grant to Referral Institutions |  |  |  |
| iii) | Financial Aid /Grant to Sentinel Sites |  |  |  |
| iv) | Financial Aid /Grant to Medical Hopitals/Institutions |  |  |  |
|  | IDSP |  |  | 5.50 |
|  | NPCB |  |  | 60.00 |
|  | Financial Aid /Grant to Others (Pl. Specify) |  |  |  |

Census data 2001

The Literacy related data is as per the District Data, 2006