**2.3.2.7: Special anti-malarial intervention for high risk group for tribal population for hard to reach area to control and prevent resurgence of malaria:**

The following are proposed for special anti-malarial intervention for hard to reach area to control and prevent resurgence of malaria in the state viz. Mamit, Lunglei, Lawngtlai and Siaha (List enclose in 2.3.2.7 Annex) –

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl No** | **Name of District** | **No. of villages** | **Name of activity** | **No. of frequency** | **Rate** | **Amount** |
| 1 | Mamit | 18 | Malaria camp/clinic in co-ordination with Local Leaders/ NGOs/VHSNC | 2 (pre and post-transmission season) | 3000/village | 108000 |
|  |  | 18 | House to house campaign by ASHA/CHV | 2 (pre and post-transmission season) | Incentives of Rs.750/ASHA/village | 27000 |
| 2 | Lunglei | 43 | Malaria camp/clinic in co-ordination with Local Leaders/ NGOs/VHSNC | 2 (pre and post-transmission season) | 3000/village | 258000 |
|  |  | 43 | House to house campaign by ASHA/CHV | 2 (pre and post-transmission season) | Incentives of Rs.750/ASHA/village | 64500 |
| 3 | Lawngtlai | 57 | Malaria camp/clinic in co-ordination with Local Leaders/ NGOs/VHSNC | 2 (pre and post-transmission season) | 3000/village | 342000 |
|  |  | 57 | House to house campaign by ASHA/CHV | 2 (pre and post-transmission season) | Incentives of Rs.750/ASHA/village | 85500 |
| 4 | Siaha | 5 | Malaria camp/clinic in co-ordination with Local Leaders/ NGOs/VHSNC | 2 (pre and post-transmission season) | 3000/village | 30000 |
|  |  | 5 | House to house campaign by ASHA/CHV | 2 (pre and post-transmission season) | Incentives of Rs.750/ASHA/village | 7500 |
| **TOTAL PROPOSED FOR FY 21- 22** | | | | | | 9,22,500 |

**Total Funds required under this head is Rs. 9.23/- lakhs.**